## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | Tanishka Reality LLP
Name of the builder company |  |  |  | Tanishka Reality LLP
Name of the Project |  |  |  | Tanishkaa Vikrant
Provided Contact Details (Name & Contact No.) |  |  |  | 9870630645
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr.Arvind 9004419810
Name / No of the Building |  |  |  | Wing A, B, C, D & E
Name / No of the Existing Building |  |  |  | Vikrant | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800052284 |  |  |  | #N/A |  |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Tanishkaa Vikrant, Plot Bearing F.P No.6, C.T.S No.5987(Pt) Redevlopement of " Lokhit CHSL, Vikrant", near Mayfair Mystic, RB Mehta Road, Sindhu Wadi, Ghatkopar, Vidyavihar East, Kurla, Mumbai - 400077. | [10 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot Bearing F.P No |  | 6, C.T.S No.5987(Pt) Redevlopement of " Lokhit CHSL, Vikrant" | [10 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Sindhu Wadi | [10 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | RB Mehta Road |  | Locality/Village |  | Ghatkopar | [6 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Vidyavihar East |  | District |  | Mumbai | [6 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kurla |  | Pin Code |  | 400077 | [9 empty] | Mahad | Daund
Nearby Landmark |  | Mayfair Mystic |  | Distance from city centre: |  | 2.8 KM from Vidyavihar Railway Station | [9 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [11 empty] | Mangaon | Ambegaon
[16 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [11 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [11 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [11 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 18.30 M W. Road |  |  | Tilak Road/Sai-Vaibhav Co-operative Housing Society
West | NA | Other Plot |  |  | Mayfair Mystic
North | NA | Existing Road |  |  | RB Mehat Road
South | NA | 27.45 M. W. Road |  |  | Barrister Nath Pai Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.074780,72.904760
Location Link |  | https://maps.app.goo.gl/DnoPNoRhHnp3Bz2Y8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5360.1
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 1.5097
Total FSI availaible for the project |  |  |  | 5.5097
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 29532.72
Total number of Buildings |  |  |  | 05 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority (SRA)
Layout Approval No |  | SRA/ENG/N/PVT/0105/20220613/AP/S |  |  | Dated | 28/04/2023.
Approved Floor plan No. |  | SRA/ENG/N/PVT/0105/20220613/AP/S |  |  | Dated | 28/04/2023.
Commencement-CC No Valid Up to: |  | N/PVT/0105/20220613/AP/S |  |  | Dated | 07/05/2024.
This CC is further extended upto full ht with OHWT+LMR in form of RCC framework for wing A to E of sale bldg as per last approved amended plans dtd.28/04/2023. This Commencement Certificate/Building Permit is granted subject to compliance of mentioned in LOI U/R No. N/PVT/0105/20220613/LOI dt 24/04/2023 IOA/U/R No. N/PVT/0105/20220613/AP/S dt 28/04/2023
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 29532.72
Approved no of units |  |  | Flats - 185, Shops - 33, Offices - 10
Approved no of Floors |  |  | A Wing = Gr + 1P to 5P + 6th to 20th Floor B Wing = Gr + 1P to 5P + 6th to 20th Floor C Wing = Gr + 1P to 5P + 6th to 20th Floor D Wing = Gr + 1P to 5P + 6th to 20th Floor E Wing = Gr + 1P to 5P + 6th to 20th Floor
Proposed no of Floors |  |  | A to E Wing = Gr + 1P to 5P + 6th to 20th Floor
B Wing = Gr + 1P to 5P + 6th to 20th Floor
C Wing = Gr + 1P to 5P + 6th to 20th Floor
D Wing = Gr + 1P to 5P + 6th to 20th Floor
E Wing = Gr + 1P to 5P + 6th to 20th Floor
Expected Completion |  |  | As per RERA - 30/06/2029
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Children's Play Area, Indoor Games, Power Backup, Lift(s), 24x7 Security, Sewage Treatment Plant, 24X7 Water Supply, Landscaping & Tree Planting, Electrification(Transformer, Solar Energy etc),Water Conservation, Rain water Harvesting, Storm Water Drains, Solid Waste Management And Disposal, Closed Car Parking, Fire Sprinklers etc. |  |  |  |  | https://housing.com/in/buy/projects/page/305248-tanishkaa-vikrant-by-tanishka-reality-llp-in-mankur
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = Gr + 1P to 5P + 6th to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 17 Floor, Internal Plaster upto 12 Floor, External Plaster upto 8 Floor Completed | , Brickwork upto 17 Floor, Internal Plaster upto 12 Floor, External Plaster upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 17 Floor, Internal Plaster upto 12 Floor, External Plaster upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 64.88% |  | 84.25% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 17 | 85% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 12 | 60% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 40% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | B Wing = Gr + 1P to 5P + 6th to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 14 Floor, Internal Plaster upto 12 Floor, External Plaster upto 8 Floor Completed | , Brickwork upto 14 Floor, Internal Plaster upto 12 Floor, External Plaster upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 14 Floor, Internal Plaster upto 12 Floor, External Plaster upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 63.75% |  | 83.5% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 14 | 70% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 12 | 60% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 40% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | C Wing = Gr + 1P to 5P + 6th to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 17 Floor, External Plaster upto 14 Floor, Flooring upto 7 Floor, Painting upto 5 Floor Completed | , Internal Plaster upto 17 Floor, External Plaster upto 14 Floor, Flooring upto 7 Floor, Painting upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 17 Floor, External Plaster upto 14 Floor, Flooring upto 7 Floor, Painting upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 75.62% |  | 89.5% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 17 | 85% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 70% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 35% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 25% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | D Wing = Gr + 1P to 5P + 6th to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 19 Floor, Internal Plaster upto 16 Floor, External Plaster upto 10 Floor Completed | , Brickwork upto 19 Floor, Internal Plaster upto 16 Floor, External Plaster upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 19 Floor, Internal Plaster upto 16 Floor, External Plaster upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 68.12% |  | 86.25% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 19 | 95% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 16 | 80% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 50% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | E Wing = Gr + 1P to 5P + 6th to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 18 Floor, External Plaster upto 11 Floor Completed | , Internal Plaster upto 18 Floor, External Plaster upto 11 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 18 Floor, External Plaster upto 11 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 69.75% |  | 87.25% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 18 | 90% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 55% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 16500
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 34000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 30000 |  |  |  |  | 34
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 800000
Sinking Fund |  |  |  |  | 300000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges for 24 months |  |  |  |  | 700000
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 13200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A & B | Shop | 5 |  | 12369.4506 |  | 19791.121
Wing C To E | Shop | 28 |  | 9632.4883 |  | 15249.4019 |  |  | 32 | 33
| Office | 1 |  | 1881.7625 |  | 3010.82
Wing A To E | Office | 9 |  | 8248.7761 |  | 13198.0418
Total |  | 43 |  | 32132.4775 |  | 51249.3846
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 28 |  | 63214.6416 |  | 101143.4266
Wing B |  | 28 |  | 49038.9649 |  | 78462.3438
Wing C |  | 28 |  | 44152.5287 |  | 70644.0459
Wing D |  | 28 |  | 37962.6151 |  | 60740.1842
Wing E |  | 73 |  | 58958.6798 |  | 94333.8876
Total |  | 185 |  | 253327.4301 |  | 405323.8881
Grand Total |  | 228 |  | 285459.9076 |  | 456573.2727
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor |  | 10.764
60%
Wing A & B
Ground Floor For Commercial, Meter Room, Lobby & Parking
1 |  | Shop Duplex With 1st Podium Floor | 7421.5627 | 0 | 11874.5004 | Ground Floor For Commercial, Meter Room, Lobby & Parking |  | 662.6027
2 |  | Shop Duplex With 1st Podium Floor | 851.2171 | 0 | 1361.9474 |  |  | 77.583
3 |  | Shop Duplex With 1st Podium Floor | 901.8079 | 0 | 1442.8927 |  |  | 83.3995
4 |  | Shop Duplex With 1st Podium Floor | 902.0232 | 0 | 1443.2371 |  |  | 83.3995
5 |  | Shop Duplex With 1st Podium Floor | 2292.8396 | 0 | 3668.5434 |  |  | 212.4565
1st Podium Floor For Commercial, Meter Room, Lobby & Parking
1 |  | Shop Duplex With Ground Floor |  |  |  | 1st Podium Floor For Commercial, Meter Room, Lobby & Parking |  | 662.6027
2 |  | Shop Duplex With Ground Floor | [5 empty] | 77.583
3 |  | Shop Duplex With Ground Floor | [5 empty] | 83.3995
4 |  | Shop Duplex With Ground Floor | [5 empty] | 83.3995
5 |  | Shop Duplex With Ground Floor | [5 empty] | 212.4565
Wing C To E
Ground Floor For Commercial Meter Room, Entrance Lobby, O.W.C & Parking | [7 empty] | 10.764
1 |  | Shop | 335.5139 | 0 | 536.8222 | Ground Floor For Commercial Meter Room, Entrance Lobby, O.W.C & Parking
2 |  | Shop | 246.9262 | 0 | 395.0819
3 |  | Shop | 260.1659 | 0 | 416.2654
4 |  | Shop | 264.5791 | 0 | 423.3266
5 |  | Shop | 266.3014 | 0 | 426.0822
6 |  | Shop | 266.8396 | 0 | 426.9433
7 |  | Shop | 332.5 | 0 | 531.9999
8 |  | Shop | 332.5 | 0 | 531.9999 |  |  | 30.0855
9 |  | Shop | 633.9996 | 0 | 1014.3994
11 |  | Shop | 372.542 | 0 | 596.0673
12 |  | Shop | 318.0762 | 0 | 508.9219
13 |  | Shop | 318.0762 | 0 | 508.9219
13A |  | Shop | 318.0762 | 0 | 508.9219
14 |  | Shop | 264.7944 | 0 | 423.671
15 |  | Shop | 259.6277 | 0 | 415.4043
16 |  | Shop | 262.211 | 0 | 419.5377
17 |  | Shop | 253.5998 | 0 | 405.7597
18 |  | Shop | 367.8059 | 0 | 588.4894
19 & 20 |  | Shop | 398.5909 | 0 | 637.7455 |  |  |  | 35.7246
21 |  | Shop | 359.1947 | 0 | 397.1485
22 |  | Shop | 248.2178 | 0 | 415.2321
23 |  | Shop | 259.52 | 0 | 412.132
24 |  | Shop | 257.5825 | 0 | 412.132
25 |  | Shop | 368.1288 | 0 | 589.0061
26 |  | Shop | 262.3187 | 0 | 419.7099
27 |  | Shop | 253.5998 | 0 | 405.7597
28 |  | Shop | 360.7016 | 0 | 577.1226
1st Podium Floor For Commercial & Parking
1 |  | Office | 1881.7625 | 0 | 3010.82 | 1st Podium Floor For Commercial & Parking |  | 174.7789
10 |  | Shop | 1190.4984 | 0 | 1904.7974
Wing A To E
2nd Podium Floor For Commercial & Parking
1 |  | Office | 5900.5019 | 0 | 9440.803 | 2nd Podium Floor For Commercial & Parking
3rd Podium Floor For Commercial & Parking
1 |  | Office | 1013.8612 | 0 | 1622.1779 | 3rd Podium Floor For Commercial & Parking
2 |  | Office | 230.242 | 0 | 368.3871
3 |  | Office | 218.8321 | 0 | 350.1314
4 |  | Office | 231.426 | 0 | 370.2816 |  |  | 21.5064
5 |  | Office | 217.3252 | 0 | 347.7203
6 |  | Office | 173.1928 | 0 | 277.1084 |  |  | 16.0866
7 |  | Office | 154.1405 | 0 | 246.6248
8 |  | Office | 109.2546 | 0 | 174.8074
4th Podium Floor For Parking
5th Podium Floor For Society Office, Fitness Center & Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Wing A
6th, 7th, 9th to 14th Floor For Residential
1 |  | 4BHK | 2190.7915 | 0 | 3505.2665 | 6th, 7th, 9th to 14th Floor For Residential |  | 199.5725 |  |  | 19354.8387 | 10972.719
2 |  | 4BHK | 2098.388 | 0 | 3357.4208
8th (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th (Part Refuge Area)
2 |  | 6.5BHK | 2999.7653 | 0 | 4799.6245 | 0
15th (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 15th (Part Refuge Area) |  | 157.58
2 |  | 6.5BHK | 3177.9634 | 0 | 5084.7414
16th & 17th Floor
1 |  | 4BHK | 2318.4849 | 0 | 3709.5758 | 16th & 17th Floor |  | 199.5725 |  |  | 16504.5826
2 |  | 4BHK | 2226.2105 | 0 | 3561.9368
18th to 20th Floor
1 |  | 4BHK | 2318.4849 | 0 | 3709.5758 | 18th to 20th Floor
2 |  | 4BHK | 2226.2105 | 0 | 3561.9368
Wing B
6th, 7th, 9th to 14th & 16th to 20th Floor For Residential
1 |  | 4BHK | 1695.5453 | 0 | 2712.8724 | 6th, 7th, 9th to 14th & 16th to 20th Floor For Residential
2 |  | 4BHK | 1695.5453 | 0 | 2712.8724
8th Floor (Part Refuge Area)
1 |  | 5BHK | 2424.4403 | 0 | 3879.1045 | 8th Floor (Part Refuge Area)
- |  | Part Refuge Area
15th Floor (Part Refuge Area)
1 |  | 5BHK | 2530.3473 | 0 | 4048.5557 | 15th Floor (Part Refuge Area)
- |  | Part Refuge Area
Wing C
6th, 7th, 9th to 14th & 16th to 20th Floor For Residential
1 |  | 4BHK | 1525.1242 | 0 | 2440.1988 | 6th, 7th, 9th to 14th & 16th to 20th Floor For Residential
2 |  | 4BHK | 1525.1242 | 0 | 2440.1988
8th Floor (Part Refuge Area)
1 |  | Part Refuge Area |  |  |  | 8th Floor (Part Refuge Area)
2 |  | 5BHK | 2303.4422 | 0 | 3685.5075 |  |  | 213.995
15th Floor (Part Refuge Area)
1 |  | Part Refuge Area |  |  |  | 15th Floor (Part Refuge Area)
2 |  | 5BHK | 2195.856 | 0 | 3513.3696
Wing D
6th, 7th, 9th to 12th Floor For Residential
1 |  | 4BHK | 1288.1386 | 0 | 2061.0218 | 6th, 7th, 9th to 12th Floor For Residential
2 |  | 4BHK | 1288.1386 | 0 | 2061.0218
8th Floor (Part Refuge Area)
1 |  | 6BHK | 1919.0436 | 0 | 3070.4698 | 8th Floor (Part Refuge Area)
2 |  | Part Refuge Area
13th, 14th, 16th to 20th Floor
1 |  | 4BHK | 1327.4595 | 0 | 2123.9353 | 8th Floor (Part Refuge Area)
2 |  | 4BHK | 1327.4595 | 0 | 2123.9353
15th Floor (Part Refuge Area)
1 |  | 6BHK | 2001.4743 | 0 | 3202.3589 | 15th Floor (Part Refuge Area)
2 |  | Part Refuge Area
Wing E
6th & 7th Floor For Residential
1 |  | 2BHK | 672.6693 | 0 | 1076.2708 | 6th & 7th Floor For Residential |  | 62.4925
2 |  | 3BHK | 876.5125 | 0 | 1402.42 |  |  | 79.225
3 |  | 2BHK | 550.0404 | 0 | 880.0646
4 |  | 3BHK | 904.0953 | 0 | 1446.5524
5 |  | 3BHK | 938.271 | 0 | 1501.2336
8th Floor (Part Refuge Area)
1 |  | 2BHK | 672.6693 | 0 | 1076.2708 | 8th Floor (Part Refuge Area)
2 |  | 3BHK | 876.5125 | 0 | 1402.42
3 |  | 2BHK | 550.0404 | 0 | 880.0646
4 |  | Part Refuge Area
5 |  | 3BHK | 938.271 | 0 | 1501.2336
9th to 11th Floor
1 |  | 2BHK | 672.6693 | 0 | 1076.2708 | 9th to 11th Floor |  |  | 13937.0125
2 |  | 3BHK | 876.5125 | 0 | 1402.42
3 |  | 2BHK | 550.0404 | 0 | 880.0646
4 |  | 3BHK | 904.0953 | 0 | 1446.5524
5 |  | 3BHK | 938.271 | 0 | 1501.2336
12th & 13th Floor
1 |  | 2BHK | 672.6693 | 0 | 1076.2708 | 12th & 13th Floor
2 |  | 3BHK | 876.5125 | 0 | 1402.42
3 |  | 2BHK | 571.8106 | 0 | 914.8969
4 |  | 3BHK | 904.0953 | 0 | 1446.5524
5 |  | 3BHK | 938.271 | 0 | 1501.2336
14th & 16th Floor
1 |  | 3BHK | 861.6851 | 0 | 1378.6962 | 14th & 16th Floor
2 |  | 3BHK | 876.5125 | 0 | 1402.42
3 |  | 2BHK | 571.8106 | 0 | 914.8969
4 |  | 3BHK | 904.0953 | 0 | 1446.5524
5 |  | 3BHK | 938.271 | 0 | 1501.2336
15th (Part Refuge Area)
1 |  | 3BHK | 861.6851 | 0 | 1378.6962 | 15th (Part Refuge Area)
2 |  | 3BHK | 876.5125 | 0 | 1402.42
3 |  | 2BHK | 571.8106 | 0 | 914.8969
4 |  | Part Refuge Area
5 |  | 3BHK | 938.271 | 0 | 1501.2336
17th & 18th Floor
1 |  | 3BHK | 861.6851 | 0 | 1378.6962 | 17th & 18th Floor
2 |  | 3BHK | 876.5125 | 0 | 1402.42
3 |  | 2BHK | 571.8106 | 0 | 914.8969
4 |  | 3BHK | 904.0953 | 0 | 1446.5524
5 |  | 3BHK | 969.2713 | 0 | 1550.8341
19th & 20th Floor
1 |  | 3BHK | 861.6851 | 0 | 1378.6962 | 17th & 18th Floor
2 |  | 3BHK | 876.5125 | 0 | 1402.42
3 |  | 2BHK | 571.8106 | 0 | 914.8969
4 |  | 3BHK | 904.0953 | 0 | 1446.5524
5 |  | 3BHK | 969.2713 | 0 | 1550.8341
Remarks:
* | Construction work is in process at the time of Visit (labour found).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned in the approved layout plan & floor plan.
* | We have updated latest CC from Rera (On 23/07/2024).
* | As per Approved Floor Plan, In C to E wing on Ground floor Shop No. 19 & 20 are merged into single shop.
Undertaking : | [11 empty] | s
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Tanishkaa Vikrant
Layout :
Google Map :
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building
Wing A
Wing B
Wing C
Wing E
Wing D
A Wing
C Wing
B Wing
D Wing
E Wing
A Wing
B Wing
C Wing
D Wing
E Wing
C Wing
E Wing
Wing A
Wing B
Wing C
Wing D
Wing E
B
A
D

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC