## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder group |  |  |  | M/s. Kalpataru Plus Sharyans
Name of the builder company |  |  |  | M/s. Kalpataru Plus Sharyans
Name of the Project |  |  |  | Kalpataru Park Riviera
Contact Details ( Name & Contact No.) |  |  |  | Mr. Krishna Mourya 9633226152
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Miss. Suchita
Name / No of the Building |  |  |  | Wing A - Indigo Wing B - Bleu Wing C - Aqua Wing D - Azure
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | Wing A & B - P52000031831 Wing C & D - P52000027454
Project location details |  | Kalpataru Park Riviera, Final Plot No.459 & 495 and Sub Plot B, Old Mumbai-Pune Highway, Old Panvel, Panvel, Panvel, Raigad.
Final Plot No |  | 459 & 495 and Sub Plot B
Road |  | Old Mumbai-Pune Highway |  | Locality/Village |  | Old Panvel
City |  | Panvel |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Near by Landmark |  | Kalpataru Riverside CHS |  | Distance from city centre: |  | 2.5Km from Panvel Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Kalpataru Riverside CHS
West | NA | NA |  |  | Cosmo CHS
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Kalundre River
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 18.9782 |  | Longitude |  | 73.1158
Location Link |  | https://goo.gl/maps/27H7jWydMxJuPZin6?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 9255.33
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.78066
Total FSI availaible for the project |  |  |  | 1.8807
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 17406.1
Total number of Buildings |  |  |  | 4 Wings
Approval Detail : Plan approval
Layout Approval No |  | PMP/NRV/16239/J.K/2741/2022 |  |  | Dated | 2022-11-15
Approved Floor plan No. |  | PMP/NRV/16239/J.K/2741/2022 |  |  | Dated | 2022-11-15
Commencement Certificate No. Valid Up to: |  | PNP/TP/Panvel/459 & 495/21-22/16325/2741/2022 |  |  | Dated | 2022-11-15
Wing A = 2B + Gr + 1st P(pt) + 2nd P(pt) + 3rd to 13th Floor Wing B, C & D = 2B + Gr + 1st P(Pt) + 2nd P(Pt) + 3rd to 14th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 17406.1
Approved no of units |  |  | Flats - 333
Approved no of Floors |  |  | Wing A (Indigo) = 2B + Gr + 1st P(pt) + 2nd P(pt) + 3rd to 13th Floor Wing B (Bleu) = 2B + Gr + 1st P(pt) + 2nd P(pt) + 3rd to 14th Floor Wing C (Aqua) = 2B + Gr + 1st P(Pt) + 2nd P(Pt) + 3rd to 14th Floor Wing D (Azure) = 2B + Gr + 1st P(Pt) + 2nd P(Pt) + 3rd to 14th Floor
Proposed no of Floors |  |  | Wing A(Indigo) = 2B + Gr + 1st P(pt) + 2nd P(pt) + 3rd to 21st Floor Wing B (Bleu) = 2B + Gr + 1st P(pt) + 2nd P(pt) + 3rd to 21st Floor Wing C(Aqua) = 2B + Gr + 1st P(Pt) + 2nd P(Pt) + 3rd to 21st Floor Wing D(Azure) = 2B + Gr + 1st P(Pt) + 2nd P(Pt) + 3rd to 21st Floor
Expected Completion |  |  | As per RERA -31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | NA
Material laying at Site: |  |  | Cement, Sand, Steel, Etc
Construction details: |  | Wing A = B 2 + B 1 + Gr + 1st P(Pt) + 2nd P(Pt) + 3rd to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 14 Slab, Brickwork upto 13 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor, Flooring upto 10 Floor, Painting upto 2 Floor Completed
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 14 Slab, Brickwork upto 13 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor, Flooring upto 10 Floor, Painting upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 55.34% |  | 75.28% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 14 | 63.64% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 13 | 61.9% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 12 | 57.14% |  |  |  |  | Basement 1 | 15.75
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 57.14% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 47.62% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 2 | 9.524% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Wing B = B 2 + B 1 + Gr + 1st P(Pt) + 2nd P(Pt) + 3rd to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor, Flooring upto 11 Floor, Painting upto 8 Floor Completed
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 12 Floor, External Plaster upto 12 Floor, Flooring upto 11 Floor, Painting upto 8 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 59.42% |  | 77.12% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 15 | 68.18% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 14 | 66.67% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 12 | 57.14% |  |  |  |  | Basement 1 | 15.75
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 57.14% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 52.38% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 38.1% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Wing C (Aqua) = B2 + B1 + Gr + 1st P(Pt) + 2nd P(Pt) + 3rd to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 13 Floor, External Plaster upto 13 Floor, Flooring upto 11 Floor, Painting upto 10 Floor Completed
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 13 Floor, External Plaster upto 13 Floor, Flooring upto 11 Floor, Painting upto 10 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 60.73% |  | 77.6% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 15 | 68.18% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 14 | 66.67% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 61.9% |  |  |  |  | Basement 1 | 15.75
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 61.9% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 52.38% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 47.62% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Wing D (Azure) = B2 + B1 + Gr + 1st P(Pt) + 2nd P(Pt) + 3rd to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 13 Floor, External Plaster upto 13 Floor, Flooring upto 11 Floor, Painting upto 10 Floor Completed
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 13 Floor, External Plaster upto 13 Floor, Flooring upto 11 Floor, Painting upto 10 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 60.73% |  | 77.6% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 15 | 68.18% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 14 | 66.67% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 61.9% |  |  |  |  | Basement 1 | 15.75
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 61.9% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 52.38% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 47.62% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 9400
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 5,00,000/-
Distressed valuation of the Property |  |  |  |  | 7520
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Wing A - Indigo |  | 71 | 54234.6078 |  | 81351.9116
Wing B - Bleu |  | 106 | 75002.1312 |  | 112503.1967
Wing C - Aqua |  | 78 | 59077.1807 |  | 88615.771
Wing D - Azure |  | 78 | 59205.2938 |  | 88807.9407
Total |  | 333 | 247519.2133 |  | 371278.82
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Wing A - Indigo
Basement - 2 Floor for Parking
Basement - 1 Floor for Parking
Ground Floor for Parking
1st Floor Podium for Parking & Residential
1 |  | 2BHK | 761.8544 | 0 | 1142.7816 | 1st Floor Podium for Parking & Residential |  | 1.5 | 64.4942
2 |  | Parking Area
3 |  | Parking Area
4 |  | Parking Area
5 |  | 2BHK | 761.8544 | 0 | 1142.7816
6 |  | 2BHK | 687.7335 | 0 | 1031.6002 |  |  | 61.1265
2nd Floor Podium for Parking, Amenities & Residential
1 |  | 2BHK | 761.8544 | 0 | 1142.7816 | 2nd Floor Podium for Parking, Amenities & Residential
2 |  | Fitness Center
3 |  | Kids Playing Area
4 |  | Society Office
5 |  | 2BHK | 761.8544 | 0 | 1142.7816
6 |  | 2BHK | 687.7335 | 0 | 1031.6002
3rd to 7th, 9th to 12th Floor for Residential
1 |  | 2BHK | 757.5918 | 0 | 1136.3878 | 3rd to 7th, 9th to 12th Floor for Residential
2 |  | 3BHK | 942.0007 | 0 | 1413.001
3 |  | 2BHK | 707.1195 | 0 | 1060.6792
4 |  | 2BHK | 753.9213 | 0 | 1130.882 |  |  | 11407.0258
5 |  | 2BHK | 757.5811 | 0 | 1136.3716
6 |  | 2BHK | 687.7335 | 0 | 1031.6002
8th Floor (Part Refuge Area)
1 |  | 2BHK | 757.5918 | 0 | 1136.3878 | 8th Floor (Part Refuge Area)
2 |  | 3BHK | 942.0007 | 0 | 1413.001
3 |  | 2BHK | 707.1195 | 0 | 1060.6792
4 |  | 2BHK | 753.9213 | 0 | 1130.882 |  |  | 11407.0258
5 |  | 2BHK | 757.5811 | 0 | 1136.3716
6 |  | 1BHK | 521.7634 | 0 | 782.6451
13th Floor (Part Refuge Area)
1 |  | 2BHK | 757.5918 | 0 | 1136.3878 | 13th Floor (Part Refuge Area)
2 |  | 3BHK | 942.0007 | 0 | 1413.001
3 |  | 2BHK | 707.1195 | 0 | 1060.6792
4 |  | 2BHK | 753.9213 | 0 | 1130.882 |  |  | 11407.0258
5 |  | 2BHK | 757.5811 | 0 | 1136.3716
Wing B - Bleu
Basement - 2 Floor for Parking
Basement - 1 Floor for Parking
Ground Floor for Parking
1st Floor Podium for Parking & Residential
1 |  | 2BHK | 749.6911 | 0 | 1124.5366 | 1st Floor Podium for Parking & Residential
2 |  | 2BHK | 685.9897 | 0 | 1028.9846
3 |  | 2BHK | 761.8759 | 0 | 1142.8139
4 |  | Parking Area
5
6
7 |  | 2BHK | 758.3453 | 0 | 1137.518
8 |  | 2BHK | 711.931 | 0 | 1067.8964
2nd Floor Podium for Amenities & Residential
1 |  | 2BHK | 749.6911 | 0 | 1124.5366 | 2nd Floor Podium for Amenities & Residential
2 |  | 2BHK | 685.9897 | 0 | 1028.9846 |  |  | 61.6132
3 |  | 2BHK | 761.8759 | 0 | 1142.8139
4 |  | Kids Playing Area
5
6
7 |  | 2BHK | 758.3453 | 0 | 1137.518
8 |  | 2BHK | 711.931 | 0 | 1067.8964
3rd to 7th, 9th to 12th & 14th Floor for Residential
1 |  | 2BHK | 749.6911 | 0 | 1124.5366 | 3rd to 7th, 9th to 12th & 14th Floor for Residential
2 |  | 2BHK | 687.6581 | 0 | 1031.4872
3 |  | 2BHK | 757.6026 | 0 | 1136.4039
4 |  | 2BHK | 757.1398 | 0 | 1135.7096 |  |  | 11358.537
5 |  | 1BHK | 490.8169 | 0 | 736.2253
6 |  | 2BHK | 757.5918 | 0 | 1136.3878
7 |  | 2BHK | 754.072 | 0 | 1131.108
8 |  | 2BHK | 711.931 | 0 | 1067.8964
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 749.6911 | 0 | 1124.5366 | 8th & 13th Floor (Part Refuge Area)
2 |  | 1BHK | 521.9248 | 0 | 782.8872
3 |  | 2BHK | 757.6026 | 0 | 1136.4039
4 |  | 2BHK | 757.0859 | 0 | 1135.6289 |  |  | 11359.3445
5 |  | 1BHK | 490.8169 | 0 | 736.2253
6 |  | 2BHK | 757.5918 | 0 | 1136.3878
7 |  | 2BHK | 754.072 | 0 | 1131.108
8 |  | 2BHK | 711.931 | 0 | 1067.8964
Wing C - Aqua
Basement - 2 Floor for Parking
Basement - 1 Floor for Parking
Ground Floor for Parking
1st Floor Podium for Parking & Residential
1 |  | 2BHK | 743.8462 | 0 | 1115.7693 | 1st Floor Podium for Parking & Residential
2 |  | 2BHK | 687.7765 | 0 | 1031.6648
3 |  | 2BHK | 761.7468 | 0 | 1142.6201
2nd Floor Podium for Amenities & Residential
1 |  | 2BHK | 743.8462 | 0 | 1115.7693 | 2nd Floor Podium for Amenities & Residential
2 |  | 2BHK | 687.7765 | 0 | 1031.6648
3 |  | 2BHK | 761.7468 | 0 | 1142.6201
3rd to 7th, 9th to 12th & 14th Floor for Residential
1 |  | 2BHK | 740.6816 | 0 | 1111.0224 | 3rd to 7th, 9th to 12th & 14th Floor for Residential
2 |  | 2BHK | 687.7981 | 0 | 1031.6971
3 |  | 2BHK | 757.4734 | 0 | 1136.2102
4 |  | 3BHK | 941.8931 | 0 | 1412.8396 |  |  | 9130.5483
5 |  | 2BHK | 707.2379 | 0 | 1060.8568
6 |  | 2BHK | 750.1216 | 0 | 1125.1824
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 740.6816 | 0 | 1111.0224 | 8th & 13th Floor (Part Refuge Area)
2 |  | 1BHK | 521.7849 | 0 | 782.6773
3 |  | 2BHK | 757.4734 | 0 | 1136.2102
4 |  | 3BHK | 941.8931 | 0 | 1412.8396 |  |  | 9130.5483
5 |  | 2BHK | 707.2379 | 0 | 1060.8568
6 |  | 2BHK | 750.1216 | 0 | 1125.1824
Wing D - Azure
Basement - 2 Floor for Parking
Basement - 1 Floor for Parking
Ground Floor for Parking
1st Floor Podium for Parking & Residential
1 |  | 2BHK | 743.8677 | 0 | 1115.8016 | 1st Floor Podium for Parking & Residential
2 |  | 2BHK | 687.7981 | 0 | 1031.6971
3 |  | 2BHK | 761.8652 | 0 | 1142.7977
2nd Floor Podium for Amenities & Residential
1 |  | 2BHK | 743.8677 | 0 | 1115.8016 | 2nd Floor Podium for Amenities & Residential
2 |  | 2BHK | 687.7981 | 0 | 1031.6971
3 |  | 2BHK | 761.8652 | 0 | 1142.7977
3rd to 7th, 9th to 12th & 14th Floor for Residential
1 |  | 2BHK | 740.6816 | 0 | 1111.0224 | 3rd to 7th, 9th to 12th & 14th Floor for Residential
2 |  | 2BHK | 687.7335 | 0 | 1031.6002
3 |  | 2BHK | 757.5918 | 0 | 1136.3878
4 |  | 2BHK | 753.9106 | 0 | 1130.8658 |  |  | 7997.412
5 |  | 2BHK | 707.2379 | 0 | 1060.8568
6 |  | 3BHK | 948.6959 | 0 | 1423.0439 |  |  | 9065.0755
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 740.6816 | 0 | 1111.0224 | 8th & 13th Floor (Part Refuge Area)
2 |  | 1BHK | 521.7418 | 0 | 782.6128
3 |  | 2BHK | 757.5918 | 0 | 1136.3878
4 |  | 2BHK | 753.9106 | 0 | 1130.8658 |  |  | 7997.412
5 |  | 2BHK | 707.2379 | 0 | 1060.8568
6 |  | 3BHK | 948.6959 | 0 | 1423.0439 |  |  | 9065.0755
Remarks:
1. Wing A, B, C & D = Construction work was in process at the time of visit. Internal Visit was not Allowed. (Very Slow Speed) 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Utility Area + AP Area. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 7. Car parking is subjected to authentic documentation. 8. We have updated revised approved floor plan & C.C of A, B, C & D Wings (on 30/11/2022). 9. Please provide revised Approved plans & CC. 8. We have updated revised approved floor plan & C.C of A, B, C & D Wings (on 15/02/2022). 8. On Site, we meet Mr.Sudhir - 8879775998.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ravindra vishwakarma |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Kalpataru Park Riviera
Google Map :
Formulas:
Old Panvel = [Old Panvel, row above]
Wing A
Wing B
Wing D
Wing C

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Kalpataru Park Riviera | 2BHK | 646 | 969 | 9333.3333 | 9044000
99 Acres | Kalpataru Park Riviera | 3BHK | 854 | 1281 | 10070.2576 | 12900000
Magic Brick | Kalpataru Park Riviera | 2BHK | 627 | 941 | 9564.2933 | 9000000
Magic Brick | Kalpataru Riverside | 2BHK | 646 | 969 | 9287.9267 | 9000001
Magic Brick | Kalpataru Riverside | 3BHK | 711 | 1067 | 10309.2784 | 11000000
Average |  |  |  |  | 9713.0179
Valuation Adopted