## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 09/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-08
Name of the builder |  |  |  | Mr. Pravin Satra
Name of the builder company |  |  |  | M/s. Darshan Developers
Old Name of the Project |  |  |  | Phoenix Tower |  |  |  |  | Phoenix Tower (Paton Towers)
New Name of the Project |  |  |  | Paton Towers
Contact Details ( Name & Contact No.) |  |  |  | 2226630527
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Ms.Sejal 9867264934 |  |  |  | Mr. Ashok 9920374514
Name / No of the Building |  |  |  | Sale Building (A, B & C Wing)
Docouments Provided |  |  |  | Approved Plans, CC, Cost sheet
RERA No. |  |  |  | P51800024618
Project location details |  | Phoenix Tower is Proposed Slum redevelopment of plot bearing CTS no. 163A/2 of village Akurli, Kandiavli East, Mumbai.
CTS No |  | 163A/2 Part
Road |  | Akurli Road |  | Locality/Village |  | Akurli |  | 518
City |  | Kandavli East |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400101
Nearby Landmark |  | Godrej Nest |  | Distance from city centre: |  | 2.9 Km from Kandavli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Slum Area
West | NA | NA |  |  | Akurli Cross Road
North | NA | NA |  |  | SRA Building
South | NA | NA |  |  | Godrej Nest
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.1972 |  | Longitude |  | 72.8679
Location Link : |  | https://maps.app.goo.gl/457xLoCManfUY45L6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4299.52
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.9652
Total FSI availaible for the project |  |  |  | 3.0652
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 13178.79
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Layout Approval No |  | RS/MHADA/0010/20060321/AP/S |  |  | Dated | 2019-11-21
Approved Floor plan No. |  | RS/MHADA/0010/20060321/AP/S |  |  | Dated | 2019-11-21
Commencement Certificate No. |  | RS/MHADA/0010/20060321/AP/S |  |  | Dated | 2021-10-13
Valid Up to: Plinth
Commencement Certificate No. |  | RS/MHADA/0010/20060321/AP/S |  |  | Dated | 2023-01-05
This part further C.C. is extended upto 10th floor (excluding portion A-B-C-D-E-F-A as marked on plan at pg.503) for sale building as per approved plans dated 21/11/2019.
Commencement Certificate No. |  | RS/MHADA/0010/20060321/AP/S |  |  | Dated | 2023-11-10
This C.C is further granted to entire work up to 11th floor and RCC work for 12th and 13th floor including portion ABCDEFA for sale building as per-approval-plan dated 21/11/2019.
Commencement Certificate No. |  | RS/MHADA/0010/20060321/AP/S |  |  | Dated | 2024-03-21
Valid Up to: This C.C is further extended for the RCC work of 14th te 17th floor for the sale building u/ref as per the appreved plan dated 21/11/2019.
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 13178.79
Approved no of units |  |  | Flats - 521, Shops - 13
Approved no of Floors |  |  | G + 1st to 23rd Floor
Proposed no of Floors |  |  | A, B & C = G + 1st to 23rd Floor
Expected Completion |  |  | As per RERA - 30/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A & B = G + 1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 23 Slab, Brickwork upto 20 Floor, Internal Plaster upto 11 Floor, External Plaster upto 11 Floor, Flooring upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 23 Slab, Brickwork upto 20 Floor, Internal Plaster upto 11 Floor, External Plaster upto 11 Floor, Flooring upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 64.09% |  | 83.32% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 23 | 95.83% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 20 | 86.96% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 47.83% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 47.83% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 8.696% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | C = G + 1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 23 Slab, Brickwork upto 20 Floor, Internal Plaster upto 11 Floor, External Plaster upto 11 Floor, Flooring upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 23 Slab, Brickwork upto 20 Floor, Internal Plaster upto 11 Floor, External Plaster upto 11 Floor, Flooring upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 64.09% |  | 83.32% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 23 | 95.83% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 20 | 86.96% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 47.83% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 47.83% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 8.696% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 13600
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 31000
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 7,00,000/-
Distressed valuation of the Property |  |  |  |  | 10880
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 5 |  | 1642.3065 |  | 2627.6905
B Wing |  | 4 |  | 1455.5942 |  | 2328.9507
C Wing |  | 4 |  | 1402.1122 |  | 2243.3795
Total |  | 13 |  | 4500.0129 |  | 7200.0207
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 167 |  | 53842.1738 |  | 83455.3695
B Wing |  | 164 |  | 52870.1846 |  | 81948.7862
C Wing |  | 166 |  | 53515.1635 |  | 82948.5035
Total |  | 497 |  | 160227.522 |  | 248352.6591
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
A Wing
Ground Floor
1 |  | Shop | 381.0456 | 0 | 609.673 | Ground Floor
2 |  | Shop | 266.7319 | 0 | 426.7711 | Ground Floor
3 |  | Shop | 266.7319 | 0 | 426.7711 | Ground Floor
4 |  | Shop | 381.0456 | 0 | 609.673 | Ground Floor
5 |  | Shop | 346.7515 | 0 | 554.8024 | Ground Floor
B Wing
Ground Floor
6 |  | Shop | 381.0456 | 0 | 609.673 | Ground Floor |  | 31246.2603
7 |  | Shop | 346.7515 | 0 | 554.8024 | Ground Floor
8 |  | Shop | 381.0456 | 0 | 609.673 | Ground Floor
9 |  | Shop | 346.7515 | 0 | 554.8024 | Ground Floor
C Wing
Ground Floor
10 |  | Shop | 381.0456 | 0 | 609.673 | Ground Floor
11 |  | Shop | 346.7515 | 0 | 554.8024 | Ground Floor
12 |  | Shop | 381.0456 | 0 | 609.673 | Ground Floor
13 |  | Shop | 293.2695 | 0 | 469.2312 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
A Wing
1st Floor For Residential & Fitness center
1 | 1 | 1BHK | 322.4894 | 0 | 499.8586 | 1st Floor For Residential & Fitness center |  | 13569.8367
2 | 2 | 1BHK | 322.4894 | 0 | 499.8586 | 1st Floor For Residential & Fitness center
3 | 3 | 1BHK | 322.4894 | 0 | 499.8586 | 1st Floor For Residential & Fitness center
2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
1 | 1 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
2 | 2 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor |  |  | 152
3 | 3 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
4 | 4 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
5 | 5 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
22 | 6 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
23 | 7 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
24 | 8 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
8th & 15th Floor (Part Refuge Area)
1 | 1 | 1BHK | 322.4894 | 0 | 499.8586 | 8th & 15th Floor (Part Refuge Area)
2 | 2 | 1BHK | 322.4894 | 0 | 499.8586 | 8th & 15th Floor (Part Refuge Area)
3 | 3 | Refuge Area |  |  |  | 8th & 15th Floor (Part Refuge Area) |  |  | 12
4 | 4 |  |  |  |  | 8th & 15th Floor (Part Refuge Area)
5 | 5 | 1BHK | 322.4894 | 0 | 499.8586 | 8th & 15th Floor (Part Refuge Area)
22 | 6 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
23 | 7 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
24 | 8 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
B Wing
1st Floor For Fitness center
4 | 1 | Fitness center |  |  |  | 1st Floor For Fitness center
5 | 2 |  |  |  |  | 1st Floor For Fitness center
2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
6 | 1 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
7 | 2 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
8 | 3 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
9 | 4 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
18 | 5 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor |  |  | 152
19 | 6 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
20 | 7 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
21 | 8 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
8th & 15th Floor (Part Refuge Area)
6 | 1 | 1BHK | 322.4894 | 0 | 499.8586 | 8th & 15th Floor (Part Refuge Area)
7 | 2 | Refuge Area |  |  |  | 8th & 15th Floor (Part Refuge Area)
8 | 3 |  |  |  |  | 8th & 15th Floor (Part Refuge Area)
9 | 4 | 1BHK | 322.4894 | 0 | 499.8586 | 8th & 15th Floor (Part Refuge Area)
18 | 5 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
19 | 6 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area) |  |  | 12
20 | 7 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
21 | 8 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
C Wing
1st Floor For Residential & Fitness center
6 | 1 | 1BHK | 322.4894 | 0 | 499.8586 | 1st Floor For Residential & Fitness center
7 | 2 | 1BHK | 322.4894 | 0 | 499.8586 | 1st Floor For Residential & Fitness center |  |  | 2
2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
10 | 1 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
11 | 2 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
12 | 3 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
13 | 4 | 1BHK | 322.4894 | 0 | 499.8586 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor |  |  | 152
14 | 5 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
15 | 6 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
16 | 7 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
17 | 8 | 1BHK | 322.2742 | 0 | 499.5249 | 2nd to 7th, 9th to 14th, 16th to 21st & 23rd Floor
8th & 15th Floor (Part Refuge Area)
10 | 1 | 1BHK | 322.4894 | 0 | 499.8586 | 8th & 15th Floor (Part Refuge Area)
11 | 2 | Refuge Area |  |  |  | 8th & 15th Floor (Part Refuge Area)
12 | 3 |  |  |  |  | 8th & 15th Floor (Part Refuge Area) |  |  | 12
13 | 4 | 1BHK | 322.4894 | 0 | 499.8586 | 8th & 15th Floor (Part Refuge Area)
14 | 5 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
15 | 6 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
16 | 7 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
17 | 8 | 1BHK | 322.2742 | 0 | 499.5249 | 8th & 15th Floor (Part Refuge Area)
Remarks:
1 | Construction work is in process at the time of Visit. Internal visit was not allowed.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet.
6 | We have considered rate by verifying it from market inquire.
7 | Car parking is subjected to authentic documentation.
8 | We have received all no. of Plans but in all plans 22nd Floor is not printed anywhere. So, Please provide 22nd Floor Plan.
9 | Name of the project Phoenix Tower's name has been changed to Paton Towers as per the rera.
10 | We have updated revised approved CC from RERA site on 11/07/2024.
11 | Construction work goes beyond permissible floor. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Rahul Salve |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Paton Towers
Google Map :
Formulas:
Mumbai = [Mumbai, row above]
Wing A
Wing B
Wing C
C wing
B wing
A wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 1bhk | 322 | 515.2 | 21933.2298 | 11300000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted