## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/07/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-07-10
Name of the builder group |  |  |  | Yashodeep Buildcon
Name of the builder company |  |  |  | Yashodeep Buildcon
Name of the Project |  |  |  | Siddhivinayak Sankalp
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Raju Kamath 9769830555
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Rohit : 8879538994
Name / No of the Building |  |  |  | Wing A & B
Name / No of the Existing Building |  |  |  | NA | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area & Cost Sheet. | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000052663 | [7 empty] | #N/A | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Siddhivinayak Sankalp, Survey No.32/11, near Siddhivinayak Garima, Internal Road, Ghotkamp Koyana Vele, Koynavele, Taloja East, Panvel, Raigad - 410208. | [10 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 32/11 | [10 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Ghotkamp Koyana Vele | [10 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Koynavele | [6 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Taloja East |  | District |  | Raigad | [6 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410208 | [9 empty] | Mahad | Daund
Nearby Landmark |  | Siddhivinayak Garima |  | Distance from city centre: |  | 3.10KM from Taloja Metro Station | [9 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [11 empty] | Mangaon | Ambegaon
[16 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [11 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [11 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [11 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Open Plot
West | NA | Survey No. 32/10 & 32/11 |  |  | Siddivinayak Darshan/Siddhivinayak Homes
North | NA | Other Plot |  |  | Open Plot
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.079334,73.112814
Location Link |  | https://maps.app.goo.gl/mNnMjHewBmYWCkHb6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 6680
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.4506
Total FSI availaible for the project |  |  |  | 2.5506
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 17038.141
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation
Layout Approval No |  | PMP/NRV/16639/J.K.918/2023 |  |  | Dated | 2023-03-31
Approved Floor plan No. |  | PMP/NRV/16639/J.K.918/2023 |  |  | Dated | 2023-03-31
Commencement-CC No |  | PMC/TP/Koynavele/32/11/21-23/ 16639/918/2023 |  |  | Dated | 2023-03-31
Valid Up to: |  | Gr + 1st to 15th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 17038.141
Approved no of units |  |  | Flats - 251
Approved no of Floors |  |  | Wing A & B = Gr + 1st to 15th Floor
Proposed no of Floors |  |  | Wing A & B = Gr + 1st to 15th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gym, Multipurpose Hall, Landscaped Garden, Decorative Entrance, Vitrified tiles flooring, Granite Kitchen Platform & etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Gr + 1st to 15th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8 Floor, External Plaster upto 4 Floor Completed | , RCC upto 14 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8 Floor, External Plaster upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8 Floor, External Plaster upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 57.17% |  | 78.92% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 14 | 87.5% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 11 | 73.33% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 8 | 53.33% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 26.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | Wing B = Gr + 1st to 15th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8 Floor, External Plaster upto 4 Floor Completed | , RCC upto 14 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8 Floor, External Plaster upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 14 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8 Floor, External Plaster upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 57.17% |  | 78.92% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 14 | 87.5% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 11 | 73.33% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 8 | 53.33% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 26.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4800 |  |  | 4500 to 4800 | Sanjay Verbal 30/08/2024
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development + Club House Charges |  |  |  |  | 175000
Legal Charges
Gas Connection Charges
Grill Charges |  |  |  |  | 50000 |  |  | 170000
Society Formation & Water Charges |  |  |  |  | 50000
Advance Maintenance Charges |  |  |  |  | 30000
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 3840
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 118 |  | 66222.7114 |  | 115670
Wing B |  | 133 |  | 61876.9347 |  | 107870
Grand Total |  | 251 |  | 128099.6461 |  | 223540
Building details Floor Wise
Details of Residential in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No. 1
Wing A
Ground Floor For Meter Room, Society Office & Parking
1st to 6th, 8th to 11th & 13th to 15th Floor For Residential
101 ,.., 1501 |  | 1BHK | 432.3361 | 0 | 750 | 1st to 6th, 8th to 11th & 13th to 15th Floor For Residential |  |  | 750 | 1.7348
102 ,.., 1502 |  | 2BHK | 603.2011 | 0 | 1055 |  |  |  | 1055 | 1.749
103 ,.., 1503 |  | 2BHK | 603.2011 | 0 | 1055 |  |  |  | 1055 | 1.749
104 ,.., 1504 |  | 2BHK | 604.2102 | 0 | 1055 |  |  |  | 1055 | 1.7461
105 ,.., 1505 |  | 2BHK | 603.2011 | 0 | 1055 |  |  |  | 1055 | 1.749
106 ,.., 1506 |  | 2BHK | 603.2011 | 0 | 1055 |  |  |  | 1055 | 1.749
107 ,.., 1507 |  | 2BHK | 596.9042 | 0 | 1045 |  |  |  | 1045 | 1.7507
108 ,.., 1508 |  | 1BHK | 425.2991 | 0 | 740 |  |  |  | 740 | 1.74
7th & 12th Floor (Part Refuge Area) | [10 empty] | 4500
701 & 1201 |  | 1BHK | 432.3361 | 0 | 750 | 7th & 12th Floor (Part Refuge Area) |  |  | 4800 | 537466.6667 | 3375000 | 4075000
702 & 1202 |  | 2BHK | 603.2011 | 0 | 1055 |  |  |  | 4265.4028 |  | 4747500 | 5447500
703 & 1203 |  | 2BHK | 603.2011 | 0 | 1055 |  |  |  | 4265.4028 |  | 4747500 | 5447500
704 & 1204 |  | 2BHK | 604.2102 | 0 | 1055 |  |  |  | 4265.4028 |  | 4747500 | 5447500
705 & 1205 |  | 2BHK | 603.2011 | 0 | 1055 |  |  |  | 4265.4028 |  | 4747500 | 5447500
706 & 1206 |  | 2BHK | 603.2011 | 0 | 1055 |  |  |  | 4265.4028 |  | 4747500 | 5447500
707 & 1207 |  | 2BHK | 596.9042 | 0 | 1045 |  |  |  | 4306.2201 | 5250.7177 | 4702500 | 5402500
708 & 1208 |  | Refuge Area
Wing B
Ground Floor For Meter Room, Drivers Room & Parking
1st to 6th, 8th to 11th & 13th to 15th Floor For Residential
101 ,.., 1501 |  | 1BHK | 431.4749 | 0 | 750 | 1st to 6th, 8th to 11th & 13th to 15th Floor For Residential |  |  | 750 | 1.7382
102 ,.., 1502 |  | 1BHK | 431.4749 | 0 | 750 |  |  |  | 750 | 1.7382
103 ,.., 1503 |  | 1BHK | 426.4159 | 0 | 740 |  |  |  | 740 | 1.7354
104 ,.., 1504 |  | 1BHK | 424.8685 | 0 | 740 |  |  |  | 740 | 1.7417
105 ,.., 1505 |  | 1BHK | 424.8685 | 0 | 740 |  |  |  | 740 | 1.7417
106 ,.., 1506 |  | 1BHK | 424.3303 | 0 | 740 |  |  |  | 740 | 1.7439
107 ,.., 1507 |  | 2BHK | 596.9042 | 0 | 1045 |  |  |  | 1045 | 1.7507
108 ,.., 1508 |  | 2BHK | 596.9042 | 0 | 1045 |  |  |  | 1045 | 1.7507
109 ,.., 1509 |  | 1BHK | 424.3303 | 0 | 740 |  |  | 4864.8649 | 740 | 1.7439
7th & 12th Floor (Part Refuge Area)
701 & 1201 |  | 1BHK | 431.4749 | 0 | 750 | 7th & 12th Floor (Part Refuge Area) |  |  | 4800
702 & 1202 |  | 1BHK | 431.4749 | 0 | 750 |  |  |  | 4800
703 & 1203 |  | 1BHK | 426.4159 | 0 | 740 |  |  |  | 4864.8649
704 & 1204 |  | 1BHK | 426.4159 | 0 | 740 |  |  |  | 4864.8649
705 & 1205 |  | Refuge Area
706 & 1206 |  | 1BHK | 424.3303 | 0 | 740 |  |  |  | 4864.8649
707 & 1207 |  | 2BHK | 596.9042 | 0 | 1045 |  |  |  | 4306.2201
708 & 1208 |  | 2BHK | 596.9042 | 0 | 1045 |  |  |  | 4306.2201
709 & 1209 |  | 1BHK | 424.3303 | 0 | 740 |  |  |  | 4864.8649
Remarks:
* | Construction work is in process at the time of Visit (Internal visit not allowed).
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Open Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates/Other Charges of the Property have been revised on 30/08/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Siddhivinayak Sankalp
Layout :
Google Map :
Formulas:
Koynavele = [Koynavele, row above]
WING A
WING B
A Wing
A Wing
A Wing
B Wing
B Wing
B Wing
A Wing
A Wing
A Wing
A Wing
B Wing
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC