## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-09
Name of the builder |  |  |  | Mr. Sangram Vilasrao Patil
Name of the builder company |  |  |  | Tejas Enterprises
Name of the Project |  |  |  | Tejas Neelkamal
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Ajay Sable 8369500049
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Rohit : 9320502234
Name / No of the Building |  |  |  | Wing A & B
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet, Builder Saleable Area
RERA No. |  |  |  | P52000050567
Project location details |  | Tejas Neelkamal, Gut No.116/2, 151/3, 151/4, near Nirmal Ganesh Building, Internal Road, Kolkhe, Deravali, Somatane West, Panvel, Raigad - 410221.
Gut No |  | 116/2, 151/3, 151/4
Locality |  | Kolkhe
Road |  | Internal Road |  | Locality/Village |  | Deravali
City |  | Somatane West |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410221
Nearby Landmark |  | Nirmal Ganesh Building |  | Distance from city centre: |  | 0.9 KM from Somatne Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 18.9587332, 73.1429221
Location Link |  | https://goo.gl/maps/6KELzWGXZMLjEvxt9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2793.471
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.096592
Total FSI availaible for the project |  |  |  | 1.0966
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 3063.299
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | CIDCO-NAINA
Layout Approval No |  | CIDCO/NAINA/Panvel/Derwali/ BP00584/ACC/2023/0342 |  |  | Dated | 2023-03-08
Approved Floor plan No. |  | CIDCO/NAINA/Panvel/Derwali/ BP00584/ACC/2023/0342 |  |  | Dated | 2023-03-08
Commencement-CC No Valid Up to: |  | CIDCO/NAINA/Panvel/Derwali/ BP00584/ACC/2023/0342 |  |  | Dated | 2023-03-08
Wing A & B = Gr/St + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 3063.299
Approved no of units |  |  | Flats - 56, Shops - 21
Approved no of Floors |  |  | Wing A & B = Gr/Stilt + 1st to 4th Floor
Proposed no of Floors |  |  | Wing A = Gr/Stilt + 1st to 4th Floor
Wing B = Gr/Stilt + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Fitness Centre, Children's Play Area, Indoor Games
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Gr/Stilt + 1st to 4th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab, Brickwork upto 1 Floor Completed | , RCC upto 4 Slab, Brickwork upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab, Brickwork upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 43.88% |  | 70.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 4 | 80% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 1 | 25% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Wing B = Gr/Stilt + 1st to 4th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 3 Slab, Brickwork upto 1 Floor Completed | , RCC upto 3 Slab, Brickwork upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 3 Slab, Brickwork upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 35.88% |  | 64.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 3 | 60% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 1 | 25% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Part II = Wing B = Gr/Stilt + 1st to 4th Floor | [5 empty] | Excavation Completed, Plinth work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation | , Plinth work is process
Stage of construction: |  | Excavation Completed, Plinth work is process | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 2
Plinth |  | 3 | 75% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Average Progress % |  | 21.69% |  | Average Disbursement % |  | 51.5%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  | Cost Sheet | Inspection | MIS | Online
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4800 |  |  | 4751.5568 | 5300 | 4250 | 4500 | 4956.2273
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 10000 |  |  |  | 10000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 175000 | [5 empty] | 5300
Club Charges
Grill & Legal Charges |  |  |  |  | 50000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Charges |  |  |  |  | 75000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 250000
Distressed valuation of the Property |  |  |  |  | 3840
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
(Wing A + B) Shops |  | 21 |  | 2143.5214 |  | 4318
Total |  | 21 |  | 2143.5214 |  | 4318
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 28 |  | 11151.8834 |  | 18232
Wing B |  | 28 |  | 11162.0312 |  | 18232
Total |  | 56 |  | 22313.9146 |  | 36464
Grand Total |  | 77 |  | 24457.4361 |  | 40782
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable area | Floor
Wing A + B
Ground Floor for Commercial & Parking
1 |  | Shop | 107.5324 | 0 | 215 | Ground Floor for Commercial & Parking |  | 9.99
2 |  | Shop | 107.5324 | 0 | 215
3 |  | Shop | 101.9136 | 0 | 205
4 |  | Shop | 101.9136 | 0 | 205
5 |  | Shop | 101.9136 | 0 | 205
6 |  | Shop | 101.9136 | 0 | 205
7 |  | Shop | 100.4066 | 0 | 205
8 |  | Shop | 100.4066 | 0 | 205
9 |  | Shop | 101.9136 | 0 | 205
10 |  | Shop | 101.9136 | 0 | 205
11 |  | Shop | 101.9136 | 0 | 205
12 |  | Shop | 101.9136 | 0 | 205
13 |  | Shop | 100.4066 | 0 | 205
14 |  | Shop | 100.4066 | 0 | 205
15 |  | Shop | 101.9136 | 0 | 205
16 |  | Shop | 101.9136 | 0 | 205
17 |  | Shop | 101.9136 | 0 | 205
18 |  | Shop | 101.9136 | 0 | 205
19 |  | Shop | 107.5324 | 0 | 215
20 |  | Shop | 107.5324 | 0 | 215
21 |  | Shop | 88.803 | 0 | 178 |  |  | 8.25
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Wing A
Ground Floor for Commercial, Dirvers Room, Meter Room & Parking
1st Floor for Residential
1 |  | 1BHK | 391.9388 | 0 | 637 | 1st Floor for Residential |  | 28.7225 | 6.42 |  | 637 | 1.6253
2 |  | 1BHK | 387.4825 | 0 | 630 | [5 empty] | 630 | 1.6259
3 |  | 1BHK | 407.4174 | 43.9978 | 714 |  |  |  |  | 4925.3573 | 714 | 1.7525
4 |  | 1BHK | 400.1275 | 43.9978 | 685 |  |  |  |  | 5148.1887 | 685 | 1.712
5 |  | 1BHK | 400.1275 | 43.9978 | 685 |  |  |  |  | 5148.1887 | 685 | 1.712
6 |  | 1BHK | 398.19 | 9.3647 | 650 | [5 empty] | 650 | 1.6324
7 |  | 1BHK | 399.4359 | 0 | 650 | [5 empty] | 650 | 1.6273
2nd to 4th Floor | [11 empty] | #DIV/0!
201 to 401 |  | 1BHK | 391.9388 | 0 | 637 | 2nd to 4th Floor |  |  |  |  | 637 | 1.6253
202 to 402 |  | 1BHK | 387.4825 | 0 | 630 | [5 empty] | 630 | 1.6259
203 to 403 |  | 1BHK | 415.6276 | 0 | 675 |  |  |  |  | 4603.1746 | 675 | 1.624
204 to 404 |  | 1BHK | 398.19 | 0 | 645 | [5 empty] | 645 | 1.6198
205 to 405 |  | 1BHK | 398.19 | 0 | 645 | [5 empty] | 645 | 1.6198
206 to 406 |  | 1BHK | 398.19 | 0 | 645 | [5 empty] | 645 | 1.6198
207 to 407 |  | 1BHK | 399.4359 | 0 | 650 | [5 empty] | 650 | 1.6273
Wing B | [11 empty] | #DIV/0!
Ground Floor for Commercial & Parking
1st Floor for Residential
1 |  | 1BHK | 391.9388 | 0 | 637 | 1st Floor for Residential
2 |  | 1BHK | 387.4825 | 0 | 630
3 |  | 1BHK | 417.5652 | 43.9978 | 714
4 |  | 1BHK | 400.1275 | 43.9978 | 685
5 |  | 1BHK | 400.1275 | 43.9978 | 685
6 |  | 1BHK | 398.19 | 9.3647 | 650
7 |  | 1BHK | 399.4359 | 0 | 650
2nd to 4th Floor
201 to 401 |  | 1BHK | 391.9388 | 0 | 637 | 2nd to 4th Floor
202 to 402 |  | 1BHK | 387.4825 | 0 | 630
203 to 403 |  | 1BHK | 415.6276 | 0 | 675
204 to 404 |  | 1BHK | 398.19 | 0 | 645 |  |  |  | 5116.2791
205 to 405 |  | 1BHK | 398.19 | 0 | 645
206 to 406 |  | 1BHK | 398.19 | 0 | 645
207 to 407 |  | 1BHK | 399.4359 | 0 | 650
2nd Floor
201 |  |  |  | 0 | #REF! | 2nd Floor
202 |  |  |  | 0 | #REF! | 2nd Floor
203 |  |  |  | 0 | #REF! | 2nd Floor
204 |  |  |  | 0 | #REF! | 2nd Floor
205 |  |  |  | 0 | #REF! | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 4th Floor
201 to 401 |  |  |  | 0 | #REF! | 2nd to 4th Floor
202 to 402 |  |  |  | 0 | #REF! | 2nd to 4th Floor
203 to 403 |  |  |  | 0 | #REF! | 2nd to 4th Floor
204 to 404 |  |  |  | 0 | #REF! | 2nd to 4th Floor
205 to 405 |  |  |  | 0 | #REF! | 2nd to 4th Floor
206 to 406 |  |  |  | 0 | #REF! | 2nd to 4th Floor
207 to 407 |  |  |  | 0 | #REF! | 2nd to 4th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | #REF! | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | #REF! | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | #REF! | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | #REF! | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | #REF! | 2nd & 5th Floor
Remarks:
* | Construction work is in process at the time of Visit.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Open Balcony + Covered Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ravindra |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Tejas Neelkamal
Layout :
Google Map :
Formulas:
Deravali = [Deravali, row above]
Wing A
Wing B
A Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted