## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 15/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-10
Name of the builder group |  |  |  |  | M/s. Xrbia Developers Ltd
Name of the builder company |  |  |  |  | M/s. Xrbia Developers Ltd
Name of the Project |  |  |  |  | Xrbia Vangani Phase III
Name of the Buildings |  |  |  |  | Building Type - F2 to F5, G1 to G7, J1 to J6
Contect Details ( Name & Contect No.) |  |  |  |  | 8291825134, 8291983882
RERA No. |  |  |  |  | P52000012385
Project location details |  | Xrbia Vangani Phase III, Proposed Revised Building Permission For Residential Purpose On Land Bearing S. No.- 24,/1, 24/3, 24/4, 24/11 to 24/13, 25/3B, Of Village - Khadyachapada (Pashane), Next To Pashane Village, Aarde Village Road, Tal.- Karjat, Dist.- Raigad 410101
S No | 24,/1, 24/3, 24/4, 24/11 to 24/13, 25/3B |  |  |  |  | Locality | Khadyachapada (Pasane), Vangani (East)
Road | Aarde Village Road |  |  |  | District | Raigad
City | Vangani |  |  |  | Pin Code | 410101
Near by Landmark |  | Aamantran Farms |  |  | Distance from city centre: |  | About 4.7Km Distance From Vangani Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Road |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.100592,73.3348381
Location Link |  | https://goo.gl/maps/EU3A6xoXvJ5JMurt5
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 94810
Permissible FSI |  |  |  |  | (94,810.00 * 0.90) * 1.10
Permissible TDR/Paid FSI |  |  |  |  | 17065.8
Total FSI availaible for the project |  |  |  |  | -
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 94464.56
Total number of Buildings |  |  |  |  | 17 Buildings
Approval Detail : Plan approval
Layout Approval No |  | SSNR/RA/BP/Village - Khadyachapada (Pasane)/Tal - Karjat/S.no.24/1 & Other/470 |  |  |  | Dated | 08/03/2019.
Building plan approval No |  | SSNR/RA/BP/Village - Khadyachapada (Pasane)/Tal - Karjat/S.no.24/1 & Other/470 |  |  |  | Dated | 08/03/2019.
C.certificate No |  | SSNR/RA/BP/Village - Khadyachapada (Pasane)/Tal - Karjat/S.no.24/1 & Other/470 |  |  |  | Dated | 08/03/2019.
Valid Up to: Building Type - F2 to F5, G1 to G6 & J1 to J4 & J6 - Ground + 1st to 7th Floor Building Type J5 - Ground + 1st to 8th Floor. Building Type G7 - Ground + 1st to 10th Floor
O. Certificate No.: |  |  |  |  | Date of approval: |  |  | Expiry date: NA
Commencement date of construction |  |  | 2019-03-08 |  | Expected Completion |  | 2025-03-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 94464.56 |  | Approved no of units residential |  |  | NA
Approved no of Floors |  | Building Type - F2 to F5, G1 to G6 & J1 to J4 & J6 - Ground + 1st to 7th Floor Building Type J5 - Ground + 1st to 8th Floor. Building Type G7 - Ground + 1st to 10th Floor
Quality of construction: Good |  |  |  |  | Projected life: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Building Type F2 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 52.14% |  | 76.43% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 2 | 28.57% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - F3 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 53.21% |  | 77.14% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 3 | 42.86% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - F4 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 36.07% |  | 64.46% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 5 | 62.5% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 1 | 14.29% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - F5 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 42.14% |  | 68.93% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 6 | 75% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 2 | 28.57% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - G1 = G + 1st to 7th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - G2 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 65% |  | 85% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - G3 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 55.36% |  | 78.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 5 | 71.43% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - G4 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 53.21% |  | 77.14% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 3 | 42.86% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - G5 & G6 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 71.07% |  | 87.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - G7 = G + 1st to 10th Floor | [6 empty] | Excavation work Completed. Plinth work is process
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 10
Stage of construction: |  | Excavation work Completed. Plinth work is process | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2.5
Excavation |  | 10 | 100% |  | 7.5% |  | 38.75% |  | Excavation in process | 5
Plinth |  | 7.5 | 75% | [5 empty] | Excavation Completed | 10
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 2.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 7.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 10
Construction details: |  | Building Type - J1 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Footing work is process
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Footing work is process | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 2.5% |  | 26.25% |  | Excavation in process | 3.5
Plinth |  | 1.75 | 25% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - J2, J3, J4 & J6 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 72.14% |  | 88.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type - J5 = G + 1st to 8th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 8
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% |  | 57.5% |  | 80% |  | Excavation in process | 4
Plinth |  | 8 | 100% | [5 empty] | Excavation Completed | 8
RCC (Including podiums) |  | 9 | 100% | [5 empty] | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 8 | 100% | [5 empty] | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 6
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 8
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (as per Builder Carpet Area)
1RK |  | 1 BHK Comfort |  | 2 BHK Smart |  |  | 2 BHK Comfort
CLP Scheme | ADF Scheme | CLP Scheme | ADF Scheme | CLP Scheme | ADF Scheme |  | CLP Scheme | ADF Scheme
4157/- | 4888/- | 4590/- | 5378/- | 4650/- | 5378/- |  | 4748/- | 5524/-
Floor rise rate Per Sq. Ft. on RERA Carpet Area | [5 empty] | 25/- per sq.ft. from 4th floor/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 3326
Remarks: 1. Construction Work Stopped at the time of visit. Type F2 to F4, G3 to G6, J3, J5 & J6 = Work same as last visit (25/06/2021). Internal visit not allowed. Type F5, G1, G2, G7, J1, J2 & J4 = Work same as visit (15/01/2021). Internal visit not allowed. 2. We have given rate verify by market inquire. 3. We have considered Other charges from cost sheet. 4. According to our observations, the construction of Xrbia projects (Xrbia Warai, Xrbia Vangani, etc.) appears to have slowed or stopped over the past two years. 5. Construction work stopped. Internal Visit was not allowed. 6. The project has received first CC on 08/03/2019, But construction work of Xrbia Vangani Phase III is Under Construction. 7. As per site visit dated 07/10/2024, We have observed Notice Banner attached to the project compound wall. We have attached photo of the Notice banner below. Please check subject of the notice from your end. 8. As per RERA, completion period of project is expired on 30/03/2025 but still project is under construction. 9. As checked on RERA portal on date 15/07/2025, we have observed that above project "Xrbia Vangani Phase 3" is kept under abeyance. Please check from your end.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Xrbia Vangani Phase III
F2 to F5, G1 to G7, J1 to J6
Notice :
Google Map :
G4
G5
G6
G7
J1
J2
J3
J4
J5
J6

## F2
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 2 | 28.57% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 4.2857 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 4.2857 | 0 | 0 | 0 | 0
Bricks | 4.2857 | 4.2857
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 54.29% | 64.29% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## F3
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 3 | 42.86% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 6.4286 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 6.4286 | 0 | 0 | 0 | 0
Bricks | 6.4286 | 6.4286
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 56.43% | 66.43% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## F4
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 4 | 50% |  | Parking |  | Rate
Bricks | 7 | 1 | 14.29% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 20 | 2.1429 | 0 | 0 | 0 | 0
RCC | 20 | 15 |  | Recommended |  | 30 | 15 | 2.1429 | 0 | 0 | 0 | 0
Bricks | 2.1429 | 2.1429
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 32.14% | 47.14% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## F5
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 6 | 75% |  | Parking |  | Rate
Bricks | 7 | 2 | 28.57% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 30 | 4.2857 | 0 | 0 | 0 | 0
RCC | 30 | 22.5 |  | Recommended |  | 30 | 22.5 | 4.2857 | 0 | 0 | 0 | 0
Bricks | 4.2857 | 4.2857
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 44.29% | 56.79% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## G1
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 1 | 10%
slab | 8 | 0 | 0% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 1 | 21 |  | Progress |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 21 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 1% | 21% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## G2
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 7 | 100% |  | Palghar |  | 100000/-
plaster | 7 | 3.5 | 50% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 5 | 5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 70% | 80% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## G3
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 5 | 71.43% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 10.7143 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 10.7143 | 0 | 0 | 0 | 0
Bricks | 10.7143 | 10.7143
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 60.71% | 70.71% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## G4
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 3 | 42.86% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 6.4286 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 6.4286 | 0 | 0 | 0 | 0
Bricks | 6.4286 | 6.4286
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 56.43% | 66.43% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## G5
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 7 | 100% |  | Palghar |  | 100000/-
plaster | 7 | 7 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 75% | 85% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## G6
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 5 | 71.43% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 10.7143 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 10.7143 | 0 | 0 | 0 | 0
Bricks | 10.7143 | 10.7143
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 60.71% | 70.71% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## G7
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 10
Particulars | total floor | 10
plinth | 10 | 5 | 50%
slab | 11 | 0 | 0% |  | Parking |  | Rate
Bricks | 10 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 10 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 10 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 10 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 10 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 5 | 25 |  | Progress |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 25 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 5% | 25% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## J1
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 3 | 30%
slab | 8 | 0 | 0% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 3 | 23 |  | Progress |  | 3 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 23 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 3% | 23% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## J2&J
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 7 | 100% |  | Palghar |  | 100000/-
plaster | 7 | 7 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 75% | 85% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## J3&J6
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 7 | 100% |  | Palghar |  | 100000/-
plaster | 7 | 7 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 75% | 85% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## J4
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 6 | 85.71% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 12.8571 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 12.8571 | 0 | 0 | 0 | 0
Bricks | 12.8571 | 12.8571
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 62.86% | 72.86% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## J5
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 8
Particulars | total floor | 8
plinth | 10 | 10 | 100%
slab | 9 | 9 | 100% |  | Parking |  | Rate
Bricks | 8 | 8 | 100% |  | Palghar |  | 100000/-
plaster | 8 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 8 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 8 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 8 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 65% | 75% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## J6
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 6 | 85.71% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 12.8571 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 12.8571 | 0 | 0 | 0 | 0
Bricks | 12.8571 | 12.8571
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 62.86% | 72.86% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Sheet2
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
proptiger. | xrbia vangani | 1RK | 142 | 213 | 4218.3099 | 599000
proptiger. | xrbia vangani | 1BHK | 232 | 348 | 4219.8276 | 979000
proptiger. | xrbia vangani | 1BHK | 387 | 580.5 | 4658.9147 | 1803000
commonfloor. | xrbia vangani | 1BHK | 217.3333 | 326 | 5171.7791 | 1124000
commonfloor. | xrbia vangani | 1BHK | 310 | 465 | 5174.1935 | 1604000
commonfloor. | xrbia vangani | 1RK | 151.3333 | 227 | 5174.0088 | 783000
commonfloor. | xrbia vangani | 2BHK | 300.6667 | 451 | 5171.8404 | 1555000
commonfloor. | xrbia vangani | 2BHK | 343.3333 | 515 | 5172.8155 | 1776000
Average |  |  |  |  | 4870.2112
Valuation Adopted |  |  |  |  | 4900