## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 09/07/2025.
Name of the builder group |  |  |  | Paper Mill Plant and Machinery Manufacturers Limited
Name of the builder company |  |  |  | Paper Mill Plant and Machinery Manufacturers Limited
Name of the Project |  |  |  | 24 Karat
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Muzib 7506533543
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr.Vivek Shetty - 7506533533
Name / No of the Building |  |  |  | Wing A, B & C
Name / No of the Existing Building |  |  |  | JME'S Multiplex Business
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet, Airport Noc
RERA No. |  |  |  | P51800050840
Project location details |  | 24 Karat, K24CTS No.218A & Redevelopment of building " JME'S Multiplex Business ", near Jamuna Amrut CHS, Swami Vivekananda Road, Momin Nagar, Bandivali, Jogeshwari West, Andheri, Mumbai - 400102. | [5 empty] | on site 24 karat multiplex
CTS No |  | 218A & Redevelopment of building " JME'S Multiplex Business "
Locality |  | Momin Nagar
Road |  | Swami Vivekananda Road |  | Locality/Village |  | Bandivali
City |  | Jogeshwari West |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400102
Nearby Landmark |  | Jamuna Amrut CHS |  | Distance from city centre: |  | 0.9 KM from Jogeshwari Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Covered Nalla |  |  | Road No. 02
West | NA | 27.45M Wide S.V. Road |  |  | Swami Vivekananda Road
North | NA | Other Plot |  |  | Jamuna Amrut CHS
South | NA | Other Plot |  |  | Flexcel Park
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.1411104, 72.84361
Location Link |  | https://goo.gl/maps/c7nUaYrZg4rMDqiy8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3600.5
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1.5
Total FSI availaible for the project |  |  |  | 2.5
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 9001.24
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | P-9632/2021/(218A)/K/W WARD/BANDIVALI-KW |  |  | Dated | 03/01/2024.
Approved Floor plan No. |  | P-9632/2021/(218A)/K/W WARD/BANDIVALI-KW |  |  | Dated | 03/01/2024.
Commencement-CC No Valid Up to: |  | P-9632/2021/(218A)/K/W Ward/BANDIVALI-KW/FCC/1/New |  |  | Dated | 25/11/2024.
|  | Further C.C. up to top of 19th floor for Wing ‘A’ i.e. height 61.25 mt. AGL, up to top of 20th floor for Wing ‘B’ i.e. height 64.15 mt. AGL and up to top of 1st Podium for wing ‘C’ i.e. height 9.05 mt. AGL as per last approved plan dated 03.01.2024. |  |  | Valid Upto Date | 10/04/2025.
Airport NOC No Valid Up to: |  | JUHU/WEST/B/050622/670628 |  |  | Dated | 20/09/2022.
|  | Valid Upto : 102.15 above MSL |  |  | Valid Upto Date | 19/09/2030.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 9001.24
Approved no of units |  |  | Flats - 190, Shops - 05, Offices - 05
Approved no of Floors |  |  | Wing A & B = 1B + Gr/Stilt + 1st to 22nd Floor Wing C = 1B + Gr/Stilt + 1st Floor
Proposed no of Floors |  |  | Wing A & B = 1B + Gr/Stilt + 1st to 22nd Floor
Wing C = 1B + Gr/Stilt + 1st Floor
Expected Completion |  |  | As per RERA - 31/03/2029
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Meditation, Yoga Room, Gymnasium, Cardio, Fitness Center, Indoor Games, Garden Area
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = 1B + Gr/Stilt + 1st to 22nd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 6 Slab, Brickwork upto 4 Floor, Internal Plaster upto 3 Floor, External Plaster upto 2.6 Floor Completed | , RCC upto 6 Slab, Brickwork upto 4 Floor, Internal Plaster upto 3 Floor, External Plaster upto 2.6 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 6 Slab, Brickwork upto 4 Floor, Internal Plaster upto 3 Floor, External Plaster upto 2.6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 24% |  | 55.01% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 6 | 26.09% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 4 | 18.18% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 3 | 13.64% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2.6 | 11.82% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Wing B = 1B + Gr/Stilt + 1st to 22nd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 4 Slab Completed | , RCC upto 4 Slab
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 4 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 16.96% |  | 50.22% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 4 | 17.39% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Wing C = 1B + Gr/Stilt + 1st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 1 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% | 30% |  | 60% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 1 | 50% |  |  |  |  | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 1
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  | Cost sheet | online | MIS | housing
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 19500 |  |  | 20203.8441 | 21000 | 17111.5322 | 22500 | Unique one
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 35000 |  |  |  | 40000 |  |  | 21201.4134
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 28000 |  |  |  | 30000
Floor Rise Rate from Floor
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1200000
Distressed valuation of the Property |  |  |  |  | 15600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing C | Shops | 5 |  | 2623.063 |  | 4196.9008
| IT Offices | 5 |  | 2849.5311 |  | 4559.2498
Total |  | 10 |  | 5472.5941 |  | 8756.1506
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 95 |  | 56215.6358 |  | 87134.2356
Wing B |  | 95 |  | 56181.514 |  | 87081.3466
Total |  | 190 |  | 112397.1498 |  | 174215.5822
Grand Total |  | 200 |  | 117869.7439 |  | 182971.7328
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Wing C
Basement Floor for Parking
Ground Floor for Commercial & Parking
1 |  | Shop | 452.2742 | 0 | 723.6387 | Ground Floor for Commercial & Parking
2 |  | Shop | 479.7127 | 0 | 767.5404
3 |  | Shop | 331.5161 | 0 | 530.4258
4 |  | Shop | 638.6647 | 0 | 1021.8635
5 |  | Shop | 720.8952 | 0 | 1153.4324
1st Floor
1 |  | IT Office | 555.8088 | 0 | 889.2941 | 1st Floor
2 |  | IT Office | 474.4276 | 0 | 759.0842
3 |  | IT Office | 331.3321 | 0 | 530.1313
4 |  | IT Office | 641.3826 | 0 | 1026.2122
5 |  | IT Office | 846.58 | 0 | 1354.528
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Wing A
Basement Floor for Parking
Ground & 1st Floor for Commercial & Parking
Basement Floor for Parking
Ground Floor for Parking
1st Floor
2nd Floor for Amenities
3rd to 6th, 8th to 13th, 15th to 20th & 22nd Floor for Residential
1 |  | 2BHK | 686.3126 | 0 | 1063.7846 | 3rd to 6th, 8th to 13th, 15th to 20th & 22nd Floor for Residential |  | 60.5105
2 |  | 2BHK | 686.0974 | 0 | 1063.4509
3 |  | 2BHK | 680.823 | 0 | 1055.2757
4 |  | 1BHK | 427.3308 | 0 | 662.3627 |  |  |  | 17362.0877
5 |  | 1BHK | 427.2232 | 0 | 662.1959 |  |  |  | 17366.4622
7th & 14th Floor (Part Refuge Area)
1 |  | 2BHK | 685.3439 | 0 | 1062.283 | 7th & 14th Floor (Part Refuge Area) |  |  | 17227.0476
2 |  | 2BHK | 686.0974 | 0 | 1063.4509 |  |  |  | 17208.1286
3 |  | 2BHK | 716.2366 | 0 | 1110.1667 |  |  |  | 16393.9348
4 |  | Refuge Area
5
21st Floor (Part Refuge Area)
1 |  | 2BHK | 686.3126 | 0 | 1063.7846 | 21st Floor (Part Refuge Area)
2 |  | 2BHK | 686.0974 | 0 | 1063.4509
3 |  | 2BHK | 680.823 | 0 | 1055.2757
4 |  | Refuge Area
5 |  | 2BHK | 554.6689 | 0 | 859.7368
Wing B
Basement Floor for Parking
Ground & 1st Floor for Parking
2nd Floor for Amenities
3rd to 6th, 8th to 13th, 15th to 20th & 22nd Floor for Residential
1 |  | 2BHK | 686.3126 | 0 | 1063.7846 | 3rd to 6th, 8th to 13th, 15th to 20th & 22nd Floor for Residential
2 |  | 2BHK | 684.3751 | 0 | 1060.7814
3 |  | 2BHK | 680.823 | 0 | 1055.2757
4 |  | 1BHK | 427.2232 | 0 | 662.1959
5 |  | 1BHK | 427.2232 | 0 | 662.1959
7th & 14th Floor (Part Refuge Area)
1 |  | 2BHK | 686.3126 | 0 | 1063.7846 | 7th & 14th Floor (Part Refuge Area)
2 |  | 2BHK | 684.3751 | 0 | 1060.7814
3 |  | 2BHK | 716.3442 | 0 | 1110.3335
4 |  | Refuge Area
5
21st Floor (Part Refuge Area)
1 |  | 2BHK | 686.3126 | 0 | 1063.7846 | 21st Floor (Part Refuge Area)
2 |  | 2BHK | 684.3751 | 0 | 1060.7814
3 |  | 2BHK | 680.823 | 0 | 1055.2757
4 |  | 2BHK | 554.6689 | 0 | 859.7368
5 |  | Refuge Area
Remarks:
* | Wing A & B = Construction work is in process at the time of Visit. Internal visit was not allowed. Wing C = Construction work same as last visit dtd 13/01/2025 but work is in process at the time of Visit.(Slow Speed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We refer Civil Aviation NOC from MCGM site.
* | As per layout, Nalla is located on East side to the project.
* | We have Updated latest apporved floor plans from MCGM Site (On 04/01/2023).
* | We have updated latetst CC from MCGM site (On 09/04/2025).
* | Validity of CC is expired on 10/04/2025. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Bhuwad |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | 24 Karat
Layout :
Google Map :
Wing B
Wing A
A Wing
B Wing
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D57: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted