## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Thane | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-07-09 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Gurukrupa Realcon Infrabuild LLP | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Gurukrupa Realcon Infrabuild LLP | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Gurukrupa Gyanam | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Devendra Naik 7208119728
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Gaurav 9619131016
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | Powai Manidwip Commercial Premises Co-Op. Housing Society Ltd | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC & Cost Sheet. | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800053259 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Gurukrupa Gyanam, CTS No.7/18, Redevlopement of "Powai Manidwip Commercial Premises Co-Op. Housing Society Ltd", near Vijay Vihar, Mhada Colony Complex Road, Powai Mhada Colony, Kopari, Powai East, Kurla, Mumbai - 400076. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 7/18, Redevlopement of "Powai Manidwip Commercial Premises Co-Op. Housing Society Ltd" | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Powai Mhada Colony | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Mhada Colony Complex Road |  | Locality/Village |  | Kopari | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Powai East |  | District |  | Mumbai | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kurla |  | Pin Code |  | 400076 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Vijay Vihar |  | Distance from city centre: |  | 3.90KM from Kanjurmarg Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 12.20 M. Wide Road |  |  | Mhada Colony Complex Road
West | NA | Other plot |  |  | Vijay Vihar
North | NA | 18.30 M. Wide Road |  |  | Powai Woods CHS Ltd
South | NA | Other plot |  |  | Mhada Colony Complex Road
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.117469,72.903923
Location Link |  | https://maps.app.goo.gl/AVQ9zxBcHG3cwDsV6
Area Statement Details : | [7 empty] | 26000
Total land area of the project in Sq. Mt. |  |  |  | 704.19
Permissible FSI |  |  |  | 3 |  |  |  | 3.0085
Permissible TDR/Paid FSI |  |  |  | 2.3581
Total FSI availaible for the project |  |  |  | 5.3581
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 3773.11
Total Approved proposed Builtup area of the project (Sq.Mt) |  |  |  | 1226.71
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority(MHADA) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | Mhada - 36/1299/2024 |  |  | Dated | 2024-05-08 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | Mhada - 36/1299/2024 |  |  | Dated | 2024-05-08 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-6/1299/2025/FCC/2/Amend |  |  | Dated | 2025-02-28 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This C.C. is now Further extended from 14th floor to 15th floor level + OHT “ { i. e. for Entire work of building having part basement floor for services + part ground floor for shops & entrance lobby + 1st to 15th upper floor for residential use with total height of 48.70 mt. from AGL and Mechanized car parking tower touching to building on west side of the plot with total height 49.07 mt. from AGL+ LMR + OHT as per last approved Amended plans issued by MHADA on dated- 25.06.2024 vide u/no. MH/EE/(B.P.)Cell/GM/ MHADA-36/1299/2024}. |  |  | Valid Upto Date | 2025-07-27 | [10 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 1226.71
Approved no of units |  |  | Flats - 13, Shops - 08
Approved no of Floors |  |  | B (pt) + Gr + 1st to 3rd Floor
Proposed no of Floors |  |  | B (pt) + Gr + 1st to 15th Floor |  |  |  |  | https://www.gurukrupa-gyanam.com/#floor
B Wing = 1B + G + 1st to 20th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Sitting Area, Yoda & Meditation area, Decorative Entrance & Landscape Garden, etc. |  |  |  |  | As per official site
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction |  |  | 5.3581
Construction details: |  | B (pt) + Gr + 1st to 15th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 13 Floor, Painting upto 11 Floor, Finishing upto 5 Floor Completed | , Flooring upto 13 Floor, Painting upto 11 Floor, Finishing upto 5 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 13 Floor, Painting upto 11 Floor, Finishing upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 89% |  | 94.33% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 86.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 11 | 73.33% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 33.33% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | B Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 10% |  | 45% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 19500 | [11 empty] | 800000 | 300000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 30000 | [11 empty] | 900000 | 350000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 400000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 500000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 600000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 700000 | 350000 | 400000
Gas Connection Charges | [8 empty] | 858 | 18648.0186 | [6 empty] | 1400000 | 800000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 900000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 1000000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000
Recommended rate of Parking |  |  |  |  | 900000 | [11 empty] | 1800000
Distressed valuation of the Property |  |  |  |  | 15600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 8 |  | 2592.4018 |  | 4018.2227
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 13 |  | 9449.5003 |  | 14174.2505
Total
Grand Total |  | 21 |  | 12041.9021 |  | 18192.4732
Building details Floor Wise
Details of Residential in Building | [7 empty] | Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Mezzanine area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Basement (Part) For Pump Room, Fire Water Tank & Domestic Water Tank
Ground Floor For Commercial, Society Office, Entrance lobby, Meter Room & Parking
1 |  | Shop | 277.3883 | 47.3616 | 324.7499 | 0 | 503.3623 |  |  |  |  | 10.764
2 |  | Shop | 277.3883 | 47.3616 | 324.7499 | 0 | 503.3623
3 |  | Shop | 275.7737 | 48.1151 | 323.8888 | 0 | 502.0276
4 |  | Shop | 275.7737 | 48.1151 | 323.8888 | 0 | 502.0276
5 |  | Shop | 275.7737 | 48.1151 | 323.8888 | 0 | 502.0276
6 |  | Shop | 275.7737 | 48.1151 | 323.8888 | 0 | 502.0276
7 |  | Shop | 275.7737 | 48.1151 | 323.8888 | 0 | 502.0276
8 |  | Shop | 275.7737 | 47.6845 | 323.4582 | 0 | 501.3602
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Deck | Gross Carpet area | Attached Terrace area | Saleable area Loading :
[7 empty] | 50% |  | 19333.3333
Ground Floor For Commercial, Society Office, Entrance lobby, Meter Room & Parking
9 |  | Multipurpose Room | 214.9571 | 0 | 214.9571 | 0 | 322.4356
1st to 3rd Floor For Residential | [10 empty] | 858
1 |  | 2BHK | 571.999 | 0 | 571.999 | 0 | 857.9984 | [5 empty] | 10.764
2 |  | 2BHK | 697.6148 | 62.3236 | 759.9384 | 0 | 1139.9076
3 |  | 2.5BHK | 807.9458 | 29.2781 | 837.2239 | 0 | 1255.8359
4 |  | 3BHK | 886.523 | 22.4968 | 909.0198 | 0 | 1363.5297
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks: | [10 empty] | 18648.0186
* | Construction work is in process at the time of Visit. Inernal visit was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan. | [7 empty] | 26000
* | We considered Gross carpet area = Net carpet + Deck.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | We have updated revised approved CC from MHADA site on 19/11/2024.
* | Please check for Environment Clearance Certificate.
* | As per site visit dated 26/04/2024, We have observed 3rd RCC slab work is completed and 4th Slab casting work is in process. Hence Please provide revised approved CC.
* | We have updated latest CC from Mhada site (On 25/04/2025).
* | Please provide revised approved Plans.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Pratik Niwate |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Gurukrupa Gyanam
Layout :
Google Map :
Formulas:
Kopari = [Kopari, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on D57: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F117: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H152: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | There are inadequate transportation options to get to the project and the area is not developed.
15 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sales plan.
16 | River located on west side of the project.
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate