## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-07-10 |  |  |  | 2025-06-07
Name of the builder group |  |  |  | Shree Vastunirman Developers
Name of the builder company |  |  |  | Shree Vastunirman Developers
Name of the Project |  |  |  | Vrundavan Park |  |  |  | Vrundavan Park Jai
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Mahendra Dhangar - 9220929282
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr.Akshay Jagtap 991506871
Name / No of the Building |  |  |  | Jai - Building No. 1 (Wing A & B) Jui - Building No. 2 (Wing A, B & C) |  |  |  | Building No. 1 (A & B Wing)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51700049309
Project location details |  | Vrundavan Park , Survey No.94/19, 94/23, 94/25, near Vrundavan society, Internal Road, Devrung, Devrung, Kalyan, Bhiwandi, Thane - 421305.
Survey No |  | 94/19, 94/23, 94/25
Locality |  | Devrung
Road |  | Internal Road |  | Locality/Village |  | Devrung
City |  | Kalyan |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421305
Nearby Landmark |  | Vrundavan society |  | Distance from city centre: |  | 7.10 KM from Kalyan Junction Railway Station |  | 8.8 KM from Kalyan Junction Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per layout |  |  | At site
East | NA | Other Plot |  |  | Open Plot
West | NA | Village Road |  |  | Internal Road
North | NA | Other Plot |  |  | Open Plot
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.283054,73.151974 | [5 empty] | 19.283465, 73.151664
Location Link |  | https://maps.app.goo.gl/GoTJMgWvmtFUUGGX6 | [5 empty] | https://goo.gl/maps/ewcKr7Zs7dMSi9K57
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2865.062 |  |  |  | 2865.062
Permissible FSI |  |  |  | 1.1 |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.1485 |  |  |  | 1.1485
Total FSI availaible for the project |  |  |  | 2.2485 |  |  |  | 2.2485
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 6441.962 |  |  |  | 6441.962
Total number of Buildings |  |  |  | 02 Buildings (05 Wings) |  |  |  | 02 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Nagar Rachna Aani Mulya Nirdharan Vibhag
Layout Approval No |  | BS/RKKN/BP/Mauje.Devrung/Tal. Bhiwandi/SSTN/2516 |  |  | Dated | 2022-10-13
Approved Floor plan No. |  | BS/RKKN/BP/Mauje.Devrung/Tal. Bhiwandi/SSTN/2516 |  |  | Dated | 2022-10-13
Commencement-CC No Valid Up to: |  | MHSL/K-1/T-8/BP/Devrung-Bhiwandi/SR-40/2022 |  |  | Dated | 2023-01-03
|  | Building No.1 (A Wing) = G + 1st to 7th Floor Building No.1 (B Wing) = G + 1st to 7th Floor Building No. 2 (Wing A, B & C) = G + 1st to 7th Floor | [5 empty] | Building No.1 (A Wing) = G + 1st to 7th Floor Building No.1 (B Wing) = G + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 6441.962
Approved no of units |  |  | Shop = 4, Flats = 147
Approved no of Floors |  |  | Building No.1 (Wing A) = G + 1st to 7th Floor Building No.1 (Wing B) = G + 1st to 7th Floor Building No.2 (Wing A, B & C) = G + 1st to 7th Floor |  |  |  |  | Building No.1 (A Wing) = G + 1st to 7th Floor Building No.1 (B Wing) = G + 1st to 7th Floor
Proposed no of Floors |  |  | Building No.1 (Wing A) = G + 1st to 7th Floor |  |  |  |  | Building No.1 (A Wing) = G + 1st to 7th Floor
|  |  | Building No.1 (Wing B) = G + 1st to 7th Floor |  |  |  |  | Building No.1 (B Wing) = G + 1st to 7th Floor
Building No.2 (Wing A, B & C) = G + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 (Wing A) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 4 Floor, Painting upto 4 Floor Completed | , Flooring upto 4 Floor, Painting upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 4 Floor, Painting upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 83.57% |  | 92.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 57.14% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 57.14% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.1 (Wing B) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 3 Floor, Painting upto 1 Floor Completed | , Flooring upto 3 Floor, Painting upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 3 Floor, Painting upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 80% |  | 92.14% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 42.86% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 1 | 14.29% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.2 (Wing A) = G + 1st to 7th Floor | [5 empty] | Excavation Completed, Footing work Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation | , Footing work Completed
Stage of construction: |  | Excavation Completed, Footing work Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 5% |  | 32.5% |  | Excavation in process | 3.5
Plinth |  | 3.5 | 50% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.2 (Wing B & C) = G + 1st to 7th Floor | [5 empty] | Excavation Completed, Plinth work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation | , Plinth work is process
Stage of construction: |  | Excavation Completed, Plinth work is process | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 3.5
Plinth |  | 5.25 | 75% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4850 |  |  | 4300 to 4700 & OC |  | Rushikesh | Cost Sheet | 2023-07-11
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 200000 |  |  | Rate 4850 bhargav verbal 23/01/2025
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges & Other Charges |  |  |  |  | 50000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 150000
Distressed valuation of the Property |  |  |  |  | 3880
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 2 (Jui) | Wing A | 4 |  | 560.1047 |  | 840.1571
Total |  | 4 |  | 560.1047 |  | 840.1571
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 1(Jai) | Wing A | 35 |  | 14205.1701 |  | 20597.4966
| Wing B | 35 |  | 14205.1701 |  | 20597.4966
Building No. 2 (Jui) | Wing A | 28 |  | 8168.8534 |  | 11844.8375 |  | OK
| Wing B | 28 |  | 8802.1534 |  | 12763.1224 |  | OK
| Wing C | 21 |  | 6601.615 |  | 9572.3418 |  | OK
Total |  | 147 |  | 51982.9619 |  | 75375.2948
Grand Total |  | 151 |  | 52543.0667 |  | 76215.4519
Building Details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No. 2 (Jui)
Wing A
Ground Floor For Commercial, Entrance Lobby & Parking
1 |  | Shop | 66.7099 | 0 | 66.7099 | 0 | 100.0648 | 100.0648
2 |  | Shop | 161.2447 | 0 | 161.2447 | 0 | 241.8671 | 241.8671
3 |  | Shop | 209.4674 | 0 | 209.4674 | 0 | 314.2012 | 314.2012
4 |  | Shop | 122.6827 | 0 | 122.6827 | 0 | 184.024 | 184.024
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet Area | Balcony Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Building No. 1(Jai)
Wing A
Ground Floor For Drivers Room, Entrance Lobby & Parking
1st to 7th Floor For Residential
1 |  | 1BHK | 278.9491 | 51.7479 | 330.697 | 0 | 479.5106 | 479.5106
2 |  | 1BHK | 278.9491 | 51.7479 | 330.697 | 0 | 479.5106 | 479.5106
3 |  | 1BHK | 278.9491 | 52.5552 | 331.5043 | 0 | 480.6812 | 480.6812
4 |  | 2BHK | 413.3645 | 104.8414 | 518.2059 | 0 | 751.3985 | 751.3985
5 |  | 2BHK | 413.3645 | 104.8414 | 518.2059 | 0 | 751.3985 | 751.3985
Wing B
Ground Floor For Entrance Lobby & Parking
1st to 7th Floor For Residential
1 |  | 2BHK | 413.3645 | 104.8414 | 518.2059 | 0 | 751.3985 | 751.3985
2 |  | 2BHK | 413.3645 | 104.8414 | 518.2059 | 0 | 751.3985 | 751.3985
3 |  | 1BHK | 278.9491 | 52.5552 | 331.5043 | 0 | 480.6812 | 480.6812
4 |  | 1BHK | 278.9491 | 51.7479 | 330.697 | 0 | 479.5106 | 479.5106
5 |  | 1BHK | 278.9491 | 51.7479 | 330.697 | 0 | 479.5106 | 479.5106
Building No. 2 (Jui)
Wing A
1st to 7th Floor For Residential
1 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
2 |  | 1RK | 202.9014 | 20.9898 | 223.8912 | 0 | 324.6422 | 324.6422
3 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
4 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
Wing B
Ground Floor For Entrance Lobby & Parking
1st to 7th Floor For Residential
1 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
2 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
3 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
4 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
Wing C
Ground Floor For Society Office, Entrance Lobby & Parking
1st to 7th Floor For Residential
1 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
2 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
3 |  | 1BHK | 264.31 | 50.0526 | 314.3626 | 0 | 455.8258 | 455.8258
Remarks:
* | Construction work is in process at the time of Visit.(Labour found)
* | We have considered Saleable area of Flats as per our Calculation.
* | #REF!
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Open Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates / Other charges of the Property have been revised on 23/01/2025.
* | As checked on the RERA portal on date 14/07/2025, we have observed that the project name has been changed from "Vrundavan Park Jai" to "Vrundavan Park".
* | We have added Approved Plans & CC of Building No. 2(Wing A, B & C) on 11/07/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Saurav Panse
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Vrundavan Park
Layout :
Google Map :
Note on H163: SACHIN: Give loading of 50% for A Category
A Wing
B Wing
A Wing
B Wing
A
B
B
Vrundavan Park
Building 2
(Wing A)
Building 2
(Wing B)
Building 2
(Wing C)
Building 1
(Wing B)
Building 1
(Wing A)
N
Wing B
Bldg No. 1 (Wing B)
Bldg No. 1
Wing A
Bldg No. 02 (Wing A)
Bldg No. 02 (Wing B)
Bldg No. 02 (Wing C)

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted