## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Goregaon |  |  |  | m |  |  | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-07-11 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | M/s. Godrej Hillside Properties Private Limited | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | M/s. Godrej Hillside Properties Private Limited | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Godrej Golf Side Estate II | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Not Provided
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Sandip 9271808528
Name / No of the Building |  |  |  | Plot = 120
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Layout Plan, Tax Paid for conversion of land to Non Agriculture use letter | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000079895 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Godrej Golf Side Estate II, Plot No.Plot No. 1/2, 1/2, 1/3, 2/4, 23/2, 55/1, 55/2, near Infinity Icon, Internal Road, Shedung, Talegaon, Khalapur, Khalapur, Raigad - 400202. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot No |  | Plot No. 1/2, 1/2, 1/3, 2/4, 23/2, 55/1, 55/2 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Shedung | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Talegaon | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Khalapur |  | District |  | Raigad | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Khalapur |  | Pin Code |  | 400202 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Infinity Icon |  | Distance from city centre: |  | 4.3 KM from Mohope Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential |  |  |  | FALSE
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 9.00 Mtr Wide Road |  |  | Internal Road
West | NA | 9.00 Mtr Wide Road |  |  | Internal Road
North | NA | Reservation For Park |  |  | Open Plot
South | NA | Plot No. 12, 13, 14, 15, 16, 17, 18, 19, 20 |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 18.923723,73.184402
Location Link |  | https://maps.app.goo.gl/GxY8RT6TQo4q9pte8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 33043.11
Permissible FSI |  |  |  | 0.38151
Permissible TDR/Paid FSI |  |  |  | 0.71834
Total FSI availaible for the project |  |  |  | 1.0999 |  |  |  | 1.0999
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 36342.56
Total number of Buildings |  |  |  | 120 Plots
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra State Road Development Corporation Limited (MSRDC) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | MSRDC/385/2025/0002/AutoDCR/1 |  |  | Dated | 2025-03-28 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | MSRDC/385/2025/0002/AutoDCR/1 |  |  | Dated | 2025-03-28 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
NA Order No Valid Up to: |  | Not Provided |  |  | Dated | NA | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Tax Paid for conversion of land to Non Agriculture use letter No. Valid Up to: |  | MSA/JAMNBAB/KT.1/10307/KDP/YR/TALEGAON/2024/8250 |  |  | Dated | 2024-12-02 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Survey No. 1/2, 1/2, 1/3, 2/4, 23/2, 55/1, 55/2 = 38500sqmt | [14 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | Survey No. 1/2, 1/2, 1/3, 2/4, 23/2, 55/1, 55/2 = 38500sqmt |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 36342.56
Approved no of units |  |  | Plot - 120
Approved no of Floors |  |  | A Wing = 1B + G + 1st to 20th Floor B Wing = 1B + G + 1st to 20th Floor C Wing = 1B + G + 1st to 20th Floor
Proposed no of Floors |  |  | Building No.1 (A Wing) = 1B + G + 1st to 20th Floor
B Wing = 1B + G + 1st to 19th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Health Club, Golf Club, Curated Gardens, Vitrified tiles flooring, Granite Kitchen Platform, Decorative Entrance, Landscaping & Garden etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Work not yet Started
Wheather the construction is as per approved Building plan : |  |  | Work not yet Started |  | Work not yet Started
Construction details:
Plot/ Banglow No | Progress % | Disburse-ment % | Stage of construction:
1 | 0% | 0% | Work not yet Started.
2 | 0% | 0% | Work not yet Started.
3 | 0% | 0% | Work not yet Started.
4 | 0% | 0% | Work not yet Started.
5 | 0% | 0% | Work not yet Started.
6 | 0% | 0% | Work not yet Started.
7 | 0% | 0% | Work not yet Started.
8 | 0% | 0% | Work not yet Started.
9 | 0% | 0% | Work not yet Started.
10 | 0% | 0% | Work not yet Started.
11 | 0% | 0% | Work not yet Started.
12 | 0% | 0% | Work not yet Started.
13 | 0% | 0% | Work not yet Started.
Construction details: |  | Building No.1 (A Wing) = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 10% |  | 45% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | B Wing = 1B + G + 1st to 19th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 10% |  | 45% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Plot Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended Rate of Plot Per Sq. Ft. |  |  |  |  | 8000 | [11 empty] | 800000 | 150000 | 100000 | 100000
Common area amenities and facilities development charges Per Sq. Ft. |  |  |  |  | 500 | [11 empty] | 900000 | 200000 | 150000 | 150000
Basic Infrastructure Charges Per Sq. Ft. |  |  |  |  | 2050 | [11 empty] | 1000000 | 250000 | 200000 | 200000
Club Charges |  |  |  |  | 90000 | [11 empty] | 1100000 | 300000 | 250000 | 250000
Corpus Fund |  |  |  |  | 50000 | [11 empty] | 1200000 | 350000 | 300000 | 300000
Society Formation Charges |  |  |  |  | 7000 | [11 empty] | 1300000 | 400000 | 350000 | 400000
Advance Maintenance Charges |  |  |  |  | 300000 | [11 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 600000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 6400 | [12 empty] | 1000000
Plot Area Details :
Building & Wing |  | No. of Units |  | Total Plot Area |  | Total Builtup Area
Plots |  | 120 |  | 228847.1716 |  | 391191.3552 |  | OK
Total |  | 120 |  | 228847.1716 |  | 391191.3552
Building details Floor Wise
Details of Plot Area
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Plot/ Bunglow No | Plot Area (Sq.Mt.) | Plot Area (Sq.Ft.) | Carpet Area | Terrace Area | Permissible Built up Area on Basic FSI (In Sq.ft) | Demarkation Status |  | Permissible Built up Area on Basic FSI = Plot Area * 1.554 *1.1
Plots
1 | 250.76 | 2699.1806 | 0 | 0 | 4613.9794 | No |  | OK
2 | 311.562 | 3353.6534 | 0 | 0 | 5732.7351 | No |  | OK
3 | 312.544 | 3364.2236 | 0 | 0 | 5750.8038 | No |  | OK
4 | 160.362 | 1726.1366 | 0 | 0 | 2950.6578 | No |  | OK
5 | 236.38 | 2544.3943 | 0 | 0 | 4349.3877 | No |  | OK
6 | 161.074 | 1733.8005 | 0 | 0 | 2963.7586 | No |  | OK
7 | 160.632 | 1729.0428 | 0 | 0 | 2955.6258 | No |  | OK
8 | 160.578 | 1728.4616 | 0 | 0 | 2954.6322 | No |  | OK
9 | 250.857 | 2700.2247 | 0 | 0 | 4615.7642 | No |  | OK
10 | 251.443 | 2706.5325 | 0 | 0 | 4626.5466 | No |  | OK
11 | 255.012 | 2744.9492 | 0 | 0 | 4692.2161 | No |  | OK
12 | 272.323 | 2931.2848 | 0 | 0 | 5010.7382 | No |  | OK
13 | 161.251 | 1735.7058 | 0 | 0 | 2967.0154 | No |  | OK
14 | 154.936 | 1667.7311 | 0 | 0 | 2850.8195 | No |  | OK
15 | 155.782 | 1676.8374 | 0 | 0 | 2866.3859 | No |  | OK
16 | 159.688 | 1718.8816 | 0 | 0 | 2938.2563 | No |  | OK
17 | 157.239 | 1692.5206 | 0 | 0 | 2893.1947 | No |  | OK
18 | 143.084 | 1540.1562 | 0 | 0 | 2632.743 | No |  | OK
19 | 144.846 | 1559.1223 | 0 | 0 | 2665.1637 | No |  | OK
20 | 252.001 | 2712.5388 | 0 | 0 | 4636.8138 | No |  | OK
21 | 233.193 | 2510.0895 | 0 | 0 | 4290.7469 | No |  | OK
22 | 177.321 | 1908.6832 | 0 | 0 | 3262.7031 | No |  | OK
23 | 176.351 | 1898.2422 | 0 | 0 | 3244.8552 | No |  | OK
24 | 168.672 | 1815.5854 | 0 | 0 | 3103.5617 | No |  | OK
25 | 168.672 | 1815.5854 | 0 | 0 | 3103.5617 | No |  | OK
26 | 168.718 | 1816.0806 | 0 | 0 | 3104.4081 | No |  | OK
27 | 182.856 | 1968.262 | 0 | 0 | 3364.547 | No |  | OK
28 | 193.918 | 2087.3334 | 0 | 0 | 3568.0876 | No |  | OK
29 | 179.319 | 1930.1897 | 0 | 0 | 3299.4663 | No |  | OK
30 | 179.271 | 1929.673 | 0 | 0 | 3298.5831 | No |  | OK
31 | 179.271 | 1929.673 | 0 | 0 | 3298.5831 | No |  | OK
32 | 186.363 | 2006.0113 | 0 | 0 | 3429.0758 | No |  | OK
33 (Services) | 0 | 0 | 0 | 0 | 0 | No |  | OK
34 | 174.355 | 1876.7572 | 0 | 0 | 3208.1288 | No |  | OK
35 | 174.355 | 1876.7572 | 0 | 0 | 3208.1288 | No |  | OK
36 | 174.355 | 1876.7572 | 0 | 0 | 3208.1288 | No |  | OK
37 | 170.011 | 1829.9984 | 0 | 0 | 3128.1993 | No |  | OK
38 | 162.988 | 1754.4028 | 0 | 0 | 2998.9762 | No |  | OK
39 | 159.335 | 1715.0819 | 0 | 0 | 2931.7611 | No |  | OK
40 | 143.686 | 1546.6361 | 0 | 0 | 2643.8198 | No |  | OK
41 | 141.79 | 1526.2276 | 0 | 0 | 2608.9334 | No |  | OK
42 | 141.742 | 1525.7109 | 0 | 0 | 2608.0502 | No |  | OK
43 | 139.488 | 1501.4488 | 0 | 0 | 2566.5766 | No |  | OK
44 | 252.658 | 2719.6107 | 0 | 0 | 4648.9026 | No |  | OK
45 | 119.194 | 1283.0042 | 0 | 0 | 2193.1674 | No |  | OK
46 | 160.635 | 1729.0751 | 0 | 0 | 2955.681 | No |  | OK
47 | 160.872 | 1731.6262 | 0 | 0 | 2960.0418 | No |  | OK
48 | 153.935 | 1656.9563 | 0 | 0 | 2832.4012 | No |  | OK
49 | 144.559 | 1556.0331 | 0 | 0 | 2659.8829 | No |  | OK
50 | 256.043 | 2756.0469 | 0 | 0 | 4711.1865 | No |  | OK
51 | 187.365 | 2016.7969 | 0 | 0 | 3447.5126 | No |  | OK
52 | 219.308 | 2360.6313 | 0 | 0 | 4035.2632 | No |  | OK
53 | 277.982 | 2992.1982 | 0 | 0 | 5114.8637 | No |  | OK
54 | 141.94 | 1527.8422 | 0 | 0 | 2611.6934 | No |  | OK
55 | 141.376 | 1521.7713 | 0 | 0 | 2601.3158 | No |  | OK
56 | 182.555 | 1965.022 | 0 | 0 | 3359.0086 | No |  | OK
57 | 156.072 | 1679.959 | 0 | 0 | 2871.7219 | No |  | OK
58 | 201.489 | 2168.8276 | 0 | 0 | 3707.3939 | No |  | OK
59 | 145.468 | 1565.8176 | 0 | 0 | 2676.6085 | No |  | OK
60 | 145.454 | 1565.6669 | 0 | 0 | 2676.3509 | No |  | OK
61 | 145.029 | 1561.0922 | 0 | 0 | 2668.5309 | No |  | OK
62 | 140.168 | 1508.7684 | 0 | 0 | 2579.0886 | No |  | OK
63 | 251.029 | 2702.0762 | 0 | 0 | 4618.929 | No |  | OK
64 | 149.43 | 1608.4645 | 0 | 0 | 2749.5093 | No |  | OK
65 | 151.249 | 1628.0442 | 0 | 0 | 2782.9788 | No |  | OK
66 | 139.894 | 1505.819 | 0 | 0 | 2574.047 | No |  | OK
67 | 140.092 | 1507.9503 | 0 | 0 | 2577.6902 | No |  | OK
68 | 140.423 | 1511.5132 | 0 | 0 | 2583.7806 | No |  | OK
69 | 140.785 | 1515.4097 | 0 | 0 | 2590.4414 | No |  | OK
70 | 201.69 | 2170.9912 | 0 | 0 | 3711.0923 | No |  | OK
71 | 198.048 | 2131.7887 | 0 | 0 | 3644.0796 | No |  | OK
72 | 150.93 | 1624.6105 | 0 | 0 | 2777.1092 | No |  | OK
73 | 154.291 | 1660.7883 | 0 | 0 | 2838.9516 | No |  | OK
74 | 157.013 | 1690.0879 | 0 | 0 | 2889.0363 | No |  | OK
75 | 141.492 | 1523.0199 | 0 | 0 | 2603.4502 | No |  | OK
76 | 145.71 | 1568.4224 | 0 | 0 | 2681.0613 | No |  | OK
77 | 145.71 | 1568.4224 | 0 | 0 | 2681.0613 | No |  | OK
78 | 145.71 | 1568.4224 | 0 | 0 | 2681.0613 | No |  | OK
79 | 145.71 | 1568.4224 | 0 | 0 | 2681.0613 | No |  | OK
80 | 145.71 | 1568.4224 | 0 | 0 | 2681.0613 | No |  | OK
81 | 145.71 | 1568.4224 | 0 | 0 | 2681.0613 | No |  | OK
82 | 245.388 | 2641.3564 | 0 | 0 | 4515.1347 | No |  | OK
83 | 238.857 | 2571.0567 | 0 | 0 | 4394.9644 | No |  | OK
84 | 150.481 | 1619.7775 | 0 | 0 | 2768.8476 | No |  | OK
85 | 147.222 | 1584.6976 | 0 | 0 | 2708.8821 | No |  | OK
86 | 147.222 | 1584.6976 | 0 | 0 | 2708.8821 | No |  | OK
87 | 147.222 | 1584.6976 | 0 | 0 | 2708.8821 | No |  | OK
88 | 147.222 | 1584.6976 | 0 | 0 | 2708.8821 | No |  | OK
89 | 147.222 | 1584.6976 | 0 | 0 | 2708.8821 | No |  | OK
90 | 147.222 | 1584.6976 | 0 | 0 | 2708.8821 | No |  | OK
91 | 147.222 | 1584.6976 | 0 | 0 | 2708.8821 | No |  | OK
92 | 142.559 | 1534.5051 | 0 | 0 | 2623.083 | No |  | OK
93 | 182.075 | 1959.8553 | 0 | 0 | 3350.1766 | No |  | OK
94 | 144.394 | 1554.257 | 0 | 0 | 2656.8469 | No |  | OK
95 | 141.527 | 1523.3966 | 0 | 0 | 2604.0942 | No |  | OK
96 | 153.191 | 1648.9479 | 0 | 0 | 2818.7116 | No |  | OK
97 | 147.668 | 1589.4984 | 0 | 0 | 2717.0885 | No |  | OK
98 | 157.722 | 1697.7196 | 0 | 0 | 2902.0819 | No |  | OK
99 | 167.004 | 1797.6311 | 0 | 0 | 3072.8705 | No |  | OK
100 | 177.234 | 1907.7468 | 0 | 0 | 3261.1023 | No |  | OK
101 | 185.143 | 1992.8793 | 0 | 0 | 3406.6278 | No |  | OK
102 | 292.726 | 3150.9027 | 0 | 0 | 5386.153 | No |  | OK
103 | 276.931 | 2980.8853 | 0 | 0 | 5095.5253 | No |  | OK
104 | 259.863 | 2797.1653 | 0 | 0 | 4781.4744 | No |  | OK
105 | 200.006 | 2152.8646 | 0 | 0 | 3680.1067 | No |  | OK
106 | 174.133 | 1874.3676 | 0 | 0 | 3204.044 | No |  | OK
107 | 217.234 | 2338.3068 | 0 | 0 | 3997.1016 | No |  | OK
108 | 260.359 | 2802.5043 | 0 | 0 | 4790.6008 | No |  | OK
109 | 343.079 | 3692.9024 | 0 | 0 | 6312.6473 | No |  | OK
110 | 144.442 | 1554.7737 | 0 | 0 | 2657.7301 | No |  | OK
111 | 177.287 | 1908.3173 | 0 | 0 | 3262.0775 | No |  | OK
112 | 183.59 | 1976.1628 | 0 | 0 | 3378.0526 | No |  | OK
113 | 146.966 | 1581.942 | 0 | 0 | 2704.1717 | No |  | OK
114 | 150.104 | 1615.7195 | 0 | 0 | 2761.9108 | No |  | OK
115 | 153.241 | 1649.4861 | 0 | 0 | 2819.6316 | No |  | OK
116 | 156.228 | 1681.6382 | 0 | 0 | 2874.5923 | No |  | OK
117 | 155.867 | 1677.7524 | 0 | 0 | 2867.9499 | No |  | OK
118 | 154.127 | 1659.023 | 0 | 0 | 2835.934 | No |  | OK
119 | 152.356 | 1639.96 | 0 | 0 | 2803.3476 | No |  | OK
120 | 186.973 | 2012.5774 | 0 | 0 | 3440.2998 | No |  | OK
Remarks:
* | Work not yet Started.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Plot area as per approved plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Please check for NA order before any disbursement.
* | Please check for Environment Clearance Certificate.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Nitesh Patil |  | Report By : |  | Shruti Fule
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Godrej Golf Side Estate II
Layout :
Google Map :
Formulas:
Talegaon = [Talegaon, row above]
Plot No. 111
Plot No. 49
Plot No. 73
Plot No. 44
Plot No. 12
Plot No. 120
Plot No. 83
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F137: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value

## Construction %
Construction details: |  | G + 1 | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 1 | Excavation, Plinth, RCC Slab
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% | 50% |  | 75% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 2 | 100% |  |  |  |  | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 1
Plot/ Banglow no | Floor |  | Excavation | Plinth | RCC | Brick work | Internal Plaster | Ext. Plaster | Flooring | Painting | Finishing | Possession | Progress % | Disbursement % | Stage of construction: | Excavation | Plinth | RCC (Including podiums) | Brickwork | Internal Plaster | Ext. Plaster & Plumbing | Flooring & Fitting | Painting & Wooden | Building Common Amenities | Possession | Piling Work in process | Excavation in process | Excavation Completed | Footing in Process | Footing Completed | Basement 1 | Basement 2 | Basement 3 | Basement 4 | Plinth in process | Plinth completed
1 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work Completed. Possession granted to the Building. | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities | Completed
2 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
1 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
2 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
3 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
4 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
5 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
6 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
7 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
8 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
9 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
10 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
11 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
12 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
13 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
14 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
15 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
16 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
17 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
18 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
19 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
20 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate