## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/07/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Sanpada | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-07-11 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Wadhwa Construction And Infrastructure Private Limited | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Wadhwa Construction And Infrastructure Private Limited | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Magnolia Cluster 3 | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Mahadev 9820740932
Site Person - Contact Details (Name & Contact No.) |  |  |  | Miss. Siya Chaudhary |  |  |  | Mr.Kundan 7977246118
Name / No of the Building |  |  |  | Plot A36 to A42 Plot B9 to B16 Plot C9 to C16 Plot D7 to D12 Plot E11 to E16 Plot F15 to F22 Plot G15 to G22 Plot H14 to H18
Name / No of the Existing Building |  |  |  | NA | [13 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, Cost Sheet, EC | [13 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000021144 |  |  |  | #N/A | [9 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Magnolia Cluster 3, Survey No.40 & Others (43/0, 44/1, 50/1(Part), 51/1, 51/2, 51/4, 51/5, 52/0, 53/0, 61/2), near The Reserves - Wadhwa Wise City, Vardoli Road, Vardoli, Vardoli, Panvel, Panvel, Raigad - 410206. | [15 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 40 & Others (43/0, 44/1, 50/1(Part), 51/1, 51/2, 51/4, 51/5, 52/0, 53/0, 61/2) | [15 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Vardoli | [15 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Vardoli Road |  | Locality/Village |  | Vardoli | [11 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Panvel |  | District |  | Raigad | [11 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410206 | [14 empty] | Mahad | Daund
Nearby Landmark |  | The Reserves - Wadhwa Wise City |  | Distance from city centre: |  | 11.7KM from Panvel Railway Station | [14 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [16 empty] | Mangaon | Ambegaon
[21 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [16 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [16 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [16 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential |  |  |  | FALSE
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [12 empty] | #VALUE!
East | NA | 12.00M Wide Road/Other Plot |  |  | Open Plot
West | NA | Other Plot |  |  | Open Plot
North | NA | 18.00 M Wide Road |  |  | Internal Road
South | NA | Other Plot |  |  | Open Plot/Kirki River
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 18.972442,73.194071
Location Link |  | https://maps.app.goo.gl/oR1AaqiqST8d2BqS6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 66161.214
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | -0.2575
Total FSI availaible for the project |  |  |  | 0.7425 |  |  |  | 0.7425
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 49125
Total number of Buildings |  |  |  | 56 Plots
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Navi Mumbai Airport Influence Notified Area (NAINA) | [14 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | CIDCO/NAINA/PANVEL/VARDOLI/LT-OO593/CC/2023/0311 |  |  | Dated | 2023-01-13 | [11 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No.(Plot No.A40) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00682/CC/2024/0515 |  |  | Dated | 2024-05-16 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.A40) |  | Not Provided |  |  | Dated | 2024-05-16 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area = 246.36 sq.m Proposed No. of units = 3 | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.A41) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00648/CC/2024/0499 |  |  | Dated | 2024-04-16 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.A41) |  | Not Provided |  |  | Dated | 2024-04-16 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area = 179.89 sq.m Proposed No. of units = 7 | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.A42) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00579/CC/2022/0263 |  |  | Dated | 2022-10-07 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to:(Plot No.A42) |  | Not Provided |  |  | Dated | 2022-10-07 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area 179.89 sq.m Proposed No. of units = 7 | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.B09 & F15) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00573/CC/2022/0257 |  |  | Dated | 2022-10-07 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: .(Plot No.B09 & F15) |  | Not Provided |  |  | Dated | 2022-10-07 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area = 163.08 sq.m Proposed No. of units = 6 | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No. (Plot No.B16) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00575/CC/2022/0259 |  |  | Dated | 2022-10-07 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to:(Plot No.B16) |  | Not Provided |  |  | Dated | 2022-10-07 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area 163.92 sq.m Proposed No. of units = 6 | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.B10, B14, C11, C13, C15, F16, F18, F20, G17, G19, G21) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00530/CC/2021/0099 |  |  | Dated | 2021-08-06 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: .(Plot No.B10, B14, C11, C13, C15, F16, F18, F20, G17, G19, G21) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00530/CC/2021/0099 |  |  | Dated | 2021-08-06 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Row House = 37Units (B.U.A = 171.27 Sq.Mt) | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.B11, B13, B15, C10, C12, C14, F17, F19, F21, G16, G18, G20) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00529/CC/2021/0098 |  |  | Dated | 2021-08-06 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.B11, B13, B15, C10, C12, C14, F17, F19, F21, G16, G18, G20) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00529/CC/2021/0098 |  |  | Dated | 2021-08-06 |  |  | 96 | [8 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Row House = 37Units (B.U.A = 171.27 Sq.Mt) | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.C09 & G15) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00574/CC/2022/0258 |  |  | Dated | 2022-10-07 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.C09 & G15) |  | Not Provided |  |  | Dated | 2022-10-07 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area 163.83 sq.m | [6 empty] | 52 | [8 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No. (Plot No.C16) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00572/CC/2022/0256 |  |  | Dated | 2022-10-07 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.C16) |  | Not Provided |  |  | Dated | 2022-10-07 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area 163.17 sq.m No of units proposed Sale component Residential –6 shall be read as Sale component = 02 units. | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No. (Plot No.D8 & D10) (Plot No. E11, E13 & E15) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00533/CC/2021/0107 |  |  | Dated | 2021-09-06 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.D8 & D10) (Plot No. E11, E13 & E15) |  | Not Provided |  |  | Dated | 2021-09-06 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[18 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No. (Plot No.D7, D9, D11, E12 & E14) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00532/CC/2021/0106 |  |  | Dated | 2021-09-06 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.D7, D9, D11, E12 & E14) |  | Not Provided |  |  | Dated | 2021-09-06 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[18 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.D12 & E16) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00570/CC/2022/0268 |  |  | Dated | 2022-10-07 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.D12 & E16) |  | Not Provided |  |  | Dated | 2022-10-07 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area 201.34 sq.m No of units proposed Sale component Residential – 9 shall be read as Sale component = 02 units. | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.F22) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00576/CC/2022/0260 |  |  | Dated | 2022-10-07 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.F22) |  | Not Provided |  |  | Dated | 2022-10-07 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area 163.17 sq.m No of units proposed Sale component Residential –6 shall be read as Sale component = 02 units. | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.G22) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00578/CC/2022/0262 |  |  | Dated | 2022-10-07 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.G22) |  | Not Provided |  |  | Dated | 2022-10-07 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area 163.17 sq.m No of units proposed Sale component Residential –6 shall be read as Sale component = 01 units. | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No. (Plot No.H18) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00651/CC/2023/0408 |  |  | Dated | 2023-07-21 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.H18) |  | Not Provided |  |  | Dated | 2023-07-21 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area 301.53 sq.m No of units proposed Sale component Residential – 4 shall be read as Sale component = 01 unit. | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No.H14) |  | CIDCO/NAINA/Wardoli/BP-00622/CC/2023/0393 |  |  | Dated | 2023-07-05 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Plot No.H14) |  | Not Provided |  |  | Dated | 2023-07-05 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area 317.67 sq.m No of units proposed Sale component Residential – 6 shall be read as Sale component = 01 unit. | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No.(Plot No. H15) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00621/CC/2023/0394 |  |  | Dated | 2023-07-05 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC NoValid Up to: (Plot No.H15) |  | Not Provided |  |  | Dated | 2023-07-05 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area = 321.05 sq.m No of units proposed Sale component Residential – 4 shall be read as Sale component = 01 unit. | [15 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
Approved Floor plan No.(Plot No. H16) |  | CIDCO/NAINA/Panvel/Wardoli/BP-00620/CC/2023/0395 |  |  | Dated | 2023-07-05 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC NoValid Up to: (Plot No.H16) |  | Not Provided |  |  | Dated | 2023-07-05 | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net Built-up Area = 321.05 sq.m No of units proposed Sale component Residential – 4 shall be read as Sale component = 01 unit. | [15 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
Environmental Clearance Certificate (EC) No Valid Up for: RZ 04 |  | SEIAA-EC-0000002284 |  |  | Dated | 2020-06-24 | [12 empty] | Town Planning Thane | Raigad Zilha Parishad
|  | Net Plot Area = 846129.39Sq.Mt Total B.U.A = 458145.51Sq.Mt | [16 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | Net Plot Area = 846129.39Sq.Mt Total B.U.A = 458145.51Sq.Mt |  |  | Dated | 0 | [12 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [12 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [18 empty] | Mira-Bhayandar Municipal Corporation
Area under Plot (Sq.Mt) |  |  | 38231.781
Approved no of units |  |  | Row House = 56
Approved no of Floors |  |  | Row House = G + 1st to 2nd Floor | [6 empty] | 51
Proposed no of Floors |  |  | Row House = G + 1st to 2nd Floor
B Wing = 1B + G + 1st to 19th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Club Magnolia, Tennis Court, Childrens Play Area, Yoga lawn, Jogging Track, Open Gymnasium, Flower Garden etc |  |  |  |  | as per sale Brochure on 99acres
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Row House = G + 1st to 2nd Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 2 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% | 10% |  | 45% |  | Excavation in process | 1
Plinth |  | 2 | 100% |  |  |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 1.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 2
Construction details: |  | B Wing = 1B + G + 1st to 19th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 10% |  | 45% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details:
Plot/ Banglow No | Progress % | Disburse-ment % | Stage of construction:
A-36 | 0% | 0% | Work not yet Started.
A-37 | 0% | 0% | Work not yet Started.
A-38 | 0% | 0% | Work not yet Started.
A-39 | 0% | 0% | Work not yet Started.
A-40 | 0% | 0% | Work not yet Started.
A-41 | 0% | 0% | Work not yet Started.
A-42 | 0% | 0% | Work not yet Started.
B-09 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed
B-10 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed
B-11 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed
B-12 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed
B-13 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed
B-14 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed
B-15 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed
B-16 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed
C-09 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
C-10 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
C-11 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
C-12 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
C-13 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
C-14 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
C-15 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
C-16 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
D-07 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed
D-08 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed
D-09 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed
D-10 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed
D-11 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed
D-12 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed
E-11 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed
E-12 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed
E-13 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
E-14 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
E-15 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
E-16 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
F-15 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
F-16 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
F-17 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor Completed
F-18 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor Completed
F-19 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor Completed
F-20 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor Completed
F-21 | 60% | 81.25% | Excavation, Plinth, RCC Slab, Brickwork Completed, External Plaster upto 0.5 Floor Completed
F-22 | 60% | 81.25% | Excavation, Plinth, RCC Slab, Brickwork Completed, External Plaster upto 0.5 Floor Completed
G-15 | 23.33% | 55% | Excavation, Plinth Completed, RCC upto 1 Slab Completed
G-16 | 23.33% | 55% | Excavation, Plinth Completed, RCC upto 1 Slab Completed
G-17 | 38.54% | 66.25% | Excavation, Plinth Completed, RCC upto 2 Slab, Brickwork upto 0.5 Floor Completed
G-18 | 38.54% | 66.25% | Excavation, Plinth Completed, RCC upto 2 Slab, Brickwork upto 0.5 Floor Completed
G-19 | 38.54% | 66.25% | Excavation, Plinth Completed, RCC upto 2 Slab, Brickwork upto 0.5 Floor Completed
G-20 | 38.54% | 66.25% | Excavation, Plinth Completed, RCC upto 2 Slab, Brickwork upto 0.5 Floor Completed
G-21 | 51.88% | 76.25% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed
G-22 | 51.88% | 76.25% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed
H-14 | 0% | 0% | Work not yet Started.
H-15 | 0% | 0% | Work not yet Started.
H-16 | 0% | 0% | Work not yet Started.
H-17 | 55.62% | 78.75% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 1.5 Floor Completed
H-18 | 0% | 0% | Work not yet Started.
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [11 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Row House Per Sq. Ft. |  |  |  |  | 9000 |  |  | 10000 TO 9000 AS DISCUSSED WITH SMITH SIR ON 11/09/2024. | [9 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. | [17 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [17 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [17 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [17 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [17 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [17 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [17 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [17 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [17 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 600000 | [12 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 7200 | [13 empty] | 1000000
Plot Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Detached |  | 3 |  | 8384.1549 |  | 12830.8376
Semi Detached |  | 24 |  | 45317.3334 |  | 69299.8844
Row House |  | 24 |  | 37155.6703 |  | 57163.9518
Total |  | 51 |  | 90857.1587 |  | 139294.6738 |  |  | 48
Grand Total |  | 51 |  | 90857.1587 |  | 139294.6738
Building details Floor Wise | [8 empty] | A40
Details of Plot Area
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Plot/ Bunglow No | Plot Type | Description | Plot Area (Sq.Ft.) | Built Up Area (Sq.Ft) | Carpet Area (Sq.Ft) | Terrace Area (Sq.Ft) | Salable Area (Sq.Ft) Loading 45% | Plot No. A-36 to A-39 Not mentioned in Approved Layout |  | 6.7936 |  |  | Permissible Built up Area on Basic FSI (In Sq.ft)
Ground Floor + 2nd Floor | [7 empty] | 40.086 | 66.6973 | 6.7936 | 10.764 |  | 2691
A-40 | Detached | G+2 | 2105.8905 | 2651.7652 | 2284.3468 | 668.692 | 3479.4759 | 52.259 | 19.8 |  |  |  | 2045.16
A-41 | Semi Detached | G+2 | 1472.0846 | 1936.3144 | 1760.463 | 551.0092 | 2690.4236 | A41 | 59.78 | 82.85 |  |  | 2045.16
A-42 | Semi Detached | G+2 | 1714.5976 | 1936.3144 | 1766.6738 | 551.0092 | 2699.4293 | [5 empty] | 2045.16
B-09 | Semi Detached | G+2 | 1706.6322 | 1755.3824 | 1588.5942 | 551.0092 | 2441.2138 | A42 |  |  |  |  | 2045.16
B-10 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 2045.16
B-11 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 2045.16
B-12 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 2045.16
B-13 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 2045.16
B-14 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 2045.16
B-15 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 2045.16
B-16 | Semi Detached | G+2 | 1744.5645 | 1755.7806 | 1588.9063 | 551.0092 | 2441.6665 | B09 & F15 |  |  |  |  | 2045.16
C-09 | Semi Detached | G+2 | 1706.6322 | 1755.3824 | 1588.5942 | 551.0092 | 2441.2138 | [5 empty] | 2045.16 |  |  | B10, B12, B14, C11,C13, C15, F16, F18, F20
C-10 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 2045.16
C-11 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | B16 |  |  |  |  | 2045.16
C-12 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 2045.16
C-13 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 2045.16
C-14 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 2045.16
C-15 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 2045.16
C-16 | Semi Detached | G+2 | 1751.1629 | 1756.4049 | 1588.7018 | 550.2557 | 2441.1816 | C16 |  |  |  |  | 2260.44
D-07 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.277 | 574.367 | 2810.5434 | [5 empty] | 2260.44
D-08 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.2447 | 574.367 | 2810.4965 | 16 |  |  |  |  | 2260.44 |  | B11,B13, B16, C10,C12, C14,F17,F19,F21,G16,G18,G20
D-09 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.277 | 574.367 | 2810.5434 | [5 empty] | 2260.44
D-10 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.2447 | 574.367 | 2810.4965 | D8 & D10 |  |  |  |  | 2260.44
D-11 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.277 | 574.367 | 2810.5434 | [5 empty] | 2260.44
D-12 | Semi Detached | G+2 | 2246.8451 | 2167.1592 | 1930.4265 | 536.0364 | 2933.1276 | [5 empty] | 2260.44
E-11 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.2447 | 574.367 | 2810.4965 | D7,D9,D11 E12,E14 |  |  |  |  | 2260.44
E-12 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.2447 | 574.367 | 2810.4965 | [5 empty] | 2260.44
E-13 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.2447 | 574.367 | 2810.4965 | [5 empty] | 2260.44
E-14 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.2447 | 574.367 | 2810.4965 | [5 empty] | 2260.44
E-15 | Semi Detached | G+2 | 1695.33 | 2246.3176 | 1839.2447 | 574.367 | 2810.4965 | [5 empty] | 2260.44
E-16 | Semi Detached | G+2 | 2246.8451 | 2167.1592 | 1930.4265 | 536.0364 | 2933.1276 | [5 empty] | 1883.7
F-15 | Semi Detached | G+2 | 1706.6322 | 1755.3824 | 1588.5942 | 551.0092 | 2441.2138 | [5 empty] | 1883.7
F-16 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 1883.7
F-17 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 1883.7
F-18 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 1883.7
F-19 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 1883.7
F-20 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 1883.7
F-21 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 1883.7
F-22 | Semi Detached | G+2 | 1751.1629 | 1756.4049 | 1588.7018 | 551.0092 | 2441.3699 | F22 |  |  |  |  | 1883.7
G-15 | Semi Detached | G+2 | 1706.6322 | 1755.3824 | 1588.5942 | 551.0092 | 2441.2138 | [5 empty] | 1883.7
G-16 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 1883.7
G-17 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 1883.7
G-18 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 1883.7
G-19 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 1883.7
G-20 | Row House | G+2 | 1210.95 | 1843.5503 | 1547.7448 | 548.0383 | 2381.2395 | [5 empty] | 1883.7
G-21 | Row House | G+2 | 1210.95 | 1843.5503 | 1548.4983 | 548.0383 | 2382.3321 | [5 empty] | 1883.7
G-22 | Semi Detached | G+2 | 1748.2135 | 1756.4049 | 1588.7018 | 551.0092 | 2441.3699 | [5 empty] | 3444.48
H-14 | Detached | G+2 | 3647.812 | 3419.3999 | 3103.8317 | 1049.4577 | 4762.9204 | H15 |  |  |  |  | 3498.3
H-15 | Semi Detached | G+2 | 2669.5151 | 3455.7176 | 3525.0378 | 1016.9612 | 5365.5451 | [5 empty] | 3498.3
H-16 | Semi Detached | G+2 | 2484.8263 | 3498.3 | 3302.3737 | 1016.9612 | 5042.6821 | [5 empty] | 3390.66
H-18 | Detached | G+2 | 2977.3762 | 3245.6689 | 2995.9764 | 977.1021 | 4588.4413
0
0
0
0
0
0
0
0
0
0
Remarks:
* | For Plot Nos A36 to A42 demarcation not done and construction work not started. For Plot Nos. B09 to H18 demarcation completed and Construction work is in process at the time of Visit. | [6 empty] | H17
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Please check for Environment Clearance Certificate.
* | We have considered plot nos from RERA.
* | Plot no. A36 to A39, H17 were not mentioned in approved plan and Floor Plans were not Provided.
* | Please provide approved CC for plot nos.A40, A41, H18, H14, H15, F22, C16, C09, G15, A42, G22, D12, E16, B16, B09, F15, D08, D10, D7, D9, D11, E12, E14.
* | Kirki River is located at 0.03km in South direction of Project.
* | Project is located at 11.7km from Panvel Railway Station & 4.2km from proposed Bhingar Railway Station. Habitation located at approx 1km from project. Wadhwa Construction And Infrastructure Private Limited other Project Wadhwa Wise City is at 1km distance from this project.
* | 1. As per the site visit dated 19/12/2024, the site engineer guided us that Building No. H18 is not yet started and Building No. H17 is under construction. 2. As per the site visit dated 05/04/2025, the site engineer guided us that Building No. H17 is not yet started and Building No. H18 is under construction. 3. We are maintaining the same construction stage for Building No. H17 as per the last visit dated 25/02/2025. 4. Please provide an architect certificate for Bldg No. 17 & 18 to confirm building naming & stage of construction. | [7 empty] | 1. As per the site visit dated 19/12/2024, the site engineer guided us that Building No. H18 is not yet started and Building No. H17 is under construction. 2. As per the site visit dated 05/04/2025, the site engineer guided us that Building No. H17 is not yet started and Building No. H18 is under construction. 3. We are maintaining the same construction stage for Building No. 17 as per the last visit dated 25/02/2025. 4. Please provide an architect certificate for Bldg No. 17 & 18 to confirm building naming & stage of construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nitesh Patil |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Magnolia Cluster 3
PHOTOGRAPHS OF PROPERTY : |  |  | Magnolia Cluster 3
Photographs :
Layout :
Google Map :
Formulas:
Vardoli = [Vardoli, row above]
Magnolia Cluster 3
A29 to A42
B7 to B8
B9 to B16
B9 to B10
B11 to B12
B13 to B14
B15 to B16
C7 to C8
C9 to C16
C9 to C10
C11 to C12
C13 to C14
C15 to C16
D9 to D10
D7 to D8
D11 to D12
E11 to E12
E13 to E14
E15 to E16
F15 to F16
F17 to F18
F19 to F20
F21 to F22
G15 to G22
H17
N
N
B9 to B16
B9 to B16
C9 to C16
D7 to D12
E11 & E12
E13 & E14
E15 & E16
F15 & F16
F17 & F18
F19 & F20
F21 & F22
G15 & G16
G17 & G18
G19 & G20
G21 & G22
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C106: SACHIN: Survey Nos.
Note on C108: SACHIN: Height from AMSL
Note on D111: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F229: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value

## Construction %
Plot/ Banglow no | Floor |  | Excavation | Plinth | RCC | Brick work | Internal Plaster | Ext. Plaster | Flooring | Painting | Finishing | Possession | Progress % | Disbursement % | Stage of construction: | Excavation | Plinth | RCC (Including podiums) | Brickwork | Internal Plaster | Ext. Plaster & Plumbing | Flooring & Fitting | Painting & Wooden | Building Common Amenities | Possession | Piling Work in process | Excavation in process | Excavation Completed | Footing in Process | Footing Completed | Basement 1 | Basement 2 | Basement 3 | Basement 4 | Plinth in process | Plinth completed
A-36 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | #REF! | Work not yet Started.
A-37 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | #REF! | Work not yet Started.
A-38 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | #REF! | Work not yet Started.
A-39 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | #REF! | Work not yet Started.
A-40 | G + 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 | #REF! | Work not yet Started.
A-41 | G + 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 | #REF! | Work not yet Started.
A-42 | G + 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 | #REF! | Work not yet Started.
B-09 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting | Completed
B-10 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting | Completed
B-11 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Flooring upto 1 Floor, Painting upto 1 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed | Completed
B-12 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Flooring upto 1 Floor, Painting upto 1 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed | Completed
B-13 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Flooring upto 1 Floor, Painting upto 1 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed | Completed
B-14 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Flooring upto 1 Floor, Painting upto 1 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed | Completed
B-15 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Flooring upto 1 Floor, Painting upto 1 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed | Completed
B-16 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Flooring upto 1 Floor, Painting upto 1 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed | Completed
C-09 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
C-10 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
C-11 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
C-12 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
C-13 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
C-14 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
C-15 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
C-16 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
D-07 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting | Completed
D-08 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting | Completed
D-09 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting | Completed
D-10 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting | Completed
D-11 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting | Completed
D-12 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 90% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting | Completed
E-11 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Flooring upto 1 Floor, Painting upto 1 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed | Completed
E-12 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 82.5% | 92.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Flooring upto 1 Floor, Painting upto 1 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed | Completed
E-13 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
E-14 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
E-15 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
E-16 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
F-15 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
F-16 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
F-17 | G + 2 | 2 | 2 | 2 | 3 | 2 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor Completed | 100% | 100% | 100% | 100% | 25% | 25% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
F-18 | G + 2 | 2 | 2 | 2 | 3 | 2 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor Completed | 100% | 100% | 100% | 100% | 25% | 25% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
F-19 | G + 2 | 2 | 2 | 2 | 3 | 2 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor Completed | 100% | 100% | 100% | 100% | 25% | 25% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
F-20 | G + 2 | 2 | 2 | 2 | 3 | 2 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor Completed | 100% | 100% | 100% | 100% | 25% | 25% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
F-21 | G + 2 | 2 | 2 | 2 | 3 | 2 | 0 | 0.5 | 0 | 0 | 0 | 0 | 60% | 81.25% | Excavation, Plinth, RCC Slab, Brickwork Completed, External Plaster upto 0.5 Floor Completed | 100% | 100% | 100% | 100% | 0% | 25% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , External Plaster upto 0.5 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
F-22 | G + 2 | 2 | 2 | 2 | 3 | 2 | 0 | 0.5 | 0 | 0 | 0 | 0 | 60% | 81.25% | Excavation, Plinth, RCC Slab, Brickwork Completed, External Plaster upto 0.5 Floor Completed | 100% | 100% | 100% | 100% | 0% | 25% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , External Plaster upto 0.5 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
G-15 | G + 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.33% | 55% | Excavation, Plinth Completed, RCC upto 1 Slab Completed | 100% | 100% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , RCC upto 1 Slab | Excavation, Plinth | Completed | Completed
G-16 | G + 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.33% | 55% | Excavation, Plinth Completed, RCC upto 1 Slab Completed | 100% | 100% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , RCC upto 1 Slab | Excavation, Plinth | Completed | Completed
G-17 | G + 2 | 2 | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 38.54% | 66.25% | Excavation, Plinth Completed, RCC upto 2 Slab, Brickwork upto 0.5 Floor Completed | 100% | 100% | 66.67% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , RCC upto 2 Slab, Brickwork upto 0.5 Floor | Excavation, Plinth | Completed | Completed
G-18 | G + 2 | 2 | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 38.54% | 66.25% | Excavation, Plinth Completed, RCC upto 2 Slab, Brickwork upto 0.5 Floor Completed | 100% | 100% | 66.67% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , RCC upto 2 Slab, Brickwork upto 0.5 Floor | Excavation, Plinth | Completed | Completed
G-19 | G + 2 | 2 | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 38.54% | 66.25% | Excavation, Plinth Completed, RCC upto 2 Slab, Brickwork upto 0.5 Floor Completed | 100% | 100% | 66.67% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , RCC upto 2 Slab, Brickwork upto 0.5 Floor | Excavation, Plinth | Completed | Completed
G-20 | G + 2 | 2 | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 38.54% | 66.25% | Excavation, Plinth Completed, RCC upto 2 Slab, Brickwork upto 0.5 Floor Completed | 100% | 100% | 66.67% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , RCC upto 2 Slab, Brickwork upto 0.5 Floor | Excavation, Plinth | Completed | Completed
G-21 | G + 2 | 2 | 2 | 2 | 3 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 51.88% | 76.25% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed | 100% | 100% | 100% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Brickwork upto 0.5 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
G-22 | G + 2 | 2 | 2 | 2 | 3 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 51.88% | 76.25% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed | 100% | 100% | 100% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Brickwork upto 0.5 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
H-14 | G + 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  | Work not yet Started.
H-15 | G + 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  | Work not yet Started.
H-16 | G + 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  | Work not yet Started.
H-17 | G + 2 | 2 | 2 | 2 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 55.62% | 78.75% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 1.5 Floor Completed | 100% | 100% | 100% | 75% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  |  | , Brickwork upto 1.5 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
H-18 | G + 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 |  | Work not yet Started.
Construction details: |  | G + 1 | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 1 | Excavation, Plinth, RCC Slab
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% | 50% |  | 75% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 2 | 100% |  |  |  |  | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 1

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate