## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com | [7 empty] | CC (Signature Not Verified)
Valuation Report
Date: |  |  |  | 30/08/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Sanpada | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-07-11 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Wadhwa Construction And Infrastructure Private Limited | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Wadhwa Construction And Infrastructure Private Limited | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Magnolia Cluster 4 | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Mahadev 9820740932 |  |  |  | 7 | 7 | 6
Site Person - Contact Details (Name & Contact No.) |  |  |  | Miss. Siya Chaudhary
Name / No of the Plot |  |  |  | Plot A43 to A51 Plot B17 to B24 Plot C16 to C23 Plot D13 to D19 Plot E17 to E22 Plot F22 to F37 Plot G23 to G28 |  |  |  | As per RERA | 8 | 5 | 10 | 5
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000021746 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Magnolia Cluster 4, Survey No.43/0, 44/1, 50/1(Part), 51/1, 51/2, 51/4, 51/5, 52/0, 53/0, 61/2 and 61/3, near The Reserves - Wadhwa Wise City, Vardoli Road, Vardoli, Vardoli, Panvel, Panvel, Raigad - 410206. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 43/0, 44/1, 50/1(Part), 51/1, 51/2, 51/4, 51/5, 52/0, 53/0, 61/2 and 61/3 | [5 empty] | refered other plots From CC | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Vardoli | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Vardoli Road |  | Locality/Village |  | Vardoli | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Panvel |  | District |  | Raigad | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410206 | [13 empty] | Mahad | Daund
Nearby Landmark |  | The Reserves - Wadhwa Wise City |  | Distance from city centre: |  | 11.6KM from Panvel Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential |  |  |  | FALSE
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 12.00M Wide Road/Other Plot |  |  | Open Plot
West | NA | Other Plot |  |  | Open Plot
North | NA | 18.00 M Wide Road |  |  | Internal Road
South | NA | Other Plot |  |  | Open Plot/Kirki River
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 18.973055,73.194670
Location Link |  | https://maps.app.goo.gl/66L9mCQokXxtArPG6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 66161.21
Permissible FSI |  |  |  | 0.19054
Permissible TDR/Paid FSI |  |  |  | 0.55197
Total FSI availaible for the project |  |  |  | 0.7425 |  |  |  | 0.7425
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 49125
Total number of Buildings |  |  |  | 60 Plots |  |  |  | As per RERA
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Navi Mumbai Airport Influence Notified Area (NAINA) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | CIDCO/NAINA/Panvel/Wardoli/LT-00593/CC/2023/0311 |  |  | Dated | 2023-01-13 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No.(Plot No.B-17) |  | CIDCO/NAINA/PANVEL/VARDOLI/LT-00567/CC/2023/0273 |  |  | Dated | 2022-10-07 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Approved Floor plan No.(Plot No.B-24) |  | CIDCO/NAINA/PANVEL/VARDOLI/LT-OO593/CC/2023/0311 |  |  | Dated | 2022-10-07 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Approved Floor plan No. |  | CIDCO/NAINA/Panvel/Wardoli/LT-00593/CC/2023/0311 |  |  | Dated | 2023-01-13 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | CIDCO/NAINA/Panvel/Wardoli/LT-00593/CC/2023/0311 |  |  | Dated | 2023-01-13 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Total Net BUA = 55000.00 Sq. M | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  |  |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 49125
Approved no of units |  |  | Semi - Detached -29, Row House -24, Detached - 7
Approved no of Floors |  |  | Row House = G + 2
Proposed no of Floors |  |  | Row House = G + 3
B Wing = 1B + G + 1st to 19th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 30/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Club Magnolia, Tennis Court, Childrens Play Area, Yoga lawn, Jogging Track, Open Gymnasium, Flower Garden etc
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details:
Plot/ Banglow No | Progress % | Disburse-ment % | Stage of construction: |  |  |  |  | 8 | 1 | 9
A43 to A51 | 0% | 0% | Work not yet Started. |  |  |  |  | 7 | 1 | 8
B17 to B24 | 0% | 0% | Work not yet Started. |  |  |  |  | 7 | 1 | 8
C16 to C23 | 0% | 0% | Work not yet Started. |  |  |  |  | 5 | 1 | 6
D13 to D19 | 0% | 0% | Work not yet Started. |  |  |  |  | 15 | 1 | 16
E17 to E22 | 0% | 0% | Work not yet Started. |  |  |  |  | 5 | 1 | 6
F22 to F37 | 0% | 0% | Work not yet Started. |  |  |  |  | 6 | 1 | 7
G23 to G28 | 0% | 0% | Work not yet Started. | [6 empty] | 60
8 | 0% | 0% | Work not yet Started.
9 | 0% | 0% | Work not yet Started.
10 | 0% | 0% | Work not yet Started.
11 | 0% | 0% | Work not yet Started.
12 | 0% | 0% | Work not yet Started.
13 | 0% | 0% | Work not yet Started.
Construction details: |  | Row House = G + 3 | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 3 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% | 10% |  | 45% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% |  |  |  |  | Excavation Completed | 3
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 2.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 3
Construction details: |  | B Wing = 1B + G + 1st to 19th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 10% |  | 45% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Plot Per Sq. Ft. |  |  |  |  | 9000 |  |  | 7500 to 8500 by smith on 21/01/2025 higher IndeX II | [8 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. | [16 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 600000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 7200 |  |  |  | RATE 9000 by SMITH VERBAL MATCHED WITH RATE OF WADHWA RZ PHASE 1 On 30/08/2025 | [8 empty] | 1000000
Plot Area Details :
Plot Type |  | No. of Units |  | Total Plot Area |  | Total Permissible Builtup Area
Semi - Detached |  | 29 |  | 57792.1851 |  | 65929.5
Row House |  | 24 |  | 29825.1603 |  | 48115.08
Detached |  | 7 |  | 25136.3727 |  | 28955.16
Total |  | 60 |  | 112753.7181 |  | 142999.74
Grand Total |  | 60 |  | 112753.7181 |  | 142999.74
Building Details Floor Wise
Details of Plot Area
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Plot/ Bunglow No | Plot Type | Plot Area (Sq.Mt.) | Plot Area (Sq.Ft.) | Carpet Area | Permissible Built up Area on Basic FSI (In Sq.ft) | Demarkation Status
Ground Floor
A-43 | Semi - Detached | 159.29 | 1714.5976 | 0 | 2045.16 | No |  |  |  | #DIV/0!
A-44 | Row House | 113.2 | 1218.4848 | 0 | 2045.16 | No
A-45 | Row House | 113.025 | 1216.6011 | 0 | 2045.16 | No
A-46 | Row House | 113.025 | 1216.6011 | 0 | 2045.16 | No |  |  |  |  | 60
A-47 | Row House | 113.025 | 1216.6011 | 0 | 2045.16 | No
A-48 | Row House | 113.025 | 1216.6011 | 0 | 2045.16 | No
A-49 | Row House | 113.025 | 1216.6011 | 0 | 2045.16 | No
A-50 | Semi - Detached | 159.29 | 1714.5976 | 0 | 2045.16 | No
A-51 | Detached | 290.898 | 3131.2261 | 0 | 4305.6 | No
B-17 | Semi - Detached | 172.512 | 1856.9192 | 0 | 2045.16 | No
B-18 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
B-19 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
B-20 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
B-21 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
B-22 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
B-23 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
B-24 | Semi - Detached | 179.55 | 1932.6762 | 0 | 2045.16 | No
C-16 | Semi - Detached | 162.687 | 1751.1629 | 0 | 2045.16 | No
C-17 | Semi - Detached | 167.778 | 1805.9624 | 0 | 2045.16 | No
C-18 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
C-19 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
C-20 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
C-21 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
C-22 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
C-23 | Row House | 112.5 | 1210.95 | 0 | 2045.16 | No
D-13 | Semi - Detached | 249.749 | 2688.2982 | 0 | 2260.44 | No
D-14 | Semi - Detached | 157.5 | 1695.33 | 0 | 2260.44 | No
D-15 | Semi - Detached | 157.5 | 1695.33 | 0 | 2260.44 | No
D-16 | Semi - Detached | 157.5 | 1695.33 | 0 | 2260.44 | No
D-17 | Semi - Detached | 157.5 | 1695.33 | 0 | 2260.44 | No
D-18 | Semi - Detached | 157.5 | 1695.33 | 0 | 2260.44 | No
D-19 | Detached | 221.435 | 2383.5263 | 0 | 2744.82 | No
E-17 | Semi - Detached | 249.927 | 2690.2142 | 0 | 2260.44 | No
E-18 | Semi - Detached | 157.5 | 1695.33 | 0 | 2260.44 | No
E-19 | Semi - Detached | 157.5 | 1695.33 | 0 | 2260.44 | No
E-20 | Semi - Detached | 157.5 | 1695.33 | 0 | 2260.44 | No
E-21 | Semi - Detached | 157.5 | 1695.33 | 0 | 2260.44 | No
E-22 | Semi - Detached | 249.165 | 2682.0121 | 0 | 2260.44 | No
F-22 | Semi - Detached | 162.687 | 1751.1629 | 0 | 1883.7 | No
F-23 | Semi - Detached | 167.292 | 1800.7311 | 0 | 1883.7 | No
F-24 | Row House | 123.75 | 1332.045 | 0 | 1883.7 | No
F-25 | Row House | 123.75 | 1332.045 | 0 | 1883.7 | No
F-26 | Row House | 123.75 | 1332.045 | 0 | 1883.7 | No
F-27 | Row House | 123.75 | 1332.045 | 0 | 1883.7 | No
F-28 | Row House | 123.75 | 1332.045 | 0 | 1883.7 | No
F-29 | Row House | 123.75 | 1332.045 | 0 | 1883.7 | No
F-30 | Semi - Detached | 170.059 | 1830.5151 | 0 | 1883.7 | No
F-31 | Detached | 305.929 | 3293.0198 | 0 | 4197.96 | No
F-32 | Semi - Detached | 214.891 | 2313.0867 | 0 | 2637.18 | No
F-33 | Semi - Detached | 215.177 | 2316.1652 | 0 | 2637.18 | No
F-34 | Semi - Detached | 215.462 | 2319.233 | 0 | 2637.18 | No
F-35 | Semi - Detached | 217.314 | 2339.1679 | 0 | 2637.18 | No
F-36 | Detached | 357.6 | 3849.2064 | 0 | 4197.96 | No
F-37 | Detached | 396.949 | 4272.759 | 0 | 5382 | No
G-23 | Detached | 268.085 | 2885.6669 | 0 | 3713.58 | No
G-24 | Semi - Detached | 222.153 | 2391.2549 | 0 | 2583.36 | No
G-25 | Semi - Detached | 212.354 | 2285.7785 | 0 | 2583.36 | No
G-26 | Semi - Detached | 205.514 | 2212.1527 | 0 | 2583.36 | No
G-27 | Semi - Detached | 198.674 | 2138.5269 | 0 | 2583.36 | No
G-28 | Detached | 494.33 | 5320.9681 | 0 | 4413.24 | No
Remarks:
1 | Construction Work has not yet Started. Boundary wall construction work is in process of Plot A43 to A51, F22 to F37 & G23 to G28.
1 | We considered Saleable area of Flat as per Builder area Sheet.
1 | We have considered Saleable area of Commercial as per our Calculation.
1 | We considered Carpet area as per Approved Plan.
2 | We considered Gross Plot area = Net Plot Area
3 | We have considered proposed No. of Floor for Stage Calculation.
4 | We have considered rate by verifying it from market inquire.
5 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
6 | Car parking is subjected to authentic documentation.
7 | We have considered plot nos from RERA.
8 | Plot No.F38 is registered on RERA but is not mentioned in approved plan.
9 | Kirki River is located at 0.03km in South direction of Project.
10 | Project is located at 11.6km from Panvel Railway Station & 4.2km from proposed Bhingar Railway Station. Habitation located at approx 1km from project. Wadhwa Construction And Infrastructure Private Limited other Project Wadhwa Wise City is at 1km distance from this project
11 | We have updated latest CC (On 08/01/2025).
12 | Recommended Rates/Other Charges of the Property have been revised on 22/01/2025. with reference to Index II of Plot No. A49, which is attached below
*
* | Please check for Environment Clearance Certificate.
13 | Recommended Rates of the Property have been revised on 30/08/2025.
Undertaking : | [7 empty] | Please check for Environment Clearance Certificate.
1) We have personally visited the property & identified the same based on the documents provided. | [7 empty] | Currently this APF Done for Plot, Therefore EC Remark removed as per dicussion with Smith sir on 02/01/2025
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nitesh Patil |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Magnolia Cluster 4
Remark No. 13
Layout :
Google Map :
Formulas:
Vardoli = [Vardoli, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C57: SACHIN: Floor with height
Note on C59: SACHIN: Survey Nos.
Note on C61: SACHIN: Height from AMSL
Note on D64: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F139: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value

## Construction %
Construction details: |  | G + 1 | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 1 | Excavation, Plinth, RCC Slab
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% | 50% |  | 75% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 2 | 100% |  |  |  |  | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 1
Plot/ Banglow no | Floor |  | Excavation | Plinth | RCC | Brick work | Internal Plaster | Ext. Plaster | Flooring | Painting | Finishing | Possession | Progress % | Disbursement % | Stage of construction: | Excavation | Plinth | RCC (Including podiums) | Brickwork | Internal Plaster | Ext. Plaster & Plumbing | Flooring & Fitting | Painting & Wooden | Building Common Amenities | Possession | Piling Work in process | Excavation in process | Excavation Completed | Footing in Process | Footing Completed | Basement 1 | Basement 2 | Basement 3 | Basement 4 | Plinth in process | Plinth completed
1 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work Completed. Possession granted to the Building. | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities | Completed
2 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
A43 to A51 | G + 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5 | 1 | 2 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 | 2 | Work not yet Started.
B17 to B24 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
C16 to C23 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
D13 to D19 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
E17 to E22 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
F22 to F37 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
G23 to G28 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
8 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
9 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
10 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
11 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
12 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
13 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
14 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
15 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
16 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
17 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
18 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
19 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
20 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!
[16 empty] | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work not yet Started. | #DIV/0! | #DIV/0!

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19
20
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate