## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-11
Name of the builder group |  |  |  | M/s. Pushpa Construction Company
Name of the builder company |  |  |  | M/s. Pushpa Construction Company
Name of the Project |  |  |  | Pearl Residency
Contact Details ( Name & Contact No.) |  |  |  | 022-2404 0348 Mr. Mahesh Sawant – 99202 66853 Mr. Ajit Sathe – 97695 43907
Name / No of the Building |  |  |  | Building No. 1=( A, B, C & D) Wing
Docouments Provided |  |  |  | Approved Plans, CC, OC.
RERA No. |  |  |  | P51900008616
Project location details |  | Development of Proposed Amalgamated & Subdivided Plots For :- Kalpataru, Jaykalimata & Jay-Bajrangbali CHS. Soc. On Plot Bearing C S No. 181(Part) & 509 At: Babu Jagjivanram Nagar & Khamdev Nagar At: Dharvi - Division Dharavi Mumbai.
CTS No |  | 181 (Pt) & 509
Locality |  | Dharavi
Road |  | Sant Rohidas Marg |  | Village |  | Dharavi
City |  | Sion |  | District |  | Mumbai
Taluka |  | Dharavi |  | Pin Code |  | 400017
Nearby Landmark |  | United Residency |  | Distance from city centre: |  | 1KM from Sion Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | United Residency
West | NA | NA |  |  | Slums
North | NA | NA |  |  | Sant Rohidas Marg
South | NA | NA |  |  | Kalpataru Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.047831, 72.8586878
Location Link |  | https://goo.gl/maps/FfnSFgTr5u2WGKvJA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 7875.34
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 1.3775
Total FSI availaible for the project |  |  |  | 4.3775
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 34474.17
Total number of Buildings |  |  |  | 04 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | SRA
Layout Approval No |  | SRA/ENG/1721/GN/ML/OCC |  |  | Dated | 2022-06-15
Approved Floor plan No. |  | SRA/ENG/1721/GN/ML/OCC |  |  | Dated | 2022-06-15
Commencement-CC No Valid Up to: |  | SRA/ENG/1721/GN/ML/AP |  |  | Dated | 2022-06-15
|  | upto 21st Floor as per amended plans dated 03/07/2019. |  |  | Valid Upto Date | 2017-12-18
Airport Authority of India NOC No. Valid upto : |  | AAI/RHQ/WR/NOC/SNCR/WEST/B/011017/190626 |  |  | Dated | 2019-03-19
80.99M
Part O. Certificate No.: Approved upto : |  | SRA/ENG/1721/GN/ML/OCC |  |  | Dated | 2022-06-15
Building No.1 ( Wing A, B, C & D) = Gr + 1st to 18th Floor
O. Certificate No.: Approved upto : |  | SRA/ENG/1721/GN/ML/OCC |  |  | Dated | 2022-10-19
Building No.1 ( Wing A, B, C & D) = 4B + 1st to 23rd Floor
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 34474.17
Approved no of units |  |  | Flats -313, Shops -40.
Approved no of Floors |  |  | Building No. 1 (A, B, C & D) Wing = 4B + Gr + 1st to 23th Floor
Proposed no of Floors |  |  | Building No. 1 (A, B, C & D) Wing = 4B + Gr + 1st to 23th Floor
B Wing = 4Basement + Gr + 1st to 23th Floor
C Wing = 4Basement + Gr + 1st to 23th Floor
D Wing = 4Basement + Gr + 1st to 23th Floor
Expected Completion |  |  | As per RERA- Completed.
Projected life of the structure |  |  | 57 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes
Construction details: |  | Building No. 1 (A, B, C & D) Wing = 4B + Gr + 1st to 23th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 4 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. OC received. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 100% |  | 100% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 3.8333
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 7.6667
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 11.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 15.3333
Flooring & Fitting | Flooring & Fitting | 23 | 100% |  |  |  |  | Basement 3 | 19.1667
Painting & Wooden |  | 23 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 23 | 100% |  |  |  |  | Plinth in process | 0
Possession |  | 23 | 100% |  |  |  |  | Plinth completed | 23
Construction details: |  | B Wing = 4Basement + Gr + 1st to 23th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 4 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 100% |  | 100% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 3.8333
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 7.6667
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 11.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 15.3333
Flooring & Fitting | Flooring & Fitting | 23 | 100% |  |  |  |  | Basement 3 | 19.1667
Painting & Wooden |  | 23 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 23 | 100% |  |  |  |  | Plinth in process | 0
Possession |  | 23 | 100% |  |  |  |  | Plinth completed | 23
Construction details: |  | C Wing = 4Basement + Gr + 1st to 23th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 4 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 100% |  | 100% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 3.8333
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 7.6667
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 11.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 15.3333
Flooring & Fitting | Flooring & Fitting | 23 | 100% |  |  |  |  | Basement 3 | 19.1667
Painting & Wooden |  | 23 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 23 | 100% |  |  |  |  | Plinth in process | 0
Possession |  | 23 | 100% |  |  |  |  | Plinth completed | 23
Construction details: |  | D Wing = 4Basement + Gr + 1st to 23th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 4 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 100% |  | 100% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 3.8333
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 7.6667
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 11.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 15.3333
Flooring & Fitting | Flooring & Fitting | 23 | 100% |  |  |  |  | Basement 3 | 19.1667
Painting & Wooden |  | 23 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 23 | 100% |  |  |  |  | Plinth in process | 0
Possession |  | 23 | 100% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 14500
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 20000
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 11600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Sale |  | 7 |  | 1624.3952 |  | 2599.0324
Rehab |  | 33 |  | 7121.0318 |  | 11393.6509
Total |  | 40 |  | 8745.4271 |  | 13992.6833
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  |  |  | 369833.2848
A Wing |  | 104 |  | 83978.8981 |  | 126563.8493 |  |  |  |  | 245492.1799
B Wing |  | 84 |  | 53227.2265 |  | 79965.8098
C Wing |  | 84 |  | 65838.5442 |  | 98757.8163
D Wing |  | 42 |  | 33702.084 |  | 50553.126
Total |  | 314 |  | 236746.7528 |  | 355840.6015
Building details Floor Wise
Details of Flats in Building
(Sale /Rehab) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Building No. 1
Wing A, B, C, D
Ground Floor Commercial & Parking
Sale | 1 | Shop | 183.8491 | 0 | 294.1586 | Ground Floor Commercial & Parking
Sale | 1A | Shop | 182.7727 | 0 | 292.4364
Sale | 2 | Shop | 348.0001 | 0 | 556.8002
Sale | 3 | Shop | 114.7442 | 0 | 183.5908
Rehab | 5 | Shop | 215.0647 | 0 | 344.1036
Rehab | 6 | Shop | 367.9135 | 0 | 588.6616
Rehab | 7 | Shop | 148.5432 | 0 | 237.6691
Rehab | 8 | Shop | 154.571 | 0 | 247.3137
Rehab | 9 | Shop | 218.6168 | 0 | 349.7869
Sale | 9A | Shop | 179.8664 | 0 | 287.7863
Rehab | 10 | Shop | 369.2052 | 0 | 590.7283
Rehab | 11 | Shop | 374.5872 | 0 | 599.3395
Rehab | 12 | Shop | 197.8423 | 0 | 316.5477
Rehab | 13 | Shop | 369.3128 | 0 | 590.9005
Rehab | 14 | Shop | 192.245 | 0 | 307.5921
Rehab | 15 | Shop | 372.7573 | 0 | 596.4117
Rehab | 16 | Shop | 218.5092 | 0 | 349.6147
Rehab | 17 | Shop | 407.525 | 0 | 652.0401
Rehab | 18 | Shop | 252.4158 | 0 | 403.8653
Rehab | 19 | Shop | 240.0372 | 0 | 384.0595
Rehab | 20 | Shop | 207.7452 | 0 | 332.3923
Rehab | 21 | Shop | 213.1272 | 0 | 341.0035
Rehab | 22 | Shop | 581.4713 | 0 | 930.354
Rehab | 23 | Shop | 218.5092 | 0 | 349.6147
Rehab | 24 | Shop | 107.4247 | 0 | 171.8796 |  |  |  | 10.764
Rehab | 25 | Shop | 91.9246 | 0 | 147.0793
Rehab | 26 | Shop | 139.932 | 0 | 223.8912
Rehab | 27 | Shop | 139.932 | 0 | 223.8912
Rehab | 28 | Shop | 72.1188 | 0 | 115.3901
Rehab | 29 | Shop | 32.7226 | 0 | 52.3561
Rehab | 30 | Shop | 135.0882 | 0 | 216.1411
Sale | 31 | Shop | 468.234 | 0 | 749.1744 |  |  | 13.4925
Rehab | 32 | Shop | 137.3486 | 0 | 219.7578
Rehab | 33 | Shop | 185.7866 | 0 | 297.2586
Rehab | 34 | Shop | 68.5667 | 0 | 109.7067
Sale | 35 | Shop | 146.9286 | 0 | 235.0858
Rehab | 36 | Shop | 202.9014 | 0 | 324.6422
Rehab | 37 | Shop | 130.1368 | 0 | 208.2188
Rehab | 38 | Shop | 186.4325 | 0 | 298.292
Rehab | 39 | Shop | 170.717 | 0 | 273.1473
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
[5 empty] | 50% |  |  |  |  | 10.764
Building No. 1
A Wing
1st to 4th Basement For Parking
1st Floor For Amenities
2nd Floor For Residential
1 |  | 2BHK | 714.7296 | 93.5069 | 1165.6013 | 2nd Floor For Residential |  | 62.6952
2 |  | 3BHK | 1048.1983 | 0 | 1572.2975
3 |  | 2BHK | 744.8688 | 0 | 1117.3032
4 |  | 1.5BHK | 603.8604 | 0 | 905.7906
3rd Floor For Residential
1 |  | 2BHK | 714.7296 | 0 | 1072.0944 | 3rd Floor For Residential |  | 62.6952
2 |  | 3BHK | 1048.1983 | 188.4346 | 1666.5148
3 |  | 2BHK | 744.8688 | 73.1145 | 1190.4177
4 |  | 3BHK | 1008.5868 | 0 | 1512.8802
5 |  | 2BHK | 571.0302 | 0 | 856.5453
4th & 5th Floor
1 |  | 2BHK | 714.7296 | 0 | 1072.0944 | 4th & 5th Floor |  | 62.6952
2 |  | 3BHK | 1048.1983 | 0 | 1572.2975
3 |  | 2BHK | 744.8688 | 0 | 1117.3032
4 |  | 3BHK | 1008.5868 | 0 | 1512.8802
5 |  | 2BHK | 571.0302 | 0 | 856.5453
6th, 8th, 9th, 10th, 11th, 12th, 13th, 15th, 16th & 17th Floor
1 |  | 2BHK | 714.7296 | 0 | 1072.0944 | 6th, 8th, 9th, 10th, 11th, 12th, 13th, 15th, 16th & 17th Floor |  | 62.6952
2 |  | 3BHK | 1048.1983 | 0 | 1572.2975
3 |  | 2BHK | 744.8688 | 0 | 1117.3032
4 |  | 3BHK | 1008.5868 | 0 | 1512.8802
5 |  | 2BHK | 571.0302 | 0 | 856.5453
7th Floor (Part Refuge Area)
1 |  | 2BHK | 714.7296 | 0 | 1072.0944 | 7th Floor (Part Refuge Area) |  | 62.6952
2 |  | 3BHK | 1048.1983 | 0 | 1572.2975
3 |  | 2BHK | 744.8688 | 0 | 1117.3032
4 |  | Refuge Area
5 |  | 2BHK | 571.0302 | 0 | 856.5453
14th Floor (Part Refuge Area)
1 |  | 2BHK | 714.7296 | 0 | 1072.0944 | 14th Floor (Part Refuge Area) |  | 62.6952 | 11193.0442
2 |  | 3BHK | 1048.1983 | 0 | 1572.2975
3 |  | 2BHK | 744.8688 | 0 | 1117.3032
4 |  | Refuge Area
5 |  | 2BHK | 571.0302 | 0 | 856.5453
18th, 19th, 20th & 22nd Floor
1 |  | 2BHK | 714.7296 | 0 | 1072.0944 | 18th, 19th, 20th & 22nd Floor |  | 62.6952
2 |  | 3BHK | 1048.1983 | 0 | 1572.2975
3 |  | 2BHK | 744.8688 | 0 | 1117.3032
4 |  | 3BHK | 1008.5868 | 0 | 1512.8802
5 |  | 2BHK | 571.0302 | 0 | 856.5453
21st Floor (Part Refuge Area)
1 |  | 2BHK | 714.7296 | 0 | 1072.0944 | 21st Floor (Part Refuge Area) |  | 62.6952
2 |  | 3BHK | 1048.1983 | 0 | 1572.2975
3 |  | 2BHK | 744.8688 | 0 | 1117.3032
4 |  | 2BHK | 610.857 | 0 | 916.2855
5 |  | 2BHK | 571.0302 | 0 | 856.5453
23rd Floor (Part Terrace Area)
1 |  | 3BHK | 968.2218 | 0 | 1452.3327 | 23rd Floor (Part Terrace Area) |  | 62.6952
2 |  | 2BHK | 565.6482 | 0 | 848.4723
B Wing
1st Floor For Amenities
2nd Floor For Residential & Amenities
1 |  | 2BHK | 719.2505 | 61.893 | 1140.7687 | 2nd Floor For Residential & Amenities
2 |  | 2BHK | 601.1694 | 126.1541 | 964.8311 |  |  |  |  | 10.764
3rd, 4th, 5th Floor For Residential
1 |  | 2BHK | 719.2505 | 0 | 1078.8757 | 3rd, 4th, 5th Floor For Residential
2 |  | 2BHK | 601.1694 | 0 | 901.7541
3 |  | 2BHK | 719.2505 | 0 | 1078.8757
4 |  | 1BHK | 501.2795 | 0 | 751.9192
6th, 8th, 9th, 10th, 11th, 12th, 13th, 15th, 16th & 17th Floor
1 |  | 2BHK | 719.2505 | 0 | 1078.8757 | 6th, 8th, 9th, 10th, 11th, 12th, 13th, 15th, 16th & 17th Floor
2 |  | 2BHK | 601.1694 | 0 | 901.7541
3 |  | 2BHK | 719.2505 | 0 | 1078.8757
4 |  | 1BHK | 501.2795 | 0 | 751.9192
7th Floor (Part Refuge Area)
1 |  | 2BHK | 719.2505 | 0 | 1078.8757 | 7th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 2BHK | 719.2505 | 0 | 1078.8757
4 |  | 1BHK | 501.2795 | 0 | 751.9192
14th Floor (Part Refuge Area)
1 |  | 2BHK | 719.2505 | 0 | 1078.8757 | 14th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 2BHK | 719.2505 | 0 | 1078.8757
4 |  | 1BHK | 501.2795 | 0 | 751.9192
18th, 19th, 20th & 22nd Floor
1 |  | 2BHK | 719.2505 | 0 | 1078.8757 | 18th, 19th, 20th & 22nd Floor
2 |  | 2BHK | 601.1694 | 0 | 901.7541
3 |  | 2BHK | 719.2505 | 0 | 1078.8757
4 |  | 1BHK | 501.2795 | 0 | 751.9192
21st Floor (Part Refuge Area)
1 |  | 2BHK | 719.2505 | 0 | 1078.8757 | 21st Floor (Part Refuge Area)
2 |  | 1RK | 350.3682 | 0 | 525.5523
3 |  | 2BHK | 719.2505 | 0 | 1078.8757
4 |  | 1BHK | 501.2795 | 0 | 751.9192
23rd Floor
1 |  | 2BHK | 719.2505 | 0 | 1078.8757 | 23rd Floor
2 |  | 2BHK | 601.1694 | 0 | 901.7541
3 |  | 2BHK | 719.2505 | 0 | 1078.8757
4 |  | 1BHK | 501.2795 | 0 | 751.9192
C Wing
1st Floor For Amenities
2nd Floor For Residential
1 |  | 1BHK | 499.9878 | 0 | 749.9817 | 2nd Floor For Residential
2 |  | 3.5BHK | 1106.001 | 0 | 1659.0015
3 |  | 2BHK | 777.699 | 0 | 1166.5485
4 |  | 2BHK | 777.699 | 0 | 1166.5485
3rd, 4th, 5th Floor For Residential
1 |  | 1BHK | 499.9878 | 0 | 749.9817 | 3rd, 4th, 5th Floor For Residential
2 |  | 3.5BHK | 1106.001 | 0 | 1659.0015
3 |  | 2BHK | 777.699 | 0 | 1166.5485
4 |  | 2BHK | 777.699 | 0 | 1166.5485
6th, 8th, 9th, 10th, 11th, 12th, 13th, 15th, 16th & 17th Floor
1 |  | 1BHK | 499.9878 | 0 | 749.9817 | 6th, 8th, 9th, 10th, 11th, 12th, 13th, 15th, 16th & 17th Floor
2 |  | 3.5BHK | 1106.001 | 0 | 1659.0015
3 |  | 2BHK | 777.699 | 0 | 1166.5485
4 |  | 2BHK | 777.699 | 0 | 1166.5485
7th Floor (Part Refuge Area)
1 |  | 1BHK | 499.9878 | 0 | 749.9817 | 7th Floor (Part Refuge Area)
2 |  | 3.5BHK | 1106.001 | 0 | 1659.0015
3 |  | 2BHK | 777.699 | 0 | 1166.5485
4 |  | Refuge Area
14th Floor (Part Refuge Area)
1 |  | 1BHK | 499.9878 | 0 | 749.9817 | 14th Floor (Part Refuge Area)
2 |  | 3.5BHK | 1106.001 | 0 | 1659.0015
3 |  | 2BHK | 777.699 | 0 | 1166.5485
4 |  | Refuge Area
18th, 19th, 20th & 22nd Floor
1 |  | 1BHK | 499.9878 | 0 | 749.9817 | 18th, 19th, 20th & 22nd Floor
2 |  | 3.5BHK | 1106.001 | 0 | 1659.0015
3 |  | 2BHK | 777.699 | 0 | 1166.5485
4 |  | 2BHK | 777.699 | 0 | 1166.5485
21st Floor (Part Refuge Area)
1 |  | 1BHK | 499.9878 | 0 | 749.9817 | 21st Floor (Part Refuge Area)
2 |  | 1BHK | 504.8316 | 0 | 757.2474
3 |  | 2BHK | 777.699 | 0 | 1166.5485
4 |  | 2BHK | 777.699 | 0 | 1166.5485
23rd Floor (Part Terrace Area)
1 |  | 1BHK | 499.9878 | 0 | 749.9817 | 23rd Floor (Part Terrace Area)
2 |  | 3.5BHK | 1106.001 | 0 | 1659.0015
D Wing
1st Floor For Amenities
2nd Floor For Residential
1 |  | 2BHK | 787.3866 | 0 | 1181.0799 | 2nd Floor For Residential
2 |  | 2BHK | 794.3832 | 0 | 1191.5748
3rd, 4th, 5th Floor For Residential
1 |  | 2BHK | 787.3866 | 0 | 1181.0799 | 3rd, 4th, 5th Floor For Residential
2 |  | 2BHK | 794.3832 | 0 | 1191.5748
6th, 8th, 9th, 10th, 11th, 12th, 13th, 15th, 16th & 17th Floor
1 |  | 2BHK | 787.3866 | 0 | 1181.0799 | 6th, 8th, 9th, 10th, 11th, 12th, 13th, 15th, 16th & 17th Floor
2 |  | 2BHK | 794.3832 | 0 | 1191.5748
7th Floor (Part Refuge Area)
1 |  | 4BHK | 1144.7514 | 0 | 1717.1271 | 7th Floor (Part Refuge Area)
2 |  | Refuge Area
14th Floor (Part Refuge Area)
1 |  | 4BHK | 1144.7514 | 0 | 1717.1271 | 14th Floor (Part Refuge Area)
2 |  | Refuge Area
18th, 19th, 20th & 22nd Floor
1 |  | 2BHK | 787.3866 | 0 | 1181.0799 | 18th, 19th, 20th & 22nd Floor
2 |  | 2BHK | 794.3832 | 0 | 1191.5748
21st Floor (Part Refuge Area)
1 |  | 2BHK | 787.3866 | 0 | 1181.0799 | 21st Floor (Part Refuge Area) |  | 10.764
2 |  | 2BHK | 624.8502 | 0 | 937.2753
23rd Floor
1 |  | 2BHK | 764.7822 | 0 | 1147.1733 | 23rd Floor
2 |  | 2BHK | 763.7058 | 0 | 1145.5587
Remarks:
* | Building No. 1 (A, B, C & D) = All work Completed. OC received.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr.Kartik (9987531056).
* | We have updated O.C (on 16/03/2023).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Uday Kumar |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Pearl Residency
Google Map :
Wing B
Wing C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted