## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-07-14
Branch Name/ID |  | Mahindra Rural Housing Finance - Kalyan |  |  | Date & Time of Site Visit | 14/07/2025 at 14:58
Name of the person met at site & Contact No |  | Ms. Riya Shah 8108389545 |  |  | Date of Report Release | 15/07/2025
Project Details
Name of the project |  | Sharda Serene
Address |  | Sharda Serene, Survey No.15/1/A and 15/1/B, near Sundew Complex, Ahilyanagar Kalyan Road, Mharal, Kalyan, Kalyan, Thane - 421103. | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 15/1/A and 15/1/B | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Mharal | [7 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Ahilyanagar Kalyan Road | [7 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Kalyan | [7 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Kalyan | [7 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Thane | [7 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 421103 | [7 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | PR1330002400054 | [10 empty] | Mahad | Daund
Landmark |  | Sundew Complex | [10 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.2460556,73.1746389 | [7 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/a2cr4AWs1xuMB1HS7 | [10 empty] | Poladpur | Purandhar
Name of the builder / developer |  | M/s. Shardhha Buildscape LLP | [10 empty] | Mahasala | Bhor
Office address (agreement) |  | Flat 701, CTS 3342, 3345, 3347, Sai Arcade, Near Gita Marriage Hall, Subhash Road, Shivaji Chowk, Bazar Peth Police Station, Tal. Kalyan, Dist. Thane 421301. | [10 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [10 empty] | Murud | Velhe
Builder Bank Details |  | Saraswat Cooperative Bank Limited IFSC Code - SRCB0000345
Contact No. |  | Mr. Rahul B Nandwani 9833537363
Location of the project Municipal Limit : |  | District Collector, Thane
Project Type (Apartments/Plot/ Combined) |  | Apartments
No of Wings / Buildings |  | Building 1 (Wing A & B) Building 2 (Wing A & B) |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | Flats = 161 |  |  | Exposure Limit (Proposed) | 24.15
Approved No. of Floor |  | Building 1 (Wing A) = G + 1st to 7th Floor Building 1 (Wing B) = G + 1st to 7th Floor Building 2 (Wing A) = G + 1st to 7th Floor Building 2 (Wing B) = G + 1st to 7th Floor
Proposed No. of Floor |  | Building 1 (Wing A) = G + 1st to 7th Floor Building 1 (Wing B) = G + 1st to 7th Floor Building 2 (Wing A) = G + 1st to 7th Floor Building 2 (Wing B) = G + 1st to 7th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | Adj S. No. 66 | Adj S. No. 68 | Adj S. No. 65 | Adj S. No. 87
|  | Physical on site |  | Sundew Complex | House | Priti Academy Law College | Mahadev Enclaves
Verification of survey No. (Title document) |  | Survey No. 15, Hissa No. 1/A and Survey No. 15, Hissa No.1/B
Plot area mentioned in the sale deed (As per 7/12) |  | 4000 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 4000
Approach road |  | Yes, Approx 9M
Connectivity |  | 1. 0.40 km from Priti Academy Law College 2. 0.80 km from Guru Gobind Singh High School 3. 0.45 km from Ulhasnagar Municipal Corporation Super Speciality Hospital 4. 1.50 km from Century Rayon Hospital Trust 5. 0.70 km from D Mart 6. 0.75 km from Siddhivinayak Bazaar 7. 0.70 km from Shiv Mandir 8. 0.75 km from Siddhivinayak Mandir 9. 2.70 km from Shahad Phatak Bus stop 10. 2.10 km from Shahad Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 4000
|  | Permissible FSI |  |  |  | 1
|  | Permissible TDR/Paid FSI |  |  |  | 1.2384
|  | Total FSI availaible for the project |  |  |  | 2.2384
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 8960
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8953.63
Building plan approvals - Approval No : |  | RPTHA/B/2024/APL/00042 |  |  |  | Date | 2024-08-06
Building height / No. of Floors |  | Building 1 (Wing A & B) = G + 1st to 7th Floor (Height = 29.51 Mtrs) Building 2 (Wing A & B) = G + 1st to 7th Floor (Height = 29.51 Mtrs)
Construction/Building Permission Valid Upto |  | RPTHA/B/2024/APL/00042 Building 1 = G + 1st to 7th Floor Building 2 = G + 1st to 7th Floor |  |  |  | Date | 2024-08-06
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA |  | Date | NA |  | ``
|  | Validity & Area mentioned: |  | NA |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions
Fire Noc No Valid Up to: | [5 empty] | Date
Environmental Clearance Certificate (EC) No Valid Up for: | [5 empty] | Date
Airport Noc No Valid Up for: | [5 empty] | Date
Valid upto Dated
Site Elevation (AMSL) = Permissible Top Elevation (AMSL) =
CONSTRUCTION PROGRESS
Baseline start date |  | 2024-10-07 |  | Baseline finish date |  | 2028-12-31
Construction details:
Building No. 1 (Wing A)= Gr + 1st + 7th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
|  |  |  | 0 | 1 | 0 | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1.75
Excavation |  | 0% |  | 7 | 100% | 25% |  | Excavation in process | 3.5
Plinth |  | 10% |  | 7 | 100% |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 40% |  | 3 | 37.5% |  |  | Footing in Process | 1.75
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 3.5
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 5.25
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 7
Building No. 1 (Wing B)= Gr + 1st + 7th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
|  |  |  | 0 | 1 | 0 | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1.75
Excavation |  | 0% |  | 7 | 100% | 15% |  | Excavation in process | 3.5
Plinth |  | 10% |  | 7 | 100% |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 40% |  | 1 | 12.5% |  |  | Footing in Process | 1.75
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 3.5
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 5.25
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 7
Building No. 2 (Wing A)= Gr + 1st + 7th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 6 Floor, Flooring upto 2 Floor Completed
|  |  |  | 0 | 1 | 0 | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 6 Floor, Flooring upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1.75
Excavation |  | 0% |  | 7 | 100% | 77.14% |  | Excavation in process | 3.5
Plinth |  | 10% |  | 7 | 100% |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 40% |  | 8 | 100% |  |  | Footing in Process | 1.75
Brickwork |  | 15% |  | 7 | 100% |  |  | Footing Completed | 3.5
Internal Plaster |  | 5% |  | 7 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 6 | 85.71% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 2 | 28.57% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 5.25
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 7
Building No. 2 (Wing B)= Gr + 1st + 7th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 6 Floor, Flooring upto 2 Floor Completed
|  |  |  | 0 | 1 | 0 | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 6 Floor, Flooring upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 1.75
Excavation |  | 0% |  | 7 | 100% | 77.14% |  | Excavation in process | 3.5
Plinth |  | 10% |  | 7 | 100% |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 40% |  | 8 | 100% |  |  | Footing in Process | 1.75
Brickwork |  | 15% |  | 7 | 100% |  |  | Footing Completed | 3.5
Internal Plaster |  | 5% |  | 7 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 6 | 85.71% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 2 | 28.57% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 5.25
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 7
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | No
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building 1 | Wing A | 35 |  | 20209.3885 |  | 29303.6133 |  | OK
| Wing B | 42 |  | 24278.5572 |  | 35203.908 |  | OK
Building 2 | Wing A | 42 |  | 24581.9083 |  | 35643.767 |  | OK
| Wing B | 42 |  | 23129.1235 |  | 33537.229 |  | OK
Total |  | 161 |  | 92198.9774 |  | 133688.5173
Grand Total
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | AP Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Building 1
Wing A
Ground Floor For Parking, Driver Room & Society Office
1st to 7th Floor For Residential
1 |  | 1.5BHK | 451.6574 | 114.1199 | 565.7774 | 0 | 820.3772
2 |  | 1BHK | 384.1672 | 84.928 | 469.0951 | 0 | 680.1879
3 |  | 2BHK | 513.981 | 178.2788 | 692.2597 | 0 | 1003.7766
4 |  | 2BHK | 515.165 | 178.2788 | 693.4438 | 0 | 1005.4935
5 |  | 1BHK | 383.8442 | 82.6352 | 466.4795 | 0 | 676.3952 | 3509.5339
Wing B
Ground Floor For Parking
1st to 7th Floor For Residential | [7 empty] | 4800
1 |  | 1BHK | 389.9797 | 93.4853 | 483.4651 | 0 | 701.0243 | 3364916.8176
2 |  | 2BHK | 509.0296 | 182.9019 | 691.9314 | 0 | 1003.3006 | 4815842.8781
3 |  | 2BHK | 509.3525 | 182.9019 | 692.2544 | 0 | 1003.7688 | 4818090.4013
4 |  | 1BHK | 376.4171 | 80.5685 | 456.9856 | 0 | 662.6291 | 3180619.9152
5 |  | 1.5BHK | 453.3797 | 104.174 | 557.5537 | 0 | 808.4528 | 3880573.5571
6 |  | 2BHK | 481.9043 | 104.2709 | 586.1751 | 0 | 849.954 | 4079779.0301
Building 2
Wing A
Ground Floor For Parking, Driver Room & Society Office
1st to 7th Floor For Residential
1 |  | 1.5BHK | 485.6717 | 106.4021 | 592.0738 | 0 | 858.507
2 |  | 1BHK | 390.9485 | 93.4853 | 484.4338 | 0 | 702.429
3 |  | 2BHK | 543.6896 | 128.8774 | 672.567 | 0 | 975.2222
4 |  | 2BHK | 549.5022 | 128.8774 | 678.3796 | 0 | 983.6504
5 |  | 1BHK | 395.6846 | 96.4885 | 492.1731 | 0 | 713.651
6 |  | 1.5BHK | 485.6717 | 106.4021 | 592.0738 | 0 | 858.507
Wing B
Ground Floor For Parking & Entrance Lobby
1st to 7th Floor For Residential
1 |  | 1BHK | 390.9485 | 93.4853 | 484.4338 | 0 | 702.429
2 |  | 1BHK | 390.9485 | 93.4853 | 484.4338 | 0 | 702.429
3 |  | 2BHK | 543.6896 | 128.8774 | 672.567 | 0 | 975.2222
4 |  | 2BHK | 549.5022 | 128.8774 | 678.3796 | 0 | 983.6504
5 |  | 1BHK | 395.6846 | 96.4885 | 492.1731 | 0 | 713.651
6 |  | 1BHK | 395.6846 | 96.4885 | 492.1731 | 0 | 713.651
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 4800
Recommended of Parking ( If Available) |  |  |  |  | 2,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit (labour found)
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + AP Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 45%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Ms. Riya Shah 8108389545
Photographs Of Property : |  | Sharda Serene
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Krishna Kambali |  | Authorized Signatory Name & Seal of the agency
Bldg 1 (Wing A)
Bldg 1 (Wing B)
Bldg 2 (Wing A)
Bldg 2 (Wing B)
Sharda Serene
Bldg 1 Wing A
Bldg 1 Wing B
Bldg 2 Wing B
Bldg 2 Wing A
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C60: RERA Start date
Note on H120: if multiple buildings are in project and are connected internally
Note on C122: AAC Block or Brick
Note on H124: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3