## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-14
Name of the builder group |  |  |  | M/s.Horizon Projects Pvt Ltd
Name of the builder company |  |  |  | M/s.Horizon Projects Pvt Ltd
Name of the Project |  |  |  | My City Phase II - Cluster 05 - (Part I, II & III)
Contact Details ( Name & Contact No.) |  |  |  | 02261133000
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Mr. Vinod : 7208497596
Name / No of the Building |  |  |  | Part I - Tower No.1 to 6 Part II - Tower No.7 to 9 Part III - Tower No.10 to 12
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | Part I - P51700019085 Part II - P51700032157 Part III - P51700027171
Project location details |  | 17/1, 17/2, 17/3/A, 17/3/B, 17/4, 17/5, 19/1, 19/2,19/3, 19/4, 20/3, 20/4, 20/5, 34/1, 36/1/A, 36/1/B, 37/1, 37/2, 38/1, 38/2, 38/3, 38/4, 70/9, 70/10, 70/11, 71/1, 71/2, 71/3, 71/4, 71/8, 91/1, 91/2, 91/3, 91/4, 91/5, 92/1, 92/2, 93(Pt), 103/2, 103/3, 103/4, 103/5, 103/6/A, 103/6/B, 103/7, 103/8, 103/9, 103/10, 103/11, 103/12, 103/13, 103/14/B, 103/15, 103/16, 103/17, 103/18, 106/2, 106/3, 107/1, 107/2A, 107/2B, 107/3, 107/4, 107/5, 107/6, 107/7, 107/8, 107/9,107/10, 107/11, 107/12, 107/13, 107/14, 107/15, 107/16, 107/17, 107/18, 107/19, 107/20, 107/22, 107/23, 107/24, 107 /2SA, 107 /25B, 107 /26A, 107 /26B, 108/1, 108/2, 108/3, 109(Pt), 134/1, 134/2, 134/3, Internal Road, Sandap Bearing S. No.2,21/1, Dombivali, Kalyan, Thane - 421201.
Survey No |  | 17/1, 17/2, 17/3/A, 17/3/B, 17/4, 17/5, 19/1, 19/2,19/3, 19/4, 20/3, 20/4, 20/5, 34/1, 36/1/A, 36/1/B, 37/1, 37/2, 38/1, 38/2, 38/3, 38/4, 70/9, 70/10, 70/11, 71/1, 71/2, 71/3, 71/4, 71/8, 91/1, 91/2, 91/3, 91/4, 91/5, 92/1, 92/2, 93(Pt), 103/2, 103/3, 103/4, 103/5, 103/6/A, 103/6/B, 103/7, 103/8, 103/9, 103/10, 103/11, 103/12, 103/13, 103/14/B, 103/15, 103/16, 103/17, 103/18, 106/2, 106/3, 107/1, 107/2A, 107/2B, 107/3, 107/4, 107/5, 107/6, 107/7, 107/8, 107/9,107/10, 107/11, 107/12, 107/13, 107/14, 107/15, 107/16, 107/17, 107/18, 107/19, 107/20, 107/22, 107/23, 107/24, 107 /2SA, 107 /25B, 107 /26A, 107 /26B, 108/1, 108/2, 108/3, 109(Pt), 134/1, 134/2, 134/3
Road |  | Internal Road |  | Locality/Village |  | Sandap
City |  | Dombivali East |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421201
Near by Landmark |  | Vetaleshwar Mandir |  | Distance from city centre: |  | 3Km from Datiwali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Road
West | NA | NA |  |  | Road
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.179933,73.0731161
Location Link |  | https://goo.gl/maps/a7aW4jnnZEoCJiSU7?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 491917.72
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.686
Total FSI availaible for the project |  |  |  | 1.686
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 829373.28
Total number of Buildings |  |  |  | 12 Buildings
Approval Detail : Plan approval
Layout Approval No |  | SROT/KGC/2401/BP/ITP/Usarghar-Sandep/01/Vol/18/1188/2022 |  |  | Dated | 2022-09-08
Approved Floor plan No. |  | SROT/KGC/2401/BP/ITP/Usarghar-Sandep/01/Vol/18/1188/2022 |  |  | Dated | 2022-09-08
Commencement Certificate No. |  | SROT/Growth Centre/2401/BP/ITP/ Usarghar-Sandep/01/Vol/18/1188/2022 |  |  | Dated | 2022-09-08
Valid Up to: Cluster 05 - Part I (Tower No.1 to 6) = Lr. Gr + Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor Cluster 05 - Part III (Tower No.10 to 12) = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor Cluster 05 - Part II (Tower No.7 to 9) = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor
O. Certificate No.: |  | SROT/Growth Centre/2401/BP/ITP-Usarghar & Sandep/01/OC-Cluster 05/1152/2024 |  | Date of approval: | Dated | 2024-11-14
Approved upto : |  | Tower 1 = LG + Gr/P + UG/P + Stilt/P + 1st to 25th Floor (154 Units) Tower 2 = LG + Gr/P + UG/P + Stilt/P + 1st to 25th Floor (208 Units) Tower 3 = LG + Gr/P + UG/P + Stilt/P + 1st to 25th Floor (206 Units)
O. Certificate No.: |  | SROT/Growth Centre/2401/BP/ITP-Usarghar & Sandep-01/OC-Cluster 05-Tower 4, 5, 6/120/2025 |  | Date of approval: | Dated | 2025-01-31
Approved upto : |  | Tower 4 = LG + Gr/P + UG/P + Stilt/P + 1st to 25th Floor (154 Units) Tower 5 = LG + Gr/P + UG/P + Stilt/P + 1st to 25th Floor (208 Units) Tower 6 = LG + Gr/P + UG/P + Stilt/P + 1st to 25th Floor (206 Units)
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 147380.67
Approved no of units |  |  | Flats - 2360, Shops - 53
Approved no of Floors |  |  | Cluster 05 - Part I (Tower No.1 to 6) = Lr. Gr + Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor Cluster 05 - Part II (Tower No.7 to 9) = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor Cluster 05 - Part III (Tower No.10 to 12) = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor
Proposed no of Floors |  |  | Cluster 05 - Part I (Tower No.1 to 6) = Lr. Gr + Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor Cluster 05 - Part II (Tower No.7 to 9) = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor Cluster 05 - Part III (Tower No.10 to 12) = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor
Expected Completion |  |  | As per RERA : Part I = 30/03/2025 Part II = 31/12/2027 Part III = 30/06/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Tower No. 1, 2, 3 & 4 = Lr. Gr + Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | All work completed. Please provide OC.
Basement | 1 | Ground | 2 | Podium | 1 | Floors | 25
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 100% |  | 100% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 100% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 25 | 100% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 25 | 100% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 25 | 100% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 25 | 100% |  |  |  |  | Plinth completed | 25 | 30%
Construction details: |  | Tower No. 4 = Lr. Gr + Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | All work completed. Please provide OC.
Basement | 1 | Ground | 2 | Podium | 1 | Floors | 25
Progress % |  | 100% |  | Disbursement % |  | 100%
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 100% |  | 100% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 100% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 25 | 100% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 25 | 100% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 25 | 100% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 25 | 100% |  |  |  |  | Plinth completed | 25 | 30%
Construction details: |  | Tower No. 5 = Lr. Gr + Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 1 | Ground | 2 | Podium | 1 | Floors | 25
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 94.2% |  | 95% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 100% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 25 | 100% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 24 | 96% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 22 | 88% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25 | 30%
Construction details: |  | Tower No. 6 = Lr. Gr + Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 1 | Ground | 2 | Podium | 1 | Floors | 25
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 94.4% |  | 95% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 100% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 25 | 100% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 25 | 100% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 22 | 88% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25 | 30%
Construction details: |  | Tower No. 07 = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 13 Floor, Painting upto 11 Floor Completed
Basement | 0 | Ground | 2 | Podium | 1 | Floors | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 13 Floor, Painting upto 11 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 82.4% |  | 92.6% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 100% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 13 | 52% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 11 | 44% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25 | 30%
Construction details: |  | Tower No. 8 = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 27 Slab, Brickwork upto 24 Floor, Internal Plaster upto 22 Floor, External Plaster upto 17 Floor Completed
Basement | 0 | Ground | 2 | Podium | 1 | Floors | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 27 Slab, Brickwork upto 24 Floor, Internal Plaster upto 22 Floor, External Plaster upto 17 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 69.17% |  | 86.53% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 27 | 96.43% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 24 | 96% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 22 | 88% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 17 | 68% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25 | 30%
Construction details: |  | Tower No. 09 = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 23 Floor, Flooring upto 11 Floor Completed
Basement | 0 | Ground | 2 | Podium | 1 | Floors | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 23 Floor, Flooring upto 11 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 78.6% |  | 91.8% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 92% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 11 | 44% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25 | 30%
Construction details: |  | Tower No. 10 = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 23 Floor, Flooring upto 10 Floor Completed
Basement | 0 | Ground | 2 | Podium | 1 | Floors | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 23 Floor, Flooring upto 10 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 78.2% |  | 91.6% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 92% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 10 | 40% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25 | 30%
Construction details: |  | Tower No. 11 = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 14 Floor, Painting upto 11 Floor Completed
Basement | 0 | Ground | 2 | Podium | 1 | Floors | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 14 Floor, Painting upto 11 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 82.8% |  | 92.8% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 100% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 14 | 56% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 11 | 44% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25 | 30%
Construction details: |  | Tower No. 12 = Gr + Up. Gr (Pt. Podium) + Stilt Floor + 1st to 25th floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 18 Floor, Painting upto 12 Floor Completed
Basement | 0 | Ground | 2 | Podium | 1 | Floors | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 18 Floor, Painting upto 12 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 84.6% |  | 93.6% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25 | 2%
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.25 | 4%
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5 | 8%
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 100% |  |  |  |  | Basement 2 | 0 | 20%
Flooring & Fitting | Flooring & Fitting | 18 | 72% |  |  |  |  | Basement 3 | 0 | 30%
Painting & Wooden |  | 12 | 48% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25 | 30%
Wheather the construction is as per approved Building plan : Under Construction | [10 empty] | 7208497596 V V Urgent
Violations Observed if any : NA | [10 empty] | tower 1 rcc Breck work plaster in out flooring kitchen platform bathroom style plumbing elc work completed doors and windows sliding complete and internal work working progress tower 2 3 4 5 6 rcc Breck work plaster in out complete flooring and Kitchen platform working progress tower 7 9 10 rcc 3/4 slap working progress 2nd slap complete tower 8 8 th slap complete 9/10 th slap working progress tower 11 rcc 6 th complete 7/8 slap working progress 12 rcc 16 slap complete 17/18 working progress side Meet Mr vinod thkare 7208497596 external visit complete
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6800 |  |  | 29/11/2022 by Abhishek, Asmi 6300 to 6800 + Other Charges
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 13300 |  |  | 12K to 13.3Kt rupti verbal Shop No.14 index 2 18/12/2024
Floor Rise Rate Per Sq.ft |  |  |  |  | 25/- from 2nd Floor
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | 1,25,000/-
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Cam Charges |  |  |  |  | 70000/-
Society & Other Charges |  |  |  |  | 55000/-
Recommended rate of Parking |  |  |  |  | 400000/-
Distressed valuation of the Property |  |  |  |  | 5440
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Part I | Tower No.5 | 6 | 1197.1721 |  | 1855.6167
| Tower No.6 | 6 | 963.0551 |  | 1492.7354
Part II | Tower No.7 | 8 | 1480.3729 |  | 2294.578
| Tower No.8 | 12 | 2182.7239 |  | 3383.2221
| Tower No.9 | 6 | 1019.7814 |  | 1580.6611
Part III | Tower No.10 | 9 | 2064.8581 |  | 3200.5301
| Tower No.11 | 6 | 914.0789 |  | 1416.8223
Total |  | 53 | 9822.0424 |  | 15224.1657 |  |  |  | 1245066.315
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Tower No.1 |  | 154 | 99847.2946 |  | 149908.5144
Tower No.2 |  | 208 | 111976.8156 |  | 168046.8145
Tower No.3 |  | 206 | 100103.3701 |  | 150285.9287
Tower No.4 |  | 142 | 92343.4949 |  | 138645.9792
Tower No.5 |  | 208 | 112115.133 |  | 168423.0648
Tower No.6 |  | 206 | 100028.5603 |  | 150423.3046
Tower No.7 |  | 206 | 96020.8002 |  | 144300.8385
Tower No.8 |  | 208 | 120857.0403 |  | 181777.2599
Tower No.9 |  | 202 | 93897.2783 |  | 141115.5556
Tower No.10 |  | 206 | 96065.0402 |  | 144390.3864
Tower No.11 |  | 208 | 112046.8892 |  | 168279.5096
Tower No.12 |  | 206 | 99942.556 |  | 150042.9454
Total |  | 2360 | 1235244.2727 |  | 1855640.1016
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Cluster 05
Part I
Tower No. 5
Ground Floor For Part Commercial
48 |  | Shop | 189.1235 | 0 | 293.1414 | Ground Floor For Part Commercial |  |  | 10.764
49 |  | Shop | 118.6193 | 0 | 183.8599
50 |  | Shop | 163.6128 | 0 | 253.5998
51 |  | Shop | 333.1458 | 0 | 516.376
52 |  | Shop | 208.714 | 0 | 323.5066
53 |  | Shop | 183.9568 | 0 | 285.133
Tower No. 6
Ground Floor For Part Commercial
42 |  | Shop | 196.5506 | 0 | 304.6535 | Ground Floor For Part Commercial
43 |  | Shop | 125.5082 | 0 | 194.5378
44 |  | Shop | 142.623 | 0 | 221.0657
45 |  | Shop | 137.3486 | 0 | 212.8904
46 |  | Shop | 155.8627 | 0 | 241.5872
47 |  | Shop | 205.1618 | 0 | 318.0009
Part II
Tower No. 7
Ground Floor For Part Commercial
34 |  | Shop | 183.2033 | 0 | 283.9651 | Ground Floor For Part Commercial |  |  | 10.764
35 |  | Shop | 178.1442 | 0 | 276.1235
36 |  | Shop | 142.5154 | 0 | 220.8988
37 |  | Shop | 146.9286 | 0 | 227.7393
38 |  | Shop | 132.8278 | 0 | 205.883
39 |  | Shop | 191.9221 | 0 | 297.4793
40 |  | Shop | 252.4158 | 0 | 391.2445
41 |  | Shop | 252.4158 | 0 | 391.2445
Tower No. 8
Ground Floor For Part Commercial
22 |  | Shop | 188.1547 | 0 | 291.6398 | Ground Floor For Part Commercial |  |  | 10.764
23 |  | Shop | 178.1442 | 0 | 276.1235
24 |  | Shop | 142.5154 | 0 | 220.8988
25 |  | Shop | 146.9286 | 0 | 227.7393
26 |  | Shop | 138.748 | 0 | 215.0593
27 |  | Shop | 154.4634 | 0 | 239.4183
28 |  | Shop | 138.3174 | 0 | 214.392
29 |  | Shop | 191.3839 | 0 | 296.6451
30 |  | Shop | 390.4103 | 0 | 605.1359
31 |  | Shop | 145.314 | 0 | 225.2367
32 |  | Shop | 179.8664 | 0 | 278.793
33 |  | Shop | 188.4776 | 0 | 292.1403
Tower No. 9
Ground Floor For Part Commercial
16 |  | Shop | 201.6097 | 0 | 312.4951 | Ground Floor For Part Commercial |  |  | 10.764
17 |  | Shop | 123.2478 | 0 | 191.0341
18 |  | Shop | 195.7972 | 0 | 303.4856
19 |  | Shop | 138.6403 | 0 | 214.8925
20 |  | Shop | 151.6648 | 0 | 235.0804
21 |  | Shop | 208.8216 | 0 | 323.6735
Part III
Tower No. 10
Ground Floor For Part Commercial
7 |  | Shop | 183.4186 | 0 | 284.2988 | Ground Floor For Part Commercial
8 |  | Shop | 179.113 | 0 | 277.6251
9 |  | Shop | 137.4563 | 0 | 213.0572
10 |  | Shop | 145.8522 | 0 | 226.0709
11 |  | Shop | 135.0882 | 0 | 209.3867
12 |  | Shop | 189.0158 | 0 | 292.9746
13 |  | Shop | 375.7712 | 0 | 582.4454
14 |  | Shop | 361.5628 | 0 | 560.4223
15 |  | Shop | 357.5801 | 0 | 554.2491
Tower No. 11
Ground Floor For Part Commercial
1 |  | Shop | 172.8698 | 0 | 267.9483 | Ground Floor For Part Commercial
2 |  | Shop | 176.3143 | 0 | 273.2872
3 |  | Shop | 136.9181 | 0 | 212.223
4 |  | Shop | 136.9181 | 0 | 212.223
5 |  | Shop | 148.6508 | 0 | 230.4088
6 |  | Shop | 142.4077 | 0 | 220.732
Ground Floor For Part Commercial
1 |  |  |  | 0 | #REF! | Ground Floor For Part Commercial
2 |  |  |  | 0 | #REF! | Ground Floor For Part Commercial
3 |  |  |  | 0 | #REF! | Ground Floor For Part Commercial
4 |  |  |  | 0 | #REF! | Ground Floor For Part Commercial
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
50%
Cluster 5
Part I
Tower No.1
Lower Ground Floor for Parking
Ground Floor for Parking
Upper Ground Floor Residential (Part Podium) | [8 empty] | 10.764
1 |  | 2BHK | 600.2006 | 0 | 900.301 | Upper Ground Floor Residential (Part Podium) |  |  | 51.0153
2 |  | Podium For Parking | [6 empty] | 4.6494
3 | [8 empty] | 55.6647
4
5 |  | 2BHK | 530.3423 | 0 | 795.5134
6 |  | 3BHK | 813.9737 | 0 | 1220.9605
Stilt/ Lobby Floor for Residential
1 |  | 2BHK | 600.2006 | 0 | 900.301 | Stilt/ Lobby Floor for Residential
2 |  | 2BHK | 600.2006 | 57.0966 | 957.3975
3 |  | Stilt Area
4 |  | 2BHK | 530.3423 | 80.476 | 875.9894
5 |  | 2BHK | 530.3423 | 0 | 795.5134
6 |  | 3BHK | 813.9737 | 0 | 1220.9605
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 600.2006 | 0 | 900.301 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 600.2006 | 0 | 900.301
3 |  | 3BHK | 814.0813 | 0 | 1221.122
4 |  | 2BHK | 530.3423 | 0 | 795.5134
5 |  | 2BHK | 530.3423 | 0 | 795.5134
6 |  | 3BHK | 813.9737 | 0 | 1220.9605
6th, 11th, 17th & 23rd Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Refuge Area |  |  |  | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 600.2006 | 0 | 900.301
3 |  | 3BHK | 814.0813 | 0 | 1221.122
4 |  | 2BHK | 530.3423 | 0 | 795.5134
5 |  | 2BHK | 530.3423 | 0 | 795.5134
6 |  | 3BHK | 813.9737 | 0 | 1220.9605
Tower No.2
Lower Ground Floor for Parking
Ground Floor for Parking
Upper Stilt Floor For Residential & Part Podium
1 |  | 2BHK | 600.4159 | 0 | 900.6239 | Upper Stilt Floor For Residential & Part Podium
2 |  | Podium
3
4 |  | 2BHK | 600.4159 | 0 | 900.6239
5 |  | 2BHK | 530.6652 | 0 | 795.9978
6 |  | 2BHK | 530.6652 | 0 | 795.9978 |  |  | 7908.8234
7 |  | 1BHK | 431.0982 | 0 | 646.6473 |  |  | 8531.2581
8 |  | 1BHK | 431.0982 | 0 | 646.6473
Stilt/ Lobby Floor for Residential | [8 empty] | 4.5975
1 |  | 2BHK | 600.4159 | 0 | 900.6239 | Stilt/ Lobby Floor for Residential |  |  | 51.0308
2 |  | 2BHK | 600.4159 | 81.5911 | 982.215 |  |  |  | 55.6283
3 |  | Stilt Area
4
5 |  | 2BHK | 530.6652 | 0 | 795.9978
6 |  | 2BHK | 530.6652 | 0 | 795.9978
7 |  | 1BHK | 431.0982 | 0 | 646.6473
8 |  | 1BHK | 431.0982 | 0 | 646.6473
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 600.4159 | 0 | 900.6239 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 600.4159 | 0 | 900.6239
3 |  | 2BHK | 600.4159 | 0 | 900.6239
4 |  | 2BHK | 600.4159 | 0 | 900.6239
5 |  | 2BHK | 530.6652 | 0 | 795.9978
6 |  | 2BHK | 530.6652 | 0 | 795.9978
7 |  | 1BHK | 431.0982 | 0 | 646.6473
8 |  | 1BHK | 431.0982 | 0 | 646.6473
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 600.4159 | 0 | 900.6239 | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 600.4159 | 0 | 900.6239
3 |  | 2BHK | 600.4159 | 0 | 900.6239
4 |  | Refuge Area
5 |  | 2BHK | 530.6652 | 0 | 795.9978
6 |  | 2BHK | 530.6652 | 0 | 795.9978
7 |  | 1BHK | 431.0982 | 0 | 646.6473
8 |  | 1BHK | 431.0982 | 0 | 646.6473
Tower No.3
Lower Ground Floor for Parking
Ground Floor for Parking
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 531.2034 | 0 | 796.8051 | Upper Ground Floor For Residential & Part Podium
2 |  | Podium Area
3
4
5
6 |  | 2BHK | 603.6451 | 0 | 905.4677
7 |  | 1BHK | 388.3651 | 0 | 582.5477
8 |  | 1BHK | 388.3651 | 0 | 582.5477
Stilt/ Lobby Floor for Residential & Parking
1 |  | 2BHK | 531.2034 | 0 | 796.8051 | Stilt/ Lobby Floor for Residential & Parking
2 |  | 2BHK | 531.2034 | 76.4911 | 873.2962 |  |  |  | 10.764
3 |  | Stilt Area
4
5 |  | 2BHK | 601.3847 | 54.3824 | 956.4594
6 |  | 2BHK | 603.6451 | 0 | 905.4677
7 |  | 1BHK | 388.3651 | 0 | 582.5477
8 |  | 1BHK | 388.3651 | 0 | 582.5477 |  |  |  | 6814.8928
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 531.2034 | 0 | 796.8051 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 531.2034 | 0 | 796.8051
3 |  | 1BHK | 429.1607 | 0 | 643.741 |  |  | 5250.5587
4 |  | 1BHK | 429.1607 | 0 | 643.741
5 |  | 2BHK | 601.3847 | 0 | 902.077
6 |  | 2BHK | 603.6451 | 0 | 905.4677
7 |  | 1BHK | 388.3651 | 0 | 582.5477 |  |  | 5132.6271
8 |  | 1BHK | 388.3651 | 0 | 582.5477
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 531.2034 | 0 | 796.8051 | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 531.2034 | 0 | 796.8051
3 |  | 1BHK | 429.1607 | 0 | 643.741 |  |  | 6167.0763
4 |  | 1BHK | 429.1607 | 0 | 643.741
5 |  | 2BHK | 601.3847 | 0 | 902.077
6 |  | Refuge Area
7 |  | 1BHK | 388.3651 | 0 | 582.5477 |  |  | 6256.9986
8 |  | 1BHK | 388.3651 | 0 | 582.5477
Tower No.4
Lower Ground Floor for Parking
Ground Floor for Parking
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 600.6312 | 0 | 900.9468 | Upper Ground Floor For Residential & Part Podium
2 |  | Podium Area
3
4
5 |  | 2BHK | 532.2798 | 0 | 798.4197
6 |  | 3BHK | 817.3105 | 0 | 1225.9658
Stilt/ Lobby Floor for Residential
1 |  | 2BHK | 600.6312 | 0 | 900.9468 | Stilt/ Lobby Floor for Residential
2 |  | 2BHK | 600.6312 | 57.4798 | 958.4266
3 |  | Stilt Area
4 |  | 2BHK | 532.2798 | 73.2571 | 871.6768
5 |  | 2BHK | 532.2798 | 0 | 798.4197
6 |  | 3BHK | 817.3105 | 0 | 1225.9658
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd Floor
1 |  | 2BHK | 600.6312 | 0 | 900.9468 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd Floor |  | 5272.2314
2 |  | 2BHK | 600.6312 | 0 | 900.9468
3 |  | 3BHK | 817.4182 | 0 | 1226.1272
4 |  | 2BHK | 532.2798 | 0 | 798.4197 |  |  | 5210.2923
5 |  | 2BHK | 532.2798 | 0 | 798.4197
6 |  | 3BHK | 817.3105 | 0 | 1225.9658
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 600.6312 | 0 | 900.9468
3 |  | 3BHK | 817.4182 | 0 | 1226.1272
4 |  | 2BHK | 532.2798 | 0 | 798.4197
5 |  | 2BHK | 532.2798 | 0 | 798.4197
6 |  | 3BHK | 817.3105 | 0 | 1225.9658
Tower No.5
Lower Ground Floor for Parking
Ground Floor for Part Podium Parking
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 600.7388 | 0 | 901.1083 | Upper Ground Floor For Residential & Part Podium
2 |  | 2BHK | 587.6068 | 110.4871 | 936.6537
3 |  | 2BHK | 587.6068 | 110.2503 | 936.5353
4 |  | Podium Area
5
6 |  | 2BHK | 532.3874 | 0 | 798.5812
7 |  | 1BHK | 430.56 | 139.9966 | 715.8383
8 |  | 1BHK | 430.56 | 139.9966 | 715.8383
Stilt/ Lobby Floor for Residential
1 |  | 2BHK | 600.7388 | 0 | 901.1083 | Stilt/ Lobby Floor for Residential
2 |  | 2BHK | 600.7388 | 0 | 901.1083
3 |  | Stilt Area
4
5 |  | 2BHK | 532.3874 | 0 | 798.5812
6 |  | 2BHK | 532.3874 | 0 | 798.5812
7 |  | 1BHK | 430.56 | 0 | 645.84
8 |  | 1BHK | 430.56 | 0 | 645.84
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 600.7388 | 0 | 901.1083 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 600.7388 | 0 | 901.1083
3 |  | 2BHK | 600.7388 | 0 | 901.1083
4 |  | 2BHK | 600.7388 | 0 | 901.1083
5 |  | 2BHK | 532.3874 | 0 | 798.5812
6 |  | 2BHK | 532.3874 | 0 | 798.5812
7 |  | 1BHK | 430.56 | 0 | 645.84
8 |  | 1BHK | 430.56 | 0 | 645.84
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 600.7388 | 0 | 901.1083 | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 600.7388 | 0 | 901.1083
3 |  | Refuge Area
4 |  | 2BHK | 600.7388 | 0 | 901.1083
5 |  | 2BHK | 532.3874 | 0 | 798.5812
6 |  | 2BHK | 532.3874 | 0 | 798.5812
7 |  | 1BHK | 430.56 | 0 | 645.84
8 |  | 1BHK | 430.56 | 0 | 645.84
Tower No.6
Lower Ground Floor for Parking
Ground Floor for Parking
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 525.3908 | 96.876 | 884.9623 | Upper Ground Floor For Residential & Part Podium
2 |  | Podium Area
3
4
5
6 |  | 2BHK | 587.822 | 96.2302 | 977.9632
7 |  | 1BHK | 381.5838 | 38.858 | 611.2337
8 |  | 1BHK | 381.5838 | 38.858 | 611.2337
Stilt/ Lobby Floor for Residential & Parking
1 |  | 2BHK | 532.3874 | 0 | 798.5812 | Stilt/ Lobby Floor for Residential & Parking
2 |  | 2BHK | 532.3874 | 56.6722 | 855.2534
3 |  | Stilt Area
4
5 |  | 2BHK | 600.9541 | 52.9696 | 954.4008
6 |  | 2BHK | 600.9541 | 0 | 901.4312
7 |  | 1BHK | 386.4276 | 0 | 579.6414
8 |  | 1BHK | 386.4276 | 0 | 579.6414
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 532.3874 | 0 | 798.5812 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 532.3874 | 0 | 798.5812
3 |  | 1BHK | 430.56 | 0 | 645.84
4 |  | 1BHK | 430.56 | 0 | 645.84
5 |  | 2BHK | 600.9541 | 0 | 901.4312
6 |  | 2BHK | 600.9541 | 0 | 901.4312
7 |  | 1BHK | 386.4276 | 0 | 579.6414
8 |  | 1BHK | 386.4276 | 0 | 579.6414
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 532.3874 | 0 | 798.5812 | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 532.3874 | 0 | 798.5812
3 |  | 1BHK | 430.56 | 0 | 645.84
4 |  | 1BHK | 430.56 | 0 | 645.84
5 |  | 2BHK | 600.9541 | 0 | 901.4312
6 |  | Refuge Area
7 |  | 1BHK | 386.4276 | 0 | 579.6414
8 |  | 1BHK | 386.4276 | 0 | 579.6414
Part II
Tower No.7
Lower Ground Floor for Parking
Ground Floor for Pump Room, Society Office, Parking & Commercial
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 586.7456 | 80.73 | 960.8485 | Upper Ground Floor For Residential & Part Podium
2 |  | Podium Area
3
4
5
6 |  | 2BHK | 523.9915 | 76.532 | 862.5193
7 |  | 1BHK | 369.7434 | 0 | 554.6151
8 |  | 1BHK | 369.7434 | 0 | 554.6151
Stilt/ Lobby Floor for Residential & Parking
1 |  | 2BHK | 601.0618 | 0 | 901.5926 | Stilt/ Lobby Floor for Residential & Parking
2 |  | 2BHK | 601.0618 | 56.1881 | 957.7807
3 |  | Stilt Area
4
5 |  | 2BHK | 530.8805 | 56.1881 | 852.5088
6 |  | 2BHK | 530.8805 | 0 | 796.3207
7 |  | 1BHK | 369.7434 | 0 | 554.6151
8 |  | 1BHK | 369.7434 | 0 | 554.6151
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 601.0618 | 0 | 901.5926 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 601.0618 | 0 | 901.5926
3 |  | 1BHK | 369.7434 | 0 | 554.6151
4 |  | 1BHK | 369.7434 | 0 | 554.6151
5 |  | 2BHK | 530.8805 | 0 | 796.3207
6 |  | 2BHK | 530.8805 | 0 | 796.3207
7 |  | 1BHK | 369.7434 | 0 | 554.6151
8 |  | 1BHK | 369.7434 | 0 | 554.6151
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 601.0618 | 0 | 901.5926
3 |  | 1BHK | 369.7434 | 0 | 554.6151
4 |  | 1BHK | 369.7434 | 0 | 554.6151
5 |  | 2BHK | 530.8805 | 0 | 796.3207
6 |  | 2BHK | 530.8805 | 0 | 796.3207
7 |  | 1BHK | 369.7434 | 0 | 554.6151
8 |  | 1BHK | 369.7434 | 0 | 554.6151
Tower No.8
Lower Ground Floor for Parking
Ground Floor for Pump Room, Society Office, Parking & Commercial
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 598.8584 | 90.5791 | 988.8666 | Upper Ground Floor For Residential & Part Podium
2 |  | Podium Area
3
4 |  | 2BHK | 598.8584 | 90.5791 | 988.8666
5 |  | 2BHK | 535.4875 | 79.8151 | 883.0463
6 |  | 2BHK | 535.4875 | 79.8151 | 883.0463
7 |  | 1BHK | 456.6487 | 47.3616 | 732.3347
8 |  | 1BHK | 456.6487 | 47.3616 | 732.3347
Stilt/ Lobby Floor for Residential & Parking
1 |  | 2BHK | 650.3727 | 0 | 975.5591 | Stilt/ Lobby Floor for Residential & Parking
2 |  | 2BHK | 650.3727 | 56.1881 | 1031.7472
3 |  | Stilt Area
4
5 |  | 2BHK | 563.1671 | 0 | 844.7506
6 |  | 2BHK | 563.1671 | 0 | 844.7506
7 |  | 1BHK | 474.1122 | 0 | 711.1683
8 |  | 1BHK | 474.1122 | 0 | 711.1683
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 650.3727 | 0 | 975.5591 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 650.3727 | 0 | 975.5591
3 |  | 2BHK | 650.3727 | 0 | 975.5591
4 |  | 2BHK | 650.3727 | 0 | 975.5591
5 |  | 2BHK | 563.1671 | 0 | 844.7506
6 |  | 2BHK | 563.1671 | 0 | 844.7506
7 |  | 1BHK | 474.1122 | 0 | 711.1683
8 |  | 1BHK | 474.1122 | 0 | 711.1683
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 650.3727 | 0 | 975.5591 | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 650.3727 | 0 | 975.5591
3 |  | 2BHK | 650.3727 | 0 | 975.5591
4 |  | Refuge Area
5 |  | 2BHK | 563.1671 | 0 | 844.7506
6 |  | 2BHK | 563.1671 | 0 | 844.7506
7 |  | 1BHK | 474.1122 | 0 | 711.1683
8 |  | 1BHK | 474.1122 | 0 | 711.1683
Tower No.9
Lower Ground Floor for Parking
Ground Floor for Parking & Commercial
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 524.9603 | 94.6532 | 882.0937 | Upper Ground Floor For Residential & Part Podium
2 |  | Podium Area
3
4
5
6 |  | 2BHK | 587.4991 | 94.6532 | 975.9019
7 |  | 1BHK | 383.629 | 37.7816 | 613.2251
8 |  | 1BHK | 383.629 | 37.7816 | 613.2251
Stilt/ Lobby Floor for Residential & Parking
1 |  | 2BHK | 532.0645 | 0 | 798.0968 | Stilt/ Lobby Floor for Residential & Parking
2 |  | 2BHK | 532.0645 | 70.0736 | 868.1704
3 |  | Stilt Area
4
5 |  | 2BHK | 600.6312 | 70.0736 | 971.0204
6 |  | 2BHK | 600.6312 | 0 | 900.9468
7 |  | 1BHK | 377.7088 | 0 | 566.5631
8 |  | 1BHK | 377.7088 | 0 | 566.5631
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 532.0645 | 0 | 798.0968 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 532.0645 | 0 | 798.0968
3 |  | 1BHK | 430.56 | 0 | 645.84
4 |  | 1BHK | 430.56 | 0 | 645.84
5 |  | 2BHK | 600.6312 | 0 | 900.9468
6 |  | 2BHK | 600.6312 | 0 | 900.9468
7 |  | 1BHK | 388.4728 | 0 | 582.7091
8 |  | 1BHK | 388.4728 | 0 | 582.7091
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 532.0645 | 0 | 798.0968 | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 532.0645 | 0 | 798.0968
3 |  | 1BHK | 430.56 | 0 | 645.84
4 |  | 1BHK | 430.56 | 0 | 645.84
5 |  | 2BHK | 600.6312 | 0 | 900.9468
6 |  | Refuge Area
7 |  | 1BHK | 388.4728 | 0 | 582.7091
8 |  | 1BHK | 388.4728 | 0 | 582.7091
Part III
Tower No.10
Ground Floor for Parking
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 600.9541 | 50.5039 | 951.9351 | Upper Ground Floor For Residential & Part Podium |  |  | 50.0637
2 |  | Podium Area | [6 empty] | 4.5975
3
4
5
6 |  | 2BHK | 531.2034 | 67.2887 | 864.0938
7 |  | 1BHK | 369.851 | 22.3151 | 577.0917 |  |  | 8329.6991
8 |  | 1BHK | 369.851 | 22.3151 | 577.0917
Stilt/ Lobby Floor for Residential
1 |  | 2BHK | 600.9541 | 0 | 901.4312 | Stilt/ Lobby Floor for Residential |  |  | 10.764
2 |  | 2BHK | 600.9541 | 56.8447 | 958.2759
3 |  | Stilt Area
4
5 |  | 2BHK | 531.2034 | 73.5585 | 870.3636
6 |  | 2BHK | 531.2034 | 0 | 796.8051
7 |  | 1BHK | 369.851 | 0 | 554.7766
8 |  | 1BHK | 369.851 | 0 | 554.7766
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 600.9541 | 0 | 901.4312 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor |  | 53.0926
2 |  | 2BHK | 600.9541 | 0 | 901.4312
3 |  | 1BHK | 369.851 | 0 | 554.7766
4 |  | 1BHK | 369.851 | 0 | 554.7766
5 |  | 2BHK | 531.2034 | 0 | 796.8051
6 |  | 2BHK | 531.2034 | 0 | 796.8051
7 |  | 1BHK | 369.851 | 0 | 554.7766
8 |  | 1BHK | 369.851 | 0 | 554.7766
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 600.9541 | 0 | 901.4312
3 |  | 1BHK | 369.851 | 0 | 554.7766
4 |  | 1BHK | 369.851 | 0 | 554.7766
5 |  | 2BHK | 531.2034 | 0 | 796.8051
6 |  | 2BHK | 531.2034 | 0 | 796.8051 |  |  | 9500.4412
7 |  | 1BHK | 369.851 | 0 | 554.7766
8 |  | 1BHK | 369.851 | 0 | 554.7766 |  |  | 13645.1331
Tower No.11
Ground Floor for Parking
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 600.4159 | 54.9341 | 955.558 | Upper Ground Floor For Residential & Part Podium
2 |  | 2BHK | 600.4159 | 0 | 900.6239
3 |  | 2BHK | 600.4159 | 0 | 900.6239
4 |  | Podium Area
5
6 |  | 2BHK | 530.3423 | 75.2215 | 870.7349
7 |  | 1BHK | 431.4211 | 0 | 647.1317
8 |  | 1BHK | 431.4211 | 0 | 647.1317
Stilt/ Lobby Floor for Residential & Parking
1 |  | 2BHK | 600.4159 | 0 | 900.6239 | Stilt/ Lobby Floor for Residential & Parking
2 |  | 2BHK | 600.4159 | 0 | 900.6239
3 |  | Stilt Area
4
5 |  | 2BHK | 530.3423 | 79.0201 | 874.5336
6 |  | 2BHK | 530.3423 | 0 | 795.5134
7 |  | 1BHK | 431.4211 | 0 | 647.1317
8 |  | 1BHK | 431.4211 | 0 | 647.1317
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 600.4159 | 0 | 900.6239 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 600.4159 | 0 | 900.6239
3 |  | 2BHK | 600.4159 | 0 | 900.6239
4 |  | 2BHK | 600.4159 | 0 | 900.6239
5 |  | 2BHK | 530.3423 | 0 | 795.5134
6 |  | 2BHK | 530.3423 | 0 | 795.5134
7 |  | 1BHK | 431.4211 | 0 | 647.1317
8 |  | 1BHK | 431.4211 | 0 | 647.1317
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 600.4159 | 0 | 900.6239 | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 600.4159 | 0 | 900.6239
3 |  | Refuge Area
4 |  | 2BHK | 600.4159 | 0 | 900.6239 |  |  |  | 6162.3949
5 |  | 2BHK | 530.3423 | 0 | 795.5134
6 |  | 2BHK | 530.3423 | 0 | 795.5134
7 |  | 1BHK | 431.4211 | 0 | 647.1317
8 |  | 1BHK | 431.4211 | 0 | 647.1317
Tower No.12
Ground Floor for Parking
Upper Ground Floor For Residential & Part Podium
1 |  | 2BHK | 530.3423 | 0 | 795.5134 | Upper Ground Floor For Residential & Part Podium
2 |  | Podium Area
3
4
5
6 |  | 2BHK | 600.4159 | 0 | 900.6239
7 |  | 1BHK | 385.7818 | 0 | 578.6726
8 |  | 1BHK | 385.7818 | 0 | 578.6726
Stilt/ Lobby Floor for Residential & Parking
1 |  | 2BHK | 530.3423 | 0 | 795.5134 | Stilt/ Lobby Floor for Residential & Parking
2 |  | 2BHK | 530.3423 | 71.8793 | 867.3927
3 |  | Stilt Area
4
5 |  | 2BHK | 600.4159 | 57.2322 | 957.8561
6 |  | 2BHK | 600.4159 | 0 | 900.6239
7 |  | 1BHK | 385.7818 | 0 | 578.6726
8 |  | 1BHK | 385.7818 | 0 | 578.6726
1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
1 |  | 2BHK | 530.3423 | 0 | 795.5134 | 1st to 5th, 7th to 10th, 12th to 16th, 18th to 22nd, 24th & 25th Floor
2 |  | 2BHK | 530.3423 | 0 | 795.5134
3 |  | 1BHK | 431.6364 | 0 | 647.4546
4 |  | 1BHK | 431.6364 | 0 | 647.4546
5 |  | 2BHK | 600.4159 | 0 | 900.6239
6 |  | 2BHK | 600.4159 | 0 | 900.6239
7 |  | 1BHK | 385.7818 | 0 | 578.6726
8 |  | 1BHK | 385.7818 | 0 | 578.6726
6th, 11th, 17th & 23rd Floor (Part Refuge Area)
1 |  | 2BHK | 530.3423 | 0 | 795.5134 | 6th, 11th, 17th & 23rd Floor (Part Refuge Area)
2 |  | 2BHK | 530.3423 | 0 | 795.5134
3 |  | 1BHK | 431.6364 | 0 | 647.4546
4 |  | 1BHK | 431.6364 | 0 | 647.4546
5 |  | 2BHK | 600.4159 | 0 | 900.6239
6 |  | Refuge Area
7 |  | 1BHK | 385.7818 | 0 | 578.6726
8 |  | 1BHK | 385.7818 | 0 | 578.6726
Remarks:
1. Tower 1 to 4 = All Work Completed OC Received. Tower 5 & 6 = OC received but window & finishing work is in process. Tower 7 to 12 = Construction work is in process at the time of Visit. Internal visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Deck Area + Utility Area 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. In approved plans tower no.4's 24th & 25th Floors are not mentioned anywhere. Maybe there is printing mistake. Plans are provided upto 23rd Floors. So please provide plans for 24th & 25th Floor of tower no.4. 8. We have updated Approved floor plan & CC of (Cluster 5 = Part I & III) on (07/10/2022) 9. Details of project are collected from Mr. vinod thakre - 7208497596. 10. We have updated approved floor plan & C.C of Tower 9 (on 02/11/2022), Tower 7 ( on 20/12/2022) & Tower 8 ( on 16/01/2023). 11. We have updated OC for Tower 1 to 3 on 17/12/2024. 12. Recommended Rates/Other Charges of the Property have been revised on 18/12/2024. 13. We have updated OC for Tower 4 to 6 (On 19/04/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Gangaram |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | My City Phase II - Cluster 05 - (Part I, II & III)
PHOTOGRAPHS OF PROPERTY :
Google Map :
Formulas:
Sandap = [Sandap, row above]
Tower 1
1
2
3
4
5
7
8
9
12
Tower 1
2
3
4
5
7
8
9
12

## Sheet1
T4 T5 T6 | Finishing work pending

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.05 | 4.72 | 14.396 | CB | 2.18 | 0.6 | 1.308 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.13 | 2.74 | 5.8362 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.74 | 3.367 | 9.2256 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.2 | 3.05 | 9.76 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.21 | 1.3 | 2.873 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.3 | 2.21 | 2.873 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 0.91 | 2.74 | 2.4934 |  |  |  | 0 |  |  | 0
| passage2 | 1.05 | 2.13 | 2.2365 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 534.9028 | 49.6937 |  |  | 14.0793 | 1.308 |  | 0 | 0
|  |  | 548.9821 | 51.0017

## Note
29/11/2022 by Abhishek, Asmi 6300 to 6800 + Other Charges

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
commonfloor. | My City- Phase II | 1BHK | 406 | 609 | 8249.5895 | 5024000
commonfloor. | My City- Phase II | 2BHK | 525 | 787.5 | 7970.7937 | 6277000
commonfloor. | My City- Phase II | 2BHK | 576 | 864 | 7965.2778 | 6882000
commonfloor. | My City- Phase II | 3BHK | 706 | 1059 | 8300.2833 | 8790000
squareyards. | My City- Phase II | 1BHK | 372 | 595.2 | 6123.9919 | 3645000
squareyards. | My City- Phase II | 1BHK | 409 | 654.4 | 6066.6259 | 3970000
squareyards. | My City- Phase II | 2BHK | 502 | 803.2 | 5984.8108 | 4807000
squareyards. | My City- Phase II | 2BHK | 570 | 912 | 6085.5263 | 5550000
squareyards. | My City- Phase II | 3BHK | 777 | 1243.2 | 6089.1248 | 7570000
Average |  |  |  |  | 6981.7804
Valuation Adopted |  |  |  |  | 8800