## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 30/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-07-15
Name of the builder group |  |  |  | Shree Laxmi Enterprises
Name of the builder company |  |  |  | Shree Laxmi Enterprises
Name of the Project |  |  |  | Park One Phase I
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr.Pratik Tiwari - 9158059099
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Miss. Varsha - 7208463276
Name / No of the Building |  |  |  | Orchid (Wing C to E) Jasmine (Wing F to I)
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P51700047479
Project location details |  | Park One Phase I, Survey No.125, H.No.1(p), near Shubh Hills Co op society, Panvel Highway, Katrap, Shirgaon, Badlapur, Ambarnath, Thane - 421503.
Survey No |  | 125, H.No.1(p)
Locality |  | Katrap
Road |  | Panvel Highway |  | Locality/Village |  | Shirgaon
City |  | Badlapur |  | District |  | Thane
Taluka |  | Ambarnath |  | Pin Code |  | 421503
Nearby Landmark |  | Shubh Hills Co op society |  | Distance from city centre: |  | 3.9KM from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.1623 |  | Longitude |  | 73.2225
Location Link |  | https://goo.gl/maps/eg8eKKrsyckzaSSR6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 8714.7
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.61142
Total FSI availaible for the project |  |  |  | 1.6114
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 14043.07
Total number of Buildings |  |  |  | 07 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kulgaon Badlapur Municipal Council (KBMC)
Layout Approval No |  | KBNP/NRV/BP/6085-79 |  |  | Dated | 2022-06-30
Approved Floor plan No. |  | KBNP/NRV/BP/6085-79 |  |  | Dated | 2022-06-30
Commencement-CC No Valid Up to: |  | KBNP/NRV/BP/6085/2022-2023/unique No.79 |  |  | Dated | 2022-06-30
C to E Wing (Orchid) = G + 1st to 7th Floor F to H Wing (Jasmine) = G + 1st to 7th Floor I Wing (Jasmine) = G + 1st to 6th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 14043.07
Approved no of units |  |  | Flats - 220
Approved no of Floors |  |  | C to E Wing (Orchid) = G + 1st to 7th Floor F to H Wing (Jasmine) = G + 1st to 7th Floor I Wing (Jasmine) = G + 1st to 6th Floor
Proposed no of Floors |  |  | C Wing (Orchid) = G + 1st to 7th Floor
D Wing (Orchid) = G + 1st to 7th Floor
E Wing (Orchid) = G + 1st to 7th Floor
F (Jasmine) = G + 1st to 7th Floor
G & H Wing (Jasmine) = G + 1st to 7th Floor
I Wing (Jasmine) = G + 1st to 6th Floor
Expected Completion |  |  | As per RERA - 31/08/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | C Wing (Orchid) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | , Flooring upto 1 Floor, Painting upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 1 Floor, Painting upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 77.14% |  | 90.71% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 1 | 14.29% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 1 | 14.29% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | D Wing (Orchid) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 75% |  | 90% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | E Wing (Orchid) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5.5 Floor Completed | , External Plaster upto 5.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 72.86% |  | 88.93% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5.5 | 78.57% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | F (Jasmine) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 6 Floor Completed | , Brickwork upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 56.43% |  | 79.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 6 | 85.71% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | G Wing (Jasmine) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 57.5% |  | 80% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | H Wing (Jasmine) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 57.5% |  | 80% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | I Wing (Jasmine) = G + 1st to 6th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 6 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.5
Excavation |  | 6 | 100% | 57.5% |  | 80% |  | Excavation in process | 3
Plinth |  | 6 | 100% |  |  |  |  | Excavation Completed | 6
RCC (Including podiums) |  | 7 | 100% |  |  |  |  | Footing in Process | 1.5
Brickwork | Brickwork & Internal Plaster | 6 | 100% |  |  |  |  | Footing Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 4.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 6
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4700 |  |  | rate 4700 by bhargav verbal on 30/08/2025
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 150000
Distressed valuation of the Property |  |  |  |  | 3760
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing C |  | 28 |  | 13517.8618 |  | 20276.7926
Wing D |  | 28 |  | 13517.8618 |  | 20276.7926
Wing E |  | 28 |  | 13517.8618 |  | 20276.7926
Wing F |  | 56 |  | 21000.9946 |  | 31501.4918
Wing G |  | 28 |  | 10500.4973 |  | 15750.7459
Wing H |  | 28 |  | 10500.4973 |  | 15750.7459
Wing I |  | 24 |  | 9000.4262 |  | 13500.6394
Total |  | 220 |  | 91556.0006 |  | 137334.001
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Wing C (Orchid)
Ground Floor For Parking & Entrance Lobby
1st, 3rd, 5th & 7th Floor For Residential | [9 empty] | Cost sheet | Sheet
1 |  | 1BHK | 481.7428 | 0 | 722.6142 | 1st, 3rd, 5th & 7th Floor For Residential |  |  | 1.4842 | 3463.1203 | 4130.8256 | 3805.6267
2 |  | 1BHK | 481.7428 | 0 | 722.6142 | [6 empty] | 2753.8837
3 |  | 1BHK | 481.7428 | 0 | 722.6142
4 |  | 1BHK | 481.7428 | 0 | 722.6142
2nd, 4th & 6th Floor For Residential | [9 empty] | 3034979.766
1 |  | 1BHK | 484.1647 | 0 | 726.2471 | 2nd, 4th & 6th Floor For Residential
2 |  | 1BHK | 484.1647 | 0 | 726.2471
3 |  | 1BHK | 484.1647 | 0 | 726.2471
4 |  | 1BHK | 484.1647 | 0 | 726.2471
Wing D (Orchid)
Ground Floor For Parking & Entrance Lobby
1st, 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 481.7428 | 0 | 722.6142 | 1st, 3rd, 5th & 7th Floor For Residential
2 |  | 1BHK | 481.7428 | 0 | 722.6142
3 |  | 1BHK | 481.7428 | 0 | 722.6142
4 |  | 1BHK | 481.7428 | 0 | 722.6142
2nd, 4th & 6th Floor For Residential
1 |  | 1BHK | 484.1647 | 0 | 726.2471 | 2nd, 4th & 6th Floor For Residential
2 |  | 1BHK | 484.1647 | 0 | 726.2471
3 |  | 1BHK | 484.1647 | 0 | 726.2471
4 |  | 1BHK | 484.1647 | 0 | 726.2471
Wing E (Orchid)
Ground Floor For Parking, Drivers Room & Entrance Lobby
1st, 3rd, 5th & 7th Floor For Residential
1 |  | 1BHK | 481.7428 | 0 | 722.6142 | 1st, 3rd, 5th & 7th Floor For Residential
2 |  | 1BHK | 481.7428 | 0 | 722.6142
3 |  | 1BHK | 481.7428 | 0 | 722.6142
4 |  | 1BHK | 481.7428 | 0 | 722.6142
2nd, 4th & 6th Floor For Residential
1 |  | 1BHK | 484.1647 | 0 | 726.2471 | 2nd, 4th & 6th Floor For Residential
2 |  | 1BHK | 484.1647 | 0 | 726.2471 |  |  |  | 3631235.4
3 |  | 1BHK | 484.1647 | 0 | 726.2471
4 |  | 1BHK | 484.1647 | 0 | 726.2471
Wing F (Jasmine)
Ground Floor For Parking & Entrance Lobby
1st to 7th Floor For Residential
1 |  | 1BHK | 375.0178 | 0 | 562.5266 | 1st to 7th Floor For Residential
2 |  | 1BHK | 375.0178 | 0 | 562.5266 |  |  |  | 2362611.888
3 |  | 1BHK | 375.0178 | 0 | 562.5266
4 |  | 1BHK | 375.0178 | 0 | 562.5266
5 |  | 1BHK | 375.0178 | 0 | 562.5266
6 |  | 1BHK | 375.0178 | 0 | 562.5266
7 |  | 1BHK | 375.0178 | 0 | 562.5266
8 |  | 1BHK | 375.0178 | 0 | 562.5266
Wing G (Jasmine)
Ground Floor For Parking & Entrance Lobby
1st to 7th Floor For Residential
1 |  | 1BHK | 375.0178 | 0 | 562.5266 | 1st to 7th Floor For Residential
2 |  | 1BHK | 375.0178 | 0 | 562.5266
3 |  | 1BHK | 375.0178 | 0 | 562.5266
4 |  | 1BHK | 375.0178 | 0 | 562.5266
Wing H (Jasmine)
Ground Floor For Parking & Entrance Lobby
1st to 7th Floor For Residential
1 |  | 1BHK | 375.0178 | 0 | 562.5266 | 1st to 7th Floor For Residential
2 |  | 1BHK | 375.0178 | 0 | 562.5266
3 |  | 1BHK | 375.0178 | 0 | 562.5266
4 |  | 1BHK | 375.0178 | 0 | 562.5266
Wing I (Jasmine)
Ground Floor For Parking & Entrance Lobby
1st to 6th Floor For Residential | [8 empty] | 2812633.2
1 |  | 1BHK | 375.0178 | 0 | 562.5266 | 1st to 6th Floor For Residential
2 |  | 1BHK | 375.0178 | 0 | 562.5266
3 |  | 1BHK | 375.0178 | 0 | 562.5266
4 |  | 1BHK | 375.0178 | 0 | 562.5266
Remarks:
* | Wing C to I = Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | #REF!
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + C.P Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates of the Property have been revised on 30/08/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Sudhir Bhosale |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Park One Phase I
Layout :
Google Map :
Formulas:
Shirgaon = [Shirgaon, row above]
C, D & E
F
H
I
F
C Wing
C Wing
D Wing
C Wing
E Wing
F Wing
G Wing
H Wing
I Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted