## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-15
Name of the builder group |  |  |  | M/s. Metro Creators
Name of the builder company |  |  |  | M/s. Metro Creators
Name of the Project |  |  |  | Metro Aangan Phase I
Contact Details ( Name & Contect No.) |  |  |  | 8888311144
Name / No of the Building |  |  |  | Building No. 1 (Wing A, B & C) |  |  |  |  | 38.0275 | 6.2625 | 476.7376
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans |  |  |  |  | 409.328
RERA No. |  |  |  | P51700020756
Project location details |  | Metro Aangan Phase I, Survey No..78/7B, 78/8B, Barrage Road, Kulgaon, Badlapur, Ambernath, Thane.
Survey No. |  | 78/7B, 78/8B
Road |  | Barrage Road |  | Locality/Village |  | Kulgaon
City |  | Badlapur |  | District |  | Thane
Taluka |  | Ambernath |  | Pin Code |  | 421503
Near by Landmark |  | Shree Gajanan Apartment Raut Chawl |  | Distance from city centre: |  | 4Km from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | D-Mart
West | NA | NA |  |  | Shree Gajanan Aapartment
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.1584 |  | Longitude |  | 73.2488
Location Link |  | https://goo.gl/maps/JWygsrLZg5SQaWsq9?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 10012
Permissible FSI |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  | 0.34527
Total FSI availaible for the project |  |  |  | 1.2453
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 12467.6
Total number of Buildings |  |  |  | 03 Building
Approval Detail : Plan approval
Layout Approval No |  | KBNP/NRV/BANDH/6899-18 |  |  | Dated | 01/09/2020.
Approved Floor plan No. |  | KBNP/NRV/BANDH/6899-18 |  |  | Dated | 01/09/2020.
Commencement Certificate No. |  | KBNP/NRV/B.P./6899/2020-2019 UNIQUE NO.18 |  |  | Dated | 01/09/2020.
Valid Up to: Wing (A & B) = Gr(St) + 1st to 8th Floor Wing C = Gr + 1st to 12th Floor
O. Certificate No.: |  | KBNP/NRV/0685/2021-2022 Wing A = Gr(St) + 1st to 8th Floor KBNP/NRV/3229/2022-2023 Wing B = Gr(St) + 1st to 8th Floor |  | Date of approval: | Dated | 21/01/2022 15/04/2022
|  | KBNP/NRV/879/2024-2025 Approved Upto : Wing C = Gr/St + 1st to 12th Floor (Residential Units = 143 Nos.) |  |  | Dated | 2024-06-19
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 12467.6
Approved no of units |  |  | Flats - 251, Shops - 25, Offices - 08
Approved no of Floors |  |  | Wing (A & B) = Gr + 8th Floor
Proposed no of Floors |  |  | Wing (A & B) = Gr + 8th Floor
Proposed no of Floors |  |  | Wing C = Gr + 1st to 12th Floor
Expected Completion |  |  | Completed.
Projected life of the structure |  |  | Wing A & B = 57 Years Wing C = 59 Years
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Nothing
Construction details: |  | Building No. 1 (Wing A & B) = Gr + 8th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 8
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100% |  | Piling Work in process | 2
|  |  |  | 1 |  | 0.8 |  | Excavation in process | 4
Plinth |  | 8 | 100% |  |  |  |  | Excavation Completed | 8
RCC (Including podiums) |  | 9 | 100% |  |  |  |  | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 8 | 100% |  |  |  |  | Plinth in process | 6
Possession |  | 8 | 100% |  |  |  |  | Plinth completed | 8
Construction details: |  | Building No. 1 (Wing C) = Gr + 1st to 12th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 8 Floor, Finishing upto 4 Floor Completed | , Painting upto 8 Floor, Finishing upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100% |  | Piling Work in process | 3
|  |  |  | #VALUE! |  | #VALUE! |  | Excavation in process | 6
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 8 Floor, Finishing upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 90% |  | 95% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 66.67% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 33.33% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Wheather the construction is as per approved Building plan : Yes
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 4500
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 8000
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6500
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 3,00,000/-
Club Charges |  |  |  |  | 1,00,000/-
Grill Charges |  |  |  |  | 40,000/-
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | 50,000/-
Recommended rate of Parking |  |  |  |  | 1,50,000/-
Distressed valuation of the Property |  |  |  |  | 3600
Commercial Area Details : Office
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area | [6 empty] | 3.05 | 1.1731
Wing A |  | 8 | 3767.9382 |  | 5892.0791 | [6 empty] | 2.6 | 4.563
Commercial Area Details : Shop | [12 empty] | 0.585
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area | [7 empty] | 0.819
Wing A |  | 13 | 2132.5637 |  | 3198.8455
Wing B |  | 12 | 1818.3087 |  | 2727.463
Total |  | 25 | 3950.8724 |  | 5926.3086
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Wing A |  | 55 | 19960.0081 |  | 35045.8106
Wing B |  | 52 | 19960.0081 |  | 31079.8498
Wing C |  | 143 | 67590.4928 |  | 120485
Total |  | 250 | 107510.5091 |  | 66125.6604
Details of Flats in Building
Flat/Shop No.(As per Approved Floor Plan) | Flat/Shop No.(As per Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Wing A
Ground Floor for Commercial, Residential & Parking
1 |  | Shop | 174.6459 | 0 | 261.9689 | Ground Floor for Commercial, Residential & Parking
2 |  | Shop | 194.9899 | 0 | 292.4848
3 |  | Shop | 318.6682 | 0 | 478.0023
4 |  | Shop | 137.8868 | 0 | 206.8303
5 |  | Shop | 180.5661 | 0 | 270.8491
6 |  | Shop | 134.0118 | 0 | 201.0177
7 |  | Shop | 121.095 | 0 | 181.6425
8 |  | Shop | 121.095 | 0 | 181.6425
9 |  | Shop | 134.0118 | 0 | 201.0177
10 |  | Shop | 180.5661 | 0 | 270.8491
11 |  | Shop | 153.0103 | 0 | 229.5154
12 |  | Shop | 134.0118 | 0 | 201.0177
13 |  | Shop | 148.005 | 0 | 222.0075
1 |  | 1BHK | 359.1409 | 0 | 520.7542 |  |  |  | 4608.6998
2 |  | 1BHK | 359.1409 | 0 | 520.7542
3 |  | 1BHK | 359.1409 | 0 | 520.7542
1st Floor For Commercial
101 |  | Office | 451.3614 | 64.1804 | 741.2225 | 1st Floor |  | 350.9333
102 |  | Office | 475.2306 | 64.1804 | 777.0263
103 |  | Office | 289.9822 | 41.1723 | 476.1455
104 |  | Office | 593.4462 | 70.6388 | 960.8081
105 |  | Office | 512.8508 | 0 | 769.2762
106 |  | Office | 497.8888 | 0 | 746.8332 |  |  | 47.335
107 |  | Office | 497.8888 | 0 | 746.8332 |  |  | 36.91
108 |  | Office | 449.2894 | 0 | 673.934
2nd Floor for Residential
201 |  | 1BHK | 365.3302 | 143.6994 | 673.4281 | 2nd Floor |  | 30.165
202 |  | 1BHK | 375.3407 | 160.1683 | 704.4123
203 |  | 1BHK | 375.3407 | 162.644 | 706.888
204 |  | 2BHK | 500.4184 | 211.9432 | 831.5782
205 |  | 2BHK | 500.4184 | 112.2685 | 781.7409
206 |  | 1BHK | 375.6636 | 125.5082 | 670.2205
207 |  | 1BHK | 375.6636 | 125.5082 | 670.2205
208 |  | 1BHK | 375.6636 | 103.6573 | 648.3695
4th & 6th Floor
401, 601 |  | 1BHK | 365.3302 | 52.313 | 582.0418 | 4th & 6th Floor
402, 602 |  | 1BHK | 375.3407 | 0 | 544.244
403, 603 |  | 1BHK | 375.3407 | 0 | 544.244
404, 604 |  | 2BHK | 500.4184 | 46.8234 | 772.43 |  |  | 4401.6932
405, 605 |  | 2BHK | 500.4184 | 56.1881 | 781.7947
406, 606 |  | 1BHK | 375.6636 | 52.313 | 597.0253
407, 607 |  | 1BHK | 375.6636 | 52.313 | 597.0253
408, 608 |  | 1BHK | 375.6636 | 52.313 | 597.0253
3rd, 5th & 7th Floor
301, 501, 701 |  | 1BHK | 365.1149 | 34.8754 | 564.2919 | 3rd, 5th & 7th Floor
302, 502, 702 |  | 1BHK | 375.9865 | 51.3443 | 596.5247
303, 503, 703 |  | 1BHK | 375.9865 | 51.3443 | 596.5247
304, 504, 704 |  | 2BHK | 502.033 | 51.3443 | 779.2921
305, 505, 705 |  | 2BHK | 502.033 | 51.3443 | 779.2921
306, 506, 706 |  | 1BHK | 377.8164 | 34.8754 | 582.7091
307, 507, 707 |  | 1BHK | 377.8164 | 34.8754 | 582.7091
308, 508, 708 |  | 1BHK | 377.8164 | 34.8754 | 582.7091
8th Floor (Part Terrace & Refuge Area)
801 | - | Natural Terrace |  |  |  | 8th Floor (Part Terrace & Refuge Area)
802 | -
803 | -
804 | -
805 | 801 | 2BHK | 500.4184 | 56.1881 | 781.7947
806 | 802 | 1BHK | 375.6636 | 52.313 | 597.0253
807 | 803 | 1BHK | 375.6636 | 52.313 | 597.0253
808 | 804 | 1BHK | 375.6636 | 52.313 | 597.0253
Wing B
Ground Floor for Commercial + Parking
14 |  | Shop | 148.005 | 0 | 222.0075 | Ground Floor
15 |  | Shop | 134.0118 | 0 | 201.0177
16 |  | Shop | 180.5661 | 0 | 270.8491
17 |  | Shop | 180.5661 | 0 | 270.8491
18 |  | Shop | 134.0118 | 0 | 201.0177
19 |  | Shop | 148.005 | 0 | 222.0075
20 |  | Shop | 148.005 | 0 | 222.0075
21 |  | Shop | 134.0118 | 0 | 201.0177
22 |  | Shop | 180.5661 | 0 | 270.8491
23 |  | Shop | 180.5661 | 0 | 270.8491
24 |  | Shop | 140.4702 | 0 | 210.7053
25 |  | Shop | 109.5237 | 0 | 164.2856
1st Floor For Residential
101 |  | 1BHK | 418.0738 | 34.8754 | 641.0823 | 1st Floor
102 |  | 1BHK | 418.0738 | 34.8754 | 641.0823
103 |  | 1BHK | 418.0738 | 34.8754 | 641.0823
104 |  | 1BHK | 375.556 | 123.3554 | 606.2339
105 |  | 1BHK | 375.8789 | 161.2447 | 625.6467
106 |  | 1BHK | 375.8789 | 161.2447 | 625.6467
107 |  | 1BHK | 375.8789 | 165.9809 | 628.0148
2nd, 4th & 6th Floor for Residential
201, 401, 601 |  | 1BHK | 376.2018 | 52.313 | 597.8057 | 2nd, 4th & 6th Floor
202, 402, 602 |  | 1BHK | 376.2018 | 52.313 | 597.8057
203, 403, 603 |  | 1BHK | 376.2018 | 52.313 | 597.8057 |  |  | 4391.0592
204, 404, 604 |  | 1BHK | 407.848 | 0 | 591.3795 |  |  | 4438.7738
205, 405, 605 |  | 1BHK | 408.0632 | 0 | 591.6917
206, 406, 606 |  | 1BHK | 408.0632 | 0 | 591.6917
207, 407, 607 |  | 1BHK | 375.8789 | 52.313 | 597.3374
3rd, 5th & 7th Floor
301, 501, 701 |  | 1BHK | 375.4483 | 34.8754 | 579.2754 | 3rd, 5th & 7th Floor
302, 502, 702 |  | 1BHK | 375.4483 | 34.8754 | 579.2754
303, 503, 703 |  | 1BHK | 375.4483 | 34.8754 | 579.2754
304, 504, 704 |  | 1BHK | 375.556 | 52.4207 | 596.9768
305, 505, 705 |  | 1BHK | 375.8789 | 52.4207 | 597.4451
306, 506, 706 |  | 1BHK | 375.8789 | 52.4207 | 597.4451
307, 507, 707 |  | 1BHK | 375.8789 | 52.313 | 597.3374
8th Floor
801 |  | 1BHK | 376.2018 | 52.313 | 597.8057 | 8th Floor
802 |  | 1BHK | 376.2018 | 52.313 | 597.8057
803 |  | 1BHK | 376.2018 | 52.313 | 597.8057
804 |  | Natural Terrace
805
806
807
Wing C
Ground Floor for for parking
1st, 3rd, 5th, 9th, 11th Floor for Residential
101 …..1101 |  | 1BHK | 371.8962 | 52.313 | 700 | 2nd, 4th & 6th Floor |  |  | 1.8822 | 26.165 | 5.6625 | 0.9 | 4.86
102 …..1102 |  | 1BHK | 394.8235 | 52.313 | 730
103 …..1103 |  | 2BHK | 570.3844 | 52.313 | 1030 |  |  | 2548.5437
104 …..1104 |  | 1BHK | 366.0836 | 52.313 | 690 |  |  | 3804.3478
105 …..1105 |  | 2BHK | 547.6723 | 47.8998 | 990 | [6 empty] | 10.764
106 …..1106 |  | 2BHK | 539.4917 | 50.2679 | 980
107 …..1107 |  | 1BHK | 380.1845 | 46.3928 | 700
108 …..1108 |  | 1BHK | 380.1845 | 46.3928 | 700 |  |  | 3750
109 …..1109 |  | 3BHK | 702.0281 | 69.7507 | 1250
1010 …..1110 |  | 2BHK | 542.2903 | 43.5942 | 975
1011 …..1111 |  | 2BHK | 487.8245 | 34.8754 | 880
1012 …..1112 |  | 1BHK | 380.1845 | 46.3928 | 700
2nd, 4th, 6th, 10th, 12th Floor
201 …..1201 |  | 1BHK | 371.8962 | 0 | 650 | 2nd, 4th & 6th Floor
202 …..1202 |  | 1BHK | 394.8235 | 0 | 685
203 …..1203 |  | 2BHK | 570.3844 | 0 | 980 |  |  | 2678.5714
204 …..1204 |  | 1BHK | 366.0836 | 0 | 645 |  |  | 4069.7674
205 …..1205 |  | 2BHK | 547.6723 | 52.313 | 1000
206 …..1206 |  | 2BHK | 539.4917 | 0 | 925
207 …..1207 |  | 1BHK | 380.1845 | 0 | 650
208 …..1208 |  | 1BHK | 380.1845 | 0 | 650 |  |  | 4038.4615
209 …..1209 |  | 3BHK | 702.0281 | 0 | 1180 |  |  | 2224.5763
210 …..1210 |  | 2BHK | 542.2903 | 0 | 945
211 …..1211 |  | 2BHK | 487.8245 | 53.2818 | 890
212 …..1212 |  | 1BHK | 380.1845 | 0 | 650
7th Floor
701 |  | 1BHK | 371.8962 | 52.313 | 700 | 2nd, 4th & 6th Floor
702 |  | 1BHK | 394.8235 | 52.313 | 730
703 |  | 2BHK | 570.3844 | 52.313 | 1053 |  |  | Flat No. C703 = sale area changes from 1030 to 1053 by bhargav staff case on 15/07/2025
704 |  | 1BHK | 366.0836 | 52.313 | 690
705 |  | 2BHK | 547.6723 | 47.8998 | 990
706 |  | 2BHK | 539.4917 | 50.2679 | 980
707 |  | 1BHK | 380.1845 | 46.3928 | 700
708 |  | 1BHK | 380.1845 | 46.3928 | 700
709 |  | 3BHK | 702.0281 | 69.7507 | 1250
710 |  | 2BHK | 542.2903 | 43.5942 | 975
711 |  | 2BHK | 487.8245 | 34.8754 | 880
712 |  | 1BHK | 380.1845 | 46.3928 | 700
8th Floor (Part Refuge Area)
801 |  | 1BHK | 371.8962 | 0 | 650 | 8th Floor (Part Refuge Area)
802 |  | 1BHK | 394.8235 | 0 | 685
803 |  | 2BHK | 570.3844 | 0 | 980 |  |  | 2678.5714
804 |  | Refuge Area | [5 empty] | #DIV/0!
805 |  | 2BHK | 547.6723 | 50.1602 | 1000
806 |  | 2BHK | 539.4917 | 0 | 925
807 |  | 1BHK | 380.1845 | 0 | 650
808 |  | 1BHK | 380.1845 | 0 | 650 |  |  | 4038.4615
809 |  | 3BHK | 702.0281 | 0 | 1180
810 |  | 2BHK | 542.2903 | 0 | 945
811 |  | 2BHK | 487.8245 | 53.2818 | 890
812 |  | 1BHK | 380.1845 | 0 | 730
Remarks:
1. Building No.1 - A to C Wing = All work Completed. OC Received. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + E.P Area. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. Car parking is subjected to authentic documentation. 8. We have updated approved floor plan of wing C on(29/08/2022) 9. We have updated OC of Wing A & B (on 10/02/2023) from RERA site. 10. We have updated OC for Wing C (On 25/06/2024). 8. On Site, we meet Mr. Ramdas - 7620554093.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Metro Aangan Phase I
Google Map :
A &B

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.3 | 9.075 | CB |  |  | 0 | 2.75 | 1.2 | 3.3
|  | 1.2 | 1.7 | 2.04 | FB |  |  | 0 |  |  | 0
|  | 0.75 | 2.75 | 2.0625 |  |  |  | 0 | 2.4 | 0.4 | 0.96
| kitch | 2.25 | 1.65 | 3.7125 | CB |  |  | 0 |  |  | 0
|  | 1.05 | 2.25 | 2.3625 | FB |  |  | 0 |  |  | 0
|  | 0.3 | 2.25 | 0.675 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 3 | 8.25 | CB | 2.75 | 0.45 | 1.2375 | 2.7 | 1.8 | 4.86
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 0.95 | 1.2 | 1.14 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 1.5 | 1.8 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 2.3 | 0.9 | 2.07 |  |  |  | 0 |  |  | 0
| passage2 | 0.7 | 1.2 | 0.84 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 366.272 | 34.0275 |  |  | 13.3204 | 1.2375 |  | 98.1677 | 9.12
|  |  | 379.5925 | 35.265

## Note
2021-10-26 | Asmi | Abhishek

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Housing | Metro Aangan | 1BHK | 359 | 520.55 | 4610.5081 | 2400000
Housing |  | 1BHK | 408 | 591.6 | 4643.3401 | 2747000
Magic Brick |  | 1BHK |  | 832 | 4745.1923 | 3948000
Magic Brick |  | 1BHK |  | 782 | 4473.1458 | 3498000
Average |  |  |  |  | 4618.0466
Valuation Adopted