## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/07/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | PNB Housing Finance Limited | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | PNB Thane | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-07-15 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Saphale Land Developers Llp | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Saphale Land Developers Llp | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Rajlaxxmi Park | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | 8308036666 / 7774000939
Site Person - Contact Details (Name & Contact No.) |  |  |  | Miss. Disha
Name / No of the Building |  |  |  | Building No.1 (Wing A & B), Building No.2, Building No.3 (Wing A & B), Building No.4 (Wing A & B), Building No.5 & Building For Housing For Affected People
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, Cost Sheet | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P99000056103 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Rajlaxxmi Park, Gut No.84/B, near Gurantara Bunglow, Tembhikhodave Road, , Mande, Saphale, Palghar, Palghar - 401102. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Gut No |  | 84/B | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | NA | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Tembhikhodave Road |  | Locality/Village |  | Mande | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Saphale |  | District |  | Palghar | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Palghar |  | Pin Code |  | 401102 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Gurantara Bunglow |  | Distance from city centre: |  | 2.7KM from Saphale Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Gut No.84(pt) |  |  | Open Plot
West | NA | 15.00 M Wide Village Road |  |  | Internal Road
North | NA | 24.00 M Wide Road No-38(MDR) |  |  | Tembhikhodave Road
South | NA | Gut No.84 |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.566489,72.797826
Location Link |  | https://maps.app.goo.gl/C3EapghQdHFBE3588
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 8338.61
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.87764
Total FSI availaible for the project |  |  |  | 1.8776
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 15656.88
Total number of Buildings |  |  |  | 09 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Collector Of Palghar | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | Mhasul/K-1/MJ1/BSP/SR/CR/32/2023 |  |  | Dated | 2023-11-09 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | Mhasul/K-1/MJ1/BSP/SR/CR/32/2023 |  |  | Dated | 2023-11-09 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | Mhasul/K-1/T-1/NAP/SR-32/2023 |  |  | Dated | 2023-11-09 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Building No.1 (Wing A & B) = Gr. + 1st to 7th Floors, Building No.2, 3( Wing A & B) & 5 = Gr. + 1st to 4th Floors, Building No.4( Wing A & B) = Gr. + 1st to 7th Floors, Housing For Affected People = Gr. + 1st to 4th Floor. Total B.U.A For (Bldg 1 to 5) = 15656.88sqm & Housing For Affected People = 1490.84sqm. | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | Building No.1 (Wing A & B) = Gr. + 1st to 7th Floors, Building No.2, 3( Wing A & B) & 5 = Gr. + 1st to 4th Floors, Building No.4( Wing A & B) = Gr. + 1st to 7th Floors, Housing For Affected People = Gr. + 1st to 4th Floor. Total B.U.A For (Bldg 1 to 5) = 15656.88sqm & Housing For Affected People = 1490.84sqm. |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 15656.88
Approved no of units |  |  | Sale Flats - 285, Housing For Affected People = 29, Shops - 14, Offices - 13
Approved no of Floors |  |  | Building No.1(Acacia) Wing A & B = Gr. + 1st to 7th Floor Building No.2(Teak) = Gr. + 1st to 4th Floor. Building No.3(Pine) Wing A & B = Gr. + 1st to 4th Floor Building No.4(Oak) Wing A & B = Gr. + 1st to 7th Floor Building No.5(Palm) = Gr. + 1st to 4th Floor. Housing For Affected People = Gr. + 1st to 4th Floor
Proposed no of Floors |  |  | Building No.1(Acacia) (Wing A&B) = G + 1st to 7th Floor
Building No.1 (Wing B) = G + 1st to 7th Floor
Building No.2(Teak) = G + 1st to 4th Floor
Building No.3(Pine) (Wing A & B) = G + 1st to 4th Floor
Building No.3(Pine) (Wing B) = G + 1st to 4th Floor
Building No.4(Oak) (Wing A&B) = G + 1st to 7th Floor
Building No.4 (Wing B) = G + 1st to 7th Floor
Building No.5(Palm) = G + 1st to 4th Floor
Housing For Affected People = Gr. + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/12/2030
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Amphitheatre/ Community Area, Swimming Pool, Kids Play Area, Game Zone, Out Door Gym, Jogging Track/ Walkway etc |  |  |  |  | As per builder brochure
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1(Acacia) (Wing A&B) = G + 1st to 7th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.2(Teak) = G + 1st to 4th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 3 Slab Completed | , RCC upto 3 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 3 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 34% |  | 63% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 3 | 60% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.3(Pine) (Wing A & B) = G + 1st to 4th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% |  |  |  |  | Plinth in process | 3
Possession |  | 4 | 100% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.3(Pine) (Wing B) = G + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 90% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.4(Oak) (Wing A) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 6 Floor, Internal Plaster upto 2 Floor Completed | , Brickwork upto 6 Floor, Internal Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 6 Floor, Internal Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 58.57% |  | 80.71% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 6 | 85.71% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 2 | 28.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.4(Oak) (Wing B) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 6 Floor, Internal Plaster upto 2 Floor Completed | , RCC upto 7 Slab, Brickwork upto 6 Floor, Internal Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 6 Floor, Internal Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 53.57% |  | 76.96% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 7 | 87.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 6 | 85.71% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 2 | 28.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.5(Palm) = G + 1st to 4th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% |  |  |  |  | Plinth in process | 3
Possession |  | 4 | 100% |  |  |  |  | Plinth completed | 4
Construction details: |  | Housing For Affected People = Gr. + 1st to 4th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3300 |  |  | 3K to 3200 | [8 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 6000 | [11 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 5000 | [11 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges + Development Charges |  |  |  |  | 80000 | [11 empty] | 1300000 | 400000 | 350000 | 400000
Generator Charges |  |  |  |  | 20000 | [11 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges |  |  |  |  | 25000 | [11 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges |  |  |  |  | 25000 | [11 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 100000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 2640 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1(Wing A+B) Shops |  | 14 |  | 2789.2753 |  | 4183.913
Building No.1(Wing A+B) Offices |  | 13 |  | 4457.48 |  | 6686.2201
Total |  | 27 |  | 7246.7554 |  | 10870.133
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 Wing A |  | 30 |  | 14180.9242 |  | 20780.311
Building No.1 Wing B |  | 30 |  | 14173.6046 |  | 20769.6977
Building No.2 |  | 32 |  | 14225.1642 |  | 20626.4881
Building No.3 Wing A |  | 32 |  | 14350.2419 |  | 20807.8507
Building No.3 Wing B |  | 27 |  | 11887.5463 |  | 17236.9422
Building No.4 Wing A |  | 49 |  | 22333.1472 |  | 32383.0634
Building No.4 Wing B |  | 42 |  | 18731.5128 |  | 27160.6936
Building No.5 |  | 43 |  | 16011.5576 |  | 23216.7586
Housing For Affected People |  | 29 |  | 12680.3149 |  | 18386.4566
Total |  | 314 |  | 138574.0138 |  | 201368.262
Grand Total |  | 341 |  | 145820.7691 |  | 212238.395
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | RERA Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No.1(Acacia) Wing A + B
Ground Floor For Commercial, Entrance Lobby, Society Office, Drivers Room & Parking
1 |  | Shop | 324.5346 | 0 | 324.5346 | 0 | 486.8019 | 29.1 | 10.764
2 |  | Shop | 262.211 | 0 | 262.211 | 0 | 393.3166
3 |  | Shop | 148.7585 | 0 | 148.7585 | 0 | 223.1377
4 |  | Shop | 181.0505 | 0 | 181.0505 | 0 | 271.5757 | 16.5
5 |  | Shop | 197.7347 | 0 | 197.7347 | 0 | 296.602
6 |  | Shop | 145.0987 | 0 | 145.0987 | 0 | 217.6481
7 |  | Shop | 194.2902 | 0 | 194.2902 | 0 | 291.4353 | 17.76
8 |  | Shop | 194.2902 | 0 | 194.2902 | 0 | 291.4353
9 |  | Shop | 161.6753 | 0 | 161.6753 | 0 | 242.5129
10 |  | Shop | 181.0505 | 0 | 181.0505 | 0 | 271.5757
11 |  | Shop | 181.0505 | 0 | 181.0505 | 0 | 271.5757
12 |  | Shop | 138.5327 | 0 | 138.5327 | 0 | 207.799 | 12.555
13 |  | Shop | 154.4634 | 0 | 154.4634 | 0 | 231.6951 | 14.025
14 |  | Shop | 324.5346 | 0 | 324.5346 | 0 | 486.8019
1st Floor For Commercial
1 |  | Office | 321.9512 | 0 | 321.9512 | 0 | 482.9269 | 29.1
2 |  | Office | 253.9228 | 0 | 253.9228 | 0 | 380.8841
3 |  | Office | 136.3799 | 0 | 136.3799 | 0 | 204.5698
4 |  | Office | 263.718 | 0 | 263.718 | 0 | 395.577
5 |  | Office | 293.6419 | 0 | 293.6419 | 0 | 440.4629 | 27.118
6 |  | Office | 263.718 | 0 | 263.718 | 0 | 395.577
7 |  | Office | 136.3799 | 0 | 136.3799 | 0 | 204.5698
8 |  | Office | 253.9228 | 0 | 253.9228 | 0 | 380.8841
9 |  | Office | 186.9707 | 0 | 186.9707 | 0 | 280.456
10 |  | Office | 285.6766 | 0 | 285.6766 | 0 | 428.5148 | 26.0225
11 |  | Office | 1431.612 | 0 | 1431.612 | 0 | 2147.418
12 |  | Office | 343.9098 | 0 | 343.9098 | 0 | 515.8647
13 |  | Office | 285.6766 | 0 | 285.6766 | 0 | 428.5148
1st Floor For Commercial
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | RERA Carpet area | Balcony + Encl. Balcony Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Building No.1(Acacia)
Wing A
Ground Floor For Commercial, Entrance Lobby & Parking
1st Floor For Commercial
2nd For Residential
1 |  | 1BHK | 322.7047 | 94.7232 | 417.4279 | 53.2818 | 658.5523 | 28.035 | 8.8
2 |  | 1BHK | 321.0901 | 93.5392 | 414.6293 | 0 | 601.2125 |  |  | 27.8825 | 5.94 |  | 2.75 | 8.69
3 |  | 2BHK | 501.3871 | 29.601 | 530.9881 | 86.112 | 856.0448 | 43.7945 | 2.75
4 |  | 2BHK | 528.4048 | 29.601 | 558.0058 | 78.5772 | 887.6856
5 |  | 1BHK | 322.0589 | 120.5568 | 442.6157 | 0 | 641.7927
3rd to 7th Floor
1 |  | 1BHK | 322.7047 | 94.7232 | 417.4279 | 0 | 605.2705 | 3155.614
2 |  | 1BHK | 320.8748 | 93.5392 | 414.414 | 0 | 600.9003
3 |  | 2BHK | 501.3871 | 29.601 | 530.9881 | 0 | 769.9328
4 |  | 2BHK | 528.4048 | 29.601 | 558.0058 | 0 | 809.1084
5 |  | 1BHK | 322.0589 | 120.5568 | 442.6157 | 0 | 641.7927
Wing B
Ground Floor For Commercial, Entrance Lobby, Driver Room, Society Office & Parking
1st Floor For Commercial
2nd Floor For Residential
1 |  | 1BHK | 322.0589 | 120.5568 | 442.6157 | 0 | 641.7927 | 27.9625 | 11.195
2 |  | 2BHK | 528.4048 | 29.601 | 558.0058 | 78.5772 | 887.6856
3 |  | 2BHK | 501.3871 | 29.601 | 530.9881 | 86.112 | 856.0448 | 43.7945 | 2.75
4 |  | 1BHK | 319.6908 | 93.5392 | 413.23 | 53.2818 | 652.4652
5 |  | 1BHK | 322.7047 | 94.7232 | 417.4279 | 0 | 605.2705 | 28.035 | 8.8
3rd to 7th Floor
1 |  | 1BHK | 322.0589 | 120.5568 | 442.6157 | 0 | 641.7927
2 |  | 2BHK | 528.4048 | 29.601 | 558.0058 | 0 | 809.1084
3 |  | 2BHK | 501.3871 | 29.601 | 530.9881 | 0 | 769.9328
4 |  | 1BHK | 319.6908 | 93.5392 | 413.23 | 0 | 599.1834
5 |  | 1BHK | 322.7047 | 94.7232 | 417.4279 | 0 | 605.2705
Building No.2(Teak)
Ground Floor For Residential,Entrance Lobby, Society Office & Parking | [9 empty] | 3000
1 |  | 1BHK | 339.9271 | 0 | 339.9271 | 0 | 492.8943 | 30.344
2 |  | 1BHK | 315.2776 | 59.202 | 374.4796 | 0 | 542.9954
3 |  | 1BHK | 315.2776 | 59.202 | 374.4796 | 0 | 542.9954
4 |  | 1BHK | 315.2776 | 59.202 | 374.4796 | 0 | 542.9954 | 27.4325 | 5.5
1st to 4th Floor
1 |  | 1BHK | 312.9095 | 88.803 | 401.7125 | 0 | 582.4831 | 27.4325 | 8.25
2 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242 |  |  | 3641.2672
3 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242 | 43.4675 | 2.75
4 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
5 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
6 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
7 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
Building No.3(Pine)
Wing A
Ground Floor For Residential,Entrance Lobby, Driver Room & Parking
1 |  | 1BHK | 315.2776 | 59.202 | 374.4796 | 0 | 542.9954
2 |  | 1BHK | 315.2776 | 59.202 | 374.4796 | 0 | 542.9954
3 |  | 1BHK | 315.2776 | 59.202 | 374.4796 | 0 | 542.9954
4 |  | 2BHK | 465.0048 | 0 | 465.0048 | 0 | 674.257
1st to 4th Floor
1 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
2 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
3 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
4 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
5 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
6 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
7 |  | 1BHK | 312.9095 | 88.803 | 401.7125 | 0 | 582.4831
Wing B
Ground Floor For Residential, Entrance Lobby & Parking
1 |  | 2BHK | 465.0048 | 0 | 465.0048 | 0 | 674.257
2 |  | 1BHK | 315.2776 | 59.202 | 374.4796 | 0 | 542.9954
3 |  | 1BHK | 315.2776 | 59.202 | 374.4796 | 0 | 542.9954
1st to 4th Floor
1 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
2 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
3 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
4 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
5 |  | 1BHK | 315.4928 | 88.803 | 404.2958 | 0 | 586.229
6 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
Building No.4(Oak)
Wing A
Ground Floor For Entrance Lobby & Parking
1st to 7th Floor
1 |  | 1BHK | 312.9095 | 88.803 | 401.7125 | 0 | 582.4831
2 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
3 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
4 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
5 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
6 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
7 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242 | 43.4675 | 2.75
Wing B
Ground Floor For Entrance Lobby, Society Office & Parking
1st to 7th Floor
1 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
2 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
3 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
4 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
5 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654
6 |  | 1BHK | 321.413 | 90.4176 | 411.8306 | 0 | 597.1544 | 27.9125 | 8.25
Building No.5(Palm)
Ground Floor For Residential, Entrance Lobby, Driver Room & Parking | [8 empty] | 3400
1 |  | 1RK | 274.9126 | 0 | 274.9126 | 0 | 398.6232 | 24.03 | 1355318.9208
2 |  | 1BHK | 365.6531 | 0 | 365.6531 | 0 | 530.197 |  | 1802669.6844
3 |  | 1RK | 274.9126 | 0 | 274.9126 | 0 | 398.6232 |  | 1355318.9208
4 |  | 1BHK | 365.6531 | 0 | 365.6531 | 0 | 530.197 | 31.0275 | 1802669.6844
5 |  | 1BHK | 365.6531 | 0 | 365.6531 | 0 | 530.197 |  | 1802669.6844
6 |  | 1RK | 243.697 | 29.601 | 273.298 | 0 | 396.282 | 21.4125 | 1347358.9428
7 |  | 1BHK | 315.4928 | 59.202 | 374.6948 | 0 | 543.3075 |  | 1847245.5612
1st to 4th Floor | [8 empty] | 0
1 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662 |  | 1974605.2092
2 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662 |  | 1974605.2092
3 |  | 1RK | 280.9404 | 29.601 | 310.5414 | 0 | 450.285 |  | 1530969.102
4 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662 |  | 1974605.2092
5 |  | 1RK | 280.9404 | 29.601 | 310.5414 | 0 | 450.285 |  | 1530969.102
6 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662 |  | 1974605.2092
7 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662 |  | 1974605.2092
8 |  | 1BHK | 316.1387 | 88.803 | 404.9417 | 0 | 587.1654 |  | 1996362.4824
9 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662 |  | 1974605.2092
Housing For Affected People
Ground Floor For Residential, Entrance Lobby & Parking
1 |  | 1BHK | 365.6531 | 0 | 365.6531 | 0 | 530.197 | 33.6975
2 |  | 2BHK | 488.9009 | 0 | 488.9009 | 0 | 708.9063
3 |  | 2BHK | 488.9009 | 0 | 488.9009 | 0 | 708.9063 | 43.6775
4 |  | 1BHK | 365.6531 | 0 | 365.6531 | 0 | 530.197
5 |  | 1BHK | 365.6531 | 0 | 365.6531 | 0 | 530.197
1st to 4th Floor
1 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662
2 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662
3 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
4 |  | 2BHK | 495.0364 | 29.601 | 524.6374 | 0 | 760.7242
5 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662
6 |  | 1BHK | 370.9274 | 29.601 | 400.5284 | 0 | 580.7662
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Building No. 2, 4 = Construction work is in process at the time of Visit (labour found). Building No. 1 & 6 = Work not yet Started. Bldg No. 3 & 5 = All work Completed. Please provide OC.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
* | Nalla Located between Building No.1 & Building No.2 & 3
* | Nomenclature of Buildings |  | As Per Floor Plan |  | As per Sale plan
* |  |  | Building No.1 |  | Acacia
* |  |  | Building No.2 |  | Teak
* |  |  | Building No.3 |  | Pine
* |  |  | Building No.4 |  | Oak
* |  |  | Building No.5 |  | Palm
* |  |  | Aminity Building No.6 |  | Tamarind
*
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gaurav Naik |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Rajlaxxmi Park
Layout :
Google Map :
Nalla
Nalla
Nalla
1
2
3
4
5
Housing for affected People
Bldg No.2
Bldg No.3
Bldg No.5
Bldg No.3
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F198: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H268: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30
31
32
33
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0