## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 17/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-16
Name of the builder group |  |  |  | Sunteck Realty Limited
Name of the builder company |  |  |  | Sunteck Realty Limited
Name of the Project |  |  |  | Sunteck One World 2 to 10
Contact Details ( Name & Contact No.) |  |  |  | 7208939478
Site Meet Person Details ( Name & Contect No.) |  |  |  | Security |  |  |  | Mr. Dev 9657602983
Name / No of the Building |  |  |  | Tower 2 to 10
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P99000032855- Tower 2 P99000032834- Tower 3 & 4 P99000033099- Tower 5 & 6 P99000033218- Tower 7 & 8 P99000033157- Tower 9 & 10
Project location details |  | Sunteck One World 2 to 10, Survey No.2 H.No.3, S.No.3 H.No.1,7,10, ... , S.No.126 H.No.2,4,12, near Sunteck West World, Naigaon East Vasai Link Road, , Tivri, Naigaon East, Vasai, Palghar - 401208.
Survey No |  | 2 H.No.3, S.No.3 H.No.1,7,10, ... , S.No.126 H.No.2,4,12
Locality
Road |  | Naigaon East Vasai Link Road |  | Village |  | Tivri
City |  | Naigaon East |  | District |  | Palghar
Taluka |  | Vasai |  | Pin Code |  | 401208
Nearby Landmark |  | Sunteck West World |  | Distance from city centre: |  | 3.4KM from Naigaon Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Naigaon East Vasai Link Road
North | NA | NA |  |  | Main Road
South | NA | NA |  |  | Railway Track
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.3671268,72.8613243
Location Link |  | https://goo.gl/maps/AKyJowbHLcAZig728
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 373827.36
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.0018601
Total FSI availaible for the project |  |  |  | 1.1019
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 411905.45
Total number of Buildings |  |  |  | 9 Towers
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Vasai-Virar City Municipal Corporation
Layout Approval No |  | VVCMC/TP/AMEND/SPA/VP/006/058/2021-22 |  |  | Dated | 2021-12-31
Approved Floor plan No. |  | VVCMC/TP/AMEND/SPA/VP/006/058/2021-22 |  |  | Dated | 2021-12-31
Commencement-CC No Valid Up to: |  | VVCMC/TP/CC/SPA/VP-0006/059/2021-22 |  |  | Dated | 2021-12-31
Tower 2, 3, 4, 5, 6, 7 to 9 & 10 = G + 1st to 23rd Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 411905.45
Approved no of units |  |  | Flats - 1533, Shops - 84 | [5 empty] | 684
Approved no of Floors |  |  | Tower 2, 3, 4, 5, 6, 7 to 9 & 10 = G + 1st to 23rd Floor
Proposed no of Floors |  |  | Tower 2, 3, 4, 5, 9 & 10 = G + 1st to 23rd Floor
Tower 7 & 8 = G + 1st to 23rd Floor
Tower 6 = G + 1st to 23rd Floor
Expected Completion |  |  | As per RERA - 31/12/2025 (T-2,3,4) 31/12/2026 (T- 5, 6,7,8,9,10)
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower 2 = G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 18 Floor, Flooring upto 5 Floor, Painting upto 5 Floor Completed | , External Plaster upto 18 Floor, Flooring upto 5 Floor, Painting upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 18 Floor, Flooring upto 5 Floor, Painting upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 76.09% |  | 90% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 78.26% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 21.74% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 21.74% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Tower 3 & 4 = G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 10 Slab, Brickwork upto 9 Floor, Internal Plaster upto 6.75 Floor, External Plaster upto 6.3 Floor Completed | , RCC upto 10 Slab, Brickwork upto 9 Floor, Internal Plaster upto 6.75 Floor, External Plaster upto 6.3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 10 Slab, Brickwork upto 9 Floor, Internal Plaster upto 6.75 Floor, External Plaster upto 6.3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 34.54% |  | 62.29% |  | Excavation in process | 11.5 |  | as per architect letter plinth is given to Tower 2
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 10 | 41.67% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 9 | 39.13% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 6.75 | 29.35% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6.3 | 27.39% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Tower 5 = G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 10% |  | 45% |  | Excavation in process | 11.5 |  | as per architect letter plinth is given to Tower 2
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Tower 6 = G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 11.67% |  | 46.25% |  | Excavation in process | 11.5 |  | as per architect letter plinth is given to Tower 2
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 1 | 4.167% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Tower 7 = G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 18 Floor, Flooring upto 5 Floor, Painting upto 5 Floor Completed | , External Plaster upto 18 Floor, Flooring upto 5 Floor, Painting upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 18 Floor, Flooring upto 5 Floor, Painting upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 76.09% |  | 90% |  | Excavation in process | 11.5 |  | as per architect letter plinth is given to Tower 2
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 78.26% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 21.74% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 21.74% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Tower 8 = G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 14 Floor Completed | , RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 14 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 14 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 62.83% |  | 82.12% |  | Excavation in process | 11.5 |  | as per architect letter plinth is given to Tower 2
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 21 | 87.5% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 20 | 86.96% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 16 | 69.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 60.87% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Tower 9 = G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 10 Floor, Painting upto 10 Floor Completed | , Flooring upto 10 Floor, Painting upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 10 Floor, Painting upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 81.52% |  | 92.17% |  | Excavation in process | 11.5 |  | as per architect letter plinth is given to Tower 2
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 43.48% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 43.48% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Tower 10 = G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 10 Floor, Painting upto 10 Floor Completed | , Flooring upto 10 Floor, Painting upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 10 Floor, Painting upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 81.52% |  | 92.17% |  | Excavation in process | 11.5 |  | as per architect letter plinth is given to Tower 2
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 43.48% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 43.48% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6750 |  |  | 6200 to 6750 | igr | Sanjay | 2023-08-11
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 10000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges |  |  |  |  | 75000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | 60000
Society Formation & Other legal Charges |  |  |  |  | 10000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 5400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops | Tower 2 | 12 |  | 6046.6339 |  | 9674.6143
| Tower 3 | 16 |  | 8007.3396 |  | 12811.7434
| Tower 4 | 12 |  | 6046.6339 |  | 9674.6143
| Tower 5 | 16 |  | 8007.3396 |  | 12811.7434
| Tower 6 | 10 |  | 6277.7263 |  | 10044.362
| Tower 9 | 10 |  | 6245.1652 |  | 9992.2643
| Tower 10 | 8 |  | 4690.6283 |  | 7505.0052
Total |  | 84 |  | 45321.4668 |  | 72514.3469
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats | Tower 2 | 171 |  | 82280.2683 |  | 124012.9978 |  |  |  | 1185576.8426
| Tower 3 | 171 |  | 82280.2683 |  | 124200.9031 |  |  |  | 784527.416
| Tower 4 | 171 |  | 82280.2683 |  | 124012.9978
| Tower 5 | 171 |  | 82280.2683 |  | 124200.9031
| Tower 6 | 171 |  | 82280.2683 |  | 124200.9031
| Tower 7 | 179 |  | 86113.0441 |  | 129169.5662
| Tower 8 | 179 |  | 86113.0441 |  | 129169.5662
| Tower 9 | 145 |  | 70958.7394 |  | 107164.9886
| Tower 10 | 175 |  | 84619.78 |  | 126929.67 |  |  | 183
Total |  | 1533 |  | 739205.9492 |  | 1113062.4957 |  |  | 187
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
[5 empty] | 60% |  |  |  | 44.9355
Sector I
Tower 2
Ground Floor For Commercial & Parking | [8 empty] | 10.764
1 |  | Shop | 782.489 | 0 | 1251.9824 | Ground Floor For Commercial & Parking
2 |  | Shop | 389.7429 | 0 | 623.5887
3 |  | Shop | 488.804 | 0 | 782.0864
4 |  | Shop | 365.0288 | 0 | 584.046
5 |  | Shop | 673.7295 | 0 | 1077.9672
6 |  | Shop | 602.6441 | 0 | 964.2305
2nd Floor
1 |  | Shop | 702.2003 | 0 | 1123.5205 | 2nd Floor
2 |  | Shop | 301.7472 | 0 | 482.7955
3 |  | Shop | 390.7655 | 0 | 625.2248
4 |  | Shop | 255.4943 | 0 | 408.7909 | [5 empty] | 45.024
5 |  | Shop | 574.0656 | 0 | 918.505
6 |  | Shop | 519.9227 | 0 | 831.8764
Tower 3
Ground Floor For Commercial & Parking
1 |  | Shop | 639.9198 | 0 | 1023.8717 | Ground Floor For Commercial & Parking
2 |  | Shop | 599.2319 | 0 | 958.771
3 |  | Shop | 670.2743 | 0 | 1072.4388
4 |  | Shop | 386.7505 | 0 | 618.8008
5 |  | Shop | 487.3939 | 0 | 779.8303
6 |  | Shop | 361.5628 | 0 | 578.5004
7 |  | Shop | 670.2743 | 0 | 1072.4388
8 |  | Shop | 554.2384 | 0 | 886.7814
2nd Floor
1 |  | Shop | 533.3562 | 0 | 853.3699 | 2nd Floor
2 |  | Shop | 496.4357 | 0 | 794.2971
3 |  | Shop | 550.471 | 0 | 880.7535
4 |  | Shop | 301.7149 | 0 | 482.7439
5 |  | Shop | 389.3339 | 0 | 622.9342
6 |  | Shop | 273.6209 | 0 | 437.7934
7 |  | Shop | 550.5786 | 0 | 880.9258
8 |  | Shop | 542.1827 | 0 | 867.4923
Tower 4
Ground Floor For Commercial & Parking | [8 empty] | 10.764
1 |  | Shop | 782.489 | 0 | 1251.9824 | Ground Floor For Commercial & Parking
2 |  | Shop | 389.7429 | 0 | 623.5887
3 |  | Shop | 488.804 | 0 | 782.0864
4 |  | Shop | 365.0288 | 0 | 584.046
5 |  | Shop | 673.7295 | 0 | 1077.9672
6 |  | Shop | 602.6441 | 0 | 964.2305
2nd Floor
1 |  | Shop | 702.2003 | 0 | 1123.5205 | 2nd Floor
2 |  | Shop | 301.7472 | 0 | 482.7955
3 |  | Shop | 390.7655 | 0 | 625.2248
4 |  | Shop | 255.4943 | 0 | 408.7909
5 |  | Shop | 574.0656 | 0 | 918.505
6 |  | Shop | 519.9227 | 0 | 831.8764
Tower 5
Ground Floor For Commercial & Parking
1 |  | Shop | 639.9198 | 0 | 1023.8717 | Ground Floor For Commercial & Parking
2 |  | Shop | 599.2319 | 0 | 958.771
3 |  | Shop | 670.2743 | 0 | 1072.4388
4 |  | Shop | 386.7505 | 0 | 618.8008
5 |  | Shop | 487.3939 | 0 | 779.8303
6 |  | Shop | 361.5628 | 0 | 578.5004
7 |  | Shop | 670.2743 | 0 | 1072.4388
8 |  | Shop | 554.2384 | 0 | 886.7814
2nd Floor
1 |  | Shop | 533.3562 | 0 | 853.3699 | 2nd Floor
2 |  | Shop | 496.4357 | 0 | 794.2971
3 |  | Shop | 550.471 | 0 | 880.7535
4 |  | Shop | 301.7149 | 0 | 482.7439
5 |  | Shop | 389.3339 | 0 | 622.9342
6 |  | Shop | 273.6209 | 0 | 437.7934
7 |  | Shop | 550.5786 | 0 | 880.9258
8 |  | Shop | 542.1827 | 0 | 867.4923
Tower 6
1 |  | Shop | 775.008 | 0 | 1240.0128 | 1st Floor For Parking
2 |  | Shop | 389.7106 | 0 | 623.537
3 |  | Shop | 488.7932 | 0 | 782.0692
4 |  | Shop | 365.0503 | 0 | 584.0805
5 |  | Shop | 1293.7036 | 0 | 2069.9258
1st Floor For Parking
2nd Floor
1 |  | Shop | 702.2111 | 0 | 1123.5377 | 2nd Floor
2 |  | Shop | 301.7687 | 0 | 482.83
3 |  | Shop | 390.7547 | 0 | 625.2076
4 |  | Shop | 277.0438 | 0 | 443.2701
5 |  | Shop | 1293.6821 | 0 | 2069.8914
Tower 9
Ground Floor For Commercial, Parking, Entrance Lobby, Society Office, Drivers Room & Meter Room
1 |  | Shop | 1280.1625 | 0 | 2048.26 | Ground Floor For Commercial, Parking, Entrance Lobby, Society Office, Drivers Room & Meter Room
2 |  | Shop | 364.8996 | 0 | 583.8394
3 |  | Shop | 506.5538 | 0 | 810.4861
4 |  | Shop | 364.8996 | 0 | 583.8394
5 |  | Shop | 777.5914 | 0 | 1244.1462
6 |  | Shop | 818.7098 | 0 | 1309.9357
1st Floor
1 |  | Double Height Shop No.1 |  |  |  | 1st Floor
2 |  | Double Height Shop No.2
3 |  | Double Height Shop No.3
4 |  | Double Height Shop No.4
5 |  | Double Height Shop No.5
6 |  | Double Height Shop No.6
2nd Floor For Part Commercial
101 |  | Shop | 1290.9265 | 0 | 2065.4824 | 2nd Floor For Part Commercial
102 |  | Shop | 276.9577 | 0 | 443.1324
103 |  | Shop | 408.8167 | 0 | 654.1068
104 |  | Shop | 276.9577 | 0 | 443.1324
105 |  | Shop | 697.3996 | 0 | 1115.8393
106 |  | Shop | 639.3816 | 0 | 1023.0106
Tower 10
Ground Floor For Commercial, Parking, Entrance Lobby, Society Office, Drivers Room & Meter Room
7 |  | Shop | 589.7596 | 0 | 943.6153 | Ground Floor For Commercial, Parking, Entrance Lobby, Society Office, Drivers Room & Meter Room
8 |  | Shop | 602.784 | 0 | 964.4544
9 |  | Shop | 886.6307 | 0 | 1418.6091
10 |  | Shop | 389.7644 | 0 | 623.6231
11 |  | Shop | 487.3939 | 0 | 779.8303
12 |  | Shop | 365.0072 | 0 | 584.0116
13 |  | Shop | 673.6111 | 0 | 1077.7778
14 |  | Shop | 695.6773 | 0 | 1113.0837
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Sector - I
Tower 2
1st Floor For Residential & Parking
2 |  | 2 | 550.034 | 0 | 825.051 | 1st Floor For Residential & Parking |  |  | 45.1757
5 |  | 2 | 550.034 | 0 | 825.051
2nd Floor
2 |  | 2 | 550.034 | 0 | 825.051 | 2nd Floor
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
3rd Floor
1 |  | 2 | 550.034 | 869.7366 | 1042.4852 | 3rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399 |  |  |  | 5880.0478
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 812.7304 | 1028.2336
7 |  | 1 | 408.1599 | 257.9679 | 698.2292
8 |  | 1 | 408.1599 | 257.9679 | 698.2292
4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2 | 550.034 | 0 | 825.051 | 4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399 |  |  | 6043.3825
8 |  | 1 | 408.1599 | 0 | 612.2399
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2 | 550.034 | 0 | 825.051 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | Refuge Area
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
Tower 3
1st Floor For Residential & Parking
2 |  | 2 | 550.034 | 0 | 825.051 | 1st Floor For Residential & Parking
5 |  | 2 | 550.034 | 0 | 825.051
2nd Floor
2 |  | 2 | 550.034 | 0 | 825.051 | 2nd Floor
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
3rd Floor
1 |  | 2 | 550.034 | 898.3634 | 1049.6419 | 3rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 1522.3858 | 1205.6475
7 |  | 1 | 408.1599 | 350.6265 | 699.8966
8 |  | 1 | 408.1599 | 350.6265 | 699.8966
4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2 | 550.034 | 0 | 825.051 | 4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2 | 550.034 | 0 | 825.051 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | Refuge Area
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
Tower 4
1st Floor For Residential & Parking
2 |  | 2 | 550.034 | 0 | 825.051 | 1st Floor For Residential & Parking |  |  | 45.1757
5 |  | 2 | 550.034 | 0 | 825.051
2nd Floor
2 |  | 2 | 550.034 | 0 | 825.051 | 2nd Floor
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
3rd Floor
1 |  | 2 | 550.034 | 869.7366 | 1042.4852 | 3rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 812.7304 | 1028.2336
7 |  | 1 | 408.1599 | 257.9679 | 698.2292
8 |  | 1 | 408.1599 | 257.9679 | 698.2292
4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2 | 550.034 | 0 | 825.051 | 4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2 | 550.034 | 0 | 825.051 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | Refuge Area
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
Tower 5
1st Floor For Residential & Parking
2 |  | 2 | 550.034 | 0 | 825.051 | 1st Floor For Residential & Parking
5 |  | 2 | 550.034 | 0 | 825.051
2nd Floor
2 |  | 2 | 550.034 | 0 | 825.051 | 2nd Floor
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
3rd Floor
1 |  | 2 | 550.034 | 898.3634 | 1049.6419 | 3rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 1522.3858 | 1205.6475
7 |  | 1 | 408.1599 | 350.6265 | 699.8966
8 |  | 1 | 408.1599 | 350.6265 | 699.8966
4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2 | 550.034 | 0 | 825.051 | 4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2 | 550.034 | 0 | 825.051 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | Refuge Area
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
Tower 6
1st Floor For Residential & Parking
2 |  | 2 | 550.034 | 0 | 825.051 | 1st Floor For Residential & Parking
5 |  | 2 | 550.034 | 0 | 825.051
2nd Floor
2 |  | 2 | 550.034 | 0 | 825.051 | 2nd Floor
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
3rd Floor
1 |  | 2 | 550.034 | 898.3634 | 1049.6419 | 3rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 1522.3858 | 1205.6475
7 |  | 1 | 408.1599 | 350.6265 | 699.8966
8 |  | 1 | 408.1599 | 350.6265 | 699.8966
4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2 | 550.034 | 0 | 825.051 | 4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2 | 550.034 | 0 | 825.051 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | Refuge Area
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
Tower 7
Ground Floor For Parking & Society Office
1st Floor For Residential
1 |  | 2 | 550.034 | 0 | 825.051 | 1st Floor For Residential
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | Double Heighted Entrance Lobby
4
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2 | 550.034 | 0 | 825.051 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2 | 550.034 | 0 | 825.051 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | Refuge Area
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
Tower 8
Ground Floor For Parking & Society Office, Drivers Room
1st Floor For Residential
1 |  | 2 | 550.034 | 0 | 825.051 | 1st Floor For Residential
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | Double Heighted Entrance Lobby
4
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2 | 550.034 | 0 | 825.051 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2 | 550.034 | 0 | 825.051 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | Refuge Area
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
Tower 9
1st Floor For Residential
2 |  | 2 | 550.034 | 0 | 825.051 | 1st Floor For Residential
5 |  | 2 | 550.034 | 0 | 825.051
2nd Floor
2 |  | 2 | 550.034 | 0 | 825.051 | 2nd Floor
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
3rd Floor
1 |  | 2 | 550.034 | 1786.9855 | 1271.7974 | 3rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 773.8993 | 1018.5258
7 |  | 1 | 408.1599 | 346.6331 | 698.8982
8 |  | 1 | 408.1599 | 346.6331 | 698.8982
4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2 | 550.034 | 0 | 825.051 | 4th to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | 1 | 408.1599 | 0 | 612.2399
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2 | 550.034 | 0 | 825.051 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2 | 550.034 | 0 | 825.051
3 |  | Refuge Area
4 |  | 1 | 408.1599 | 0 | 612.2399
5 |  | 2 | 550.034 | 0 | 825.051
6 |  | 2 | 550.034 | 0 | 825.051
7 |  | 1 | 408.1599 | 0 | 612.2399
8 |  | 1 | 408.1599 | 0 | 612.2399
Tower 10
1st Floor
1 |  | Void |  |  |  | 1st Floor
2 |  | 2 | 552.4519 | 0 | 828.6778
3 |  | Double Heighted Entrance Lobby
4
5 |  | 2 | 552.4519 | 0 | 828.6778
6 |  | Void
7
8
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2 | 552.4519 | 0 | 828.6778 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2 | 552.4519 | 0 | 828.6778 |  |  |  | 175
3 |  | 1 | 410.5778 | 0 | 615.8667
4 |  | 1 | 410.5778 | 0 | 615.8667
5 |  | 2 | 552.4519 | 0 | 828.6778
6 |  | 2 | 552.4519 | 0 | 828.6778
7 |  | 1 | 410.5778 | 0 | 615.8667
8 |  | 1 | 410.5778 | 0 | 615.8667
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2 | 552.4519 | 0 | 828.6778 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2 | 552.4519 | 0 | 828.6778
3 |  | 1 | 410.5778 | 0 | 615.8667
4 |  | Refuge Area
5 |  | 2 | 552.4519 | 0 | 828.6778
6 |  | 2 | 552.4519 | 0 | 828.6778
7 |  | 1 | 410.5778 | 0 | 615.8667
8 |  | 1 | 410.5778 | 0 | 615.8667
Remarks:
* | Building No. 2 to 4 & 7 to 10 =Constrcution work is in process. Internal photo was not allowed. Building No. 5 & 6 = Work is same as last visit.09/10/2023
* | Details taken from Mr.Mahesh(sales) - 9920729702.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + D.B Area + F.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Tower 1 is Club house.
* | We have updated Approved plan & CC of Tower 9 on 04/01/2023.
* | We have updated Approved plan & CC of Tower 7 & 8 on 18/01/2023.
* | We have updated Approved plan & CC of Tower 10 on 27/03/2023
* | We have updated Approved plan & CC of Tower 6 (on 21/07/2023).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sunteck One World 2 to 10
Google Map :
Formulas:
Tivri = [Tivri, row above]
T - 2 & 3
T - 4 & 5
T - 6
T - 8
T - 9
T - 10
Tower 8
Tower 9
Tower 10
Bldg no.2
Bldg no.2
Bldg no.3
Bldg no.4
Bldg no.5
Bldg no.6

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted