## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2024-07-15 |  | 2024-07-23 | 2024-04-24
Project Name |  | Supremo Phase II, Wing C (Sakura) |  | Date & Time of Site Visit |  | 16/07/2025 at 10:21AM
Name of the person met at site & Contact No. |  | NA |  | Date of Report Release |  | 18/07/2025 |  | Mr. Riddhesh 9702723941
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | K V Buildhome LLP |  | Developer Name |  | K V Buildhome LLP
Developer Office Address |  | Shivangan society, Lokmanya Tilak Rd, Jaihind Colony, Tata Colony, Mulund East, Mumbai, Maharashtra 400081
Project Address | As per ARF | Shivangan society, Lokmanya Tilak Rd, Jaihind Colony, Tata Colony, Mulund East, Mumbai, Maharashtra 400081
| As per Legal Documents | Supremo Phase II, Wing C, CTS No.1289(Pt), 1290(Pt), 1292(Pt), 1294(Pt), 1295(Pt), 1296(Pt) & 1297(Pt), near Shubh Labh CHS, Tata Colony Road, Mulund, Mulund, Mulund East, Kurla, Mumbai - 400081.
| As per Actual at site | Supremo Phase II, Wing C, CTS No.1289(Pt), 1290(Pt), 1292(Pt), 1294(Pt), 1295(Pt), 1296(Pt) & 1297(Pt), near Shubh Labh CHS, Tata Colony Road, Mulund, Mulund, Mulund East, Kurla, Mumbai - 400081.
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, Fire NOC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai (MCGM)
RERA Registration No. | : | P51800052921 |  | RERA Registration Validity | : | 2030-12-31
Project Launch Date | : | 2023-10-05 |  | Construction Start Date | : | 2023-10-05
Proposed Date of Completion (As per RERA) | : | 2030-12-31 |  | Developer Bank Name (As per RERA) | : | ICICI BANK IFSC Code ICIC0000988
Project Type (Mixed, Residential, Comm.) | : | Residential |  | Plot Area (In Sq.Mt) | : | 25426.16
FSI/FAR Permissible | : | 1 |  | Net Plot Area (In Sq.Mt) | : | 15217.63
Permissible Built up Area (In Sq.Mt) | : | 36515.54 |  | Proposed Built up Area (In Sq.Mt) | : | 27047.19
Total Number of Units Approved | : | Flats = 154 & Shop = 18 |  | Total Number of Units Planned | : | As per RERA Site Flats = 98
Latitude, Longitude | : | 19.1636309,72.9587639 |  | Landmark | : | Shubh Labh CHS
Location Link | : | https://maps.app.goo.gl/XQr7kwPvoAM3KcaMA
Extra Amenities available | : | Terrace Garden, Banquet Hall, Sit Out Area, Jogging Track, Swimming Pool, Kids Play Area, Gym, Basketball Court, Yoga Area.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 9m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 74 M from Maratha Mandal Bus Stop
Distance from the nearest School (Km) | : | About 450M from VPMS English High School |  | Distance from Hospital (Km) | : | About 190 M form Galaxy Superspeciality Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.1 KM from Mulund Local Market. 2. Approx. 2 KM from Ratna Super Market. |  | Distance from Railway Station (Km) | : | 1 KM from Mulund Railway Station 3.1 KM from Nahur Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East | West
East |  | Plot C |  |  | Other Plot
West |  | 27.45 M W Road |  |  | VB Phadake Road
North |  | 13.40 M W Road |  |  | Road
South |  | 18.30 M W Road |  |  | Tata Colony Road
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing C |  | Sale | 1B + G + P1 to P7 + S + 1st to 41st Floor |  |  | 1B + G + P1 to P7 + S + 1st to 20th Floor
Tower 2 |  | Sale
Tower 3 |  | Sale
Tower 4 |  | Sale
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | CHE/ES/2027/T/337(New) |  |  |  | Date: | 2024-01-12
Approved Plan Details | : | CHE/ES/2027/T/337(New) |  |  |  | Date: | 2024-01-12
CC Details Valid Up to: |  | CHE/ES/2027/T/337(NEW)/FCC/1/Amend |  |  |  | Date: | 2024-03-04
|  | Further CC is granted for Wing C upto 20th upper floor and Wing D upto 23rd upper floors as per approved amended plan dated 12.01.2024''excluding 24th to 35th upper floors or wing D (restricted for non-handing over of D.P. Roads & availing instalment facility) CC for podium is proposed within building line only for both wings i.e. wing ‘C’ and ‘D’, subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  |  | Valid Upto Date | 2024-03-19
Environmental Clearance Details | : |  |  |  |  | Date:
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
CC Details Valid Up to: |  | CHE/ES/2027/T/337(NEW)/FCC/3/Amend |  |  |  | Date: | 2025-02-24
|  | Further CC for Wing C upto 36th upper floors and Wing D upto 41st upper floors is granted as per approved amended plan dated 05.02.2025, by restricting shopping and 37th to 41st upper floors of wing C for non-handing over of D.P. Roads & availing instalment facility subject to timely renewal of B.G., SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction along with precautionary measures for air pollution. |  |  |  | Valid Upto Date | 2025-03-19
Fire Noc Details: Valid Up to : |  | CHE/ES/2027/T/337(NEW)-CFO/1/NEW |  |  |  | Date: | 2022-11-15
Building no.1 comprising of five Wings (i.e. Wing ‘A’,Wing ‘B’, Wing ‘C’, Wing ’D’ & Wing ‘E’), having part basement + Ground floor + 1st & 3rd podium + 4th to 6th floors + 7th podium floor + service floor + 1st to 41st floors for residential (total height of the building is 158.075 mtrs.)
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Wing C= 1B + G + P1 to P7 + S + 1st to 41st Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 36 Slab, Brickwork upto 27 Floor, Internal Plaster upto 20.25 Floor, External Plaster upto 20.25 Floor Completed
|  |  | 1 | 2 |  | 7 | 41 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.25
Excavation |  | 41 | 100% | 58.76% |  | Excavation work Completed. Plinth work completed, RCC upto 36 Slab, Brickwork upto 27 Floor, Internal Plaster upto 20.25 Floor, External Plaster upto 20.25 Floor Completed |  | Excavation in process | 20.5
Plinth |  | 41 | 100% |  |  |  |  | Excavation Completed | 41
RCC (Including podiums) |  | 36 | 72% |  |  |  |  | Footing in Process | 8.2
Brickwork |  | 27 | 65.85% |  |  |  |  | Footing Completed | 16.4
Internal Plaster |  | 20.25 | 49.39% |  |  |  |  | Basement 1 | 0
External Plaster |  | 20.25 | 49.39% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 26.65
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 41
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Tower 2= . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 2 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 1
Plinth |  | 2 | 100% |  |  |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.4
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 0.8
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 1.4
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 2
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Tower 3= . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 3 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 1.5
Plinth |  | 3 | 100% |  |  |  |  | Excavation Completed | 3
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 1.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 2.1
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 3
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 58.76%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 21000 to 22000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 700000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 6272.7611
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 12386.6592
Distress Value (Rs. Per sqft) |  |  |  |  | : | 5018.2088
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Shops |  | - |  | 18 |  | 3187.1213
Total |  | - |  | 18 |  | 3187.1213
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Flats |  | - |  | 154 |  | 78429.6121
Total |  | - |  | 154 |  | 78429.6121 | 0
Grand Total |  | - |  | 172 |  | 81616.7334
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Wing C
Basement For Domestic Tank, Fire Tank, Raw Water Tank & Pump Room
Ground Floor For Commercials, Meter Room & Parking | [8 empty] | 10.764
12 |  | - | Shop | 167.9991 | 0 | 0 | 167.9991
13 |  | - | Shop | 165.4007 | 0 | 0 | 165.4007
14 |  | - | Shop | 167.3039 | 0 | 0 | 167.3039
15 |  | - | Shop | 181.4366 | 0 | 0 | 181.4366
16 |  | - | Shop | 185.5531 | 0 | 0 | 185.5531
17 |  | - | Shop | 194.6804 | 0 | 0 | 194.6804
1st Podium Floor For Commercials & Parking
17 |  | - | Shop | 167.9991 | 0 | 0 | 167.9991
18 |  | - | Shop | 165.4007 | 0 | 0 | 165.4007
19 |  | - | Shop | 167.3039 | 0 | 0 | 167.3039
20 |  | - | Shop | 181.4366 | 0 | 0 | 181.4366
21 |  | - | Shop | 185.5531 | 0 | 0 | 185.5531
22 |  | - | Shop | 194.6804 | 0 | 0 | 194.6804
2nd Podium Floor For Parking
3rd Podium Floor For Commercials & Parking
17 |  | - | Shop | 167.9991 | 0 | 0 | 167.9991
18 |  | - | Shop | 165.4007 | 0 | 0 | 165.4007
19 |  | - | Shop | 167.3039 | 0 | 0 | 167.3039
20 |  | - | Shop | 181.4366 | 0 | 0 | 181.4366
21 |  | - | Shop | 185.5531 | 0 | 0 | 185.5531
22 |  | - | Shop | 194.6804 | 0 | 0 | 194.6804
4th to 6th Podium Floor For Commercials & Parking
7th Podium Floor For Amenities & Parking
8th Floor For Service Area
1st, 8th & 15th Floor For Residential Floor (Part Refuge Area)
101,..,1501 |  | - | 1BHK | 405.9293 | 47.4692 | 0 | 453.3985 | [5 empty] | 101,..,1501 | 101 | 1501
102,..,1502 |  | - | 1BHK | 400.7114 | 47.4692 | 0 | 448.1807 | [5 empty] | 102,..,1502 | 102 | 1502
103,..,1503 |  | - | 2BHK | 558.9099 | 48.438 | 0 | 607.3479 | [5 empty] | 103,..,1503 | 103 | 1503
104,..,1504 |  | - | 1BHK | 405.9293 | 47.4692 | 0 | 453.3985 | [5 empty] | 104,..,1504 | 104 | 1504
105,..,1505 |  | - | 1BHK | 405.9293 | 47.4692 | 0 | 453.3985 | [5 empty] | 105,..,1505 | 105 | 1505
106,..,1506 |  | - | 2BHK | 557.1662 | 48.438 | 0 | 605.6042 | [5 empty] | 106,..,1506 | 106 | 1506
107,..,1507 |  | - | Refuge Area | [9 empty] | 107,..,1507 | 107 | 1507
108,..,1508 |  | - | [10 empty] | 108,..,1508 | 108 | 1508
2nd to 7th, 9th to 14th & 16th to 20th Floor For Residential Floor
201,..,2001 |  | - | 1BHK | 405.9293 | 47.4692 | 0 | 453.3985 | [5 empty] | 201,..,2001 | 201 | 2001
202,..,2002 |  | - | 1BHK | 400.7114 | 47.4692 | 0 | 448.1807 | [5 empty] | 202,..,2002 | 202 | 2002
203,..,2003 |  | - | 2BHK | 558.9099 | 48.438 | 0 | 607.3479 | [5 empty] | 203,..,2003 | 203 | 2003
204,..,2004 |  | - | 1BHK | 405.9293 | 47.4692 | 0 | 453.3985 | [5 empty] | 204,..,2004 | 204 | 2004
205,..,2005 |  | - | 1BHK | 405.9293 | 47.4692 | 0 | 453.3985 | [5 empty] | 205,..,2005 | 205 | 2005
206,..,2006 |  | - | 2BHK | 557.1662 | 48.438 | 0 | 605.6042 | [5 empty] | 206,..,2006 | 206 | 2006
207,..,2007 |  | - | 2BHK | 557.1662 | 48.438 | 0 | 605.6042 | [5 empty] | 207,..,2007 | 207 | 2007
208,..,2008 |  | - | 1BHK | 405.9293 | 47.4692 | 0 | 453.3985 | [5 empty] | 208,..,2008 | 208 | 2008
5th to 6th Floor For Commercials & Parking
1 |  |  |  | 0 | 0 | 0 | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [5 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [5 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [5 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [5 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [5 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [5 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [5 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [5 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [5 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [5 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [5 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [5 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [5 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [5 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [5 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [5 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [5 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [5 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [5 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [5 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [5 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit. (Internal Visit not allowed).
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We have updated revised CC (On 18/07/2025).
* | Validity of CC is expired on 19/03/2025. Please provide Revised CC & revised approved plans.
* | Remark for Environment Clearance Certificate.
Site & Building/Tower Photographs
Name of the Project |  |  | Supremo Phase II, Wing C (Sakura)
Project Site Address |  |  | Shivangan society, Lokmanya Tilak Rd, Jaihind Colony, Tata Colony, Mulund East, Mumbai, Maharashtra 400081
Site Visit Date & Time |  |  | 16/07/2025 at 10:21AM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Nainesh Tambe |  | Authorized Signatory Name & Signature
Wing C
Wing C
Wing C
Wing C
Wing C
Wing C
Note on C9: SACHIN: As per initiation Mail
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G118: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%