## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-07-16
Branch Name/ID |  | Mahindra Rural Housing Finance - Thane |  |  | Date & Time of Site Visit | 22/07/2025 at 12:25PM
Name of the person met at site & Contact No |  | Mr Yogesh (Site Engineer) 9702554612 |  |  | Date of Report Release | 28/07/2025
Project Details
Name of the project |  | Neovalley Kaveri Wing A
Address |  | Neovalley Kaveri Wing A, CTS No.15 (PT), near Saidarshan CHS, Sai Hill Road, Kanjur, Bhandup (W), Kurla, Mumbai - 400078. | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune
CTS No |  | 15 (PT) | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Kanjur | [12 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Sai Hill Road | [12 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Bhandup (W) | [12 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Kurla | [12 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Mumbai | [12 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 400078 | [12 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P51800026955 | [15 empty] | Mahad | Daund
Landmark |  | Saidarshan CHS | [15 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.150492,72.926400 | [12 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/e69WyNzTdNdd8kUh7 | [15 empty] | Poladpur | Purandhar
Name of the builder / developer |  | M/s Nexzone Fiscal Services Pvt Ltd | [15 empty] | Mahasala | Bhor
Office address (agreement) |  | 702, 7th Floor, Marathon Max, Mulund Goregaon link Road, near Bhandup Sonapur Signal, Mulund West, Kurla, Mumbai 400080 | [15 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [15 empty] | Murud | Velhe
Builder Bank Details |  | HDFC BANK IFSC Code - HDFC0000652
Contact No. |  | Mr. Amol Ghorpade 9320090407 |  |  | Mr. Amol Ghorpade 9320090407
Location of the project Municipal Limit : |  | Slum Rehabilitation Authority (SRA)
Project Type (Apartments/Plot/ Combined) |  | Apartments
No of Wings / Buildings |  | 01 Building |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | Flats = 22, M.P Room = 247 |  |  | Exposure Limit (Proposed) | 40.35
Approved No. of Floor |  | Building 02 (Sale) Wing A = Stilt + 1st to 22nd Floor
Proposed No. of Floor |  | Building 02 (Sale) Wing A = Stilt + 1st to 22nd Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | 6.00M. W Existing Road/ 9.15 M.W. Road (Sanctioned) | Adj CTS No. 21/Adj CTS No. 15 | CTS 14 (PT) | CTS No. 11
|  | Physical on site |  | Sai Hill Road | Slum | Slum | Slum
Verification of survey No. (Title document) |  | Survey No. 124(part), Present Survey No. 124/5, CTS No. 15(Part)
Plot area mentioned in the sale deed (As per 7/12) |  | 4072 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 3861.28
Approach road |  | Yes, Approx 19ft
Connectivity |  | 1. 0.085km from Shree Saraswati Vidya Mandir 2. 0.65km from Bright Angels English School 3. 0.55km from Sudhanshu Multi Speciality Hospital & ICCU 4. 0.85km from Bhandup Criti Care Hospital 5. 0.45km from Geeta Super Market 6. 3.5km from DMart 7. 0.9km from Vihar Lake 8. 0.28km from Shrimant Icchapurti Maha Ganpati Devasthan 9. 0.75km from Sarvodaya Nagar (Bhandup West) Bus stop 10. 2.2km from Bhandup Railway Station | [5 empty] | 69.5
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 3861.28 |  | 3.163
|  | Permissible FSI |  |  |  | 3.16
|  | Permissible TDR/Paid FSI |  |  |  | 0.0030159
|  | Total FSI availaible for the project |  |  |  | 3.163
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 12213.29
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 12213.29
Building plan approvals - Approval No : |  | S/PVT/0118/20140630/AP/S |  |  |  | Date | 2025-02-10
Building height / No. of Floors |  | Building 2 Kaveri Wing A = Stilt + 1st to 22nd Floor (Height = 74.90m upto OHT)
Construction/Building Permission Valid Upto |  | S/PVT/0118/20140630/AP/S This CC is re-endorsed and Further extended to Sale Wing 'A' from Stilt + 1st to 17th upper floors with brick-work & plasterand 18th to 21st upper floors for R.C.C. framed structure as per appreved amended IOA dtd. 10/02/2025. |  |  |  | Date | 2025-03-17
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA |  | Date | NA |  | ``
|  | Validity & Area mentioned: |  | NA |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions
Fire Noc No Valid Up to: |  | FB/NR/RVI/214 Building No. 2 Wing A = Stilt + 1st to 22nd Floors (Height = 69.95m) Building No. 2 Wing B = B (Pt) + Stilt + 1st to 22nd Floor (Height = 69.95m) Building No. 2 Wing C = G + 1st to 2nd Floor (Height = 11.70m) |  |  |  | Date | 2022-03-31
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/MIS/267933/2022 |  |  |  | Date | 2022-08-07
CTS No = 15 (Pt) Net Plot Area = 3861.28 Sq.mt TBUA = 31537.39 Sq.mt Sale Building No. 2 (Wing A & B) = Stilt + 1st to 22nd upper Floors
Airport Noc No Valid Up for: | [5 empty] | Date
Valid upto Dated
Site Elevation (AMSL) = Permissible Top Elevation (AMSL) =
CONSTRUCTION PROGRESS
Baseline start date |  | 2020-11-07 |  | Baseline finish date |  | 2027-06-30 |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 3 Floor Completed
Construction details:
Sale Building No. 2 Wing A = Stilt + 1st + 22nd Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 22 | Piling Work in process | 5.5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 3 Floor Completed | [5 empty] | Excavation in process | 11
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 22
Excavation |  | 0% |  | 22 | 100% | 20.74% |  | Footing in Process | 5.5
Plinth |  | 10% |  | 22 | 100% |  |  | Footing Completed | 11
RCC (Including podiums) |  | 40% |  | 5 | 21.74% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 3 | 13.64% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 16.5
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 22
Building Common Amenities |  | 5% |  | 0 | 0%
Possession |  | 5% |  | 0 | 0%
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | No
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A
Total |  | 0 |  | 0 |  | 0
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | MP Room | 247 |  | 49310.5298 |  | 73965.7948
| Flat | 22 |  | 7104.24 |  | 10656.36
Wing B
Total |  | 269 |  | 56414.7698 |  | 84622.1548
Grand Total |  | 269 |  | 56414.7698 |  | 84622.1548
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Building No.1
Ground Floor
1 |  | Shop |  |  | 0 | 0 | 0
2 |  | Shop |  |  | 0 | 0 | 0
3 |  | Shop |  |  | 0 | 0 | 0
4 |  | Shop |  |  | 0 | 0 | 0
5 |  | Shop |  |  | 0 | 0 | 0
6 |  | Shop |  |  | 0 | 0 | 0
7 |  | Shop |  |  | 0 | 0 | 0
8 |  | Shop |  |  | 0 | 0 | 0
9 |  | Shop |  |  | 0 | 0 | 0
10 |  | Shop |  |  | 0 | 0 | 0
11 |  | Shop |  |  | 0 | 0 | 0
12 |  | Shop |  |  | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | RERA Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading: | 10.764
50%
Building No.2 Kaveri (Wing A)
Ground Floor For Entrance Lobby, Meter Room & Parking
1st Floor For Residential & Fitness Center | [7 empty] | 1
1 |  | Partially Use For School (Wing C)
2
3 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
4 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
5 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
6 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
7 |  | Fitnesss Center
8
9 |  | Void
10
11
12
13 |  | Partially Use For School (Wing C)
14
2nd & 3rd Floor | [7 empty] | 2
1 |  | Partially Use For School (Wing C)
2
3 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
4 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
5 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
6 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
7 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
8 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
9 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
10 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
11 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
12 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
13 |  | Partially Use For School (Wing C)
14
4th Floor | [7 empty] | 1
1 |  | Terrace Area For School (Wing C)
2
3 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
4 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
5 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
6 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
7 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
8 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
9 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
10 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
11 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
12 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
13 |  | Terrace Area For School (Wing C)
14
5th to 6th Floor | [7 empty] | 2
1 |  | Terrace Area Below For School (Wing C)
2
3 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482 | 16.3375
4 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
5 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
6 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 | 28.375
7 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
8 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
9 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
10 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
11 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
12 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
13 |  | Terrace Area Below For School (Wing C)
14
7th & 14th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | Refuge Area
2
3
4
5 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
6 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
7 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
8 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
9 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
10 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
11 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
12 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
13 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
14 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
8th to 13th, 15th to 20th Floor | [7 empty] | 12
1 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
2 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349 |  |  |  | 3702000 | 10412.4793
3 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
4 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
5 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
6 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 |  |  |  | 5150000 | 10632.1483
7 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
8 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
9 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
10 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616 |  |  |  | 3383000 | 10690.0806
11 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
12 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
13 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
14 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
21st Floor (Part Refuge Area) | [7 empty] | 1
1 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
2 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
3 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
4 |  | Refuge Area
5 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616 | [5 empty] | 12481.7671
6 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38 | [5 empty] | 16412.7338 | 15463.0662
7 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065 | [5 empty] | 16052.6664
8 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349 | [5 empty] | 11110.0198
9 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482 | [5 empty] | 14390.7433
10 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616 | [5 empty] | 12481.7671
11 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616 | [5 empty] | 12481.7671
12 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482 | [5 empty] | 14390.7433
13 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349 | [5 empty] | 11110.0198
14 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
22nd Floor | [7 empty] | 1
1 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
2 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
3 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
4 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
5 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
6 |  | 1BHK | 322.92 | 0 | 322.92 | 0 | 484.38
7 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
8 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
9 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
10 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
11 |  | MP Room | 210.9744 | 0 | 210.9744 | 0 | 316.4616
12 |  | MP Room | 182.988 | 0 | 182.988 | 0 | 274.482
13 |  | MP Room | 237.0233 | 0 | 237.0233 | 0 | 355.5349
14 |  | MP Room | 164.0434 | 0 | 164.0434 | 0 | 246.065
1st Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 12000 |  |  | 12900 Axis | YesB 11500 | IndexTAP | 10500-11000
Recommended of Parking ( If Available) |  |  |  |  | 5,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit. Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received. Work not yet Started.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr Yogesh (Site Engineer) 9702554612
11 | As per the approved plans dated 10/02/2025, Wing A Flat Nos. 1, 2, 13 & 14 are partially used for School area from Gr + 1st to 6th Floor. And School area is mentioned in approved plans as Wing C.
Photographs Of Property : |  | Neovalley Kaveri Wing A
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Nainesh Tambe |  | Authorized Signatory Name & Seal of the agency
Wing A
Wing B
Wing C (School)
N
Wing A
Wing B
Wing C
N
Wing A
Wing B
Rehab bldg
Marathon
NeoValley
Kaveri
Wing A
Wing A
Wing A
Wing B
Wing B
Wing B
Wing A
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C60: RERA Start date
Note on H78: if multiple buildings are in project and are connected internally
Note on C80: AAC Block or Brick
Note on H82: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3