## Sheet1
PROJECT TECHNICAL REPORT
Project Name | Runwal Pinnacle |  |  | RBL BRANCH NAME | Airoli
Valuer Details
Name Of Valuation Agency/Firm |  | V.S Jadon & Co.Valuers LLP
Name Of Valuer |  | Mr. Vishwajeet Singh Jadon
Official Email Id |  | vsjc.apf@gmail.com
Contact Person Name & Number |  | Mr. Sachin Sawant - 9820058999
Rvo Name Of Which Valuer Is Member
Address Of Valution Agency |  | Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80
Apf Technical Report Assignment Details
Date of Assignment | 2025-07-17 | Assigned By | Mr. Abhishek Manjrekar | Documents received on: | 2024-01-11
Date of Visit | 2025-07-17 | Property Visited By (Name) |  | Nainesh Tambe
Date of Valuation | 17/07/2025 | Report Prepared By (Name) |  | Shruti Tathare
Builder Company/Entity Details - Seller Of The Project
Name Of Entity Formed For Current Project |  | Runwal Apartments Private Limited
Project Address Details
Project Name | Runwal Pinnacle (Tower 1 to 5)
Project Location details | Runwal Pinnacle, CTS No..681/A/7, 681/A/8 & 681/A/9, near Runwal Greens, Mulund Goregoan Link Road, Nahur, Runwal Greens Complex, Mulund West, Kurla, Mumbai - 400078.
CTS No. | 681/A/7, 681/A/8 & 681/A/9 |  | Locality | Runwal Greens Complex
Street Name &/No. | Mulund Goregoan Link Road |  | City | Mulund West
Village | Nahur |  | Landmark | Runwal Greens
Taluka | Kurla |  | District | Mumbai
State | Maharashtra |  | Country | India
Pincode | 400078 |  | Lat, Long | 19.160517,72.942787
Location Link | https://maps.app.goo.gl/981LTuJqMJhswP7B9
Nearest Rbl Bank Location | RBL Bank Ltd - Mulund Link Road Branch Shop no. 10, Marathon Max, Mulund - Goregaon Link Rd |  | Distance From Rbl Bank Location (Kms.) | 850m
Project Boundaries Verification
|  | North | South | East | West
As Per Ownership Docs |  | CTS No. 681A/5 | CTS No. 765, 766, 767, 768 | CTS No. 681A/7, 681A/8 | CTS No. 681A/8B
As Per Layout Plan |  | Mulund Goregaon Link Road | Other Plot | Other Plot | Other Plot/ 18.30 M. Wide Road
As Per Site Investigation |  | Fortis Hospital | Open Plot/Building | Runwal Greens | Open Plot/Building
General Details
Municipal Limit |  | Municipal Corporation Of Greater Mumbai (MCGM) |  |  |  | Same
Municipal Authority (Name) |  | Municipal Corporation Of Greater Mumbai (MCGM)
Approach Road To Project |  | Mulund Goregoan Link Road
Location Type* |  | Developed
Quality Of Construction* |  | Good
Overall % Completion Of Project |  | 55.49%
Project Falling In Caution Area |  | No
Reason For Caution |  | No
Project Architect Name |  | Aakar Architects & Consultants
Project Area Details ( As Per Approved Plan )
Area Type |  | Square Meter
Total Plot Area |  | 82054.2
Net Plot Area |  | 63288.9
Total Built Up Area |  | 262107.08
Residential Built Up Area For Tower 1 to 5 |  | 60691.44
Total Commercial Built Up Area |  | -
Area Under Road Set Back |  | 2517.3
Area Under D.P. Road |  | 5692
Area Handover to Hospital Reservation |  | 3283.72
Area Under Amenity/Open Space |  | 10556
Area Under R.G./Garden |  | 16543.61
FSI / FAR Details
Plot FSI / FAR |  | 1
Premium FSI / FAR |  | 0.5
TDR FSI |  | 0.78798
Fungible FSI |  | 1.0416
Incentive FSI |  | 0.68701
Addl .FSI Under Road Setback/land Handover |  | 0.12971
Addl .FSI Under any Other Regulation(2)
Total FSI/FAR |  | 4.1463 |  |  |  | 4.1414
Overall Remarks on Project Area & FSI /FAR
Total No. Of Units/Tenaments |  | Flats = 810
Total No. Of Parking |  | Cars = 917
Residential /Commercial Ratio |  | 100 : 00
Surrounding External Amenities
| Nearestr Bus Stop | Nearest Bank | Nearest School/ College | Nearest Hospital | Nearest Multiplex / Mall/ Market
Name Of The Premises/Description | Fortis Hospital | ICICI Bank Nahur | Holy Angels Marthoma School | Fortis Hospital | Dmart
Approx. Distance From Property (In Kms) | 230m | 550m | 400m | 190m | 650m
Internal Project Specs - Comment On Availability & Quality
| Structural Elements & Wall Thickness | Plaster & Painting | Electrification | Plumbing & Bath Fittings | Door, Windows
Availability (Y/N) | Yes & 0.15m | Yes | Yes | Yes | Yes
| Potable Water Connection | Sewerage System | Lift | Power Backup | Parking
Availability (Y/N) | Yes | Yes | Yes | Yes | Yes
QUALITY, SPECS
| Clubhouse | Gym | Swimming Pool | Garden | Community Hall
Availability (Y/N) | No | No | No | No | No
QUALITY, SPECS
Any Additional Amenities, To Above, Pls Specify | Swimming Pool, Spa, Jacuzzi, Sports, Kid's Play Area, Gaming Zone, Party Hall, Mini Theatre, Billiards/Pool Room, Table Tennis, Library, Sky Lounge, Stargazing Deck, Jogging Track, Sky Gym, etc.
Technical Documents Details
Approving Authority Name | Municipal Corporation Of Greater Mumbai (MCGM)
Document Name | Applicability & Availability | Approving Authority | Details Of Approval
Approved Layout Plan | Applicable and Received | MCGM | CHE/ES/4261/S/337NEW Date : 18/09/2023
Approved Floor Plan | Applicable and Received | MCGM | CHE/ES/4261/S/337NEW Date : 18/09/2023
Construction / Building Permission / Commencement Certificate | Applicable and Received | MCGM | CHE/ES/4261/S/337(NEW)/FCC/3/Amend Date : 11/01/2024
Valid Upto: Further C.C. is granted for tower 03 and 04 upto 48th upper floors and C.C. is re-endorsed for tower 01,02 and 05 as per amended approved plan dated 05.03.2024 subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. Valid Upto date : 10/06/2025
Construction / Building Permission / Commencement Certificate | Applicable and Received | MCGM | CHE/ES/4261/S/337(NEW)/FCC/4/Amend Date : 19/06/2024
Valid Upto: Further C.C. is granted for Tower 1, 2 & 5 upto 37th floor as per approved amended plans dated 05/03/2024 by restricting C.C. from 38th to 40th floor for Tower 1, 2 & 5 for instalment facility subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. Valid Upto date : 12/06/2026
Non Agricultural Permission / Land Conversion / Diversion | Not Applicable | NA | NA
Building Completion / Occupation Permission / Use Permission | Not Applicable | NA | NA
Location Sketch/ Certificate | Not Applicable | NA | NA
Authority Allotment Letter | Not Applicable | NA | NA
Fire Noc & Plans | Applicable and Received | MCGM Fire Brigade | CHE/ES/4261/S/337(NEW)-CFO Date : 02/06/2019 Valid For : Building No. 2 (Tower 1 to 5) Basement (Total depth 14.70mtrs.) + Ground floor + 1st to 9th podium floors + Club house level-1 & 2 + 1st to 53rd upper residential floors (Height 210.95mtrs)
Environmental Clearance | Applicable and Not Received | SEIAA | SEIAA-EC-0000001541 Date : 28/05/2019 Valid For : Net Plot Area = 60005.18 Sqm, Total Builtup Area = 686525.30
Coastal Regulatory Zonex ( Crz ) Noc | Not Applicable | NA | NA
Ownership Doc 1 | Applicable and Received | NA | Verified By Wadia Ghandy & Co.
Ownership Doc 2
Remarks On Documents Verified
Rera Details ( If Applicable)
Rera Applicable | Yes | If Applicable, Rera Registration Status | Registered | Rera Registration No | P51800021322
Project Start Date As Per Rera | 2019-06-21 |  | Project Completion Date As Per Rera | 2027-06-30
If Any Litigation Record On Project As Per Rera | Yes |  | Litigation Details As Per Rera Website | Court Name = City Civil Court Bombay Case No. = LC Suit No.10052/2023 Case Type = Civil, Year = 2013 Status = Pending
Critical Parameters
Seismic Zone | Zone III |  | Flood Prone Area | No
Zoning As Per Development Plan | Yes |  | Coastal Regulatory Zone | Not Appicable
Falling In Reservation As Per Development Plan | No |  | Falling In Present Or Proposed Road Widening | No
Property Within 30 Mtrs From Railway Boundary ? | No |  | Property Near High/Low Tension (Ht)/(Lt) Lines ? | No
Fsi Deviation | No |  | Presence Of Nallah/ Lake / Water Body Nearby | No
Vertical Deviation | No |  | Unit Deviation | No
Habitation In ( % ) Within 1 Kms Around Project |  | Yes
Remarks In Case Project Affected By Any Of Critical Parameter |  | No
Technical Deviations Observed In Project
Detail Of Deviation, If Any |  |  |  | Demolition Risk
NA |  |  |  | No
Total Phases | Total No. Of Buildings | Total No. Of Wings | Total No. Of Approved Units (A) | Total No. Of Unapproved Units (B) | Total No. Of (A+B) Units
1 | 5 | 0 | Flats = 810 | - | 810
Approved no of Floors |  | Building No. 2 (Tower 1, 2 & 5 ) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 39th Floor Building No. 2 (Tower 3 & 4 ) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 40th Floor | [6 empty] | 3
Proposed no of Floors |  | Building No. 2 (Tower 1, 2 & 5 ) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 53rd Floor
Building No. 2 (Tower 3 & 4 ) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 53rd Floor
Building No. 2 (Tower 1 to 5 ) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 40th Floor
Is The Project Technically Acceptable ? |  | Yes
Is The Project Marketable ? |  | Yes
Comment On Builder Group Involved In Project Development |  | Runwal Bliss, Runwal Forest, Runwal Greens, Runwal Orchid, Runwal Heights, etc.
Overall Comments On Project Acceptability & Marketablity |  | Project Name is approved by MCGM. Surrounded by Runwal Greens, Atmosphere By Wadhava Group, Ashford Royale. Hospital, School, Dmart, Local Market are within 1.00km from project.
Construction details:
Building No. 2 (Tower 1) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 53rd Floor |  | Basement | Ground | Podium | Floors | Plinth work completed, RCC upto 19 Slab, Brickwork upto 7 Floor, Internal Plaster upto 5 Floor Completed
|  | 5 | 1 | 11 | 53 | [5 empty] | YET TO START
Stage of construction: | Plinth work completed, RCC upto 19 Slab, Brickwork upto 7 Floor, Internal Plaster upto 5 Floor Completed |  |  |  |  | All work Completed. OC Received. |  |  |  |  | FOUNDATION WIP
Type of Work | Project Progress % | Slab/Floor | Complition % | Completion % | [6 empty] | PLINTH WIP
Plinth | 35% | 53 | 100% | 46.36%
RCC (Including podiums) | 35% | 19 | 29.23% |  |  | Excavation in Process | 7.5714
Brickwork | 5% | 7 | 13.21% |  |  | Foundation in Process | 7.5714
Plaster | 5% | 5 | 9.434% |  |  | Basement 1 | 15.1429
Flooring & Fitting | 5% | 0 | 0% |  |  | Basement 2 | 22.7143
Electrical & Plumbing | 5% | 0 | 0% |  |  | Basement 3 | 30.2857
Painting & Wooden | 5% | 0 | 0% |  |  | Basement 4 | 37.8571
Finishing | 2.5% | 0 | 0% |  |  | Plinth in process | 0
Possession | 2.5% | 0 | 0% |  |  | Plinth completed | 53
Building No. 2 (Tower 2) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 53rd Floor |  | Basement | Ground | Podium | Floors | Plinth work completed, RCC upto 18 Slab, Brickwork upto 6 Floor, Internal Plaster upto 5 Floor Completed
|  | 5 | 1 | 11 | 53 | [5 empty] | YET TO START
Stage of construction: | Plinth work completed, RCC upto 18 Slab, Brickwork upto 6 Floor, Internal Plaster upto 5 Floor Completed |  |  |  |  | All work Completed. OC Received. |  |  |  |  | FOUNDATION WIP
Type of Work | Project Progress % | Slab/Floor | Complition % | Completion % | [6 empty] | PLINTH WIP
Plinth | 35% | 53 | 100% | 45.73%
RCC (Including podiums) | 35% | 18 | 27.69% |  |  | Excavation in Process | 7.5714
Brickwork | 5% | 6 | 11.32% |  |  | Foundation in Process | 7.5714
Plaster | 5% | 5 | 9.434% |  |  | Basement 1 | 15.1429
Flooring & Fitting | 5% | 0 | 0% |  |  | Basement 2 | 22.7143
Electrical & Plumbing | 5% | 0 | 0% |  |  | Basement 3 | 30.2857
Painting & Wooden | 5% | 0 | 0% |  |  | Basement 4 | 37.8571
Finishing | 2.5% | 0 | 0% |  |  | Plinth in process | 0
Possession | 2.5% | 0 | 0% |  |  | Plinth completed | 53
Building No. 2 (Tower 3 & 4 ) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 53rd Floor |  | Basement | Ground | Podium | Floors | Plinth work completed, RCC upto 53 Slab, Brickwork upto 41 Floor, Internal Plaster upto 28 Floor, Flooring upto 2 Floor Completed
|  | 5 | 1 | 11 | 53 | [5 empty] | YET TO START
Stage of construction: | Plinth work completed, RCC upto 53 Slab, Brickwork upto 41 Floor, Internal Plaster upto 28 Floor, Flooring upto 2 Floor Completed |  |  |  |  | All work Completed. OC Received. |  |  |  |  | FOUNDATION WIP
Type of Work | Project Progress % | Slab/Floor | Complition % | Completion % | [6 empty] | PLINTH WIP
Plinth | 35% | 53 | 100% | 70.24%
RCC (Including podiums) | 35% | 53 | 81.54% |  |  | Excavation in Process | 7.5714
Brickwork | 5% | 41 | 77.36% |  |  | Foundation in Process | 7.5714
Plaster | 5% | 28 | 52.83% |  |  | Basement 1 | 15.1429
Flooring & Fitting | 5% | 0 | 0% |  |  | Basement 2 | 22.7143
Electrical & Plumbing | 5% | 2 | 3.774% |  |  | Basement 3 | 30.2857
Painting & Wooden | 5% | 0 | 0% |  |  | Basement 4 | 37.8571
Finishing | 2.5% | 0 | 0% |  |  | Plinth in process | 0
Possession | 2.5% | 0 | 0% |  |  | Plinth completed | 53
Building No. 2 (Tower 5) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 53rd Floor |  | Basement | Ground | Podium | Floors | Plinth work completed, RCC upto 17 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3 Floor Completed
|  | 5 | 1 | 11 | 53 | [5 empty] | YET TO START
Stage of construction: | Plinth work completed, RCC upto 17 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3 Floor Completed |  |  |  |  | All work Completed. OC Received. |  |  |  |  | FOUNDATION WIP
Type of Work | Project Progress % | Slab/Floor | Complition % | Completion % | [6 empty] | PLINTH WIP
Plinth | 35% | 53 | 100% | 44.91%
RCC (Including podiums) | 35% | 17 | 26.15% |  |  | Excavation in Process | 7.5714
Brickwork | 5% | 5 | 9.434% |  |  | Foundation in Process | 7.5714
Plaster | 5% | 3 | 5.66% |  |  | Basement 1 | 15.1429
Flooring & Fitting | 5% | 0 | 0% |  |  | Basement 2 | 22.7143
Electrical & Plumbing | 5% | 0 | 0% |  |  | Basement 3 | 30.2857
Painting & Wooden | 5% | 0 | 0% |  |  | Basement 4 | 37.8571
Finishing | 2.5% | 0 | 0% |  |  | Plinth in process | 0
Possession | 2.5% | 0 | 0% |  |  | Plinth completed | 53
Building No. 2 (Tower 1 to 5 ) = 5B + Gr + 1st to 9th Podium + Club House Level 1 & 2 + 1st to 40th Floor |  | Basement | Ground | Podium | Floors | Work not yet Started.
|  | 0 | 1 | 0 | 40 | [5 empty] | YET TO START
Stage of construction: | Work not yet Started. |  |  |  |  | All work Completed. OC Received. |  |  |  |  | FOUNDATION WIP
Type of Work | Project Progress % | Slab/Floor | Complition % | Completion % | [6 empty] | PLINTH WIP
Plinth | 35% | 0 | 0% | 0%
RCC (Including podiums) | 35% | 0 | 0% |  |  | Excavation in Process | 5.7143
Brickwork | 5% | 0 | 0% |  |  | Foundation in Process | 11.4286
Plaster | 5% | 0 | 0% |  |  | Basement 1 | 0
Flooring & Fitting | 5% | 0 | 0% |  |  | Basement 2 | 0
Electrical & Plumbing | 5% | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden | 5% | 0 | 0% |  |  | Basement 4 | 0
Finishing | 2.5% | 0 | 0% |  |  | Plinth in process | 22.8571
Possession | 2.5% | 0 | 0% |  |  | Plinth completed | 40
Overall % Completion Of Project |  |  |  | 55.49%
BUILDING/TOWERWISE UNIT - AREA DETAILS
Total Phases | Total No. Of Buildings | Total No. Of Wings | Total No. Of Approved Units (A) | Total No. Of Unapproved Units (B) | Total No. Of (A+B) Units
1 | 5 | 0 | Flats = 810 | - | 810
Residential Area Details : Flats
Building & Wing | No. of Units | Total Carpet Area |  | Total Saleable Area
Tower 1 | 150 | 126601.4318 |  | 189902.1478
Tower 2 | 212 | 124344.221 |  | 186516.3316
Tower 3 | 134 | 73560.0996 |  | 110340.1494
Tower 4 | 137 | 106123.0295 |  | 159184.5442
Tower 5 | 177 | 109498.1893 |  | 164247.284
Total | 810 | 540126.9713 |  | 810190.4569
Grand Total | 810 | 540126.9713 |  | 810190.4569
Building details Floor Wise
Details of Commercial in Building
Shop No. (Approved Plan) | Description | Gross Carpet area | Builtup Area | Attached Terrace area | Saleable area Loading:
50%
Wing A
Ground Floor For Commercial, Entrance Lobby & Garage For Parking
1 |  |  | 0 | 0 | 0
2 |  |  | 0 | 0 | 0
3 |  |  | 0 | 0 | 0
4 |  |  | 0 | 0 | 0
5 |  |  | 0 | 0 | 0
6 |  |  | 0 | 0 | 0
1st Floor for Commercial & Parking
1 |  |  | 0 | 0 | 0
2 |  |  | 0 | 0 | 0
3 |  |  | 0 | 0 | 0
4 |  |  | 0 | 0 | 0
5 |  |  | 0 | 0 | 0
6 |  |  | 0 | 0 | 0
2nd Floor for Commercial & Parking
1 |  |  | 0 | 0 | 0
2 |  |  | 0 | 0 | 0
3 |  |  | 0 | 0 | 0
4 |  |  | 0 | 0 | 0
5 |  |  | 0 | 0 | 0
6 |  |  | 0 | 0 | 0
Details of Flats in Building
Flat No. (Approved Plan) | Description | Gross Carpet area | Builtup Area | Attached Terrace area | Saleable area Loading :
[5 empty] | 50% | 10.764
Building No. 2
Tower 1 to 5
1st to 5th Basement Floor For Parking
Ground Floor For Society Office, Entrance Lobby & Garden
1st to 9th Podium floor for Parking
1st & 2nd Club House Level For Billiards, Community Hall, Badminton, Gym, Kids play area, Creche, Swimming Pool, Jacuzzi, yoga Area & Other Amenities.
Service Floor Between 2nd Level Club House & 1st Floor
Tower 1
1st Floor For Residential (Part Refuge Area) | [5 empty] | 1
1 | Refuge Area
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
2nd to 4th Floor | [5 empty] | 3
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181 | 83.9942 |  | 1 | 2 to 7, 9 to 14, 16-21, 23-28, 30-35 | 89.95
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861 |  |  | 2 | 1-40 | 79.22
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783 |  |  | 3 | 1-40 | 82.18
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136 |  |  | 4 | 1-27 | 62.97 | 28-39 | 66.81
5th, 16th to 18th Floor | [5 empty] | 4
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
6th, 7th & 9th Floor | [5 empty] | 3
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
8th Floor (Part Refuge Area) | [5 empty] | 1
1 | Refuge Area
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
10th Floor | [5 empty] | 1
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
11th, 12th & 14th, 19th to 21st Floor | [5 empty] | 6
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
13th Floor | [5 empty] | 1
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
15th Floor (Part Refuge Area) | [5 empty] | 1
1 | Refuge Area
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [5 empty] | 1
1 | Refuge Area
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
23rd to 27th Floor | [5 empty] | 5
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 677.8091 | 813.3709 | 0 | 1016.7136
28th, 33rd to 35th, 37th & 38th Floor | [5 empty] | 6
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 719.1428 | 862.9714 | 0 | 1078.7143
29th & 36th Floor (Part Refuge Area) | [5 empty] | 2
1 | Refuge Area
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 719.1428 | 862.9714 | 0 | 1078.7143
30th to 32nd Floor | [5 empty] | 3
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181 |  |  | 18060.0214
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861 |  |  | 17879.4212
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 719.1428 | 862.9714 | 0 | 1078.7143
39th Floor | [5 empty] | 1
1 | 3BHK | 967.1454 | 1160.5745 | 0 | 1450.7181 |  |  | 17370.7077
2 | 2.5BHK | 852.7241 | 1023.2689 | 0 | 1279.0861
3 | 3BHK | 884.5855 | 1061.5026 | 0 | 1326.8783
4 | 2BHK | 719.1428 | 862.9714 | 0 | 1078.7143
40th Floor For Terrace Area | [5 empty] | 1
Tower 2
1st Floor For Residential (Part Refuge Area) | [5 empty] | 1
1 | 2BHK | 661.6631 | 793.9957 | 0 | 992.4946 |  |  | 1 | 1-21 | 61.47 | 22-39 | 56.79
2 | 2BHK | 705.9031 | 847.0837 | 0 | 1058.8547 |  |  | 2 | 1-21 | 65.58 | 22-39 | 61.32
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179 |  |  | 3 | 1-39 | 42.87
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967 |  |  | 4 | 1-39 | 42.58
5 | Refuge Area | [6 empty] | 5 | 5-7, 9-14, 16-21, 23-27 | 56.80 | 28, 33-35, 37 & 38-40 | 61.11
6 | Wind Pressure Defusing Shaft | [6 empty] | 6 | 6-14, 19-21, 23-28, 29 & 36, 30-35, 37 & 38 | 64.19
2nd to 4th Floor | [5 empty] | 3
1 | 2BHK | 661.6631 | 793.9957 | 0 | 992.4946
2 | 2BHK | 705.9031 | 847.0837 | 0 | 1058.8547
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | Void
6 | Wind Pressure Defusing Shaft
5th, 16th to 18th Floor | [5 empty] | 4
1 | 2BHK | 661.6631 | 793.9957 | 0 | 992.4946
2 | 2BHK | 705.9031 | 847.0837 | 0 | 1058.8547
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | 2BHK | 611.3952 | 733.6742 | 0 | 917.0928
6 | Wind Pressure Defusing Shaft
6th, 7th & 9th Floor | [5 empty] | 3
1 | 2BHK | 661.6631 | 793.9957 | 0 | 992.4946
2 | 2BHK | 705.9031 | 847.0837 | 0 | 1058.8547
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | 2BHK | 611.3952 | 733.6742 | 0 | 917.0928
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117
8th Floor (Part Refuge Area) | [5 empty] | 1
1 | 2BHK | 661.6631 | 793.9957 | 0 | 992.4946
2 | 2BHK | 705.9031 | 847.0837 | 0 | 1058.8547
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | Refuge Area
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117 |  |  | 1 | 1-21 | 61.47 | 22-39 | 56.79
10th Floor | [5 empty] | 1 |  | 2 | 1-21 | 65.58 | 22-39 | 61.32
1 | 2BHK | 661.6631 | 793.9957 | 0 | 992.4946 |  |  | 3 | 1-39 | 42.87
2 | 2BHK | 705.9031 | 847.0837 | 0 | 1058.8547 |  |  | 4 | 1-39 | 42.58
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179 |  |  | 5 | 5-7, 9-14, 16-21, 23-27 | 56.80 | 28, 33-35, 37 & 38-40 | 61.11
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967 |  |  | 6 | 6-14, 19-21, 23-28, 29 & 36, 30-35, 37 & 38 | 64.19
5 | 2BHK | 611.3952 | 733.6742 | 0 | 917.0928
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117
11th, 12th & 14th, 19th to 21st Floor | [5 empty] | 6
1 | 2BHK | 661.6631 | 793.9957 | 0 | 992.4946
2 | 2BHK | 705.9031 | 847.0837 | 0 | 1058.8547
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | 2BHK | 611.3952 | 733.6742 | 0 | 917.0928
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117
13th Floor | [5 empty] | 1
1 | 2BHK | 661.6631 | 793.9957 | 0 | 992.4946
2 | 2BHK | 705.9031 | 847.0837 | 0 | 1058.8547
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | 2BHK | 611.3952 | 733.6742 | 0 | 917.0928
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117
15th Floor (Part Refuge & Terrace Area) | [5 empty] | 1
1 | 2BHK | 661.6631 | 793.9957 | 0 | 992.4946
2 | 2BHK | 705.9031 | 847.0837 | 0 | 1058.8547
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | Refuge Area
6 | Terrace Area
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [5 empty] | 1
1 | 2BHK | 611.2876 | 733.5451 | 0 | 916.9313
2 | 2BHK | 660.0485 | 792.0582 | 0 | 990.0727
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | Refuge Area
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117
23rd to 27th Floor | [5 empty] | 5
1 | 2BHK | 611.2876 | 733.5451 | 0 | 916.9313
2 | 2BHK | 660.0485 | 792.0582 | 0 | 990.0727
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967 |  |  | 1687.2809
5 | 2BHK | 611.3952 | 733.6742 | 0 | 917.0928
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117
28th, 33rd to 35th, 37th & 38th Floor | [5 empty] | 6
1 | 2BHK | 611.2876 | 733.5451 | 0 | 916.9313
2 | 2BHK | 660.0485 | 792.0582 | 0 | 990.0727
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | 2BHK | 657.788 | 789.3456 | 0 | 986.6821
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117
29th & 36th Floor (Part Refuge Area) | [5 empty] | 2
1 | 2BHK | 611.2876 | 733.5451 | 0 | 916.9313
2 | 2BHK | 660.0485 | 792.0582 | 0 | 990.0727
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | Refuge Area
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117
30th to 32nd Floor | [5 empty] | 3
1 | 2BHK | 611.2876 | 733.5451 | 0 | 916.9313
2 | 2BHK | 660.0485 | 792.0582 | 0 | 990.0727
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | Refuge Area Below @ 29th Floor
6 | 2BHK | 690.9412 | 829.1294 | 0 | 1036.4117
39th Floor (Part Terrace Area) | [5 empty] | 1
1 | 2BHK | 611.2876 | 733.5451 | 0 | 916.9313
2 | 2BHK | 660.0485 | 792.0582 | 0 | 990.0727
3 | 1BHK | 461.4527 | 553.7432 | 0 | 692.179
4 | 1BHK | 458.3311 | 549.9973 | 0 | 687.4967
5 | 2BHK | 657.788 | 789.3456 | 0 | 986.6821
6 | Terrace Area
40th Floor For Terrace Area | [5 empty] | 1
Tower 3 | [5 empty] | 10.764
1st Floor For Residential (Part Refuge Area) | [5 empty] | 1
1 | Refuge Area | [6 empty] | 1 | 5-7, 9-14, 16-21, 23-27 | 57.44 | 28, 33-35, 37 & 38-39 |  | 61.75
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435 |  |  | 2 | 1-39 | 42.49
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395 |  |  | 3 | 1-39 | 43.01
4 | Wind Pressure Defusing Shaft | [6 empty] | 4 | 6-14, 19-21, 23-28, 29 & 36, 30-35, 37 & 38 | 66.15
2nd to 4th Floor | [5 empty] | 3
1 | Refuge Area Below @ 1st Floor
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | Wind Pressure Defusing Shaft
5th, 16th to 18th Floor | [5 empty] | 4
1 | 2BHK | 618.2842 | 741.941 | 0 | 927.4262
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | Wind Pressure Defusing Shaft
6th, 7th & 9th Floor | [5 empty] | 3
1 | 2BHK | 618.2842 | 741.941 | 0 | 927.4262
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
8th Floor (Part Refuge Area) | [5 empty] | 1
1 | Refuge Area
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
10th Floor | [5 empty] | 1
1 | 2BHK | 618.2842 | 741.941 | 0 | 927.4262
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
11th, 12th & 14th, 19th to 21st Floor | [5 empty] | 6
1 | 2BHK | 618.2842 | 741.941 | 0 | 927.4262
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
13th Floor | [5 empty] | 1
1 | 2BHK | 618.2842 | 741.941 | 0 | 927.4262
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
15th Floor (Part Refuge Area) | [5 empty] | 1
1 | Refuge Area
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | Terrace Area
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [5 empty] | 1
1 | Refuge Area
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
23rd to 27th Floor | [5 empty] | 5
1 | 2BHK | 618.2842 | 741.941 | 0 | 927.4262
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
28th, 33rd to 35th, 37th & 38th Floor | [5 empty] | 6
1 | 2BHK | 664.677 | 797.6124 | 0 | 997.0155
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
29th & 36th Floor (Part Refuge Area) | [5 empty] | 2
1 | Refuge Area
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
30th to 32nd Floor | [5 empty] | 3
1 | Refuge Area Below @ 29th Floor
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | 2BHK | 712.0386 | 854.4463 | 0 | 1068.0579
39th Floor | [5 empty] | 1
1 | 2BHK | 664.677 | 797.6124 | 0 | 997.0155
2 | 1BHK | 457.3624 | 548.8348 | 0 | 686.0435
3 | 1BHK | 462.9596 | 555.5516 | 0 | 694.4395
4 | Terrace Area
40th Floor For Terrace Area | [5 empty] | 1
Tower 4
1st Floor For Residential (Part Refuge Area) | [5 empty] | 1
1 | Wind Pressure Defusing Shaft | [6 empty] | 1 | 6-14, 19-21, 23-28, 29 & 36, 30-35, 37 & 38 | 66.31
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011 |  |  | 2 | 1-40 | 93.98
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109 |  |  | 3 | 1-40 | 46.65
4 | Refuge Area | [6 empty] | 4 | 5, 6, 7, 9, 10, 16-18, 11, 12, 14, 19-21, 23-27 | 81.3 | 28, 33-35, 37-40 | 85.61
2nd to 4th Floor | [5 empty] | 3
1 | Wind Pressure Defusing Shaft
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109 |  |  |  | 12686194.919 | 113805.081
4 | Refuge Area Below @ 1st Floor | [7 empty] | 16823.9732
5th, 16th to 18th Floor | [5 empty] | 4
1 | Wind Pressure Defusing Shaft
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | 3BHK | 875.1132 | 1050.1358 | 0 | 1312.6698
6th, 7th & 9th Floor | [5 empty] | 3
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | 3BHK | 875.1132 | 1050.1358 | 0 | 1312.6698
8th Floor (Part Refuge Area) | [5 empty] | 1
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | Refuge Area
10th Floor | [5 empty] | 1
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | 3BHK | 875.1132 | 1050.1358 | 0 | 1312.6698
11th, 12th & 14th, 19th to 21st Floor | [5 empty] | 6
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | 3BHK | 875.1132 | 1050.1358 | 0 | 1312.6698
13th Floor | [5 empty] | 1
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | 3BHK | 875.1132 | 1050.1358 | 0 | 1312.6698
15th Floor (Part Refuge & Terrace Area) | [5 empty] | 1
1 | Terrace Area
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | Refuge Area
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [5 empty] | 1
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | Refuge Area
23rd to 27th Floor | [5 empty] | 5
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | 3BHK | 875.1132 | 1050.1358 | 0 | 1312.6698
28th, 33rd to 35th, 37th & 38th Floor | [5 empty] | 6
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | 3BHK | 921.506 | 1105.8072 | 0 | 1382.2591
29th & 36th Floor (Part Refuge Area) | [5 empty] | 2
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | Refuge Area
30th to 32nd Floor | [5 empty] | 3
1 | 2BHK | 713.7608 | 856.513 | 0 | 1070.6413
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | Refuge Area Below @ 29th Floor
39th Floor (Part Terrace Area) | [5 empty] | 1
1 | Terrace Area
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | 3BHK | 921.506 | 1105.8072 | 0 | 1382.2591
40th Floor | [5 empty] | 1
1 | Terrace Area Below @ 39th Floor
2 | 3BHK | 1011.6007 | 1213.9209 | 0 | 1517.4011
3 | 1BHK | 502.1406 | 602.5687 | 0 | 753.2109
4 | 3BHK | 921.506 | 1105.8072 | 0 | 1382.2591
Tower 5
1st Floor For Residential (Part Refuge Area) | [5 empty] | 1
1 | Wind Pressure Defusing Shaft | [6 empty] | 1 | 6-14, 19-21, 23-28, 29, 36, 30-35, 37, 38 | 63.79
2 | Refuge Area | [6 empty] | 2 | 5, 6, 7, 9, 10, 16-18, 11, 12, 14, 19-21, 23-27 | 63.08 | 28.33-35.37.38-40 | 67.39
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894 |  |  | 3 | 1-40, | 42.53
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478 |  |  | 4 | 1-40, | 42.93
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681 |  |  | 5 | 1-40, | 77.59
2nd to 4th Floor | [5 empty] | 3
1 | Wind Pressure Defusing Shaft
2 | Refuge Area Below @ 1st Floor
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
5th, 16th to 18th Floor | [5 empty] | 4
1 | Wind Pressure Defusing Shaft
2 | 2BHK | 678.9931 | 814.7917 | 0 | 1018.4897
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
6th, 7th & 9th Floor | [5 empty] | 3
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | 2BHK | 678.9931 | 814.7917 | 0 | 1018.4897
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
8th Floor (Part Refuge Area) | [5 empty] | 1
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | Refuge Area
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
10th Floor | [5 empty] | 1
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | 2BHK | 678.9931 | 814.7917 | 0 | 1018.4897
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
11th, 12th & 14th, 19th to 21st Floor | [5 empty] | 6
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | 2BHK | 678.9931 | 814.7917 | 0 | 1018.4897
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
13th Floor | [5 empty] | 1
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | 2BHK | 678.9931 | 814.7917 | 0 | 1018.4897
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
15th Floor (Part Refuge & Terrace Area) | [5 empty] | 1
1 | Terrace Area
2 | Refuge Area
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [5 empty] | 1
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | Refuge Area
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
23rd to 27th Floor | [5 empty] | 5
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | 2BHK | 678.9931 | 814.7917 | 0 | 1018.4897
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
28th, 33rd to 35th, 37th & 38th Floor | [5 empty] | 6
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | 2BHK | 725.386 | 870.4632 | 0 | 1088.0789
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894 |  |  | 16892.6451
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478 |  |  | 16735.248
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
29th & 36th Floor (Part Refuge Area) | [5 empty] | 2
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | Refuge Area
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
30th to 32nd Floor | [5 empty] | 3
1 | 2BHK | 686.6356 | 823.9627 | 0 | 1029.9533
2 | Refuge Area Below @ 29th Floor
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
39th Floor (Part Terrace Area) | [5 empty] | 1
1 | Terrace Area
2 | 2BHK | 725.386 | 870.4632 | 0 | 1088.0789 |  |  | 3101024.979 | 17082839.358
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894 |  |  | 20183864.337
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
40th Floor | [5 empty] | 1
1 | Terrace Area Below @ 39th Floor
2 | 2BHK | 725.386 | 870.4632 | 0 | 1088.0789
3 | 1BHK | 457.7929 | 549.3515 | 0 | 686.6894
4 | 1BHK | 462.0985 | 554.5182 | 0 | 693.1478
5 | 3BHK | 835.1788 | 1002.2145 | 0 | 1252.7681
VALUE PARAMETERS
Sr.No. | Building /Wing - Name /No |  | Base Rate Psf Rs. | Base Rate Considered On Area - Carpet/ Bua/ Saleale
1 | Tower 1 to 5 |  | 16800 | Saleable Area
2 |  |  |  | Saleable Area
3 |  |  |  | Saleable Area
4 |  |  |  | Saleable Area
5 |  |  |  | Saleable Area
6 |  |  |  | Saleable Area
Floor Rise (If Applicable) | In Rs. Psf (If Applicable) | In Lumpsum Basis (If Applicable) | Applicable From Floor No. | Applicable To Floor No. | Applicable To Building /W ing
Floor Rise 1 | NA | NA
Floor Rise 2
Floor Rise 3
Floor Rise 4
Plc Charges (If Applicable) | In Rs. Psf (If Applicable) | In Lumpsum Basis (If Applicable) | Details Of Plc/View |  | List Of Unit Nos - Plc Applicable
PLC Type 1 | NA | NA
PLC Type 2
PLC Type 3
Amenities Details | In Rs. Psf (If Applicable) | In Lumpsum Basis (If Applicable) | Details Of Amenity Cost - Optional/Compulsory To Buyer, No Of Years, Etc |  | Remarks, If Any
Parking | NA | 700000
Clubhouse & Recreational
Electricity & Water Con.
Infra
Development
Maintenance
Any Other Amenity 1
Any Other Amenity 2
Any Other Amenity 3
Remarks:
1 | Construction Work is in process at the time of visit.
2 | Internal visit was not allowed.
3 | Labours & Materials were found on site at the time of visit.
4 | We have considered Saleable area of Flats as per our Calculation.
5 | We considered Gross carpet area = Net carpet + Deck + Utility.
6 | We have considered rate by verifying it from market inquire.
7 | On Site, we meet Mr Raj Mandhana (sales) - 8655133244
8 | Car parking is subjected to authentic documentation.
9 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
10 | We have updated revised CC from MCGM site on 17/07/2025.
11 | Please provide revised approved plans dtd. 05/03/2024.
12 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan
Photographs Of Property : |  | Runwal Pinnacle
Layout Of Property :
Google Map :
Name of Engineer Visited the property | Nainesh Tambe | Authorized Signatory Name & Seal of the agency
Note on D99: SACHIN: Title certifcate lawyer name
Note on C128: Sachin: Builder"s recent project names take from builder documents
Note on C129: Sachin: Approved by authority name Positive or negavtive points Surrounding buildings or mall etc or less distance from stn
Building No. 2
Tower 1 to 5
Tower 4
Tower 5
Tower 3
Tower 2
Tower 1
Tower 4
Tower 1
Tower 2
Tower 2
Tower 5
Tower 3
Tower 4
Tower 4

## Sheet2
Construction details: |  | g +7 |  |  |  | All work completed. Please provide OC.
Basement | 0 | 1 | 0 | 7
Stage of construction: |  | All work Completed. OC Received. |  |  |  | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % | Disbursement % | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% | 100% | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  | Plinth completed | 7
Work not yet Started., RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Work not yet Started., RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting