## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/07/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-07-18
Name of the builder group |  |  |  |  | M/S. Shree Samarth Realty
Name of the builder company |  |  |  |  | M/S. Shree Samarth Realty
Name of the Project |  |  |  |  | Crown Phase 1 & Crown C
Building no. |  |  |  |  | A, B, C Wings
Contact No. |  |  |  |  | 2779897070
RERA Number |  |  |  |  | A, B Wing = P52000013990 C Wing = P52000026298
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of CC.
Project location details |  | Crown, S.No. 17/C/2 at Village-Gundge, Tal.Karjat Dist.-Raigad
S. No | 17/C/2 |  |  | Plot No | 2 | Locality | Gundge, Karjat.
Road | Village Gundge Road |  |  |  | District | Raigad
City | Panvel, Karjat |  |  |  | Pin Code | 410 201.
Near by Landmark |  | Gajanan Park |  |  | Distance from city centre: |  | About 1.9 Km from Karjat Railway Station.
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Railway Track |  | Road |  | Building |  | Village
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | Latitude |  | 18.9011 |  | Longitude |  | 73.3176
Location Link |  | https://goo.gl/maps/LL6Jm6p5tX9kubC5A
Approval details:
Approved usage of the Property: Residential & Commercial (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 2006.57
Permissible FSI |  |  |  |  | 1.68
Permissible TDR/Paid FSI |  |  |  |  | 0.096105
Total FSI availaible for the project |  |  |  |  | 1.7761
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 3563.88
Total number of Buildings |  |  |  |  | 03 Wings
Approval Detail : Plan approval
Layout Approval No (A, B, C Wing) |  | S.R.33/17-18 |  |  |  | Dated | 30/08/2017.
Building approval No (A & B Wing) |  | S.R.33/17-18 |  |  |  | Dated | 30/08/2017.
C.certificate No (A & B Wing) |  | Building/KT-1/S.R.33/17-18 Valid Up to: G + 4th Floor |  |  |  | Dated | 30/08/2017. | Expiry date: One year from date of issue
Part O. Certificate No.: |  | 502/21-22 Wing B = Gr/Stilt + 1st to 4th Floor |  |  | Date of approval: NA | Dated | 2022-03-16 | Expiry date: NA
|  | JVK No.2808/19-20 Wing A = Gr/Stilt + 1st to 4th Floor |  |  | Date of approval: NA | Dated | 2019-12-26
Approval Detail : Plan approval
Layout Approval No (A, B, C Wing) |  | CCRUM/B/2019/APL/00073 |  |  |  | Dated | 25/09/2019. | Expiry date: One year from date of issue
Building approval No (C Wing) |  | CCRUM/B/2019/APL/00073 |  |  |  | Dated | 25/09/2019.
C.certificate No (C Wing) |  | CCRUM/B/2019/APL/00073 Valid Up to: G + 4th Floor |  |  |  | Dated | 25/09/2019. | Expiry date: One year from date of issue
O. Certificate No.: |  | CCRUM/FO/2025/APL/00071 Building A, B & C = Gr/St + 1st to 4th Floor |  |  | Date of approval: NA | Dated | 2025-02-28 | Expiry date: NA
Commencement date of construction |  |  | 25/09/2019. |  | Expected Completion |  | Wing A, B & C = Completed
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 3563.88 |  | Approved no of units |  |  | Shop - 09 Flats - 120
Approved no of Floors |  | A, B, C Wing = G+4th Floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years
Material laying at Site: :Nothing
Construction details: A Wing = G+ 1st to 4th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 4 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. Provide OC. | [6 empty] | All work Completed. Provide OC.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 4 | 100% |  | 100% |  | 100%
Plinth |  | 4 | 100%
RCC |  | 5 | 100% | [5 empty] | Excavation in process |  | 2
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Excavation Completed |  | 4
Internal Plaster | Brickwork & Internal Plaster | 4 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Footing in Process |  | 1
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Footing Completed |  | 2
Painting & Wooden |  | 4 | 100% | [5 empty] | Plinth in process |  | 3
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth completed |  | 4
Possession |  | 4 | 100%
Construction details: A & B Wing = G+ 1st to 4th Floor | [8 empty] | 00, RCC upto Slab/Floor Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 5 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 4 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Construction details: C Wing = G + 1st to 4th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 4 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. Provide OC.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 4 | 100% |  | 100% |  | 100%
Plinth |  | 4 | 100%
RCC |  | 5 | 100% | [5 empty] | Excavation in process |  | 2
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Excavation Completed |  | 4
Internal Plaster | Brickwork & Internal Plaster | 4 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Footing in Process |  | 1
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Footing Completed |  | 2
Painting & Wooden |  | 4 | 100% | [5 empty] | Plinth in process |  | 3
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth completed |  | 4
Possession |  | 4 | 100%
Wheather the construction is as per approved Building plan : Yes
Violations Observed if any : NA
Proposed Amenities : 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on saleable area) | [5 empty] | 4400
Recommended rate of the Shop Per Sq. Ft. ( on saleable area) | [5 empty] | 7000
Society formation charges | [5 empty] | 1000/-
Recommended rate of Parking | [5 empty] | 100000/-
Water, Meter Connection & Infrastructure Development Charges | [5 empty] | 1,80,000/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 3520
Building details floor wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | Floor
Wing A
Ground Floor For Parking & Commercial
1 |  | Shop | 95.692 |  | 0 | 143.5379 | Ground Floor For Parking & Commercial
2 |  | Shop | 143.9147 | 0 | 0 | 215.872
3 |  | Shop | 161.9982 | 0 | 0 | 242.9973
4 |  | Shop | 140.3626 | 0 | 0 | 210.5438
5 |  | Shop | 75.2404 | 0 | 0 | 112.8605
6 |  | Shop | 74.9174 | 0 | 0 | 112.3762
1st to 4th Typical Floor
1 |  | 1BHK | 323 |  | 0 | 468.35 | 1st to 4th Typical Floor |  |  | 2060740
2 |  | 1BHK | 323 | 0 | 0 | 468.35
3 |  | 1BHK | 323 | 0 | 0 | 468.35
4 |  | 1BHK | 221 | 0 | 0 | 320.45
5 |  | 1BHK | 323 | 0 | 0 | 468.35
6 |  | 2BHK | 404 | 0 | 0 | 585.8
7 |  | 1RK | 200 | 0 | 0 | 290
8 |  | 1BHK | 264 | 0 | 0 | 382.8 |  |  |  | 4655.1724
9 |  | 1BHK | 325 | 0 | 0 | 471.25
10 |  | 1RK | 197 | 0 | 0 | 285.65
Wing B
Ground Floor For Parking
1st to 4th Typical Floor
1 |  | 1BHK | 303 | 0 | 0 | 439.35 | 1st to 4th Typical Floor
2 |  | 1BHK | 303 | 0 | 0 | 439.35 | [5 empty] | 1.45
3 |  | 1BHK | 320 | 0 | 0 | 464
4 |  | 1BHK | 209 | 0 | 0 | 303.05
5 |  | 1BHK | 320 | 0 | 0 | 464
6 |  | 1BHK | 320 | 0 | 0 | 464 |  |  |  | 2909.4828
7 |  | 1RK | 192 | 0 | 0 | 278.4
8 |  | 2BHK | 385 | 0 | 0 | 558.25
9 |  | 1BHK | 303 | 0 | 0 | 439.35
10 |  | 1RK | 192 | 0 | 0 | 278.4
C Wing
Ground Floor For Parking & Shop
1 |  | Shop | 239.3914 |  | 0 | 359.087 | Ground Floor
2 |  | Shop | 184.172 |  | 0 | 276.2581
3 |  | Shop | 154.4634 |  | 0 | 231.6951
1st Floor
1 |  | 1RK | 311.5102 |  | 19.8058 | 471.4955 | 1st Floor
2 |  | 2BHK | 431.6095 |  | 0 | 625.8338
3 |  | 1RK | 261.7805 |  | 0 | 379.5817
4 |  | 1RK | 262.4263 |  | 0 | 380.5182
5 |  | 1RK | 261.7805 |  | 0 | 379.5817
6 |  | 2BHK | 458.8693 |  | 0 | 665.3605
7 |  | 2BHK | 479.7515 |  | 17.949 | 713.5886 |  |  |  | 1071
8 |  | 1RK | 293.9648 |  | 22.2608 | 448.5098
9 |  | 1RK | 293.9648 |  | 22.2608 | 448.5098
10 |  | 1RK | 295.5794 |  | 22.2608 | 450.851
2nd, 3rd, 4th Floor
1 |  | 1RK | 311.5102 |  | 0 | 451.6897 | 2nd, 3rd, 4th Floor |  |  | 3021.9859
2 |  | 2BHK | 431.6095 |  | 0 | 625.8338
3 |  | 1RK | 261.7805 |  | 0 | 379.5817
4 |  | 1RK | 262.4263 |  | 0 | 380.5182
5 |  | 1RK | 261.7805 |  | 0 | 379.5817
6 |  | 2BHK | 458.8693 |  | 0 | 665.3605
7 |  | 2BHK | 479.7515 |  | 0 | 695.6396
8 |  | 1RK | 293.9648 |  | 0 | 426.249
9 |  | 1RK | 293.9648 |  | 0 | 426.249
10 |  | 1RK | 295.5794 |  | 0 | 428.5902
Remarks: 1. Wing A, B & C = All work completed. OC received. 2. We considered saleable area as per our calculation. 3. We have considered rate by verifying it from market inquire. 4. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 5. We have considered Other charges from cost sheet. 6. Car parking is subjected to authentic documentation. 7. OC taken from Rera Site(Wing B). 8. We Have updated OC from Rera for Wing A (On 29/02/2024). 9. We have updated full OC (On 19/07/2025). 10. Please provide revised approved floor plans. 8. On Site, we meet Mr.Harshad Gharat (Sales) - 7276090689.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : Crown
Google Map :
A Wing
A Wing
B Wing
C Wing

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
25/01/2021. | Asmi | Cost Sheet by Akash
rate from 4100 to 4400

## A%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 5 | 5
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 5 | 5
| 4 | 4 | 100
plaster | Total Floor | completed Floor | 100
| 4 | 4 | 100
Flooring | Total Floor | completed Floor
| 4 | 4 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 4 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 4 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 5 | 5
|  |  |  | Finishing | 5 | 5
|  |  |  | total | 95 | 100

## B%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 1.875 | 0
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 1.875 | 0
| 4 | 4 | 100
plaster | Total Floor | completed Floor | 37.5
| 4 | 4 | 0
Flooring | Total Floor | completed Floor
| 4 | 4 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 1.5 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 0 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 1.875 | 1.875
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 86.875 | 91.875

## C%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 60 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 3 | 0 | Progress |  |  | 10 | 24 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 18 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 24 | 18
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 34 | 48

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0