## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/07/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-07-18
Name of the builder group |  |  |  |  | Chaitanya Builders & Developers
Name of the builder company |  |  |  |  | Chaitanya Builders & Developers
Name of the Project |  |  |  |  | Pandurang Park
Contect Details ( Name & Contect No.) |  |  |  |  | 9260163224
Name / No of the Building |  |  |  |  | Building No.1 (A, B & C Wing) Building No.2 (A & B Wing) Building No.3 (A & B Wing) Building No.4 (A & B Wing)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P99000020314
Project location details |  | Pandurang Park, Gut No.139/1 (Old S.No. 5/5), Internal Road, Saravali, Boisar, Palghar.
Gut No |  | 139/1 (Old S.No. 5/5)
Road |  | Internal Road |  |  | Locality/Village |  | Saravali
City |  | Boisar |  |  | District |  | Palghar
Taluka |  | Palghar |  |  | Pin Code |  | 401501
Near by Landmark |  | Nirmala Park |  |  | Distance from city centre: |  | About 2.5 Km from Boisar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building |  | Open Space |  | Nirmala Park |  | Hari I'm Park
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.77928,72.754807
Location Link |  | https://goo.gl/maps/vkmFcnE2ziwWT2Ld6
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 8770
Permissible FSI |  |  |  |  | 0.89
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.89
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 7893.3
Total number of Buildings |  |  |  |  | 04 Buildings (09 Wing)
Approval Detail : Plan approval
Layout Approval No |  | JK/PZP/GP/PD/883 |  |  |  | Dated | 11/10/2019.
Approved Floor plan No. |  | JK/PZP/GP/PD/883 |  |  |  | Dated | 11/10/2019.
Commencement Certificate No. |  | J.K.PZP/G.P/PD/638 Valid Up to: Building No 1(A, B & C) - G + 4th Floor Building No 2(A & B) - G + 1st to 4th Floor Building No 3(A & B) - G + 1st to 4th Floor Building No 4(A & B) - G + 1st to 2nd Floor |  |  |  | Dated | 18/03/2019. | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 18/03/2019. |  | Expected Completion |  | 2026-06-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 7893.3 |  | Approved no of units |  | Flats = 173
Approved no of Floors |  | Building No 1(A, B & C) - G + 1st to 4th Floor Building No 2(A & B) - G + 1st to 4th Floor Building No 3(A & B) - G + 1st to4th Floor Building No 4(A & B) - G + 1st to 2nd Floor |  |  |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Building No.1(A, B, C Wing) = G + 1st to 4th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth in process | 3
Possession |  | 4 | 100% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.2 (Wing A & B) = G + 1st to 4th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth in process | 3
Possession |  | 4 | 100% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.3 (Wing A) = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 86.25% |  | 93.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 75% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.3 Wing B = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 86.25% |  | 93.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 75% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.4 (A & B Wing) = G + 1st to 4th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 2
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 4
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3500 |  |  |  | 1. Rate changed from 3000 to 3300 - Akash Sir
Society Formation | [5 empty] | 50000/-
Development Charges | [5 empty] | 100000/-
Recommended rate of Parking | [5 empty] | 50000/-
Distressed valuation of the Property | [5 empty] | 2800
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Building No 01 - A |  | 18 | 7756.646 |  |  | 11247.1368
Building No 01 - B |  | 28 | 14100.1942 |  |  | 20445.2815
Building No 01 - C |  | 18 | 7671.6104 |  |  | 11123.8351
Building No 02 - A |  | 16 | 5820.0948 |  |  | 8439.1375
Building No 02 - B |  | 24 | 9580.6058 |  |  | 13891.8785
Total |  | 104 | 44929.1513 |  |  | 65147.2694
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No.1
A Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 379.8077 |  | 0 | 550.7212 | N | Ground Floor
2 |  | 1BHK | 379.8077 |  | 0 | 550.7212 | N |  |  | 2
1st to 4th Floor
1 |  | 1BHK | 433.0626 |  | 0 | 627.9408 | N | 1st to 4th Floor
2 |  | 1BHK | 441.5662 |  | 0 | 640.271 | N
3 |  | 1BHK | 441.5662 |  | 0 | 640.271 | N |  |  | 16
4 |  | 1BHK | 433.0626 |  | 0 | 627.9408 | N
B Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 337.0208 |  | 0 | 488.6802 | N | Ground Floor for Residential & Parking
2 |  | 1BHK | 371.3042 |  | 0 | 538.3911 | N |  |  | 4
3 |  | 2BHK | 542.398 |  | 0 | 786.477 | N
4 |  | 2BHK | 476.899 |  | 0 | 691.5036 | N
1st to 4th Floor
1 |  | 1BHK | 401.7394 |  | 0 | 582.5221 | N | 1st to 4th Floor
2 |  | 1BHK | 433.0626 |  | 0 | 627.9408 | N
3 |  | 1BHK | 433.0626 |  | 0 | 627.9408 | N |  |  | 24
4 |  | 2BHK | 631.6046 |  | 0 | 915.8267 | N
5 |  | 2BHK | 631.6046 |  | 0 | 915.8267 | N
6 |  | 2BHK | 562.0692 |  | 0 | 815.0003 | N
C Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 371.3042 |  | 0 | 538.3911 | N | Ground Floor |  | 2
2 |  | 1BHK | 371.3042 |  | 0 | 538.3911 | N
1st to 4th Floor
1 |  | 1BHK | 433.0626 |  | 0 | 627.9408 | N | 1st to 4th Floor |  | 16
2 |  | 1BHK | 433.0626 |  | 0 | 627.9408 | N
3 |  | 1BHK | 433.0626 |  | 0 | 627.9408 | N
4 |  | 1BHK | 433.0626 |  | 0 | 627.9408 | N
Building No.2
A Wing
Ground Floor for Residential & Parking
1 |  | 2BHK | 433.5201 |  | 0 | 628.6041 | N | Ground Floor |  | 3
2 |  | 1BHK | 333.7378 |  | 0 | 483.9198 | N
3 |  | 1BHK | 345.7397 |  | 0 | 501.3225 | N
1st to 4th Floor
1 |  | 1BHK | 342.0261 |  | 0 | 495.9378 | N | 1st to 4th Floor
2 |  | 2BHK | 433.5201 |  | 0 | 628.6041 | N
3 |  | 1BHK | 333.7378 |  | 0 | 483.9198 | N
4 |  | 1BHK | 345.7397 |  | 0 | 501.3225 | N
B Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 346.6546 |  | 0 | 502.6492 | N | Ground Floor
2 |  | 1BHK | 346.9775 |  | 0 | 503.1174 | N
3 |  | 1BHK | 345.7397 |  | 0 | 501.3225 | N
4 |  | 2BHK | 420.4957 |  | 0 | 609.7187 | N
5 |  | 2BHK | 467.642 |  | 0 | 678.0809 | N
1st to 4th Floor
1 |  | 1BHK | 346.6546 |  | 0 | 502.6492 | N | 1st to 4th Floor
2 |  | 1BHK | 346.9775 |  | 0 | 503.1174 | N
3 |  | 1BHK | 345.7397 |  | 0 | 501.3225 | N
4 |  | 2BHK | 420.4957 |  | 0 | 609.7187 | N
5 |  | 2BHK | 467.642 |  | 0 | 678.0809 | N
6 |  | 2BHK | 467.642 |  | 0 | 678.0809 | N
Building No.3
A Wing
Ground Floor for Residential & Parking
1 |  | 2BHK | 494.7673 |  | 0 | 717.4125 | N | Ground Floor
2 |  | 2BHK | 431.2597 |  | 0 | 625.3265 | N
3 |  | 1BHK | 345.7935 |  | 0 | 501.4006 | N
4 |  | 2BHK | 494.3367 |  | 0 | 716.7882 | N
1st to 4th Floor
1 |  | 2BHK | 497.0277 |  | 0 | 720.6902 | N | 1st to 4th Floor
2 |  | 2BHK | 497.0277 |  | 0 | 720.6902 | N
3 |  | 2BHK | 420.4957 |  | 0 | 609.7187 | N
4 |  | 1BHK | 345.7935 |  | 0 | 501.4006 | N
5 |  | 2BHK | 494.3367 |  | 0 | 716.7882 | N
6 |  | 2BHK | 494.3367 |  | 0 | 716.7882 | N
B Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 341.2726 |  | 0 | 494.8453 | N | Ground Floor
2 |  | 1BHK | 341.2726 |  | 0 | 494.8453 | N
1st to 4th Floor
1 |  | 1BHK | 341.2726 |  | 0 | 494.8453 | N | 1st to 4th Floor
2 |  | 1BHK | 353.4359 |  | 0 | 512.4821 | N
3 |  | 1BHK | 341.2726 |  | 0 | 494.8453 | N
4 |  | 1BHK | 341.2726 |  | 0 | 494.8453 | N
Building No.4
A Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 346.6546 |  | 0 | 502.6492 | N | Ground Floor
2 |  | 1BHK | 346.6546 |  | 0 | 502.6492 | N
3 |  | 2BHK | 467.5343 |  | 0 | 677.9248 | N
1st & 2nd Floor
1 |  | 1BHK | 497.0277 |  | 0 | 720.6902 | N | 1st & 2nd Floor
2 |  | 1BHK | 497.0277 |  | 0 | 720.6902 | N
3 |  | 1BHK | 420.4957 |  | 0 | 609.7187 | N
4 |  | 1BHK | 345.7935 |  | 0 | 501.4006 | N
5 |  | 2BHK | 494.3367 |  | 0 | 716.7882 | N
6 |  | 2BHK | 494.3367 |  | 0 | 716.7882 | N
B Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 346.7353 |  | 0 | 502.7663 | N | Ground Floor
2 |  | 1BHK | 346.6546 |  | 0 | 502.6492 | N
3 |  | 1BHK | 346.6546 |  | 0 | 502.6492 | N
1st & 2nd Floor
1 |  | 1BHK | 346.7353 |  | 0 | 502.7663 | N | 1st & 2nd Floor
2 |  | 1BHK | 346.7353 |  | 0 | 502.7663 | N
3 |  | 2BHK | 420.4957 |  | 0 | 609.7187 | N
4 |  | 1BHK | 345.7935 |  | 0 | 501.4006 | N
5 |  | 1BHK | 346.6546 |  | 0 | 502.6492 | N
6 |  | 1BHK | 346.6546 |  | 0 | 502.6492 | N
Remarks:
1. Building No.1 (A, B & C Wing) & 2 (A & B Wing) = All work completed. Please provide OC. Building No.3 (A & B Wing) = Construction work was in process at the time of visit. Building No.4 (A & B Wing) = Work not yet Started. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony + C.B Area. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. Car parking is subjected to authentic documentation. 8. We update revised Plans (on 29/08/2020). 9. On site we met Mr. Dipesh : 9011186742. 10. As checked on RERA portal on date 18/07/2025, we have observed that above project "Pandurang Park" is kept under abeyance. Please check from your end. 11. Since building no.4 (Wing A & B) have received CC on 18/03/2019, but as of construction work is not started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnesh |  | Report Prepared By : |  |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Pandurang Park
Google Map :
Building No.4

## 1-A,
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0.5 | 12.5% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 0 | 0.625 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0 | 0.625 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 0 | 0
Wood & painting | 0.625 | 0.625
Finishing | 0 | 0
total | 75.62% | 85.62% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 1-B% (2)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 3 | 75% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 7.5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 7.5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 7.5 | 7.5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 72.5% | 82.5% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 1-C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 3 | 75% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 7.5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 7.5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 7.5 | 7.5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 72.5% | 82.5% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 2-A%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 4 | 80% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 32 | 0 | 0 | 0 | 0 | 0
RCC | 32 | 24 |  | Recommended |  | 30 | 24 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 42% | 54% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 2-B%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 4 | 80% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 32 | 0 | 0 | 0 | 0 | 0
RCC | 32 | 24 |  | Recommended |  | 30 | 24 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 42% | 54% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 3-A%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 5 | 50%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 5 | 25 |  | Progress |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 25 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 5% | 25% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 3-B%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 3 | 30%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 3 | 23 |  | Progress |  | 3 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 23 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 3% | 23% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2020-12-19 | Pratiksha
23/01/2021. |  | 1. Rate changes from 3000 to 3300 with ref.to IGR
3297.4052
3271.9836
3361.8952

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.7 | 2.75 | 10.175 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2 | 2.15 | 4.3 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.05 | 2.75 | 8.3875 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 1.85 | 2.22 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.85 | 1.2 | 2.22 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.5 | 0.52 | 0.78 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 302.28 | 28.0825 |  |  | 0 | 0 |  | 0 | 0
|  |  | 302.28 | 28.0825