## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 08/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-19
Name of the builder group |  |  |  | M/s. Greenpath Realty Private Limited
Name of the builder company |  |  |  | M/s. Greenpath Realty Private Limited
Name of the Project |  |  |  | Anant Serene Park
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Jitesh Agarwal & 8108113311
Site Person - Contact Details (Name & Contact No.) |  |  |  | Miss. Prachi : 8108113355
Name / No of the Building |  |  |  | Building No.1-Wing A (Lily) Building No.2 -Wing B (Orchid)
Name / No of the Existing Building |  |  |  | NA | [9 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet | [9 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000052516 |  |  |  | #N/A | [5 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Anant Serene Park, Survey No.140/2, near Vardoli lake & ZP School, Interal Road, Wardoli, Wardoli, Mohope East, Panvel, Raigad - 410206. | [11 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 140/2 | [11 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Wardoli | [11 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Interal Road |  | Locality/Village |  | Wardoli | [7 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Mohope East |  | District |  | Raigad | [7 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410206 | [10 empty] | Mahad | Daund
Nearby Landmark |  | Vardoli lake & ZP School |  | Distance from city centre: |  | 3.9 KM from Mohope Railway Station | [10 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [12 empty] | Mangaon | Ambegaon
[17 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [12 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [12 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [12 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 12.0 M Wide Internal Road |  |  | Open Plot
West | NA | Open Space/Building/A.D.J.S.No.140/1 |  |  | Open Plot/ZP School
North | NA | Area Widening 436.23 Sq.Mt/15 Mt. Wide Proposed Road |  |  | Internal Road/ Kirki River
South | NA | 9.00 M Wide Road/9-MT Buffer For Lake,A.D.J S.No.141 |  |  | Open plot/Vardoli lake
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 18.969611,73.193306
Location Link |  | https://maps.app.goo.gl/cyKzPkiHwxB8idLe8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 9463.77
Permissible Sale FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | -0.0033919
Total FSI availaible for the project |  |  |  | 0.99661
Total Approved sale Builtup area of the project (Sq.Mt) |  |  |  | 9431.67
Total number of Buildings |  |  |  | 02 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Navi Mumbai Airport Influence Notified Area (NAINA)
Layout Approval No |  | CIDCO/NAINA/Panvel/Wardoli/BP-00603/CC/2023/0410 |  |  | Dated | 2023-08-03
Approved Floor plan No. |  | CIDCO/NAINA/Panvel/Wardoli/BP-00603/CC/2023/0410 |  |  | Dated | 2023-08-03
Commencement-CC No Valid Up to: |  | CIDCO/NAINA/Panvel/Wardoli/BP-00603/CC/2023/0410 |  |  | Dated | 2023-08-03
Building 1-Wing A (Lily) = Gr + 1st to 7th Floor Building 2 -Wing B (Orchid) = Gr + 1st to 7th Floor Total Net Built-up Area : 11405.84 Sq.m
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved Built-up area of Building 1 & 2 (Sq.Mt) |  |  | 5392.96
Approved no of units |  |  | Flats - 112, Shops - 24
Approved no of Floors |  |  | Building No.1-Wing A (Lily) = Gr + 1st to 7th Floor Building No.2 -Wing B (Orchid) = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Building 1-Wing A (Lily) = Gr + 1st to 7th Floor
Building 2 -Wing B (Orchid) = Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Grand Club House, Indoor Gymnasium, Fitted Kitchen, Landscape Garden, Kids Play Area, Sr. Citizen Sitting Area, Yoga Deck, Jogging Track, Gazebo Sitting, Power Backup for Lifts and Common Area, EV Charging, High Speed Elevators, AC Fitted Bed Room etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building 1-Wing A (Lily) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 6 Slab Completed | , RCC upto 6 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 6 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 40% |  | 67.5% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 6 | 75% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building 2 -Wing B (Orchid) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 6 Floor, External Plaster upto 3 Floor Completed | , Internal Plaster upto 6 Floor, External Plaster upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 6 Floor, External Plaster upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 68.21% |  | 86.43% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 42.86% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5000 |  |  | 4K to 5K | RATE 4900 by SMITH VERBAL & COST SHEET On 02/08/2025
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 9000 |  |  |  | Park 3L by Smith On 07/08/2025
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 180000 |  |  |  | RATE 5000 by smith on 08/08/2025
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 50000
Advance Maintenance Charges |  |  |  |  | 30000
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 4000
Commercial Area Details : Shop
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A (Lily) |  | 12 |  | 1034.2374 |  | 1603.068
Wing B (Orchid) |  | 12 |  | 1034.2374 |  | 1603.068
Total |  | 24 |  | 2068.4748 |  | 3206.136
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A (Lily) |  | 56 |  | 26429.818 |  | 44180
Wing B (Orchid) |  | 56 |  | 26429.818 |  | 44180
Total |  | 112 |  | 52859.6359 |  | 88360
Grand Total |  | 136 |  | 54928.1107 |  | 91566.136
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Building No.1
Wing A (Lily)
Ground Floor For Commercial, Lobby, Meter Room & Parking
1 |  | Shop | 98.3291 | 0 | 152.4102 | Ground Floor For Commercial, Lobby, Meter Room & Parking |  | 9.135
2 |  | Shop | 74.5945 | 0 | 115.6215
3 |  | Shop | 91.5478 | 0 | 141.8991 |  |  | 8.505
4 |  | Shop | 91.5478 | 0 | 141.8991
5 |  | Shop | 67.8132 | 0 | 105.1105 |  |  | 6.3
6 |  | Shop | 93.2485 | 0 | 144.5352
7 |  | Shop | 93.2485 | 0 | 144.5352
8 |  | Shop | 67.8132 | 0 | 105.1105
9 |  | Shop | 91.5478 | 0 | 141.8991
10 |  | Shop | 91.5478 | 0 | 141.8991
11 |  | Shop | 74.5945 | 0 | 115.6215
12 |  | Shop | 98.4045 | 0 | 152.527
Building No.2
Wing B (Orchid)
Ground Floor For Lobby, Meter Room & Parking
1 |  | Shop | 98.3291 | 0 | 152.4102 | Ground Floor For Lobby, Meter Room & Parking
2 |  | Shop | 74.5945 | 0 | 115.6215
3 |  | Shop | 91.5478 | 0 | 141.8991
4 |  | Shop | 91.5478 | 0 | 141.8991
5 |  | Shop | 67.8132 | 0 | 105.1105
6 |  | Shop | 93.2485 | 0 | 144.5352
7 |  | Shop | 93.2485 | 0 | 144.5352
8 |  | Shop | 67.8132 | 0 | 105.1105
9 |  | Shop | 91.5478 | 0 | 141.8991
10 |  | Shop | 91.5478 | 0 | 141.8991
11 |  | Shop | 74.5945 | 0 | 115.6215
12 |  | Shop | 98.4045 | 0 | 152.527
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
45%
Building No.1
Wing A (Lily) | [7 empty] | 10.764
1st Floor For Residential | [9 empty] | b
1 |  | 1BHK | 404.8556 | 55.3593 | 725 | 1st Floor For Residential |  | 31.4075 | 5.0875 |  | 4136.5517 | 725 | 1.7908
2 |  | 2BHK | 539.0611 | 55.3593 | 930 | [5 empty] | 3224.7312 | 930 | 1.7252
3 |  | 2BHK | 539.0611 | 55.3593 | 930 |  |  | 38.715 |  | 8.635 | 3224.7312 | 930 | 1.7252
4 |  | 1BHK | 404.8663 | 55.3593 | 725 |  |  | 31.4075 |  | 5.143 | 4136.5517 | 725 | 1.7907
5 |  | 1BHK | 404.8663 | 56.7478 | 725 |  |  |  |  | 5.2725 | 4136.5517 | 725 | 1.7907
6 |  | 2BHK | 539.0611 | 56.7586 | 930 | [5 empty] | 3224.7312 | 930 | 1.7252
7 |  | 2BHK | 539.0611 | 55.3593 | 930 | [5 empty] | 3224.7312 | 930 | 1.7252
8 |  | 1BHK | 404.8556 | 55.3593 | 725 | [5 empty] | 4136.5517 | 725 | 1.7908
2nd, 4th & 6th Floor | [7 empty] | 4500
1 |  | 1BHK | 404.8556 | 0 | 635 | 2nd, 4th & 6th Floor |  | 2857500 | 5118.1102 | 4722.8346 |  | 635 | 1.5685
2 |  | 2BHK | 539.0611 | 0 | 840 |  |  | 3780000 | 5654.7619 |  |  | 840 | 1.5583
3 |  | 2BHK | 539.0611 | 0 | 840 |  |  | 3780000 | 4760.7143 |  |  | 840 | 1.5583
4 |  | 1BHK | 404.8663 | 0 | 635 |  |  | 2857500 |  |  |  | 635 | 1.5684
5 |  | 1BHK | 404.8663 | 0 | 635 |  |  | 2857500 |  |  |  | 635 | 1.5684
6 |  | 2BHK | 539.0611 | 0 | 840 |  |  | 3780000 | 5236.9048 |  |  | 840 | 1.5583
7 |  | 2BHK | 539.0611 | 0 | 840 |  |  | 3780000 |  |  |  | 840 | 1.5583
8 |  | 1BHK | 404.8556 | 0 | 635 |  |  | 2857500 |  |  |  | 635 | 1.5685
3rd, 5th & 7th Floor
1 |  | 1BHK | 404.8556 | 55.3593 | 725 | 3rd, 5th & 7th Floor
2 |  | 2BHK | 539.0611 | 55.3593 | 930
3 |  | 2BHK | 539.0611 | 55.3593 | 930
4 |  | 1BHK | 404.8663 | 55.3593 | 725
5 |  | 1BHK | 404.8663 | 56.7478 | 725
6 |  | 2BHK | 539.0611 | 56.7586 | 930
7 |  | 2BHK | 539.0611 | 55.3593 | 930
8 |  | 1BHK | 404.8556 | 55.3593 | 725
Building No.2
Wing B (Orchid)
1st Floor For Residential
1 |  | 1BHK | 404.8556 | 55.3593 | 725 | 1st Floor For Residential
2 |  | 2BHK | 539.0611 | 55.3593 | 930
3 |  | 2BHK | 539.0611 | 55.3593 | 930
4 |  | 1BHK | 404.8663 | 55.3593 | 725
5 |  | 1BHK | 404.8663 | 56.7478 | 725
6 |  | 2BHK | 539.0611 | 56.7586 | 930
7 |  | 2BHK | 539.0611 | 55.3593 | 930
8 |  | 1BHK | 404.8556 | 55.3593 | 725
2nd, 4th & 6th Floor
1 |  | 1BHK | 404.8556 | 0 | 635 | 2nd, 4th & 6th Floor
2 |  | 2BHK | 539.0611 | 0 | 840
3 |  | 2BHK | 539.0611 | 0 | 840
4 |  | 1BHK | 404.8663 | 0 | 635
5 |  | 1BHK | 404.8663 | 0 | 635
6 |  | 2BHK | 539.0611 | 0 | 840
7 |  | 2BHK | 539.0611 | 0 | 840
8 |  | 1BHK | 404.8556 | 0 | 635
3rd, 5th & 7th Floor
1 |  | 1BHK | 404.8556 | 55.3593 | 725 | 3rd, 5th & 7th Floor
2 |  | 2BHK | 539.0611 | 55.3593 | 930
3 |  | 2BHK | 539.0611 | 55.3593 | 930
4 |  | 1BHK | 404.8663 | 55.3593 | 725
5 |  | 1BHK | 404.8663 | 56.7478 | 725
6 |  | 2BHK | 539.0611 | 56.7586 | 930
7 |  | 2BHK | 539.0611 | 55.3593 | 930
8 |  | 1BHK | 404.8556 | 55.3593 | 725
Remarks:
* | Building No.1 & 2 = Construction work is in process.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Cantilever Open Balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Recommended Rates & Other Charges of the Property have been revised on 02/08/2025, 07/08/2025 & 08/08/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nitesh patil |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Anant Serene Park
Layout :
Google Map :
Formulas:
Wardoli = [Wardoli, row above]
Wing A (Lily)
Wing B (Orchid)
A Wing
A Wing
A Wing
B Wing
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC