## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 21/07/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-07-21
Name of the builder |  |  |  | Mr. Mangal Arjun Varatha
Name of the builder company |  |  |  | M/s. Varatha Properties
Name of the Project |  |  |  | Armaan Lotus
Contact Details ( Name & Contact No.) |  |  |  | 9820524525
Site Meet Contact Details ( Name & Contact No.) |  |  |  | Mr. Arman : 9820524525
Name / No of the Building |  |  |  | Building No.1 (Wing A & B)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P99000027113
Project location details |  | Armaan Lotus, Survey No.148(Pt), near Arjun Apartment, Achole Road, Achole, Nalasopara (East), Vasai, Palghar - 401209.
Survey No |  | 148(Pt)
Road |  | Achole Road |  | Locality/Village |  | Achole
City |  | Nalasopara (East) |  | District |  | Palghar
Taluka |  | Vasai |  | Pin Code |  | 401209
Nearby Landmark |  | Arjun Apartment |  | Distance from city centre: |  | 0.450 KM from Nalasopara Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Reliable Prestige 1
West | NA | NA |  |  | Lucky Rahbat Apartment
North | NA | NA |  |  | Arjun Apartment
South | NA | NA |  |  | Achole Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.4172891,72.8228493
Location Link |  | https://goo.gl/maps/PhKcJjVEPPUM2XLE8?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3398.37
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 3398.37
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Vasai-Virar City Municipal Corporation
Layout Approval No |  | VVCMC/AMEND/BP/VP4985/173/2020-21 |  |  | Dated | 2021-01-14
Approved Floor plan No. (Gr. + 2nd Floor) |  | VVCMC/AMEND/BP/VP4985/173/2020-21 |  |  | Dated | 2021-01-14
Approved Floor plan No. (3rd + 4th to 6th, 8th to 16th, 18th to 21st Floor) |  | VVCMC/AMEND/BP/VP4985/682/2021-22 |  |  | Dated | 2021-12-28
Commencement Certificate No. |  | VVCMC/AMEND/BP/VP4985/682/2021-22 |  |  | Dated | 2021-12-28
Valid Up to: Building No.1 (Wing A & B) = Gr/St + 1st to 21st Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 3398.37
Approved no of units |  |  | Flats - 153, Shops - 16, Offices -52
Approved no of Floors |  |  | Building No.1(Wing A & B) = Gr/St + 1st to 21st Floor
Proposed no of Floors |  |  | Building No.1(Wing A & B) = Gr/St + 1st to 21st Floor
Building No.1 = (Wing C) = Gr/St + 1st to 11th Floor
Expected Completion |  |  | As per RERA - 30/06/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 (Wing A) = Gr/St + 1st to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 21 Slab Completed, Brickwork upto 16 Floor Completed, Internal Plaster upto 10 Floor Completed, External Plaster upto 3 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 21 Slab Completed, Brickwork upto 16 Floor Completed, Internal Plaster upto 10 Floor Completed, External Plaster upto 3 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 58.9% |  | 80.54% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 21 | 95.45% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 16 | 76.19% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 10 | 47.62% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 14.29% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Building No.1(Wing B) = Gr/St + 1st to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 21 Slab Completed, Brickwork upto 18 Floor Completed, Internal Plaster upto 14 Floor Completed, External Plaster upto 5 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 21 Slab Completed, Brickwork upto 18 Floor Completed, Internal Plaster upto 14 Floor Completed, External Plaster upto 5 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 61.99% |  | 82.45% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 21 | 95.45% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 18 | 85.71% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 14 | 66.67% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 23.81% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 7300
Recommended rate of the shop Per Sq. Ft. (on Saleable area) |  |  |  |  | 14000
Recommended rate of the Office Per Sq. Ft. (on Saleable area) |  |  |  |  | 10000
Floor Rise Rate Per Sq.ft |  |  |  |  | From 7th Floor Rs 30/- per Sft
Development Charges
Club Charges
Legal Services Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society & Development Charges |  |  |  |  | 190000
Maintenance for 18th Months |  |  |  |  | 120000
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 5840
Commercial Area Details for Shops
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 (Wing A & B) |  | 16 |  | 4287.3012 |  | 6645.3169
Commercial Area Details for Offices
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 (Wing A & B) |  | 52 |  | 9819.1361 |  | 15219.6609
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 (Wing A & B) |  | 153 |  | 74290.6254 |  | 111949.8652
C Wing |  | 141 |  | 31049.7268 |  | 46574.5901
Total |  | 294 |  | 105340.3521 |  | 158524.4554
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Building No.1(Wing A & B)
Ground Floor for Commercial & Parking
1 |  | Shop | 306.4511 | 0 | 474.9992 | Ground Floor for Commercial & Parking
2 |  | Shop | 183.8491 | 0 | 284.9661
3 |  | Shop | 257.4749 | 0 | 399.0861
4 |  | Shop | 320.0137 | 0 | 496.0213
5 |  | Shop | 335.8368 | 0 | 520.547
6 |  | Shop | 482.7654 | 0 | 748.2864
7 |  | Shop | 339.066 | 0 | 525.5523
8 |  | Shop | 203.5472 | 0 | 315.4982
9 |  | Shop | 203.5472 | 0 | 315.4982
10 |  | Shop | 203.5472 | 0 | 315.4982
11 |  | Shop | 266.1937 | 0 | 412.6003
12 |  | Shop | 329.2708 | 0 | 510.3697
13 |  | Shop | 248.1102 | 0 | 384.5708
14 |  | Shop | 227.8739 | 0 | 353.2045
15 |  | Shop | 174.915 | 0 | 271.1182
16 |  | Shop | 204.8389 | 0 | 317.5003
1st & 2nd Floor
1 |  | Office | 160.0607 | 0 | 248.0941 | 1st & 2nd Floor
2 |  | Office | 124.97 | 0 | 193.7036
3 |  | Office | 160.0607 | 0 | 248.0941
4 |  | Office | 160.0607 | 0 | 248.0941
5 |  | Office | 124.97 | 0 | 193.7036
6 |  | Office | 160.0607 | 0 | 248.0941
7 |  | Office | 160.0607 | 0 | 248.0941
8 |  | Office | 124.97 | 0 | 193.7036
9 |  | Office | 160.0607 | 0 | 248.0941
10 |  | Office | 160.0607 | 0 | 248.0941
11 |  | Office | 179.9741 | 0 | 278.9598
12 |  | Office | 224.6447 | 0 | 348.1993
13 |  | Office | 128.9527 | 0 | 199.8767
14 |  | Office | 176.7449 | 0 | 273.9546
15 |  | Office | 206.7764 | 0 | 320.5035
16 |  | Office | 216.787 | 0 | 336.0198
17 |  | Office | 311.0796 | 0 | 482.1734
18 |  | Office | 216.787 | 0 | 336.0198
19 |  | Office | 206.7764 | 0 | 320.5035
20 |  | Office | 206.7764 | 0 | 320.5035
21 |  | Office | 206.7764 | 0 | 320.5035
22 |  | Office | 397.6222 | 0 | 616.3143
23 |  | Office | 205.3771 | 0 | 318.3345
24 |  | Office | 185.4637 | 0 | 287.4688
25 |  | Office | 140.0396 | 0 | 217.0614
26 |  | Office | 203.6549 | 0 | 315.6651
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building No.1(Wing A & B)
3rd Floor for Residential
1 |  | 1BHK | 357.3379 | 75.0789 | 611.0857 | 3rd Floor for Residential |  |  | 25.8475
2 |  | 1BHK | 357.3379 | 63.7767 | 599.7835
3 |  | 2BHK | 531.9569 | 228.6543 | 874.1534
4 |  | 2BHK | 540.2452 | 118.4578 | 869.5966
5 |  | 2BHK | 540.2452 | 145.0987 | 882.9171
6 |  | 2BHK | 540.2452 | 108.0706 | 864.403
7 |  | 2BHK | 513.9003 | 205.9153 | 839.4888
8 |  | 1BHK | 371.1427 | 22.2007 | 578.9148
9 |  | 1BHK | 371.1427 | 22.2007 | 578.9148
4th to 6th, 8th to 16th, 18th to 21st Floor | [7 empty] | On Site, All Incl. | Costsheet | Housing | dwello | MIS
1 |  | 1BHK | 388.984 | 0 | 583.4761 | 4th to 6th, 8th to 16th, 18th to 21st Floor |  | 10111.8114 | 9116.055 | 6495.5534 | 7026.852 | 5000-6500
2 |  | 1BHK | 388.984 | 0 | 583.4761 |  |  | 8238.5555
3 |  | 2BHK | 568.4468 | 0 | 852.6703 |  |  | 6331.8732 | 9167.0841 | 6321.3182 | 7036.7178
4 |  | 2BHK | 573.8288 | 0 | 860.7433 |  |  | 4802765.7775 | 9441.8398 | 6453.7247
5 |  | 2BHK | 573.8288 | 0 | 860.7433 |  |  | 6272.4859 | 9441.8398 | 6453.7247
6 |  | 2BHK | 573.8288 | 0 | 860.7433 |  |  |  | 9143.8416 | 6325.9281
7 |  | 2BHK | 547.4839 | 0 | 821.2259 |  |  |  | 9262.1321 | 6410.0498
8 |  | 1BHK | 385.0283 | 0 | 577.5424
9 |  | 1BHK | 385.0283 | 0 | 577.5424
7th Floor
3 |  | 2BHK | 559.7011 | 0 | 839.5516 | 7th Floor
4 |  | 2BHK | 624.6349 | 0 | 936.9524 | 7th Floor
5 |  | 2BHK | 624.6349 | 0 | 936.9524 | 7th Floor
6 |  | 2BHK | 581.9557 | 0 | 872.9335 | 7th Floor
C Wing
Ground Floor for Parking
1st to 7th, 9th to 11th Floor
1 |  | MP Room | 206.8841 | 0 | 310.3261 | 1st to 7th, 9th to 11th Floor
2 |  | 1RK | 434.2198 | 0 | 651.3296 | 1st to 7th, 9th to 11th Floor
3 |  | MP Room | 197.5194 | 0 | 296.2791 | 1st to 7th, 9th to 11th Floor
4 |  | MP Room | 178.3595 | 0 | 267.5392 | 1st to 7th, 9th to 11th Floor
5 |  | MP Room | 206.8841 | 0 | 310.3261 | 1st to 7th, 9th to 11th Floor
6 |  | 1BHK | 304.6212 | 0 | 456.9318 | 1st to 7th, 9th to 11th Floor
7 |  | MP Room | 178.3595 | 0 | 267.5392 | 1st to 7th, 9th to 11th Floor
8 |  | MP Room | 201.0715 | 0 | 301.6073 | 1st to 7th, 9th to 11th Floor
9 |  | MP Room | 174.4844 | 0 | 261.7267 | 1st to 7th, 9th to 11th Floor
10 |  | MP Room | 178.79 | 0 | 268.1851 | 1st to 7th, 9th to 11th Floor
11 |  | MP Room | 201.0715 | 0 | 301.6073 | 1st to 7th, 9th to 11th Floor
12 |  | MP Room | 189.0158 | 0 | 283.5238 | 1st to 7th, 9th to 11th Floor
13 |  | MP Room | 206.8841 | 0 | 310.3261 | 1st to 7th, 9th to 11th Floor
8th Floor (Part Refuge Area)
1 |  | MP Room | 206.8841 | 0 | 310.3261 | 8th Floor (Part Refuge Area)
2 |  | 1RK | 434.2198 | 0 | 651.3296 | 8th Floor (Part Refuge Area)
3 |  | MP Room | 197.5194 | 0 | 296.2791 | 8th Floor (Part Refuge Area)
4 |  | MP Room | 178.3595 | 0 | 267.5392 | 8th Floor (Part Refuge Area)
5 |  | MP Room | 206.8841 | 0 | 310.3261 | 8th Floor (Part Refuge Area)
6 |  | 1RK | 304.6212 | 0 | 456.9318 | 8th Floor (Part Refuge Area)
7 |  | MP Room | 178.3595 | 0 | 267.5392 | 8th Floor (Part Refuge Area)
8 |  | MP Room | 201.0715 | 0 | 301.6073 | 8th Floor (Part Refuge Area)
9 |  | MP Room | 174.4844 | 0 | 261.7267 | 8th Floor (Part Refuge Area)
10 |  | MP Room | 178.79 | 0 | 268.1851 | 8th Floor (Part Refuge Area)
11 |  | Refuge Area |  |  |  | 8th Floor (Part Refuge Area)
12 | [5 empty] | 8th Floor (Part Refuge Area)
13 |  | MP Room | 206.8841 | 0 | 310.3261 | 8th Floor (Part Refuge Area)
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + D.B Area + F.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Sohail - 9820524525.
* | On RERA site, A, B, C Wings are registered but we have received only A & B Wing's Builder details.
* | We have updated approved floor plan of A & B Wing (on 28/07/2022)
* | Please provide approved floor plan of 7th & 17th Floor.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Armaan Lotus
Google Map :
Formulas:
Achole = [Achole, row above]
Wing B
A
B
A Wing
A Wing
A Wing
B Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted