## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 25/07/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-07-25
Name of the builder |  |  |  |  | Mr.Sachin Shantilal Joshi
Name of the builder company |  |  |  |  | M/s.Guru Krupa Infra Creations.
Name of the Project |  |  |  |  | Anand Park Mamta Heights
Contect Details ( Name & Contect No.) |  |  |  |  | 2226844679
Name / No of the Building |  |  |  |  | Building No.1 (Dharmi) Building No.2 (Zeal) - A & B Wings
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P99000004112
Project location details |  | Anand Park Mamta Heights, G No.2, Boisar Road, Maan, Boisar, Palghar, Palghar.
G No |  | 2
Road |  | Boisar Road |  |  | Village |  | Maan
City |  | Boisar |  |  | District |  | Palghar
Taluka |  | Palghar |  |  | Pin Code |  | 401501
Near by Landmark |  | Petrol Pump & Sai Complex |  |  | Distance from city centre: |  | About 6.9Km from Umroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Land |  | Open Land |  | Road |  | Open Land
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.77899208, 72.79546215
Location Link |  | https://goo.gl/maps/DHD222W48DeKEdMV7?coh=178572&entry=tt
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 2480
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 2232
Total number of Buildings |  |  |  |  | 02 Buildings (02 Wings)
Approval Detail : Plan approval
Layout Approval No |  | MHSL/K-1/T-1/NAP/SAR-80/2019 |  |  |  | Dated | 10/01/2020.
Approved Floor plan No. (Building no.1) |  | MHSL/K-1/MJ-1/NAP/SAR/194/14 |  |  |  | Dated | 16/06/2015.
Approved Floor plan No. (Building no.2) |  | MHSL/K-1/T-1/NAP/SAR-80/2019 |  |  |  | Dated | 10/01/2020.
Commencement Certificate No. |  | MHSL/K-1/T-1/NAP/SAR-80/2019 Valid Up to: Building No.1 & Building No.2(A & B wing) = G + 3rd Floor |  |  |  | Dated | 10/01/2020.
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 10/01/2020. |  | Expected Completion |  | 2025-03-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 2232 |  | Approved no of units |  | Flats = 61
Approved no of Floors |  | Building No.1 & 2 (A & B wing) = G + 1st to 3rd Floor
Approved no of Floors |  | Building No.1 = G + 1st to 3rd Floor Building No.2 (A & B wing) = G + 1st to 4th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Building No.1 (Dharmi) = G + 1st to 3rd Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 100% |  | 100% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 100% | [5 empty] | Plinth in process | 2.25
Possession |  | 3 | 100% | [5 empty] | Plinth completed | 3
Construction details: |  | Building No.2 (Zeal) (Wing A & B) = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 2 Floor, Flooring upto 2 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 2 Floor, Flooring upto 2 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 77.5% |  | 90% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 50% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 50% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Stage of construction Building No.2 (Zeal) - B Wing: Plinth & RCC slab work completed. Brick upto 2nd floor work completed. Other work are in process…
|  | Type of Work |  |  | % Complition
|  | Plinth |  |  | 100%
|  | RCC |  |  | 100%
|  | Brick |  |  | 100%
|  | Plaster |  |  | 0%
|  | Flooring |  |  | 0%
|  | Painting & Wooden Work |  |  | 0%
|  | Finishing |  |  | 0%
% Progress |  |  | 65% |  | % Disbursement |  |  | 75%
Wheather the construction is as per approved Building plan : Under Construction.
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3200
Development Charges, Electric meter,Water meter | [5 empty] | 200000/-
Society & maintenance Charges | [5 empty] | 75000/-
Recommended rate of Parking | [5 empty] | 100000/-
Distressed valuation of the Property | [5 empty] | 2560
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
Building No.1 |  | 23 | 7421.2398 |  |  | 10983.4349
Building No.2 - A Wing |  | 16 | 6025.0414 |  |  | 9110
Building No.2 - B Wing |  | 22 | 10018.3777 |  |  | 14925.2263
Total |  | 61 | 23464.6589 |  |  | 35018.6612
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No.1 (Dharmi)
Ground Floor is for Parking
1st to 2nd Floor
1 |  | 1 RK | 325.0728 |  | 0 | 481.1077 | N | 1st to 2nd Floor
2 |  | 1 RK | 324.7499 |  | 0 | 480.6298 | N
3 |  | 1 RK | 312.0484 |  | 0 | 461.8316 | N
4 |  | 1 RK | 316.2463 |  | 0 | 468.0446 | N
5 |  | 1 RK | 325.0728 |  | 0 | 481.1077 | N
6 |  | 1 RK | 324.7499 |  | 0 | 480.6298 | N
7 |  | 1 RK | 324.7499 |  | 0 | 480.6298 | N
8 |  | 1 RK | 325.0728 |  | 0 | 481.1077 | N
3rd Floor (Part Terrace Area)
1 |  | 1 RK | 325.0728 |  | 0 | 481.1077 | N | 3rd Floor
2 |  | 1 RK | 324.7499 |  | 0 | 480.6298 | N
3 |  | 1 RK | 316.2463 |  | 0 | 468.0446 | N
4 |  | 1 RK | 325.0728 |  | 0 | 481.1077 | N
5 |  | 1 RK | 324.7499 |  | 0 | 480.6298 | N
6 |  | 1 RK | 324.7499 |  | 0 | 480.6298 | N
7 |  | 1 RK | 325.0728 |  | 0 | 481.1077 | N
Building No.2 (Zeal)
A Wing
Ground Floor is for Residential
1 |  | 1BHK | 382.0144 |  | 0 | 575 | N | Ground Floor is for Residential |  | 1.5052
2 |  | 2 BHK | 454.779 |  | 0 | 690 | N |  |  | 1.5172
3 |  | 1 RK | 300.4232 |  | 0 | 450 | N |  |  | 1.4979
4 |  | 1 RK | 225.7211 |  | 0 | 340 | N |  |  | 1.5063
1st & 2nd Floor
1 |  | 1BHK | 448.9664 |  | 0 | 675 | N | 1st & 2nd Floor |  | 1.5035
2 |  | 2 BHK | 533.8944 |  | 0 | 795 | N |  |  | 1.4891
3 |  | 1 RK | 341.4341 |  | 0 | 475 | N |  |  | 1.3912
4 |  | 1 RK | 307.0969 |  | 0 | 455 | N |  |  | 1.4816
3rd Floor
1 |  | 1 RK | 301.8226 |  | 124.5395 | 575 | N | 3rd Floor |  | 1.9051
2 |  | 1 BHK | 448.9664 |  | 72.5494 | 750 | N |  |  | 1.6705
3 |  | 1 RK | 341.4341 |  | 0 | 475 | N |  |  | 1.3912
4 |  | 1 RK | 307.0969 |  | 0 | 455 | N |  |  | 1.4816
B Wing
Ground Floor is for Parking & Residential
1 |  | 1 RK | 270.8222 |  | 0 | 410.2957 | N | Ground Floor is for Parking & Residential
2 |  | 1 BHK | 373.1879 |  | 0 | 560 | N
3 |  | 1 RK | 253.1693 |  | 0 | 380 | N
4 |  | 1 RK | 245.4192 |  | 0 | 370 | N
5 |  | 1 BHK | 382.0144 |  | 0 | 575 | N
6 |  | 1 RK | 253.1693 |  | 0 | 380 | N
1st & 2nd Floor
1 |  | 1 RK | 307.0969 |  | 0 | 455 | N | 1st & 2nd Floor
2 |  | 1 BHK | 426.4697 |  | 0 | 620 | N
3 |  | 1 RK | 288.5828 |  | 0 | 429.9884 | N
4 |  | 1 BHK | 448.9664 |  | 0 | 665 | N
5 |  | 1 BHK | 448.9664 |  | 0 | 675 | N
6 |  | 1 RK | 288.5828 |  | 0 | 429.9884 | N
3rd Floor
1 |  | 1 RK | 307.0969 |  | 0 | 455 | N | 3rd Floor
2 |  | 1 BHK | 423.5634 |  | 0 | 620 | N
3 |  | 1 BHK | 441.9698 |  | 0 | 675 | N
4 |  | 1 BHK | 441.9698 |  | 0 | 675 | N
Remarks:
1. Building No.1 (Dharmi) = All work completed. Please provide OC. Building No.2 (Zeal) = Construction work was not active at the time of visit. Gate was locked. 2. We considered Building No.2 (A & B Wing) Saleable area as per Builder area sheet & Building No.1 Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. We update Building No.2 Approved Plan & CC (on 08/02/2021) 9. Please provide Revised plans & CC of Building No.1 & 2 10. Construction stage is calculated as per proposed no of Floors. 11. As per RERA, completion period of project Anand Park Mamta Heights is expired on 30/03/2025 but still Building No.2 (Zeal) is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report Prepared By : |  |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Anand Park Mamta Heights
Google Map :

## B1
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 4 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 3 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 3 | 100% |  | Panvel |  | 300000/-
Wood & painting | 3 | 3 | 100% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 2 | 66.67% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 10 | 5 | 3.3333
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 5 | 5 | 3.3333
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 10 | 5
Wood & painting | 5 | 5
Finishing | 3.3333 | 3.3333
total | 93.33% | 98.33% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B2A
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 4 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 0.5 | 16.67% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 3 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 1.6667 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 1.6667 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 1.6667 | 1.6667
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 66.67% | 76.67% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B2B
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 4 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 3 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 65% | 75% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.55 | 2.75 | 9.7625 | CB | 5.6 | 0.9 | 5.04 |  |  | 0
|  | 1.6 | 2.8 | 4.48 | FB |  |  | 0 |  |  | 0
|  | 1.8 | 1.2 | 2.16 |  |  |  | 0 |  |  | 0
| kitch | 1.05 | 1.25 | 1.3125 | CB |  |  | 0 |  |  | 0
|  | 2.6 | 2.75 | 7.15 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 267.6469 | 24.865 |  |  | 54.2506 | 5.04 |  | 0 | 0
|  |  | 321.8974 | 29.905