## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-07-28
Project Name |  | Arkade Rare |  | Date & Time of Site Visit |  | 29/07/2025 at 02:24PM
Name of the person met at site & Contact No. |  | Mr. Siddhesh CRM 8652734528 |  | Date of Report Release |  | 22/09/2025
Data from APF Request Form
Branch Name/ID |  | GHFL Thane |  | Request from GHF Employee |  | Miss Tanvi
Builder Group Name |  | Arkade Developers Limited |  | Developer Name |  | Arkade Developers Limited
Developer Office Address |  | Arkade House, 2nd Floor, Opp. Bhoomi Arkade, Next to Children's Academy, AS Marg, Ashok Nagar, Kandivali ( E ), Mumbai - 400101
Project Address | As per ARF | Arkade Rare, 403B ,403B/1 ,403B/2 ,403B/3 ,403B/4 at Kanjurmarg, Kurla, Mumbai Suburban, 400078
| As per Legal Documents | Proposed Residential Building on Plot bearing CTS No. 403B/1, 403B, 403B/2, 403B/3 and 403B/4, Kanjur West, Mumbai Situated in S Ward
| As per Actual at site | Arkade Rare, CTS No. 403B/1, 403B, 403B/2, 403B/3 and 403B/4, near Samriddhi Garden, Samriddhi Garden Road, Bhandup West, Kurla, Mumbai - 400078
Documents Provided by GHF |  | Approved Layout & Floor Plans, RERA certificate, Cost Sheet & EC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Municpal Council of Greater Mumbai (MCGM)
RERA Registration No. | : | P51800077307 |  | RERA Registration Validity | : | 2028-12-31
Project Launch Date | : | 2024-08-06 |  | Construction Start Date | : | 2024-05-01 |  | as per RERA 1st Architect letter
Proposed Date of Completion (As per RERA) | : | 2028-12-31 |  | Developer Bank Name (As per RERA) | : | HDFC BANK IFSC Code - HDFC0000667
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 11967.4
FSI/FAR Permissible | : | 1 |  | Net Plot Area (In Sq.Mt) | : | 10734.51
Permissible Built up Area (In Sq.Mt) | : | 31880.9 |  | Proposed Built up Area (In Sq.Mt) | : | 31880.9
Total Number of Units Approved | : | Flat = 432 Office = 47 |  | Total Number of Units Planned | : | As per RERA Site Flat = 432 & Office = 47 |  | 479
Latitude, Longitude | : | 19.144783,72.931719 |  | Landmark | : | Samriddhi Garden
Location Link | : | https://maps.app.goo.gl/sZKauiJa5SqJq3CZ9
Extra Amenities available | : | Kids Play Area, Multipurpose Court, Fitness Center, Swimming Pool, Tree house, Zem Garden, Kids Pool, etc. | [5 empty] | https://arkadeshubharambh.in/?utm_source=GoogleSearch&utm_medium=FE_03_AG_01_Phrasekw_Rare_p_arkade%20rare&utm_campaign=FE_03_Arkade_Shubharambh_Search_MaxConv_Brand_Keyword&utm_Display=FE_03_AG_01_AD_01_Rare_RSA&gad_source=1&gad_campaignid=22789493263&gbraid=0AAAAA-EUfy5bfnlJFQoiW_IbwQZ1CvqYC&gclid=CjwKCAjwv5zEBhBwEiwAOg2YKDbWK44501TEs3yFeLSV-tqvz9RxeJ6bA0mZgyHCMQ-dcoPGDw_msRoC9lUQAvD_BwE
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Concrete |  | Width of the Road | : | 12.20m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.6 KM from Bhandup Station (W) Road Bus Stop
Distance from the nearest School (Km) | : | About 1.3 KM from NES High School |  | Distance from Hospital (Km) | : | About 1.3K form Dr. Meena's Multispeciality Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.3KM from Neptune Magnet Mall. 2. Approx. 2.3 KM from DMart. |  | Distance from Railway Station (Km) | : | 0.8KM from Bhandup Railway Station 2.1KM from Kanjurmarg Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East | West
East |  | Other Plot / 12.20m Existing Road |  |  | Samriddhi Garden Road / Samriddhi Garden
West |  | Other Plot |  |  | Shreegan Apartment
North |  | Other Plot |  |  | Devi Dayal Compound
South |  | Other Plot |  |  | Ashtavinayak Group Auto Consultant
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing A |  | Sale | St + 5P + 6th to 21st Floor |  |  | St + 5P + 6th to 21st Floor |  | https://www.arkaderarebhandupwest.com/?utm_source=google&utm_medium=cpc&utm_campaign=Arkade+Rare+Central&utm_term=arkade%20rare&utm_Physical_Location=9062223&utm_Targetid=kwd-2321075479859&utm_Target=&utm_Placement=&utm_Adposition=&gad_source=1&gad_campaignid=21616592589&gbraid=0AAAAA9iUuL4ddRxdBNH9G9dpK8gf7qML2&gclid=CjwKCAjwv5zEBhBwEiwAOg2YKHwft_d7XSWvehr_4DS5HwhpdO0ZiDi51NnaGwuXr6Mu0mS_moXnEhoCZekQAvD_BwE
Wing B |  | Sale | St + 5P + 6th to 21st Floor |  |  | St + 5P + 6th to 21st Floor
Wing C |  | Sale | St + 5P + 6th to 21st Floor |  |  | St + 5P + 6th to 21st Floor
Wing D |  | Sale | St + 5P + 6th to 21st Floor |  |  | St + 5P + 6th to 21st Floor
Wing E |  | Sale | St + 5P + 6th to 21st Floor |  |  | St + 5P + 6th to 21st Floor
Wing F |  | Sale | St + 5P + 6th to 21st Floor |  |  | St + 5P + 6th to 21st Floor
Wing G |  | Sale | St + 5P + 6th to 21st Floor |  |  | St + 5P + 6th to 21st Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | P-18427/2023/(403B And Other)/S Ward/KANJUR-W/337/3/Amend |  |  |  | Date: | 2025-01-15
Approved Plan Details | : | P-18427/2023/(403B And Other)/S Ward/KANJUR-W/337/3/Amend |  |  |  | Date: | 2025-01-15
CC Details Valid Up to: |  | P-18427/2023/(403B And Other)/SWard/KANJUR-W/FCC/1/New |  |  |  | Date: | 2025-03-07
[6 empty] | Valid Upto Date | 2025-07-04
Further CC for Wing-A & B is granted upto 11th floor (by restricting C.C. of 12th to 21st floors of Wing A & B forFSI benefit of Amenity open space and BUA of Temporary structure) and full C.C. for wing C, D, E, F & G is granted, as per approved amended plans dated 15.01.2025, subject to timely renewal of B.G., SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction along with precautionary measures for air pollution
Airport Authority Clearance Details Valid Up to: |  | SNCR/WEST/B/021924/918016 |  |  |  | Date: | 02/04/2024
[6 empty] | Valid Upto Date: | 2032-03-31
Site Elevation (AMSL) = 16.9M Permissible Top Elevation (AMSL) = 166.9M
Fire Noc Valid Up to: | : | P-18427/2023/(403B And Other)/S Ward/ KANJUR-W-CFO/1/New. Wing A to G = St + 1st to 5th Podium + 6th to 21st Floor (Height = 69.95m) |  |  |  | Date: | 2023-11-07
Environmental Clearance Details Valid Up to: |  | IA/MH/INFRA2/461068/2024 |  |  |  | Date: | 2024-07-18
CTS no 403/B, 403/B/1, 403B/2, 403B/3 and 403/B/4 Total Plot Area = 11,967.40 sq. m
Construction Status | [7 empty] | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
Wing A= St + 5P + 6th to 21st Floor. |  |  | Basement | Ground |  | Podium | Floors | All work Completed. OC Received.
|  |  | 0 | 1 |  | 0 | 21 | Piling Work in process | 5.25
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Excavation in process | 10.5
Excavation |  | 21 | 100% | 27.27% |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed |  | Excavation Completed | 21
Plinth |  | 21 | 100% |  |  |  |  | Footing in Process | 4.2
RCC (Including podiums) |  | 2 | 9.091% |  |  |  |  | Footing Completed | 8.4
Brickwork |  | 0 | 0% |  |  |  |  | Basement 1 | 0
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 3 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Plinth in process | 14.7
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Electrical & Sanitary fittings |  | 0 | 0%
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status | [7 empty] | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
Wing B= St + 5P + 6th to 21st Floor. |  |  | Basement | Ground |  | Podium | Floors | All work Completed. OC Received.
|  |  | 0 | 1 |  | 0 | 21 | Piling Work in process | 5.25
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Excavation in process | 10.5
Excavation |  | 21 | 100% | 26.14% |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed |  | Excavation Completed | 21
Plinth |  | 21 | 100% |  |  |  |  | Footing in Process | 4.2
RCC (Including podiums) |  | 1 | 4.545% |  |  |  |  | Footing Completed | 8.4
Brickwork |  | 0 | 0% |  |  |  |  | Basement 1 | 0
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 3 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Plinth in process | 14.7
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Electrical & Sanitary fittings |  | 0 | 0%
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status | [7 empty] | Excavation work Completed. Plinth work completed
Wing C= St + 5P + 6th to 21st Floor. |  |  | Basement | Ground |  | Podium | Floors | All work Completed. OC Received.
|  |  | 0 | 1 |  | 0 | 21 | Piling Work in process | 5.25
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Excavation in process | 10.5
Excavation |  | 21 | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation Completed | 21
Plinth |  | 21 | 100% |  |  |  |  | Footing in Process | 4.2
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing Completed | 8.4
Brickwork |  | 0 | 0% |  |  |  |  | Basement 1 | 0
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 3 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Plinth in process | 14.7
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Electrical & Sanitary fittings |  | 0 | 0%
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status | [7 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed
Wing D= St + 5P + 6th to 21st Floor. |  |  | Basement | Ground |  | Podium | Floors | All work Completed. OC Received.
|  |  | 0 | 1 |  | 0 | 21 | Piling Work in process | 5.25
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Excavation in process | 10.5
Excavation |  | 21 | 100% | 31.82% |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed |  | Excavation Completed | 21
Plinth |  | 21 | 100% |  |  |  |  | Footing in Process | 4.2
RCC (Including podiums) |  | 6 | 27.27% |  |  |  |  | Footing Completed | 8.4
Brickwork |  | 0 | 0% |  |  |  |  | Basement 1 | 0
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 3 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Plinth in process | 14.7
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Electrical & Sanitary fittings |  | 0 | 0%
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status | [7 empty] | Excavation work Completed. Plinth work completed, RCC upto 5 Slab Completed
Wing E= St + 5P + 6th to 21st Floor. |  |  | Basement | Ground |  | Podium | Floors | All work Completed. OC Received.
|  |  | 0 | 1 |  | 0 | 21 | Piling Work in process | 5.25
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Excavation in process | 10.5
Excavation |  | 21 | 100% | 30.68% |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab Completed |  | Excavation Completed | 21
Plinth |  | 21 | 100% |  |  |  |  | Footing in Process | 4.2
RCC (Including podiums) |  | 5 | 22.73% |  |  |  |  | Footing Completed | 8.4
Brickwork |  | 0 | 0% |  |  |  |  | Basement 1 | 0
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 3 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Plinth in process | 14.7
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Electrical & Sanitary fittings |  | 0 | 0%
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status | [7 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed
Wing F= St + 5P + 6th to 21st Floor. |  |  | Basement | Ground |  | Podium | Floors | All work Completed. OC Received.
|  |  | 0 | 1 |  | 0 | 21 | Piling Work in process | 5.25
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Excavation in process | 10.5
Excavation |  | 21 | 100% | 31.82% |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed |  | Excavation Completed | 21
Plinth |  | 21 | 100% |  |  |  |  | Footing in Process | 4.2
RCC (Including podiums) |  | 6 | 27.27% |  |  |  |  | Footing Completed | 8.4
Brickwork |  | 0 | 0% |  |  |  |  | Basement 1 | 0
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 3 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Plinth in process | 14.7
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Electrical & Sanitary fittings |  | 0 | 0%
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status | [7 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed
Wing G= St + 5P + 6th to 21st Floor. |  |  | Basement | Ground |  | Podium | Floors | All work Completed. OC Received.
|  |  | 0 | 1 |  | 0 | 21 | Piling Work in process | 5.25
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Excavation in process | 10.5
Excavation |  | 21 | 100% | 31.82% |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed |  | Excavation Completed | 21
Plinth |  | 21 | 100% |  |  |  |  | Footing in Process | 4.2
RCC (Including podiums) |  | 6 | 27.27% |  |  |  |  | Footing Completed | 8.4
Brickwork |  | 0 | 0% |  |  |  |  | Basement 1 | 0
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 3 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Plinth in process | 14.7
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Electrical & Sanitary fittings |  | 0 | 0%
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 29.22%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 24000 to 25000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 800000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 5392.9766
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 13213.4894
Distress Value (Rs. Per sqft) |  |  |  |  | : | 4314.3813
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Office (Commercial Wing 1 + 2) |  | - |  | 47 |  | 19623.4178
Total |  | - |  | 47 |  | 19623.4178
Unit Details, Nomenclature and Area Details (Flat)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing A |  | - |  | 62 |  | 36567.6761
Wing B |  | - |  | 62 |  | 34359.5491
Wing C |  | - |  | 77 |  | 59303.9351
Wing D |  | - |  | 30 |  | 31881.8916 |  | 10.764
Wing E |  | - |  | 77 |  | 58612.8863
Wing F |  | - |  | 62 |  | 34759.7546 |  | Office 3, 4 & 5 in Commercial Wing 2
Wing G |  | - |  | 62 |  | 36556.4815
Total |  | - |  | 432 |  | 292042.1743
Grand Total |  | - |  | 479 |  | 311665.5922
Details of Residential & Commercial in Building
Flat/ Office No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | RERA Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Wing A, B & C
Commercial Wing 1 + 2
Ground Floor For Entrance Lobby, Commercial & Parking
1 |  | - | Office | 518.8248 | 0 | 0 | 518.8248
2 |  | - | Office | 590.836 | 0 | 0 | 590.836
3 |  | - | Office | 427.9766 | 0 | 0 | 427.9766
4 |  | - | Office | 583.0859 | 0 | 0 | 583.0859
5 |  | - | Office | 674.9028 | 0 | 0 | 674.9028
6 |  | - | Duplex Office (With 1st Floor) | 1015.691 | 0 | 0 | 1015.691
1st Podium Floor For Commercial
Duplex Office (With Ground Floor)
1 |  | - | Office | 213.6654 | 0 | 0 | 213.6654
2 |  | - | Office | 262.534 | 0 | 0 | 262.534
3 |  | - | Office | 210.6515 | 0 | 0 | 210.6515
4 |  | - | Office | 471.0326 | 0 | 0 | 471.0326
5 |  | - | Office | 489.3314 | 0 | 0 | 489.3314
6 |  | - | Office | 411.9383 | 0 | 0 | 411.9383
7 |  | - | Office | 302.0378 | 0 | 0 | 302.0378
8 |  | - | Office | 465.9736 | 0 | 0 | 465.9736
2nd Podium Floor
1 |  | - | Office | 585.6692 | 0 | 0 | 585.6692
2 |  | - | Office | 413.6605 | 0 | 0 | 413.6605
3 |  | - | Office | 213.6654 | 0 | 0 | 213.6654
4 |  | - | Office | 262.534 | 0 | 0 | 262.534
5 |  | - | Office | 210.6515 | 0 | 0 | 210.6515
6 |  | - | Office | 471.0326 | 0 | 0 | 471.0326
7 |  | - | Office | 489.3314 | 0 | 0 | 489.3314
8 |  | - | Office | 411.9383 | 0 | 0 | 411.9383
9 |  | - | Office | 302.0378 | 0 | 0 | 302.0378
10 |  | - | Office | 308.0657 | 0 | 0 | 308.0657 | 44.5904
11 |  | - | Office | 659.7256 | 0 | 0 | 659.7256
3rd & 4th Podium Floor
1 |  | - | Office | 585.6692 | 0 | 0 | 585.6692
2 |  | - | Office | 413.6605 | 0 | 0 | 413.6605
3 |  | - | Office | 213.6654 | 0 | 0 | 213.6654
4 |  | - | Office | 262.534 | 0 | 0 | 262.534 | 10.764
5 |  | - | Office | 210.6515 | 0 | 0 | 210.6515
6 |  | - | Office | 471.0326 | 0 | 0 | 471.0326 | 1
7 |  | - | Office | 489.3314 | 0 | 0 | 489.3314 | 2
8 |  | - | Office | 411.9383 | 0 | 0 | 411.9383 | 1
9 |  | - | Office | 302.0378 | 0 | 0 | 302.0378 | 1
10 |  | - | Office | 308.0657 | 0 | 0 | 308.0657 | 14
11 |  | - | Office | 659.7256 | 0 | 0 | 659.7256
5th Floor (Service Floor)
Wing A
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking | [7 empty] | 2
2nd & 3rd Podium Floor For Parking
4th Podium Floor For Courtyard, Fitness Center & Parking
5th Podium Floor For Amenity & Society Office
6th, 8th to 13th, 15th to 21st Floor For Residential
1 |  | - | 2BHK | 523.4533 | 0 | 0 | 523.4533 | 1
2 |  | - | 2BHK | 625.9266 | 0 | 0 | 625.9266
3 |  | - | 2BHK | 627.2183 | 0 | 0 | 627.2183
4 |  | - | 2BHK | 587.2838 | 0 | 0 | 587.2838
7th & 14th Floor (Part Refuge Area)
1 |  | - | 2BHK | 523.4533 | 0 | 0 | 523.4533 | 10.764
2 |  | - | 2BHK | 625.9266 | 0 | 0 | 625.9266
3 |  | Refuge Area | [5 empty] | 1
4 |  | - | 2BHK | 587.2838 | 0 | 0 | 587.2838 | 2
Wing B | [7 empty] | 24990.1375 |  | 25562.4307 | 22342.8025
Ground Floor For Entrance Lobby (Double Heighted) & Parking | [10 empty] | #REF!
1st Podium Floor For Meter Room & Parking | [7 empty] | 2 |  |  | #REF!
2nd & 3rd Podium Floor For Parking | [7 empty] | 25090.2686 |  |  | #REF!
4th Podium Floor For Courtyard, Fitness Center & Parking | [10 empty] | #REF!
5th Podium Floor For Amenity & Society Office
6th, 8th to 13th, 15th to 21st Floor For Residential
1 |  | - | 2BHK | 524.2068 | 0 | 0 | 524.2068 | 10.764
2 |  | - | 2BHK | 525.3908 | 0 | 0 | 525.3908
3 |  | - | 2BHK | 585.131 | 0 | 0 | 585.131 | 1
4 |  | - | 2BHK | 585.8845 | 0 | 0 | 585.8845 | 2
7th & 14th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | - | 2BHK | 524.2068 | 0 | 0 | 524.2068 | 1
2 |  | - | 2BHK | 525.3908 | 0 | 0 | 525.3908 | 14
3 |  | Refuge Area
4 |  | - | 2BHK | 585.8845 | 0 | 0 | 585.8845
Wing C
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking
2nd & 3rd Podium Floor For Parking | [7 empty] | 1
4th Podium Floor For Courtyard, Fitness Center & Parking
5th Podium Floor For Amenity
6th, 8th to 13th, 15th to 21st Floor For Residential
1 |  | - | 3BHK | 802.6715 | 0 | 0 | 802.6715
2 |  | - | 2BHK | 679.2084 | 0 | 0 | 679.2084
3 |  | - | 2BHK | 681.7918 | 51.129 | 0 | 732.9208 | 1
4 |  | - | 2BHK | 726.8929 | 0 | 0 | 726.8929
5 |  | - | 3BHK | 864.7798 | 48.3304 | 0 | 913.1101
7th Floor (Part Refuge Area)
1 |  | - | 3BHK | 802.6715 | 0 | 0 | 802.6715
2 |  | - | 2BHK | 679.2084 | 0 | 0 | 679.2084
3 |  | - | 2BHK | 681.7918 | 51.129 | 0 | 732.9208
4 |  | - | 2BHK | 726.8929 | 0 | 0 | 726.8929 | 10.764
5 |  | Refuge Area
14th Floor (Part Refuge Area & Society Office) | [7 empty] | 1
1 |  | - | 3BHK | 802.6715 | 0 | 0 | 802.6715 | 2
2 |  | - | 2BHK | 679.2084 | 0 | 0 | 679.2084 | 1
3 |  | Refuge Area | [5 empty] | 1
4 | [7 empty] | 1
- |  | Society Office | [5 empty] | 8
5 |  | - | 3BHK | 864.7798 | 48.3304 | 0 | 913.1101
Wing D
Ground Floor For Entrance Lobby (Double Heighted) & Parking | [7 empty] | 7
1st Podium Floor For Meter Room & Parking
2nd & 3rd Podium Floor For Parking
4th Podium Floor For Courtyard, Fitness Center & Parking | [7 empty] | 10.764
5th Podium Floor For Amenity
6th Floor For Void | [7 empty] | 1
8th, 10th, 12th, 14th, 16th, 18th, 20th & 21st Floor | [7 empty] | 2
1 |  | - | 3BHK | 1014.1841 | 47.7922 | 0 | 1061.9762 | 1
2 |  | - | 3BHK | 1015.691 | 47.7922 | 0 | 1063.4832 | 1
7th, 9th, 11th, 13th, 15th, 17th & 19th Floor (Refuge Area at Midlanding of Staircase) | [7 empty] | 14
1 |  | - | 3BHK | 1014.1841 | 47.7922 | 0 | 1061.9762
2 |  | - | 3BHK | 1015.691 | 47.7922 | 0 | 1063.4832
Wing E
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking
2nd & 3rd Podium Floor For Parking | [7 empty] | 1
4th Podium Floor For Courtyard, Fitness Center & Parking
5th Podium Floor For Amenity & Society Office (Wing D & Wing E)
6th, 8th to 13th, 15th to 21st Floor For Residential
1 |  | - | 3BHK | 863.4881 | 48.3304 | 0 | 911.8184
2 |  | - | 2BHK | 676.8403 | 0 | 0 | 676.8403
3 |  | - | 2BHK | 679.639 | 0 | 0 | 679.639 | 1
4 |  | - | 2BHK | 682.8682 | 51.2366 | 0 | 734.1048
5 |  | - | 3BHK | 802.6715 | 0 | 0 | 802.6715
7th Floor (Part Refuge Area)
1 |  | Refuge Area
2 |  | - | 2BHK | 676.8403 | 0 | 0 | 676.8403
3 |  | - | 2BHK | 679.639 | 0 | 0 | 679.639 | 10.764
4 |  | - | 2BHK | 682.8682 | 51.2366 | 0 | 734.1048
5 |  | - | 3BHK | 802.6715 | 0 | 0 | 802.6715
14th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | - | 3BHK | 863.4881 | 48.3304 | 0 | 911.8184 | 2
2 |  | Refuge Area | [5 empty] | 1
3 | [7 empty] | 1
4 |  | - | 2BHK | 682.8682 | 51.2366 | 0 | 734.1048 | 14
5 |  | - | 3BHK | 802.6715 | 0 | 0 | 802.6715
Wing F
Basement Floor For Plant Room
Ground Floor For Entrance Lobby (Double Heighted) & Parking
1st Podium Floor For Meter Room & Parking | [7 empty] | 2
2nd & 3rd Podium Floor For Parking
4th Podium Floor For Courtyard, Fitness Center & Parking
5th Podium Floor For Amenity & Society Office
6th, 8th to 13th, 15th to 21st Floor For Residential
1 |  | - | 2BHK | 609.673 | 0 | 0 | 609.673 | 10.764
2 |  | - | 2BHK | 586.5304 | 0 | 0 | 586.5304
3 |  | - | 2BHK | 525.3908 | 0 | 0 | 525.3908 | 1
4 |  | - | 2BHK | 524.2068 | 0 | 0 | 524.2068 | 1
7th & 14th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | - | 2BHK | 609.673 | 0 | 0 | 609.673 | 1
2 |  | Refuge Area | [5 empty] | 14
3 |  | - | 2BHK | 525.3908 | 0 | 0 | 525.3908
4 |  | - | 2BHK | 524.2068 | 0 | 0 | 524.2068
Wing G
Ground Floor For Entrance Lobby (Double Heighted), Meter Room & Parking
1st Podium Floor For Entrance Lobby Below | [7 empty] | 2
2nd Podium Floor For Fitness Center/Badminton Court & Parking
3rd & 4th Podium Floor For Parking
5th Podium Floor For Amenity & Society Office
6th, 8th to 13th, 15th to 21st Floor For Residential
1 |  | - | 2BHK | 587.2838 | 0 | 0 | 587.2838
2 |  | - | 2BHK | 625.9266 | 0 | 0 | 625.9266
3 |  | - | 2BHK | 625.9266 | 0 | 0 | 625.9266
4 |  | - | 2BHK | 523.8839 | 0 | 0 | 523.8839
7th & 14th Floor (Part Refuge Area)
1 |  | - | 2BHK | 587.2838 | 0 | 0 | 587.2838
2 |  | Refuge Area
3 |  | - | 2BHK | 625.9266 | 0 | 0 | 625.9266
4 |  | - | 2BHK | 523.8839 | 0 | 0 | 523.8839
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit (labour found).
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = RERA carpet + Balcony Area
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We have referred Approved Floor plans, CC & Fire Noc From MCGM site.
* | We have referred Airport Noc from AAI site.
* | As per the approved plans dated 15/01/2025 in Wing A, B & C are partially used for Commercial area (i.e Offices) from Gr + 1st to 4th Podium Floor And is mentioned in approved plans as Commercial Wing 1 & 2.
* | We have updated Environmental Clearance certificate on 30/07/2025
* | Validity of CC is expired on 04/07/2025. Provide revised approved CC.
Site & Building/Tower Photographs
Name of the Project |  |  | Arkade Rare
Project Site Address |  |  | Arkade Rare, 403B ,403B/1 ,403B/2 ,403B/3 ,403B/4 at Kanjurmarg, Kurla, Mumbai Suburban, 400078
Site Visit Date & Time |  |  | 29/07/2025 at 02:24PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Nainesh Tambe |  | Authorized Signatory Name & Signature
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per maps
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G184: Ready Recknor
Wing A
Wing B
Wing D
F
E
G
Wing A
Wing B
Wing C
Wing D
Wing E
Wing F
Wing G
Arkade Rare (Wing A to G)
A
B
C
D
E
F
G

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0