## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com | [9 empty] | EC & Fire NOC required
Valuation Report
Date: |  |  |  | 29/07/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-07-29 |  |  |  | 2024-01-12
Name of the builder group |  |  |  | Arihant Superstructures Limited
Name of the builder company |  |  |  | Arihant Superstructures Limited
Name of the Project |  |  |  | Arihant Aaradhya Phase I & II
Provided Contact Details ( Name & Contact No.) |  |  |  | Miss.Chaitali 9619007738
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Aman 9167277682 Mrs. Nisha 8657767248 |  |  |  | Mr. Rupesh 9594755288 | Mrs Nisha 8657767248
Name / No of the Building |  |  |  | Phase I - Valentia, Wesley, Laura, Mabel Phase II - Naldo, Osane, Patricia, Querida
Docouments Provided |  |  |  | Approved Plans, Cost Sheet |  |  |  | CC was refered from RERA site
RERA No. |  |  |  | Phase I - P51700045430 Phase II - P51700049981
Project location details |  | Arihant Aaradhya Phase I & II, Survey No.14/1, near Jay Ambe Park, Internal road, Bapgaon, Bapgaon, Bhiwandi, Bhiwandi, Thane - 421302.
Survey No |  | 14/1
Locality |  | Bapgaon
Road |  | Internal road |  | Locality/Village |  | Bapgaon
City |  | Bhiwandi |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421302
Nearby Landmark |  | Jay Ambe Park |  | Distance from city centre: |  | 5.7KM from Kalyan Junction Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Adj. S. No.13 & 19 |  |  | Jay Ambe Park
West | NA | Open Plot |  |  | Open Plot
North | NA | 12 M W Road |  |  | Internal Road
South | NA | Adj. S. No.118 |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.271635,73.144382
Location Link |  | https://goo.gl/maps/LvRsXwL7TivTvnUu9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 26144.99
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.5378
Total FSI availaible for the project |  |  |  | 2.6378
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 68966.49
Total number of Buildings |  |  |  | 8 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Town Planning, Thane
Layout Approval No |  | BS/Rekhankan/BP/Mouje-Bapgaon/T-Bhiwandi/SSTN/784 |  |  | Dated | 2022-03-14
Approved Floor plan No. |  | BS/Rekhankan/BP/Mouje-Bapgaon/T-Bhiwandi/SSTN/784 |  |  | Dated | 2022-03-14
Commencement-CC No Valid Up to: |  | Mahsul/K-1/T-8/B.P/Mj-Bapgaon-Bhiwandi/SR-09/2022 |  |  | Dated | 2022-03-24
Phase I Laura = G + 1st to 14th Floor Mable = G + 1st to 14th Floor Valentia = G + 1st to 14th Floor Wesley = G + 1st to 14th Floor Phase II Naldo = G + 1st to 14th Floor Osane = G + 1st to 14th Floor Patricia = G + 1st to 14th Floor Querida = G + 1st to 14th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 68966.49
Approved no of units |  |  | Flats - 852
Approved no of Floors |  |  | Laura, Mable, Valentia & Wesley = G + 1st to 14th Floor
Proposed no of Floors |  |  | Laura = G + 1st to 14th Floor Mable = G + 1st to 14th Floor
Mable = G + 1st to 14th Floor
Valentia = G + 1st to 14th Floor Wesley = G + 1st to 14th Floor
Naldo = G + 1st to 14th Floor
Osane = G + 1st to 14th Floor
Patricia = G + 1st to 14th Floor
Querida = G + 1st to 14th Floor
Expected Completion |  |  | As per RERA - 31/03/2029
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Clubhouse
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Mable = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 8 Floor, Painting upto 8 Floor Completed | , Flooring upto 8 Floor, Painting upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 8 Floor, Painting upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 83.57% |  | 92.86% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 57.14% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 57.14% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Laura = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 10 Floor, Flooring upto 2 Floor Completed | , External Plaster upto 10 Floor, Flooring upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 10 Floor, Flooring upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 73.57% |  | 89.29% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 71.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 14.29% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Valentia = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 13 Floor, Painting upto 12 Floor, Finishing upto 3 Floor Completed | , Flooring upto 13 Floor, Painting upto 12 Floor, Finishing upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 13 Floor, Painting upto 12 Floor, Finishing upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 89.64% |  | 94.64% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 92.86% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 85.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 21.43% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Wesley = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 13 Floor, Painting upto 12 Floor, Finishing upto 3 Floor Completed | , Flooring upto 13 Floor, Painting upto 12 Floor, Finishing upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 13 Floor, Painting upto 12 Floor, Finishing upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 89.64% |  | 94.64% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 92.86% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 85.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 21.43% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Naldo = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 9 Slab, Brickwork upto 5 Floor, Internal Plaster upto 2 Floor Completed | , RCC upto 9 Slab, Brickwork upto 5 Floor, Internal Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 9 Slab, Brickwork upto 5 Floor, Internal Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 37.75% |  | 65.5% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 9 | 60% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 5 | 35.71% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 2 | 14.29% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Osane = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 8 Slab, Brickwork upto 4 Floor Completed | , RCC upto 8 Slab, Brickwork upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 8 Slab, Brickwork upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 33.48% |  | 62.43% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 8 | 53.33% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 4 | 28.57% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Patricia = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 2 Slab Completed | , RCC upto 2 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 2 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 15.33% |  | 49% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 2 | 13.33% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Querida = G + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 10% |  | 45% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6000
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 200000 |  |  |  | DC add | 2023-04-28 | smithpal
Recommended rate of Parking |  |  |  |  | 250000
Distressed valuation of the Property |  |  |  |  | 4800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase I Flats | Laura | 110 |  | 40986.9439 |  | 61480.4159
| Mabel | 110 |  | 40986.9439 |  | 61480.4159
| Valentia | 110 |  | 40986.9439 |  | 61480.4159
| Wesley | 110 |  | 58265.1014 |  | 87397.6522
Phase II Flats | Naldo | 82 |  | 42908.9638 |  | 64363.4456
| Osane | 110 |  | 58258.0833 |  | 87387.125
| Patricia | 110 |  | 40986.9439 |  | 61480.4159
| Querida | 110 |  | 58258.0833 |  | 87387.125
Total |  | 852 |  | 381638.0075 |  | 572457.0113
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0
3 |  |  |  | 0 | 0
4 |  |  |  | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Phase I
Laura
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential | [9 empty] | 10.764
101,.., 1401 |  | 1 | 380.938 | 0 | 571.4069 | 1st to 7th, 9th to 12th & 14th Floor For Residential |  |  | 31.5275 | 3428441.64 |  | 101 | 1401 | 101,.., 1401
102,.., 1402 |  | 1 | 364.5767 | 0 | 546.865 |  |  |  | 29.8025 | 3281190.12 |  | 102 | 1402 | 102,.., 1402
103,.., 1403 |  | 1 | 364.5767 | 0 | 546.865 |  |  |  |  | 3281190.12 |  | 103 | 1403 | 103,.., 1403
104,.., 1404 |  | 1 | 380.938 | 0 | 571.4069 |  |  |  |  | 3428441.64 |  | 104 | 1404 | 104,.., 1404
105,.., 1405 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 6125.2319 |  | 3428441.64 |  | 105 | 1405 | 105,.., 1405
106,.., 1406 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 6400.1168 |  | 3281190.12 |  | 106 | 1406 | 106,.., 1406
107,.., 1407 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 6400.1168 |  | 3281190.12 |  | 107 | 1407 | 107,.., 1407
108,.., 1408 |  | 1 | 380.938 | 0 | 571.4069 |  |  |  |  | 3428441.64 |  | 108 | 1408 | 108,.., 1408
8th & 13th Floor (Part Refuge Area) | [9 empty] | 0
801 to 1301 |  | 1 | 380.938 | 0 | 571.4069 | 8th & 13th Floor (Part Refuge Area) |  | 5748.9676 |  | 3428441.64 |  | 801 | 1301 | 801 to 1301
802 to 1302 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 5760.1051 |  |  |  | 802 | 1302 | 802 to 1302
803 to 1303 |  | 1 | 364.5767 | 0 | 546.865 | [6 empty] | 803 | 1303 | 803 to 1303
804 to 1304 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 4375.1656 | 5250.1987 |  |  | 804 | 1304 | 804 to 1304
805 to 1305 |  | 1 | 380.938 | 0 | 571.4069 | [6 empty] | 805 | 1305 | 805 to 1305
806 to 1306 |  | 1 | 364.5767 | 0 | 546.865 | [6 empty] | 806 | 1306 | 806 to 1306
807 to 1307 |  | 1 | 364.5767 | 0 | 546.865 | [6 empty] | 807 | 1307 | 807 to 1307
808 to 1308 |  | Refuge Area | [9 empty] | 808 | 1308 | 808 to 1308
Mabel
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,.., 1401 |  | 1 | 380.938 | 0 | 571.4069 | 1st to 7th, 9th to 12th & 14th Floor For Residential |  | 2857034.7 | 2857034.7 | 3428441.64 |  | 101 | 1401 | 101,.., 1401
102,.., 1402 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 2734325.1 | 2734325.1 | 3281190.12 |  | 102 | 1402 | 102,.., 1402
103,.., 1403 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 2734325.1 | 2734325.1 | 3281190.12 |  | 103 | 1403 | 103,.., 1403
104,.., 1404 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 2857034.7 | 2857034.7 | 3428441.64 |  | 104 | 1404 | 104,.., 1404
105,.., 1405 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 2857034.7 | 2857034.7 | 3428441.64 |  | 105 | 1405 | 105,.., 1405
106,.., 1406 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 2734325.1 | 2734325.1 | 3281190.12 |  | 106 | 1406 | 106,.., 1406
107,.., 1407 |  | 1 | 364.5767 | 0 | 546.865 |  |  |  | 2734325.1 | 3281190.12 |  | 107 | 1407 | 107,.., 1407
108,.., 1408 |  | 1 | 380.938 | 0 | 571.4069 |  |  |  | 2857034.7 | 3428441.64 |  | 108 | 1408 | 108,.., 1408
8th & 13th Floor (Part Refuge Area) | [8 empty] | 0
801 to 1301 |  | 1 | 380.938 | 0 | 571.4069 | 8th & 13th Floor (Part Refuge Area) |  | 4375.1656 | 2857034.7 |  |  | 801 | 1301 | 801 to 1301
802 to 1302 |  | 1 | 364.5767 | 0 | 546.865 | [6 empty] | 802 | 1302 | 802 to 1302
803 to 1303 |  | 1 | 364.5767 | 0 | 546.865 | [6 empty] | 803 | 1303 | 803 to 1303
804 to 1304 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 5250.1987 |  |  |  | 804 | 1304 | 804 to 1304
805 to 1305 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 5250.1987 |  |  |  | 805 | 1305 | 805 to 1305
806 to 1306 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 5485.8144 |  |  |  | 806 | 1306 | 806 to 1306
807 to 1307 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 5485.8144 |  |  |  | 807 | 1307 | 807 to 1307
808 to 1308 |  | Refuge Area | [5 empty] | #DIV/0! |  |  |  | 808 | 1308 | 808 to 1308
Valentia
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,.., 1401 |  | 1 | 380.938 | 0 | 571.4069 | 1st to 7th, 9th to 12th & 14th Floor For Residential |  | 2628471.924 |  |  |  | 101 | 1401 | 101,.., 1401
102,.., 1402 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 2515579.092 |  |  |  | 102 | 1402 | 102,.., 1402
103,.., 1403 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 2515579.092 |  |  |  | 103 | 1403 | 103,.., 1403
104,.., 1404 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 2628471.924 |  |  |  | 104 | 1404 | 104,.., 1404
105,.., 1405 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 2628471.924 |  |  |  | 105 | 1405 | 105,.., 1405
106,.., 1406 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 2515579.092 |  |  |  | 106 | 1406 | 106,.., 1406
107,.., 1407 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 2515579.092 |  |  |  | 107 | 1407 | 107,.., 1407
108,.., 1408 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 2628471.924 |  |  |  | 108 | 1408 | 108,.., 1408
8th & 13th Floor (Part Refuge Area)
801 to 1301 |  | 1 | 380.938 | 0 | 571.4069 | 8th & 13th Floor (Part Refuge Area) |  | 5950.2252 |  |  |  | 801 | 1301 | 801 to 1301
802 to 1302 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 6217.2563 |  |  |  | 802 | 1302 | 802 to 1302
803 to 1303 |  | 1 | 364.5767 | 0 | 546.865 |  |  | 6217.2563 |  |  |  | 803 | 1303 | 803 to 1303
804 to 1304 |  | 1 | 380.938 | 0 | 571.4069 |  |  | 5950.2252 |  |  |  | 804 | 1304 | 804 to 1304
805 to 1305 |  | 1 | 380.938 | 0 | 571.4069 | [6 empty] | 805 | 1305 | 805 to 1305
806 to 1306 |  | 1 | 364.5767 | 0 | 546.865 | [6 empty] | 806 | 1306 | 806 to 1306
807 to 1307 |  | 1 | 364.5767 | 0 | 546.865 | [6 empty] | 807 | 1307 | 807 to 1307
808 to 1308 |  | Refuge Area | [9 empty] | 808 | 1308 | 808 to 1308
Wisley
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,.., 1401 |  | 2 | 548.5334 | 0 | 822.8002 | 1st to 7th, 9th to 12th & 14th Floor For Residential |  | 6076.8097 | 46.4225 | 4936800.96 |  | 101 | 1401 | 101,.., 1401
102,.., 1402 |  | 2 | 511.5053 | 0 | 767.2579 |  |  | 6516.7134 | 43.2975 | 4603547.52 |  | 102 | 1402 | 102,.., 1402
103,.., 1403 |  | 2 | 511.5053 | 0 | 767.2579 |  |  | 6516.7134 |  | 4603547.52 |  | 103 | 1403 | 103,.., 1403
104,.., 1404 |  | 2 | 548.5334 | 0 | 822.8002 |  |  |  |  | 4936800.96 |  | 104 | 1404 | 104,.., 1404
105,.., 1405 |  | 2 | 548.5334 | 0 | 822.8002 |  |  |  |  | 4936800.96 |  | 105 | 1405 | 105,.., 1405
106,.., 1406 |  | 2 | 511.5053 | 0 | 767.2579 |  |  | 5469.1287 |  | 4603547.52 |  | 106 | 1406 | 106,.., 1406
107,.., 1407 |  | 2 | 511.5053 | 0 | 767.2579 |  |  | 5865.0421 |  | 4603547.52 |  | 107 | 1407 | 107,.., 1407
108,.., 1408 |  | 2 | 548.5334 | 0 | 822.8002 |  |  | 5865.0421 |  | 4936800.96 |  | 108 | 1408 | 108,.., 1408
8th & 13th Floor (Part Refuge Area)
801 & 1301 |  | 2 | 548.5334 | 0 | 822.8002 | 8th & 13th Floor (Part Refuge Area) |  | 5854.3985 | 4114000.8 | 3784880.736 |  | 801 | 1301 | 801 & 1301
802 & 1302 |  | 2 | 511.5053 | 0 | 767.2579 |  |  | 5865.0421 | 3836289.6 | 3529386.432 |  | 802 | 1302 | 802 & 1302
803 & 1303 |  | 2 | 511.5053 | 0 | 767.2579 |  |  |  | 3836289.6 | 3529386.432 |  | 803 | 1303 | 803 & 1303
804 & 1304 |  | 2 | 548.5334 | 0 | 822.8002 |  |  | 4861.4478 | 4114000.8 | 3784880.736 |  | 804 | 1304 | 804 & 1304
805 & 1305 |  | 2 | 548.5334 | 0 | 822.8002 |  |  | 4861.4478 | 4114000.8 | 3784880.736 |  | 805 | 1305 | 805 & 1305
806 & 1306 |  | 2 | 511.5053 | 0 | 767.2579 |  |  | 5213.3708 | 3836289.6 | 3529386.432 |  | 806 | 1306 | 806 & 1306
807 & 1307 |  | 2 | 511.5053 | 0 | 767.2579 |  |  | 5213.3708 | 3836289.6 | 3529386.432 |  | 807 | 1307 | 807 & 1307
808 & 1308 |  | Refuge Area | [5 empty] | #DIV/0! |  |  |  | 808 | 1308 | 808 & 1308
Phase II
Naldo | [13 empty] | to
Ground Floor For Entrance Lobby, Society Office & Parking | [13 empty] | to
1st to 7th, 9th to 12th & 14th Floor For Residential | [13 empty] | to
101,.., 1401 |  | 2BHK | 511.5053 | 0 | 767.2579 | 1st to 7th, 9th to 12th & 14th Floor For Residential | [7 empty] | to
102,.., 1402 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
103,.., 1403 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
104,.., 1404 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
105,.., 1405 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
106,.., 1406 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
8th & 13th Floor (Part Refuge Area) | [13 empty] | to
801 & 1301 |  | 2BHK | 511.5053 | 0 | 767.2579 | 8th & 13th Floor (Part Refuge Area) | [7 empty] | to
802 & 1302 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
803 & 1303 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
804 & 1304 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
805 & 1305 |  | Refuge Area | [11 empty] | to
806 & 1306 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
Osane | [13 empty] | to
Ground Floor For Entrance Lobby & Parking | [13 empty] | to
1st to 7th, 9th to 12th & 14th Floor For Residential | [7 empty] | 12 | [5 empty] | to
101,.., 1401 |  | 2BHK | 548.6411 | 0 | 822.9616 | 1st to 7th, 9th to 12th & 14th Floor For Residential |  | 47.9975 | [5 empty] | to
102,.., 1402 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
103,.., 1403 |  | 2BHK | 511.5053 | 0 | 767.2579 |  |  | 44.8275 | [5 empty] | to
104,.., 1404 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
105,.., 1405 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
106,.., 1406 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
107,.., 1407 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
108,.., 1408 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
8th & 13th Floor (Part Refuge Area) | [7 empty] | 2 | [5 empty] | to
801 & 1301 |  | 2BHK | 548.6411 | 0 | 822.9616 | 8th & 13th Floor (Part Refuge Area) | [7 empty] | to
802 & 1302 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
803 & 1303 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
804 & 1304 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
805 & 1305 |  | 2BHK | 542.2257 | 0 | 813.3386 | [8 empty] | to
806 & 1306 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
807 & 1307 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
808 & 1308 |  | Refuge Area | [11 empty] | to
Patricia | [13 empty] | to
Ground Floor For Entrance Lobby & Parking | [13 empty] | to
1st to 7th, 9th to 12th & 14th Floor For Residential | [13 empty] | to
101,.., 1401 |  | 1BHK | 380.938 | 0 | 571.4069 | 1st to 7th, 9th to 12th & 14th Floor For Residential | [7 empty] | to
102,.., 1402 |  | 1BHK | 364.5767 | 0 | 546.865 | [8 empty] | to
103,.., 1403 |  | 1BHK | 364.5767 | 0 | 546.865 | [8 empty] | to
104,.., 1404 |  | 1BHK | 380.938 | 0 | 571.4069 | [8 empty] | to
105,.., 1405 |  | 1BHK | 380.938 | 0 | 571.4069 | [8 empty] | to
106,.., 1406 |  | 1BHK | 364.5767 | 0 | 546.865 | [8 empty] | to
107,.., 1407 |  | 1BHK | 364.5767 | 0 | 546.865 | [8 empty] | to
108,.., 1408 |  | 1BHK | 380.938 | 0 | 571.4069 | [8 empty] | to
8th & 13th Floor (Part Refuge Area) | [13 empty] | to
801 & 1301 |  | 1 | 380.938 | 0 | 571.4069 | 8th & 13th Floor (Part Refuge Area) | [7 empty] | to
802 & 1302 |  | 1 | 364.5767 | 0 | 546.865 | [8 empty] | to
803 & 1303 |  | 1 | 364.5767 | 0 | 546.865 | [8 empty] | to
804 & 1304 |  | 1 | 380.938 | 0 | 571.4069 | [8 empty] | to
805 & 1305 |  | 1 | 380.938 | 0 | 571.4069 | [8 empty] | to
806 & 1306 |  | 1 | 364.5767 | 0 | 546.865 | [8 empty] | to
807 & 1307 |  | 1 | 364.5767 | 0 | 546.865 | [8 empty] | to
808 & 1308 |  | Refuge Area | [11 empty] | to
Querida | [13 empty] | to
Ground Floor For Entrance Lobby & Parking | [13 empty] | to
1st to 7th, 9th to 12th & 14th Floor For Residential | [7 empty] | 12 | [5 empty] | to
101,.., 1401 |  | 2BHK | 548.6411 | 0 | 822.9616 | 1st to 7th, 9th to 12th & 14th Floor For Residential | [7 empty] | to
102,.., 1402 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
103,.., 1403 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
104,.., 1404 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
105,.., 1405 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
106,.., 1406 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
107,.., 1407 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
108,.., 1408 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
8th & 13th Floor (Part Refuge Area) | [7 empty] | 2 | [5 empty] | to
801 & 1301 |  | 2BHK | 548.6411 | 0 | 822.9616 | 8th & 13th Floor (Part Refuge Area) | [7 empty] | to
802 & 1302 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
803 & 1303 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
804 & 1304 |  | 2BHK | 548.6411 | 0 | 822.9616 | [8 empty] | to
805 & 1305 |  | 2BHK | 542.2257 | 0 | 813.3386 | [8 empty] | to
806 & 1306 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
807 & 1307 |  | 2BHK | 511.5053 | 0 | 767.2579 | [8 empty] | to
808 & 1308 |  | Refuge Area | [11 empty] | to
Ground Floor | [13 empty] | to
1 |  |  |  | 0 | 0 | Ground Floor | [7 empty] | to
2 |  |  |  | 0 | 0 | [8 empty] | to
3 |  |  |  | 0 | 0 | [8 empty] | to
4 |  |  |  | 0 | 0 | [8 empty] | to
5 |  |  |  | 0 | 0 | [8 empty] | to
6 |  |  |  | 0 | 0 | [8 empty] | to
7 |  |  |  | 0 | 0 | [8 empty] | to
8 |  |  |  | 0 | 0 | [8 empty] | to
2nd Floor | [13 empty] | to
201 |  |  |  | 0 | 0 | 2nd Floor | [7 empty] | to
202 |  |  |  | 0 | 0 | [8 empty] | to
203 |  |  |  | 0 | 0 | [8 empty] | to
204 |  |  |  | 0 | 0 | [8 empty] | to
205 |  |  |  | 0 | 0 | [8 empty] | to
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor | [13 empty] | to
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor | [7 empty] | to
302 ,.., 1502 |  |  |  | 0 | 0 | [8 empty] | to
303 ,.., 1503 |  |  |  | 0 | 0 | [8 empty] | to
304 ,.., 1504 |  |  |  | 0 | 0 | [8 empty] | to
305 ,.., 1505 |  |  |  | 0 | 0 | [8 empty] | to
2nd to 5th Floor | [13 empty] | to
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor | [7 empty] | to
202 to 502 |  |  |  | 0 | 0 | [8 empty] | to
203 to 503 |  |  |  | 0 | 0 | [8 empty] | to
204 to 504 |  |  |  | 0 | 0 | [8 empty] | to
205 to 505 |  |  |  | 0 | 0 | [8 empty] | to
2nd & 5th Floor | [13 empty] | to
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor | [7 empty] | to
202 & 502 |  |  |  | 0 | 0 | [8 empty] | to
203 & 503 |  |  |  | 0 | 0 | [8 empty] | to
204 & 504 |  |  |  | 0 | 0 | [8 empty] | to
205 & 505 |  |  |  | 0 | 0 | [8 empty] | to
Remarks:
* | Laura, Mabel, Valentia, Wesley, Patricia = Construction work is in process. Naldo, Osane = Construction work is in process at the time of Visit. Querida = Construction work is in process (Labour found).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised plans & CC of Phase II (on 19/09/2024).
* | We have done APF valuation for Buildings (Laura, Mable, Valentia, Wesley, Naldo, Osane, Patricia, Querida) which are mentioned on RERA site
* | We have taken approved CC from RERA Site.
* | Please Check for Environment Clearance Certificate, Fire NOC.
* | Recommended Rates / Other charges of the Property have been revised on 28/04/2023.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Arihant Aaradhya Phase I & II
Layout Plan :
Google Map :
Formulas:
Bapgaon = [Bapgaon, row above]
Mable
Laura
Valentia
Wesley
Laura
Mabel
Phase I ( Valentia, Wesley, Laura, Mabel)
Querida
Patricia
Osane
Naldo
Phase II ( Naldo, Osane, Patricia, Querida)
Arihant Aaradhya Phase I & II
VALENTIA
WESLEY
LAURA
MABEL
Querida
Patricia
Osane
Naldo
Mable
Naldo
Naldo
Naldo
Querida

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted