## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 01/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-07-31
Name of the builder group |  |  |  | Mr.Anil Hardasmal Tharwani
Name of the builder company |  |  |  | Mr.Anil Hardasmal Tharwani
Name of the Project |  |  |  | Tharwani Solitaire Phase II, III, IV
Contact Details ( Name & Contact No.) |  |  |  | Pratik Kulkarni - 9920222642
Name / No of the Building |  |  |  | Phase II = Danburite C3, Emerald B5, Fluorite B4, Garnet C2, Ivory G1, Jade C1, Kyanite B3 Phase III = Hiddenite G2, Opal E1 Phase IV = Topaz H, Spinel I, Vivianite J
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51700004565 - Tharwani Solitaire Phase II P51700005135 - Tharwani Solitaire Phase III P51700030172 - Tharwani Solitaire Phase IV
Project location details |  | Tharwani Solitaire Phase II, III, IV, Survey No.8/1, 8/2, 12/1-12/7, 13/1, 13/2, 14/1-14/4, near Regency Avana, Internal Road, Maharal Khurd, Shahad, Kalyan, Thane - 421301.
Survey No |  | 8/1, 8/2, 12/1-12/7, 13/1, 13/2, 14/1-14/4
Road |  | Internal Road |  | Locality/Village |  | Maharal Khurd
City |  | Shahad |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421301
Nearby Landmark |  | Regency Avana |  | Distance from city centre: |  | 2.4 KM from Shahad Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residentail
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Konark Meadows
West | NA | NA |  |  | Regency Avana
North | NA | NA |  |  | Tharwani Solitaire Wing B
South | NA | NA |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.2478 |  | Longitude |  | 73.1759
Location Link |  | https://goo.gl/maps/hx7Zchd82zjpjH3g7?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 42230.35
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | -1.184e-07
Total FSI availaible for the project |  |  |  | 1.1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 46453.38
Total number of Buildings |  |  |  | 12 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Town Planner Thane
Layout Approval No |  | BS/Sudharit/BP/Muje Maharal/T.kalyan/SS thane/1215 |  |  | Dated | 2021-07-06
Approved Floor plan No. |  | BS/Sudharit/BP/Muje Maharal/T.kalyan/SS thane/1215 |  |  | Dated | 2021-07-06
Commencement-CC No Valid Up to: |  | BSP/BP/Muje Maharal/T.Kalyan/SS Thane/1215 |  |  | Dated | 2021-07-06
Phase - III = Wing E1 = Gr/St + 1st to 8th Floor Phase - IV =Wing H, Wing I & Wing J = Gr/st + P + 1st to 15th Floor
Approved Floor plan No. Phase II = Danburite C3 |  | BSP/BP/Muje Maharal/T.Kalyan/SS Thane/609 |  |  | Dated | 2017-04-07
Commencement-CC No Valid Up to: |  | BSP/BP/Muje Maharal/T.Kalyan/SS Thane/609 |  |  | Dated | 2017-04-07
Phase -Phase II = Danburite C3 = Gr/St + 1st to 7th Floor
O. Certificate No.: |  | Phase II = Mahsul/Kaksh-1/T-7/Muje Maharal Approved upto : B-3, C-1, C-2, C-3, B-4, B-5, G-1 = Gr/St + 1st to 7th Floor |  |  | Dated | 2019-10-15
O. Certificate No.: |  | Phase III = Mahsul/Kaksh-1/T-7/Muje Maharal Approved upto : G-2 = Gr/St + 1st to 7th Floor |  |  | Dated | 2021-12-20
O. Certificate No.: |  | Phase III = Mahsul/Kaksh-1/T-7/Mharal/Kalyan/Part OC Approved upto : E-1 = Gr/St + 1st to 8th Floor |  |  | Dated | 2023-01-09
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 46453.38
Approved no of units |  |  | Phase II = Danburite C3 = Flats - 42 Phase III = Opal (E1) = Flats - 32 Phase IV = Topaz (H), Spinel (I), Vivanite (J) = Flats - 208
Approved no of Floors |  |  | Phase II = Danburite C3, Emerald B5, Fluorite B4, Garnet C2, Ivory G1, Jade C1, Kyanite B3 = Gr/St + 1st to 7th Floor Phase III = Hiddenite (G2) = Gr/st + 1st to 7th Floor Phase III = Opal (E1) = Gr/St + 1st to 8th Floor Phase IV = Topaz (H), Spinel (I), Vivanite (J) = Gr/St + P + 1st to 15th Floor
Proposed no of Floors |  |  | Phase II = Danburite C3, Emerald B5, Fluorite B4, Garnet C2, Ivory G1, Jade C1, Kyanite B3 = Gr/St + 1st to 7th Floor
Phase III = Hiddenite (G2) = Gr/st + 1st to 7th Floor Phase III = Opal (E1) = Gr/St + 1st to 8th Floor
Phase IV = Topaz (H) = Gr/St + P + 1st to 15th Floor
Phase IV = Spinel (I) = Gr/St + P + 1st to 15th Floor
Phase IV = Vivanite (J) = Gr/St + P + 1st to 15th Floor
Expected Completion |  |  | As per RERA - Completed = (Phase = II) Completed = (Phase = III) 30/07/2025 (Phase =IV)
Projected life of the structure |  |  | 55 Years
Projected life of the structure |  |  | Phase VI - Under Construction
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes
Construction details: |  | Phase II = Danburite C3, Emerald B5, Fluorite B4, Garnet C2, Ivory G1, Jade C1, Kyanite B3 = Gr/St + 1st to 7th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | Phase III = Hiddenite (G2) = Gr/st + 1st to 7th Floor Phase III = Opal (E1) = Gr/St + 1st to 8th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 8
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% | 93.75% |  | 96.88% |  | Excavation in process | 4
Plinth |  | 8 | 100% |  |  |  |  | Excavation Completed | 8
RCC (Including podiums) |  | 9 | 100% |  |  |  |  | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 7 | 87.5% |  |  |  |  | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 7 | 87.5% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 87.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 87.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 87.5% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 87.5% |  |  |  |  | Plinth in process | 6
Possession |  | 7 | 87.5% |  |  |  |  | Plinth completed | 8
Construction details: |  | #REF! | [5 empty] | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF!
Stage of construction: |  | All work completed. OC Received. | [5 empty] | All work Completed. Wait for OC
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | #REF! | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 8 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 8 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 8 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 8 | #REF! |  |  |  |  | Plinth completed | #REF!
Construction details: |  | Phase IV = Topaz (H) = Gr/St + P + 1st to 15th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 93% |  | 95% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 14 | 93.33% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 10 | 66.67% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | Phase IV = Spinel (I) = Gr/St + P + 1st to 15th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 13 Slab Completed, Brickwork upto 3 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 13 Slab Completed, Brickwork upto 3 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 44% |  | 70.38% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 13 | 81.25% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 3 | 20% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | Phase IV = Vivanite (J) = Gr/St + P + 1st to 15th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 10 Floor Completed, External Plaster upto 4 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 1 | Floors | 15
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 10 Floor Completed, External Plaster upto 4 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 65.17% |  | 84.67% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 17 | 100% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 10 | 66.67% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 26.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6000 |  |  | 5200 to 6000 & OC |  | Rushikesh | Verbal | 2023-05-30
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Other Charges |  |  |  |  | 500000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 400000 |  |  | by Rushikesh
Distressed valuation of the Property |  |  |  |  | 4800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase II - Danburite C3 |  | 42 |  | 41082.7407 |  | 61624.111
Topaz (Wing H) |  | 88 |  | 89022.2412 |  | 133533.3617
Spinel (Wing I) |  | 60 |  | 63088.5575 |  | 94632.8362
Vivanite (Wing J) |  | 60 |  | 51132.7674 |  | 76699.1511
Opal (E1) |  | 32 |  | 47277.1069 |  | 70915.6604
Total |  | 282 |  | 291603.4136 |  | 437405.1204
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Phase II
Danburite Wing C3
Ground Floor for Commercial
1st to 7th Floor for Residential
1 |  | 3BHK | 1144.7826 | 0 | 1717.1739 | 1st to 7th Floor for Residential |  | 4949.9936 | 42
2 |  | 2BHK | 815.8628 | 0 | 1223.7941 |  |  | 6945.6126
3 |  | 2BHK | 847.1146 | 0 | 1270.6718 |  |  | 6689.3747
4 |  | 3BHK | 1054.6968 | 0 | 1582.0452 |  |  | 4108.6057
5 |  | 3BHK | 1075.0139 | 0 | 1612.5208 |  |  | 4030.9558
6 |  | 2BHK | 931.4923 | 0 | 1397.2385 |  |  | 4652.0332
Phase III
Opal (E1)
Ground Floor for Parking
1st to 8th Floor
1 |  | 4BHK | 1477.4096 | 0 | 2216.1144 | 1st to 8th Floor |  | 5640.5031
2 |  | 4BHK | 1477.4096 | 0 | 2216.1144
3 |  | 4BHK | 1477.4096 | 0 | 2216.1144
4 |  | 4BHK | 1477.4096 | 0 | 2216.1144
Phase IV
Topaz (Wing H)
Ground Floor for Parking
1st to 6th, 8th to 11th, 13th to 15th Floor for Residential
1 |  | 3BHK | 1097.2176 | 0 | 1645.8264 | 1st to 6th, 8th to 11th, 13th to 15th Floor for Residential |  | 5164.5788
2 |  | 3BHK | 1097.2176 | 0 | 1645.8264 |  |  | 5164.5788
3 |  | 3BHK | 1231.7245 | 0 | 1847.5868 |  |  | 4600.5958
4 |  | 2BHK | 903.0243 | 0 | 1354.5364 |  |  | 4798.6899
5 |  | 2BHK | 833.8117 | 0 | 1250.7176 |  |  | 5197.0165
6 |  | 2BHK | 829.6676 | 0 | 1244.5014 |  |  | 5222.9753
7th & 12th Floor (Part Refuge Floor)
1 |  | 3BHK | 1097.2176 | 0 | 1645.8264 | 7th & 12th Floor (Part Refuge Floor)
2 |  | 3BHK | 1097.2176 | 0 | 1645.8264
3 |  | 4BHK | 1471.8909 | 0 | 2207.8363
4 |  | Refuge Area
5 |  | 3BHK | 1062.8158 | 0 | 1594.2237
6 |  | 2BHK | 829.6676 | 0 | 1244.5014
Spinel (Wing I)
Ground Floor for Parking
1st to 6th, 8th to 11th, 13th to 15th Floor for Residential
1 |  | 3BHK | 1144.1917 | 0 | 1716.2875 | 1st to 6th, 8th to 11th, 13th to 15th Floor for Residential
2 |  | 3BHK | 1138.8635 | 0 | 1708.2952
3 |  | 3BHK | 1104.6232 | 0 | 1656.9348
4 |  | 2BHK | 818.2255 | 0 | 1227.3382
7th & 12th Floor (Part Refuge Floor)
1 |  | 3BHK | 1144.1917 | 0 | 1716.2875 | 7th & 12th Floor (Part Refuge Floor)
2 |  | 3BHK | 1138.8635 | 0 | 1708.2952
3 |  | 3BHK | 1104.6232 | 0 | 1656.9348
4 |  | 2BHK | 818.2255 | 0 | 1227.3382
Vivanite (Wing J)
Ground Floor for Parking
1st to 6th, 8th to 11th, 13th to 15th Floor for Residential
1 |  | 2BHK | 871.1843 | 0 | 1306.7765 | 1st to 6th, 8th to 11th, 13th to 15th Floor for Residential
2 |  | 2BHK | 871.1843 | 0 | 1306.7765
3 |  | 2BHK | 833.2412 | 0 | 1249.8619
4 |  | 2BHK | 833.2412 | 0 | 1249.8619
7th & 12th Floor (Part Refuge Floor)
1 |  | 2BHK | 871.1843 | 0 | 1306.7765 | 7th & 12th Floor (Part Refuge Floor)
2 |  | 2BHK | 871.1843 | 0 | 1306.7765
3 |  | 2BHK | 833.2412 | 0 | 1249.8619
4 |  | 2BHK | 833.2412 | 0 | 1249.8619
Remarks:
* | Phase II = All work Completed. OC Received. Phase III (Opal - E1) = All work completed. OC Received. Phase IV (Topaz - H) = Finishing work is in process. Phase IV (Spinel - I, Vivianite - J) = Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + A.P Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have received approved plans of Following Buildings which are under construction : Phase III = Opal - E1 & Phase IV = Topaz - H, Spinel - I, Vivianite - J
* | We have Not received approved plans of following Buildings which are already completed : Phase II = Emerald B5, Fluorite B4, Garnet C2, Ivory G1, Jade C1, Kyanite B3 Phase III = Hiddenite - G2
* | On Site, we meet Miss Simran - 7770026077.
* | As per approved floor plan of C3 wing is mentioned as typical floor G + 7th floor but during our site visit, we have observed that the ground floor is for commercial and parking. So we have not considered Ground Floor for Area Calculation and have drafted area for 1st to 7th floor
* | We have updated approved floor plan & CC of Phase II = Danburite C3 wing on (03/01/2023).
* | Provide approved Ground floor plan of Phase II = Danburite C3 wing.
* | We have updated OC from Rera for Phase III (Opal - E1) (On 30/05/2023).
* | On site we met Miss. Simran : 7770026077.
* | As per RERA, completion period of project Tharwani Solitaire Phase IV is expired on 30/07/2025 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Krishna Kambali |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Tharwani Solitaire Phase II, III, IV
Phase IV (Spinel - I)
Google Map :
Formulas:
Maharal Khurd = [Maharal Khurd, row above]
Phase IV (Topaz - H)
Phase IV (Topaz - H)
Phase IV (Spinel - I)
Phase IV (Vivianite J)
Phase IV (Topaz - H)
Phase IV (Topaz - H)

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
88.074