## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-07-30
Branch Name/ID |  | Mahindra Rural Housing Finance - Kalyan |  |  | Date & Time of Site Visit | 31/07/2025 at 13:20 |  |  |  | s
Name of the person met at site & Contact No |  | Mr. Aniket Jadhav 8550998822 |  |  | Date of Report Release | 01/08/2025
Project Details
Name of the project |  | Vedant Millenia Happiness Phase II (Wing C)
Address |  | Vedant Millenia Happiness Phase II (Wing C), Survey No.221, Hissa No.3/1, S.No.221, Hissa No.3/2(P), S.No.221, Hissa No.4(P), S.No.221, Hissa No.6/A(P), near Chhatrapati Shivaji Maharaj Chowk, Internal Road, Titwala, Titwala East, Kalyan, Thane - 421605. | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 221, Hissa No.3/1, S.No.221, Hissa No.3/2(P), S.No.221, Hissa No.4(P), S.No.221, Hissa No.6/A(P) | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Titwala | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Internal Road | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Titwala East | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Kalyan | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Thane | [8 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 421605 | [8 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P51700050205 | [11 empty] | Mahad | Daund
Landmark |  | Chhatrapati Shivaji Maharaj Chowk | [11 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.303722,73.224083 | [8 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/NLNuVG84wnifmHm58 | [11 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Mr. Mohan Hardasmal Tharwani | [11 empty] | Mahasala | Bhor
Office address (agreement) |  | First Floor, Tharwani Infrastructure, Tharwani Infrastructure, Near Sanjeevani Clinic, Ulhasnagar, Thane 421003 | [11 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [11 empty] | Murud | Velhe
Builder Bank Details |  | Bank Name - Punjab National Bank IFSC Code - PUNB0046100
Contact No. |  | Mr. Rahul Tharvani 8484946708
Location of the project Municipal Limit : |  | Kalyan-Dombivli Municipal Corporation
Project Type (Apartments/Plot/ Combined) |  | Apartment
No of Wings / Buildings |  | Wing C |  |  | Other HFC's Approval / Funding | None |  | 17.55
No. of Tenements / Units in Project |  | Sale Flat = 95 Mhada Flat = 22 |  |  | Exposure Limit (Proposed) | 14.25
Approved No. of Floor |  | Wing C = Gr/St + 1st to 15th Floor
Proposed No. of Floor |  | Wing C = Gr/St + 1st to 25th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | Wing D | Wing B | 15.00 M. W. D.P. Road | R.G
|  | Physical on site |  | Open Plot | Vedant Millenia Happiness Phase II (Wing B) | Internal Road | Open Plot
Verification of survey No. (Title document) |  | S. No.221, Hissa No.3/1(P), S.No.221, Hissa No.3/2(P), S.No.221, Hissa No.4(P), S.No.221, Hissa No.6/A(P)
Plot area mentioned in the sale deed (As per 7/12) |  | 13920 Sq.M |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 11372 Sq.M
Approach road |  | Yes, Approx 9ft
Connectivity |  | 1. 0.85 Km From KNT Public School 2. 0.90 Km From Vedaviyas vidyalaya 3. 1.1 Km From Shree Maha Ganapati Hospital 4. 2.6 Km From Shree Krishna Hospital 5. 0.45 Km From Shree Siddhivinayaka Mandir 6. 0.55 Km From Shree Vitthal Rukmini Mandir 7. 0.80 Km From Reliance SMART Point U009 8. 1.1 Km From Ganpati Super Market 9. 0.60 Km From Titwala Mandir Bus Stop 10. 2.8 Km From Titwala Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 11372
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 1.3104
|  | Total FSI availaible for the project |  |  |  | 2.4104
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 27436.8
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 27410.56
|  | Total Approved Builtup area of Wing C (Sq.Mt) |  |  |  | 6084.37
Building plan approvals - Approval No : |  | KDMCC/RB/2024/APL/00030 |  |  |  | Date | 2024-02-08
Building height / No. of Floors |  | Wing C = Gr/St + 1st to 15th Floor (Height =47.55 Mt.)
Construction/Building Permission |  | KDMCC/RB/2025/APL/00157 Valid Upto - Wing C = Gr + 1st to 21st Floor |  |  |  | Date | 2025-04-29
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA
|  | Validity & Area : mentioned |  | NA |  |  |  | Date - NA. Area - Sq.Mt.
Other statutory permissions
Fire NOC Valid upto |  | FIRE/HQ/KDMC/OW/2021/399 Wing C = Gr + 1st to 23rd Floor (Height = 70.35 Mt.) |  |  |  | Date | 2021-06-04
Environmental Clearance Valid upto |  | SEIAA-EC-0000000249 S. No. 218, 221/3/1, 221/3/2, 221/6(P), 221/8, 221/9 |  |  |  | Date | 2018-04-26 | SEIAA-EC-0000000249
CONSTRUCTION PROGRESS
Baseline start date |  | 27/03/2023 |  | Baseline finish date | 2027-12-31
Construction details:
Wing C = Gr/St + 1st to 25th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 12 Floor, Internal Plaster upto 9 Floor Completed
|  |  |  | 0 | 1 | 0 | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 12 Floor, Internal Plaster upto 9 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 6.25
Excavation |  | 0% |  | 25 | 100% | 45.15% |  | Excavation in process | 12.5
Plinth |  | 10% |  | 25 | 100% |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 40% |  | 17 | 65.38% |  |  | Footing in Process | 6.25
Brickwork |  | 15% |  | 12 | 48% |  |  | Footing Completed | 12.5
Internal Plaster |  | 5% |  | 9 | 36% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 18.75
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 25
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing C
Total |  | 0 |  | 0 |  | 0
Residential Area Details : (Sale Flat)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing C |  | 95 |  | 47716.403 |  | 75202.494
Total |  | 95 |  | 47716.403 |  | 75202.494
Residential Area Details :(Mhada Flat)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing C |  | 22 |  | 10969.9907 |  | 17320.5192 |  | Details of Residential & Commercials in Building
Total |  | 22 |  | 10969.9907 |  | 17320.5192
Grand Total |  | 117 |  | 58686.3936 |  | 92523.0133
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Wing C
Ground Floor
1 |  | Shop |  |  | 0 |  | 0
2 |  | Shop |  |  | 0 |  | 0
3 |  | Shop |  |  | 0 |  | 0
4 |  | Shop |  |  | 0 |  | 0
5 |  | Shop |  |  | 0 |  | 0
6 |  | Shop |  |  | 0 |  | 0
7 |  | Shop |  |  | 0 |  | 0
8 |  | Shop |  |  | 0 |  | 0
9 |  | Shop |  |  | 0 |  | 0
10 |  | Shop |  |  | 0 |  | 0
11 |  | Shop |  |  | 0 |  | 0
12 |  | Shop |  |  | 0 |  | 0 | 10.764
Flat No. (Approved Plan) | Sale / Mhada | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Balcony +A.P + Chajja Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Wing C | [8 empty] | 4.95 | terrace
Ground Floor For Parking
1st Floor For Part Society Ofiice & Driver Room
1 | Double Height Area | [5 empty] | -
2 | Mhada | 2BHK | 472.7549 | 105.0297 | 577.7846 | 40.5534 | 907.2303 | Balcony rplce
3 | Mhada | 1BHK | 321.5207 | 60.6282 | 382.1489 | 40.5534 | 613.7767
4 | Mhada | 1BHK | 321.5207 | 60.6282 | 382.1489 | 40.5534 | 613.7767
5 | Mhada | 2BHK | 464.2513 | 105.0297 | 569.2811 | 40.5534 | 894.4749
6 | Mhada | 2BHK | 464.2513 | 105.0297 | 569.2811 | 40.5534 | 894.4749
7 | Society Ofiice & Driver Room | [5 empty] | -
8 | [6 empty] | -
2nd Floor For Residential
1 | Sale | 1BHK | 345.7397 | 38.9764 | 384.7161 | 227.3088 | 652.8438
2 | Sale | 2BHK | 472.7549 | 105.0297 | 577.7846 | 39.9614 | 906.6383
3 | Mhada | 1BHK | 320.229 | 60.6282 | 380.8572 | 39.9614 | 611.2472
4 | Sale | 1BHK | 320.229 | 60.6282 | 380.8572 | 39.9614 | 611.2472
5 | Sale | 2BHK | 463.0673 | 105.0297 | 568.097 | 39.9614 | 892.1069
6 | Sale | 2BHK | 463.0673 | 105.0297 | 568.097 | 39.9614 | 892.1069
7 | Sale | 2BHK | 528.0818 | 55.8652 | 583.947 | 34.0412 | 909.9616 | add chajja
8 | Sale | 2BHK | 528.0818 | 59.498 | 587.5798 | 34.0412 | 915.4109
3rd & 5th Floor
1 | Mhada | 1BHK | 340.8959 | 61.1772 | 402.0731 | 40.5534 | 643.663
2 | Mhada | 2BHK | 472.7549 | 105.0297 | 577.7846 | 40.5534 | 907.2303
3 | Mhada | 1BHK | 321.5207 | 60.6282 | 382.1489 | 40.5534 | 613.7767
4 | Mhada | 1BHK | 321.5207 | 60.6282 | 382.1489 | 40.5534 | 613.7767
5 | Mhada | 2BHK | 464.2513 | 105.0297 | 569.2811 | 40.5534 | 894.4749
6 | Mhada | 2BHK | 464.2513 | 105.0297 | 569.2811 | 40.5534 | 894.4749
7 | Mhada | 2BHK | 528.0818 | 55.8652 | 583.947 | 34.0412 | 909.9616
8 | Mhada | 2BHK | 528.0818 | 59.498 | 587.5798 | 34.0412 | 915.4109
7th, 9th, 11th & 15th Floor
1 | Sale | 1BHK | 340.8959 | 61.1772 | 402.0731 | 40.5534 | 643.663
2 | Sale | 2BHK | 472.7549 | 105.0297 | 577.7846 | 40.5534 | 907.2303
3 | Sale | 1BHK | 321.5207 | 60.6282 | 382.1489 | 40.5534 | 613.7767
4 | Sale | 1BHK | 321.5207 | 60.6282 | 382.1489 | 40.5534 | 613.7767
5 | Sale | 2BHK | 464.2513 | 105.0297 | 569.2811 | 40.5534 | 894.4749
6 | Sale | 2BHK | 464.2513 | 105.0297 | 569.2811 | 40.5534 | 894.4749
7 | Sale | 2BHK | 528.0818 | 55.8652 | 583.947 | 34.0412 | 909.9616
8 | Sale | 2BHK | 528.0818 | 59.498 | 587.5798 | 34.0412 | 915.4109
4th, 6th, 10th, 12th & 14th Floor
1 | Sale | 1BHK | 339.8195 | 61.1772 | 400.9967 | 39.9614 | 641.4564
2 | Sale | 2BHK | 471.3556 | 105.0297 | 576.3853 | 39.9614 | 904.5393
3 | Sale | 1BHK | 320.229 | 60.6282 | 380.8572 | 39.9614 | 611.2472
4 | Sale | 1BHK | 320.229 | 60.6282 | 380.8572 | 39.9614 | 611.2472
5 | Sale | 2BHK | 463.0673 | 105.0297 | 568.097 | 39.9614 | 892.1069
6 | Sale | 2BHK | 463.0673 | 105.0297 | 568.097 | 39.9614 | 892.1069
7 | Sale | 2BHK | 528.0818 | 55.8652 | 583.947 | 34.0412 | 909.9616
8 | Sale | 2BHK | 528.0818 | 59.498 | 587.5798 | 34.0412 | 915.4109
8th Floor (Part Refuge Area)
1 | Sale | 1BHK | 339.8195 | 61.1772 | 400.9967 | 39.9614 | 641.4564
2 | Sale | 2BHK | 471.3556 | 105.0297 | 576.3853 | 39.9614 | 904.5393
3 | Sale | 1RK | 207.3146 | 60.6282 | 267.9429 | 0 | 401.9143
- | Refuge Area | [5 empty] | -
4 | Sale | 1RK | 207.3146 | 60.6282 | 267.9429 | 0 | 401.9143
5 | Sale | 2BHK | 463.0673 | 105.0297 | 568.097 | 39.9614 | 892.1069
6 | Sale | 2BHK | 463.0673 | 105.0297 | 568.097 | 39.9614 | 892.1069
7 | Sale | 2BHK | 528.0818 | 55.8652 | 583.947 | 34.0412 | 909.9616
8 | Sale | 2BHK | 528.0818 | 59.498 | 587.5798 | 34.0412 | 915.4109
13th Floor (Part Refuge Area)
1 | Sale | 1BHK | 340.8959 | 61.1772 | 402.0731 | 40.5534 | 643.663
2 | Sale | 2BHK | 472.7549 | 105.0297 | 577.7846 | 40.5534 | 907.2303
3 | Sale | 1RK | 213.2348 | 38.4275 | 251.6623 | 40.5534 | 418.0469
- | Refuge Area | [5 empty] | -
4 | Sale | 1RK | 213.2348 | 38.4275 | 251.6623 | 40.5534 | 418.0469
5 | Sale | 2BHK | 464.2513 | 105.0297 | 569.2811 | 40.5534 | 894.4749
6 | Sale | 2BHK | 464.2513 | 105.0297 | 569.2811 | 40.5534 | 894.4749
7 | Sale | 2BHK | 528.0818 | 55.8652 | 583.947 | 34.0412 | 909.9616
8 | Sale | 2BHK | 528.0818 | 59.498 | 587.5798 | 34.0412 | 915.4109
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 4500
Development Charge |  |  |  |  | 2,00,000/-
Club House |  |  |  |  | 1,50,000/-
Recommended of Parking ( If Available) |  |  |  |  | 2,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit (Internal visit not allowed) Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received. Work not yet Started.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Few Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Balcony + A.P + Chajja Area
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Miss. Leena 8550998841
11 | According to the approved floor plan, Flats no.7 & 8 from 2nd to 15th Floor (i.e. 207 to 1507 & 208 to 1508) have attached terrace to Bedroom, but as per site visit bedroom terrace area is enclosed by wall
12 | As Environmental Clearance certificate is given for large land parcel (Not able to check plot size, builtup area), please check from ur end.
13 | We have updated CC from RERA on 26/05/2025.
14 | Please provide revised approved plans.
Photographs Of Property : |  | Vedant Millenia Happiness Phase II (Wing C)
Layout Of Property :
Remark No.11 :
Google Map :
Name of Engineer Visited the property |  | Mr. Mangesh Bapardekar |  | Authorized Signatory Name & Seal of the agency
A Wing
B Wing
C Wing
D Wing
E Wing
N
Vedant Millenia Happiness Phase II (Wing C)
Terrace Area
Terrace Area
Enclosed Terrace Area by Wall
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on I27: 15% of Total No of Flats
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C48: height should also be mentioned
Note on C57: RERA Start date
Note on F57: RERA completion date
Note on H75: if multiple buildings are in project and are connected internally
Note on C77: AAC Block or Brick
Note on H79: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3