## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Thane | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-08-01 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | M/s. Macrotech Developers Limited | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | M/s. Macrotech Developers Limited | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Lodha Codename Premier - Fiora J & K | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Rajendra Giri 9820248856
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Rajendra Giri 9820248856
Name / No of the Building |  |  |  | Cluster 15.04 - Fiora (Wing J & K)
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | Fiora K = P51700052406 Fiora J = P51700052421 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Lodha Codename Premier - Fiora J & K, Sector.O & R, Survey No. 24/1A (Pt), 24/1B (Pt),260/1A & 260/1B, near Codename Premier Casa Fiora-A, Central Ave Road, Sonar Pada, Hedutane, Dombivali East, Kalyan, Thane - 421203. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Sector |  | O & R, Survey No. 24/1A (Pt), 24/1B (Pt),260/1A & 260/1B | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Sonar Pada | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Central Ave Road |  | Locality/Village |  | Hedutane | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Dombivali East |  | District |  | Thane | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kalyan |  | Pin Code |  | 421203 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Codename Premier Casa Fiora-A |  | Distance from city centre: |  | 5.5 KM from Dombivli Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Garden Casa Fiora |  |  | Internal Rd/Garden Casa Fiora
West | NA | 6M Wide Rd/Other Plot |  |  | Other Plot
North | NA | Other Plot |  |  | Open Plot
South | NA | Codename Premier Casa Fiora A |  |  | Codename Premier Casa Fiora A
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.1804516,73.0946081
Location Link |  | https://maps.app.goo.gl/vqkLjAAxatVJ7PC26
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 184911
Permissible FSI |  |  |  | 1.8
Permissible TDR/Paid FSI |  |  |  | 1.3803
Total FSI availaible for the project |  |  |  | 3.1803
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 588078.23
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Town Planning Thane | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | Ekatmikrut Nagarvasahat /M. Antarli, Khoni, Hedutane, Kole, Gharivali, Katai & Mangaon T. Kalyan & M. Umbroli, T. Ambernath SSTHANE/4770 |  |  | Dated | 2024-12-30 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. (Wing K) |  | Ekatmikrut Nagarvasahat /M. Antarli, Khoni, Hedutane, Kole, Gharivali, Katai & Mangaon T. Kalyan & M. Umbroli, T. Ambernath SSTHANE/1188 |  |  | Dated | 2024-03-15 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Wing K) |  | Ekatmikrut Nagarvasahat /M. Antarli, Khoni & Other/ Sector "B,D,I2,O,P,Q & R" SSTHANE/1188 |  |  | Dated | 2024-03-15 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Cluster 15.04 Fiora (Wing K) = G + 23rd Floor | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Approved Floor plan No. (Wing J) |  | Ekatmikrut Nagarvasahat /M. Antarli, Khoni, Hedutane, Kole, Gharivali, Katai & Mangaon T. Kalyan & M. Umbroli, T. Ambernath SSTHANE/4770 |  |  | Dated | 2024-12-30 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: (Wing J) |  | Ekatmikrut Nagarvasahat /M. Antarli, Khoni & Other/ Sector "C,D,E,F,I1,I2,O & P" SSTHANE/4770 |  |  | Dated | 2024-12-30 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Cluster 15.04 Fiora (Wing J) = G + 23rd Floor | [5 empty] | page No.52 | [8 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | MFS/51/2024/75 |  |  | Dated | 2024-02-15 |  | MFS/51/2022/810 |  |  | Dated | 2022-11-18 |  |  |  |  | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Sector O, Cluster 15.04 Wing J & K = Gr + 1st to 23rd Floor (69.90M Height) | [5 empty] | Sector O, Cluster 15.04 Wing K = Gr + 1st to 23rd Floor (69.90M Height) | [8 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/MIS/63043/2021 |  |  | Dated | 2022-02-26 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
|  | Plot Area = 5539590.50sq.mt Total Builtup Area = 17168486.98sq.mt | [15 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | Plot Area = 5539590.50sq.mt Total Builtup Area = 17168486.98sq.mt |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) Cluster 15.04 - Fiora (Wing J & K) |  |  | 19985.6
Approved no of units |  |  | Flats - 301
Approved no of Floors |  |  | Cluster 15.04 Fiora (Wing J & K) = G + 23rd Floor
Proposed no of Floors |  |  | Cluster 15.04 Fiora (Wing J & K) = G + 23rd Floor
Expected Completion |  |  | As per RERA - Wing J = 31/01/2029 Wing K = 31/01/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Community Spaces, Sports Ground, Kids Play Area, Swimming Pool, Banquet Hall, Ganesh Temple, Gymnasium, Café, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Cluster 15.04 Fiora (Wing J) = G + 23rd Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 10% |  | 45% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Cluster 15.04 Fiora (Wing K) = G + 23rd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 19 Slab, Brickwork upto 18 Floor, Internal Plaster upto 13.5 Floor, External Plaster upto 10 Floor Completed | , RCC upto 19 Slab, Brickwork upto 18 Floor, Internal Plaster upto 13.5 Floor, External Plaster upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 19 Slab, Brickwork upto 18 Floor, Internal Plaster upto 13.5 Floor, External Plaster upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 56.29% |  | 77.77% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 19 | 79.17% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 18 | 78.26% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 13.5 | 58.7% |  |  |  |  | Basement 1 | 0 |  | 10.2
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 43.48% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | #REF! | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | 19 | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | 0 | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7800 |  |  | 7200 to 7800 by sanjay on 30/04/2025 | [8 empty] | 800000 | 150000 | 100000 | 100000
Provisional Building Common Area Maintenance (CAM) Charges |  |  |  |  | 70000 | [11 empty] | 900000 | 200000 | 150000 | 150000
Provisional Federation Common Area Maintenance (CAM) Charges |  |  |  |  | 180000 | [11 empty] | 1000000 | 250000 | 200000 | 200000
Utility Connection &amp. Related Expenses* |  |  |  |  | 90000 | [11 empty] | 1100000 | 300000 | 250000 | 250000
Electricity Deposit Reimbursement* |  |  |  |  | 5000 | [11 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 400000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 6240 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing J |  | 140 |  | 80486.303 |  | 120729.4546
Wing K |  | 161 |  | 74163.7727 |  | 111245.6591
Grand Total |  | 301 |  | 154650.0757 |  | 231975.1136
Building details Floor Wise
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Sector O
Cluster 15.04 (Fiora)
Wing J
Ground Floor For Residential, Meter Room & Entrance Lobby | [9 empty] | chajja
1 |  | 2BHK | 570.9226 | 18.4064 | 589.329 | 0 | 883.9935 | 49.6304
2 |  | 2BHK | 570.9226 | 18.4064 | 589.329 | 0 | 883.9935
3 |  | 2BHK | 570.9226 | 18.4064 | 589.329 | 0 | 883.9935
4 |  | 2BHK | 570.9226 | 18.4064 | 589.329 | 0 | 883.9935
5 |  | 1BHK | 505.3698 | 19.0523 | 524.4221 | 0 | 786.6331
1st & 2nd Floor For Residential
1 |  | 2BHK | 523.4533 | 18.4064 | 541.8598 | 0 | 812.7896 | 45.6644
2 |  | 2BHK | 523.4533 | 18.4064 | 541.8598 | 0 | 812.7896
3 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193 | 45.6554
4 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
5 |  | 2BHK | 527.7589 | 136.3799 | 664.1388 | 0 | 996.2082 |  | 12.25
6 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
3rd to 7th & 9th to 12th Floor
1 |  | 2BHK | 529.0506 | 44.3477 | 573.3983 | 0 | 860.0974
2 |  | 2BHK | 529.0506 | 44.3477 | 573.3983 | 0 | 860.0974 |  | 4.1311
3 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193 |  | 4.1311
4 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
5 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
6 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
14th to 17th (15th to 18th Floor as per Builder) & 19th to 23rd Floor (20th to 24th Floor as per Builder)
1 |  | 2BHK | 529.0506 | 44.3477 | 573.3983 | 0 | 860.0974
2 |  | 2BHK | 529.0506 | 44.3477 | 573.3983 | 0 | 860.0974 |  | 4.1311
3 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193 |  | 4.1311
4 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
5 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
6 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
1 |  | 2BHK | 529.0506 | 44.3477 | 573.3983 | 0 | 860.0974
2 |  | 2BHK | 529.0506 | 44.3477 | 573.3983 | 0 | 860.0974
3 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
4 |  | Refuge Area
5 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
6 |  | 2BHK | 527.7589 | 47.254 | 575.0129 | 0 | 862.5193
Wing K
Ground Floor For Residential, Meter Room & Entrance Lobby
1 |  | 1BHK | 402.1915 | 142.7048 | 544.8963 | 0 | 817.3444
2 |  | 1BHK | 402.1915 | 155.3148 | 557.5063 | 0 | 836.2595
3 |  | Entrance Lobby / Meter Room | [6 empty] | 10.764
4 |  | 1BHK | 401.8955 | 155.6378 | 557.5332 | 0 | 836.2998
5 |  | 1BHK | 324.2956 | 118.94 | 443.2357 | 0 | 664.8535
6 |  | 1BHK | 395.2756 | 142.3227 | 537.5983 | 0 | 806.3974
7 |  | 1BHK | 395.2756 | 154.9919 | 550.2675 | 0 | 825.4013
1st to 7th, 9th to 12th Floor For Residential
1 |  | 1BHK | 401.8955 | 56.1644 | 458.0599 | 0 | 687.0898
2 |  | 1BHK | 402.1915 | 56.5745 | 458.766 | 0 | 688.149
3 |  | 1BHK | 395.0011 | 56.5745 | 451.5756 | 0 | 677.3635
4 |  | 1BHK | 401.8955 | 56.5745 | 458.47 | 0 | 687.705
5 |  | 1BHK | 401.8955 | 56.1644 | 458.0599 | 0 | 687.0898
6 |  | 1BHK | 395.2756 | 56.8371 | 452.1128 | 0 | 678.1691
7 |  | 1BHK | 395.5716 | 24.5322 | 420.1039 | 0 | 630.1558
14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
1 |  | 1BHK | 401.8955 | 56.1644 | 458.0599 | 0 | 687.0898
2 |  | 1BHK | 402.1915 | 56.5745 | 458.766 | 0 | 688.149
3 |  | 1BHK | 395.0011 | 56.5745 | 451.5756 | 0 | 677.3635
4 |  | 1BHK | 401.8955 | 56.5745 | 458.47 | 0 | 687.705
5 |  | 1BHK | 401.8955 | 56.1644 | 458.0599 | 0 | 687.0898
6 |  | 1BHK | 395.2756 | 56.8371 | 452.1128 | 0 | 678.1691
7 |  | 1BHK | 395.5716 | 24.5322 | 420.1039 | 0 | 630.1558
8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
1 |  | 3BHK | 740.4825 | 80.6966 | 821.1791 | 0 | 1231.7687
3 |  | Refuge Area
4 |  | 1BHK | 401.8955 | 56.5745 | 458.47 | 0 | 687.705
5 |  | 1BHK | 401.8955 | 56.1644 | 458.0599 | 0 | 687.0898
6 |  | 1BHK | 395.2756 | 56.8371 | 452.1128 | 0 | 678.1691
7 |  | 1BHK | 395.5716 | 24.5322 | 420.1039 | 0 | 630.1558
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Wing J & K = Construction work is in process at the time of Visit. Internal Photographs was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Dry Balcony + Otla.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Construction details collected from Mr. Rajendra Giri.
* | Please check for Fire NOC.
* | We have referred EC from the Pragati portal, the EC does not consist of particular survey numbers, only village Hedutane, Kole, Gharivali, Katai, and Mangaon are mentioned.
* | We have added Wing J on 04/04/2023.
* | Recommended Rates/Other Charges of the Property have been revised on 30/04/2025.
* | We have updated Fire Noc on 16/09/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gangaram parshuram Lambore |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Lodha Codename Premier - Fiora J & K
Layout :
Google Map :
Formulas:
Hedutane = [Hedutane, row above]
Cluster 15.04
(Fiora)
Wing K
D
E
F
G
H
I
A
J
C
B
Cluster 15.04
(Fiora)
Wing K
Wing J
Fiora K
Fiora K
Fiora K
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C58: SACHIN: Floor with height
Note on I58: SACHIN: Floor with height
Note on C60: SACHIN: Survey Nos.
Note on C62: SACHIN: Height from AMSL
Note on D65: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F123: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H152: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27
28
29
30
31
32
33
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0