## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 05/08/2025
CPC Name: |  |  |  | Axis Badlpaur
Date Of Property Visit |  |  |  | 2025-08-05
Name of the builder group |  |  |  | M/s.Charms Developers
Name of the builder company |  |  |  | M/s.Charms Developers
Name of the Project |  |  |  | Charms Padmavati Royal Phase I & II
Contact Details ( Name & Contact No.) |  |  |  | Jhon Mathew 9930554400
Site Meet Contact Details ( Name & Contact No.) |  |  |  | Mr. Nitesh : 7045523045
Name / No of the Building |  |  |  | Phase I = Building No. 4, 5, 6, 10, 11 (Each Building consists of A & B Wings) Phase II = Building No. 1, 2, 7 & 9 (Each Building consists of A & B Wings)
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | Phase I = P51700045436 Phase II = P51700045389
Project location details |  | Charms Padmavati Royal Phase I & II, Survey No.89/1(A), 95/1(A), 95/2, 95/10, near Sai Icon Residency, Titwala - Goveli Road, Titwala, Titwala, Titwala east, Kalyan, Thane - 421605.
Survey No |  | 89/1(A), 95/1(A), 95/2, 95/10
Locality |  | Titwala
Road |  | Titwala - Goveli Road |  | Village |  | Titwala
City |  | Titwala east |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421605
Nearby Landmark |  | Sai Icon Residency |  | Distance from city centre: |  | 4.4 KM from Titwala Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Open Plot
West | NA | 30M Wide Dp Rd |  |  | Titwala- Goveli Road
North | NA | Other Plot |  |  | Open Plot
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.289873, 73.230060
Location Link |  | https://goo.gl/maps/xCzLpJN8SjGyDbTK9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 32553.45
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.53082
Total FSI availaible for the project |  |  |  | 1.5308
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 49833.36
Total number of Buildings |  |  |  | 18 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority (MHADA)
Layout Approval No |  | EE/BP/PMAY/A/MHADA/326/2024 |  |  | Dated | 2024-05-06
Approved Floor plan No. |  | EE/BP/PMAY/A/MHADA/326/2024 |  |  | Dated | 2024-05-06
Commencement-CC No Valid Up to: |  | EE/BP/PMAY/A/MHADA/227/2022 |  |  | Dated | 2022-05-08
|  | This C.C is valid up to & issued for the work up to plinth level for 4 building i.e. Bldg. No. 4, 6, 10 & 11. |  |  | Valid Upto Date | 2023-05-05
Commencement-CC No Valid Up to: |  | EE/BP/PMAY/A/MHADA/434/2023 |  |  | Dated | 2023-06-01
|  | This Plinth C.C is valid up to & issued for the work up to plinth level for 5 building i.e. Bldg. No. 1, 2, 5, 7 & 9 |  |  | Valid Upto Date | 2024-05-31
Commencement-CC No Valid Up to: |  | EE/BP/PMAY/A/MHADA/124/2023 |  |  | Dated | 2023-02-16
Building No. 4(A & B Wing) = G + 1st to 7th Floor
Commencement-CC No Valid Up to: |  | EE/BP/PMAY/A/MHADA/909/2023 |  |  | Dated | 2023-11-28
Building No. 9(A & B Wing) = G + 1st to 7th Floor
Commencement-CC No Valid Up to: |  | EE/BP/PMAY/A/MHADA/306/2024 |  |  | Dated | 2024-04-23
Bldg No.5, 6 & 11 = Gr/St + 1st to 7th Floor Bldg No.2 & 7 = Gr/St + 1st to 11th Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 49833.36
Approved no of units |  |  | Flats - 942, Shop = 54
Approved no of Floors |  |  | Phase I = Building No. 4, 5, 6, 10 & 11 = G + 1st to 7th Floor Phase II = Building No. 1, 2 & 7 = Gr + 1st to 11th Floor Building No. 9 = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Phase I - Building No. 4 = G + 7th Floor
Phase I - Building No. 5 = G + 7th Floor
Phase I - Building No. 10 & 11 = G + 7th Floor
Phase I - Building No. 6 = G + 1st to 7th Floor
Phase II - Building No. 9 = Gr + 1st to 11th Floor
Phase II - Building No. 1, 2 & 7 = Gr + 1st to 11th Floor
Expected Completion |  |  | As per RERA (Phase I & II) = 30/04/2027 Phase II = 30/04/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Phase II - Building No. 1 (A Wing) = Gr + 1st to 11th Floor | [5 empty] | Excavation work in process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 |  | Excavation work in process
Stage of construction: |  | Excavation work in process
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 5.5 | 50% | 0% |  | 10% |  | Excavation in process | 5.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 11
Construction details: |  | Phase II - Building No. 1 (B Wing) = Gr + 1st to 11th Floor | [5 empty] | Excavation Completed, Footing work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | Excavation | , Footing work is process
Stage of construction: |  | Excavation Completed, Footing work is process | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% | 2.5% |  | 26.25% |  | Excavation in process | 5.5
Plinth |  | 2.75 | 25% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 11
Construction details: |  | Phase II - Building No. 2 = Gr + 1st to 11th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 7 Floor Completed | , External Plaster upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% | 71.36% |  | 88.18% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 12 | 100% |  |  |  |  | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 11 | 100% |  |  |  |  | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 63.64% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 11
Construction details: |  | Phase I - Building No. 4 A Wing = G + 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 6 Floor, Painting upto 6 Floor Completed | , Flooring upto 6 Floor, Painting upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 6 Floor, Painting upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 87.86% |  | 94.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 85.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Phase I - Building No. 4 B Wing = G + 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 5 Floor, Painting upto 4 Floor Completed | , Flooring upto 5 Floor, Painting upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 5 Floor, Painting upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 85% |  | 93.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 71.43% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 57.14% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Phase I - Building No. 5 = G + 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 6 Floor Completed | , External Plaster upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 73.57% |  | 89.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Phase I - Building No. 6 = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 3 Slab, Brickwork upto 2 Floor Completed | , RCC upto 3 Slab, Brickwork upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 3 Slab, Brickwork upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 27.14% |  | 57.68% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 3 | 37.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 2 | 28.57% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Phase II - Building No. 7 = Gr + 1st to 11th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 7 Floor Completed | , External Plaster upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% | 71.36% |  | 88.18% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 12 | 100% |  |  |  |  | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 11 | 100% |  |  |  |  | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 63.64% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 11
Construction details: |  | Phase II - Building No. 9 = Gr + 1st to 11th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% | 13.33% |  | 47.5% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 1 | 8.333% |  |  |  |  | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 11
Construction details: |  | Phase I - Building No. 10 (A Wing) = G + 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor Completed | , External Plaster upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 72.14% |  | 88.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Phase I - Building No. 10 (B Wing) = G + 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 15% |  | 48.75% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 1 | 12.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Phase I - Building No. 11 = G + 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 5.25 Floor, External Plaster upto 4.9 Floor Completed | , Internal Plaster upto 5.25 Floor, External Plaster upto 4.9 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 5.25 Floor, External Plaster upto 4.9 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 70.12% |  | 87.25% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75 |  | 1 |  | 0
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 5.25 | 75% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4.9 | 70% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3800 |  |  |  | 3100 to 3800 | 2023-05-09 | Rushikesh | IGR
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8500 |  |  | 7000 to 8500 | 2025-03-21 | Bhargav | Building No. 2 Shop 11
Development Charges |  |  |  |  | 150000
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 3040
Commercial Area Details :
Building & Wing |  |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Phase - II | Bldg No. 1 | Shop | 12 | 1686.2882 |  | 2613.7468
Wing A + B
| Bldg No. 2 | Shop | 12 | 1686.2882 |  | 2613.7468
Wing A + B
| Bldg No. 7 | Shop | 12 | 1686.2882 |  | 2613.7468
Wing A + B
| Amenity Building | Shop | 12 | 1686.2882 |  | 6483.1464
|  | Conventional Centre | 2 | 7927.3631 |  | 6143.7064
|  | MP Room | 4 | 1926.3793 |  | 1492.9439
Total |  |  | 54 | 16598.8953 |  | 21961.0371
Residential Area Details :
Building & Wing |  |  | No. of Units | Total Carpet Area |  | Total Saleable Area |  |  | rate sheet
Phase I | Building No. 4 | Wing A | 46 | 18088.1055 |  | 27132.1582 |  |  | cost sheet | visitor | market
|  | Wing B | 46 | 18088.1055 |  | 27132.1582 |  |  | 3400 | 3000 | 3000
| Building No. 5 | Wing A | 46 | 18088.1055 |  | 27132.1582
|  | Wing B | 46 | 18088.1055 |  | 27132.1582
| Building No. 6 | Wing A | 46 | 18088.1055 |  | 27132.1582
|  | Wing B | 46 | 18088.1055 |  | 27132.1582
| Building No. 10 | Wing A | 46 | 18088.1055 |  | 27132.1582
|  | Wing B | 46 | 18088.1055 |  | 27132.1582
| Building No. 11 | Wing A | 46 | 18088.1055 |  | 27132.1582
|  | Wing B | 46 | 18088.1055 |  | 27132.1582
Phase - II | Building No. 1 | Wing A | 65 | 27181.791 |  | 40772.6865
|  | Wing B | 65 | 27181.791 |  | 40772.6865
| Building No. 2 | Wing A | 65 | 27181.791 |  | 40772.6865
|  | Wing B | 65 | 27181.791 |  | 40772.6865
| Building No. 7 | Wing A | 65 | 27181.791 |  | 40772.6865
|  | Wing B | 65 | 27181.791 |  | 40772.6865
| Building No. 9 | Wing A | 46 | 18088.1055 |  | 27132.1582
|  | Wing B | 46 | 18088.1055 |  | 27132.1582
Total |  |  | 942 | 380148.0116 |  | 570222.0174
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Phase II
Building No. 1
Wing A + B
Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
1 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  | 7.41 | 10.764
2 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  | 7.125
3 |  | Shop | 244.2352 | 0 | 378.5645 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  | 3028515.984
4 |  | Shop | 144.6682 | 0 | 224.2356 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
5 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
6 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
7 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
8 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
9 |  | Shop | 144.6682 | 0 | 224.2356 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
10 |  | Shop | 244.2352 | 0 | 378.5645 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
11 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
12 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
Building No. 2
Wing A + B
Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
1 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 82.7752
2 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 80.0842
3 |  | Shop | 244.2352 | 0 | 378.5645 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 137.1334
4 |  | Shop | 144.6682 | 0 | 224.2356 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 137.1334
5 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 118.404
6 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 82.6675
7 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 82.6675
8 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 118.404
9 |  | Shop | 144.6682 | 0 | 224.2356 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 137.1334
10 |  | Shop | 244.2352 | 0 | 378.5645 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 137.1334
11 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 80.0842
12 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking |  |  | 82.7752
Building No. 7
Wing A + B
Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
1 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
2 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
3 |  | Shop | 244.2352 | 0 | 378.5645 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
4 |  | Shop | 144.6682 | 0 | 224.2356 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
5 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
6 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
7 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
8 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
9 |  | Shop | 144.6682 | 0 | 224.2356 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
10 |  | Shop | 244.2352 | 0 | 378.5645 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
11 |  | Shop | 122.1714 | 0 | 189.3657 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
12 |  | Shop | 104.949 | 0 | 162.671 | Ground Floor For Commercial, Society Office, Drivers Room, Meter Room & Parking
Amenity Building
Ground Floor For Commercial & Parking
1 |  | Shop | 197.4118 | 0 | 305.9882 | Ground Floor For Commercial & Parking
2 |  | Shop | 197.4118 | 0 | 305.9882 | Ground Floor For Commercial & Parking
3 |  | Shop | 281.9092 | 0 | 436.9592 | Ground Floor For Commercial & Parking
4 |  | Shop | 281.9092 | 0 | 436.9592 | Ground Floor For Commercial & Parking |  |  |  | 0
5 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking |  |  |  | 0
6 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
7 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
8 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
9 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
10 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
11 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
12 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
13 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
14 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
15 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
16 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
17 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
18 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
19 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
20 |  | Shop | 201.5021 | 0 | 312.3282 | Ground Floor For Commercial & Parking
1st Floor For Commrecial
1 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
2 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
3 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
4 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial |  |  |  | 0
5 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial |  |  |  | 0
6 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
7 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
8 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
9 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
10 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
11 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
12 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
13 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
14 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
15 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
16 |  | Shop | 197.5194 | 0 | 306.1551 | 1st Floor For Commrecial
2nd & 3rd Floor For Commercial
1 |  | Conventional Centre | 3963.6815 | 0 | 6143.7064 | 2nd & 3rd Floor For Commercial
2 |  | Multipurpose Room - 1 | 565.998 | 0 | 877.2969 | 2nd & 3rd Floor For Commercial
3 |  | Multipurpose Room - 2 | 397.1916 | 0 | 615.647 | 2nd & 3rd Floor For Commercial
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Phase I
Building No. 4
Wing A
Ground Floor For Residential, Drivers Room & Parking
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Drivers Room & Parking |  | 28.955 |  | 1453140
2 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
3 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
4 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
1st to 7th Floor For Residential | [9 empty] | 0
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential |  | 3415.7268 | cost sheet | 1799617.014
2 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  | 2998.9714 | visitor | 1799617.014
3 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  | 3000.6384 |  | 1799617.014
4 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
5 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
6 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
Wing B | [9 empty] | 0
Ground Floor For Residential, Society Office & Parking | [9 empty] | 0
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Society Office & Parking |  |  |  | 1453140
2 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Society Office & Parking |  |  |  | 1453140
3 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Society Office & Parking |  |  |  | 1453140
4 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Society Office & Parking |  |  |  | 1453140
1st to 7th Floor For Residential | [9 empty] | 0
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential |  |  |  | 1799617.014
2 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
3 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
4 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
5 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
6 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
Building No. 5 | [9 empty] | 0
Wing A | [9 empty] | 0
Ground Floor For Residential, Drivers Room & Parking | [9 empty] | 0
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor |  |  |  | 1453140
2 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
3 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
4 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
1st to 7th Floor For Residential | [9 empty] | 0
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential |  |  |  | 1799617.014
2 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
3 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
4 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
5 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
6 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
Wing B | [9 empty] | 0
Ground Floor For Residential, Society Office & Parking | [9 empty] | 0
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor |  |  |  | 1453140
2 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
3 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
4 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
1st to 7th Floor For Residential | [9 empty] | 0
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential |  |  |  | 1799617.014
2 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
3 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
4 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
5 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
6 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
Building No. 6 | [9 empty] | 0
Wing A | [9 empty] | 0
Ground Floor For Residential, Drivers Room & Parking | [9 empty] | 0
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Drivers Room & Parking |  |  |  | 1453140
2 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
3 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
4 |  | 1BHK | 322.92 | 0 | 484.38 |  |  |  |  | 1453140
1st to 7th Floor For Residential | [9 empty] | 0
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential |  |  |  | 1799617.014
2 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
3 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
4 |  | 1BHK | 399.9149 | 0 | 599.8723 |  |  |  |  | 1799617.014
5 |  | 1BHK | 399.9149 | 0 | 599.8723
6 |  | 1BHK | 399.9149 | 0 | 599.8723
Wing B
Ground Floor For Residential, Society Office & Parking
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Society Office & Parking
2 |  | 1BHK | 322.92 | 0 | 484.38
3 |  | 1BHK | 322.92 | 0 | 484.38
4 |  | 1BHK | 322.92 | 0 | 484.38
1st to 7th Floor For Residential
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential
2 |  | 1BHK | 399.9149 | 0 | 599.8723
3 |  | 1BHK | 399.9149 | 0 | 599.8723
4 |  | 1BHK | 399.9149 | 0 | 599.8723
5 |  | 1BHK | 399.9149 | 0 | 599.8723
6 |  | 1BHK | 399.9149 | 0 | 599.8723
Building No. 10
Wing A
Ground Floor For Residential, Drivers Room & Parking
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Drivers Room & Parking
2 |  | 1BHK | 322.92 | 0 | 484.38
3 |  | 1BHK | 322.92 | 0 | 484.38
4 |  | 1BHK | 322.92 | 0 | 484.38
1st to 7th Floor For Residential
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential
2 |  | 1BHK | 399.9149 | 0 | 599.8723
3 |  | 1BHK | 399.9149 | 0 | 599.8723
4 |  | 1BHK | 399.9149 | 0 | 599.8723
5 |  | 1BHK | 399.9149 | 0 | 599.8723
6 |  | 1BHK | 399.9149 | 0 | 599.8723
Wing B
Ground Floor For Residential, Society Office & Parking
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Society Office & Parking
2 |  | 1BHK | 322.92 | 0 | 484.38
3 |  | 1BHK | 322.92 | 0 | 484.38
4 |  | 1BHK | 322.92 | 0 | 484.38
1st to 7th Floor For Residential
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential
2 |  | 1BHK | 399.9149 | 0 | 599.8723
3 |  | 1BHK | 399.9149 | 0 | 599.8723
4 |  | 1BHK | 399.9149 | 0 | 599.8723
5 |  | 1BHK | 399.9149 | 0 | 599.8723
6 |  | 1BHK | 399.9149 | 0 | 599.8723
Building No. 11
Wing A
Ground Floor For Residential, Drivers Room & Parking
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Drivers Room & Parking
2 |  | 1BHK | 322.92 | 0 | 484.38
3 |  | 1BHK | 322.92 | 0 | 484.38
4 |  | 1BHK | 322.92 | 0 | 484.38
1st to 7th Floor For Residential
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential
2 |  | 1BHK | 399.9149 | 0 | 599.8723
3 |  | 1BHK | 399.9149 | 0 | 599.8723
4 |  | 1BHK | 399.9149 | 0 | 599.8723
5 |  | 1BHK | 399.9149 | 0 | 599.8723
6 |  | 1BHK | 399.9149 | 0 | 599.8723
Wing B
Ground Floor For Residential, Society Office & Parking
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Society Office & Parking
2 |  | 1BHK | 322.92 | 0 | 484.38
3 |  | 1BHK | 322.92 | 0 | 484.38
4 |  | 1BHK | 322.92 | 0 | 484.38
1st to 7th Floor For Residential
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential
2 |  | 1BHK | 399.9149 | 0 | 599.8723
3 |  | 1BHK | 399.9149 | 0 | 599.8723
4 |  | 1BHK | 399.9149 | 0 | 599.8723
5 |  | 1BHK | 399.9149 | 0 | 599.8723
6 |  | 1BHK | 399.9149 | 0 | 599.8723
Phase II
Building No. 1
Wing A
1st to 7th & 9th to 11th Floor For Residential
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 1st to 7th & 9th to 11th Floor For Residential |  | 27.48
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
5 |  | 1BHK | 418.1814 | 0 | 627.2721
6 |  | 1BHK | 418.1814 | 0 | 627.2721
8th Floor ( Part Refuge Floor )
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 8th Floor ( Part Refuge Floor )
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
- |  | Refuge Area
5 |  | 1BHK | 418.1814 | 0 | 627.2721
Wing B
1st to 7th & 9th to 11th Floor For Residential
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 1st to 7th & 9th to 11th Floor For Residential
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
5 |  | 1BHK | 418.1814 | 0 | 627.2721
6 |  | 1BHK | 418.1814 | 0 | 627.2721
8th Floor ( Part Refuge Floor )
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 8th Floor ( Part Refuge Floor )
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
- |  | Refuge Area
5 |  | 1BHK | 418.1814 | 0 | 627.2721
Building No. 2
Wing A
1st to 7th & 9th to 11th Floor For Residential
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 1st to 7th & 9th to 11th Floor For Residential
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
5 |  | 1BHK | 418.1814 | 0 | 627.2721
6 |  | 1BHK | 418.1814 | 0 | 627.2721
8th Floor ( Part Refuge Floor )
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 8th Floor ( Part Refuge Floor )
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
- |  | Refuge Area
5 |  | 1BHK | 418.1814 | 0 | 627.2721
Wing B
1st to 7th & 9th to 11th Floor For Residential
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 1st to 7th & 9th to 11th Floor For Residential
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
5 |  | 1BHK | 418.1814 | 0 | 627.2721
6 |  | 1BHK | 418.1814 | 0 | 627.2721
8th Floor ( Part Refuge Floor )
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 8th Floor ( Part Refuge Floor )
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
- |  | Refuge Area
5 |  | 1BHK | 418.1814 | 0 | 627.2721
Building No. 7
Wing A
1st to 7th & 9th to 11th Floor For Residential
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 1st to 7th & 9th to 11th Floor For Residential
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
5 |  | 1BHK | 418.1814 | 0 | 627.2721
6 |  | 1BHK | 418.1814 | 0 | 627.2721
8th Floor (Part Refuge Floor )
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 8th Floor (Part Refuge Floor )
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
- |  | Refuge Area
5 |  | 1BHK | 418.1814 | 0 | 627.2721
Wing B
1st to 7th & 9th to 11th Floor For Residential
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 1st to 7th & 9th to 11th Floor For Residential
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
5 |  | 1BHK | 418.1814 | 0 | 627.2721
6 |  | 1BHK | 418.1814 | 0 | 627.2721
8th Floor ( Part Refuge Floor )
1 |  | 1BHK | 418.1814 | 0 | 627.2721 | 8th Floor ( Part Refuge Floor )
2 |  | 1BHK | 418.1814 | 0 | 627.2721
3 |  | 1BHK | 418.1814 | 0 | 627.2721
4 |  | 1BHK | 418.1814 | 0 | 627.2721
- |  | Refuge Area
5 |  | 1BHK | 418.1814 | 0 | 627.2721
Building No. 9
Wing A
Ground Floor For Residential, Drivers Room & Parking
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Drivers Room & Parking
2 |  | 1BHK | 322.92 | 0 | 484.38
3 |  | 1BHK | 322.92 | 0 | 484.38
4 |  | 1BHK | 322.92 | 0 | 484.38
1st to 7th Floor For Residential
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential
2 |  | 1BHK | 399.9149 | 0 | 599.8723
3 |  | 1BHK | 399.9149 | 0 | 599.8723
4 |  | 1BHK | 399.9149 | 0 | 599.8723
5 |  | 1BHK | 399.9149 | 0 | 599.8723
6 |  | 1BHK | 399.9149 | 0 | 599.8723
Wing B
Ground Floor For Residential, Society Office & Parking
1 |  | 1BHK | 322.92 | 0 | 484.38 | Ground Floor For Residential, Society Office & Parking
2 |  | 1BHK | 322.92 | 0 | 484.38
3 |  | 1BHK | 322.92 | 0 | 484.38
4 |  | 1BHK | 322.92 | 0 | 484.38
1st to 7th Floor For Residential
1 |  | 1BHK | 399.9149 | 0 | 599.8723 | 1st to 7th Floor For Residential
2 |  | 1BHK | 399.9149 | 0 | 599.8723
3 |  | 1BHK | 399.9149 | 0 | 599.8723
4 |  | 1BHK | 399.9149 | 0 | 599.8723
5 |  | 1BHK | 399.9149 | 0 | 599.8723
6 |  | 1BHK | 399.9149 | 0 | 599.8723
Remarks:
* | Bldg No. 1 (A Wing) = Work is same as last visit (20/06/2025). Bldg No.1 (B Wing), 2, 4, 5, 6, 7 & 11 = Construction work is in process at the time of visit. Bldg No. 9 = Work is same as last visit (07/08/2024). Bldg No. 10 (A Wing) = Work is same as last visit (20/06/2025). Building No. 10 (B Wing) = Work is same as last visit (15/02/2024).
* | Phase - II - Building No. 3 & 8 for future expansion.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + C.B Area + E.P Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates / Other charges of the Property have been revised on 09/05/2023 & 21/03/2025.
* | We have Updated Approved Plans of all buildings on 21/03/2025.
* | On Site, we meet Mr. Tushar (9619968874)
* | We have Updated CC for Building No. 9 (on 18/03/2024).
* | We have Updated CC for Building No.5, 6, 11, 2 & 7 (dtd.29/04/2024).
* | Since the project has received first CC on 01/06/2023., But construction work of Building No. 1 is not yet started.
* | Validity of CC for building no.10 is expired on 05/05/2023 & construction work goes beyond CC. Please provide revised CC for Building No. 10.
* | Validity of CC for building no.1 is expired on 31/05/2024. Please provide revised CC for Building No.1.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area. | [7 empty] | Phase I = Building No. 4, 5, 6, 10, 11 (Each Building consists of A & B Wings)
Inspected By : |  | Gangaram parshuram Lambore |  | Report By : |  | Pooja Kawale |  | Phase II = Building No. 1, 2, 7 & 9 (Each Building consists of A & B Wings)
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Charms Padmavati Royal Phase I & II
PHOTOGRAPHS OF PROPERTY : |  |  | Charms Padmavati Royal Phase I & II
Layout : | Charms Padmavati Royal Phase I & II
Google Map : |  | Charms Padmavati Royal Phase I & II
Building No.4
Building No.10 & 11
Building No.6
Building No.4
Building No.4
Building No.10 & 11
Building No.6
Building No.4
Building No.10 & 11
Building No.6
Bldg No.1A
01
02
03
04
05
06
07
08
09
10
11
Bldg 2
Bldg No.1A
Bldg 7
01
02
03
04
05
06
07
08
09
10
11

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted