## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-02
Project Name |  | Arihant Aaradhya Phase I (Valentia, Wesley, Laura, Mabel) Arihant Aaradhya Phase II (Naldo, Patracia, Querida, Osane) |  | Date & Time of Site Visit |  | 02/08/2025 @02:52 PM |  |  | 2025-05-05 | 2025-08-05
Name of the person met at site & Contact No. |  | Ms. Nisha 8657767248 Mr. Aman 9167217682 |  | Date of Report Release |  | 2025-05-06 |  |  |  | 92
Data from APF Request Form | [8 empty] | 2025-05-16 | -81
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Arihant Superstructures Limited |  | Developer Name |  | Arihant Superstructures Limited
Developer Office Address |  | Floor No. 26, Plot No 13/1 - TTC Industrial Area, Thane Belapur Road, Turbhe MIDC, Turbhe, Navi Mumbai, Maharashtra - 400705
Project Address | As per ARF | Survey No.14/1, Village, Sonale-Bapgaon Rd, Taluka, Bhiwandi, Maharashtra 421302
| As per Legal Documents | Arihant Aaradhya Phase I, Survey No.14, near Jay Ambe Park, Kalyan Sape Road, Bapgaon, Bapgaon, Bhiwandi, Bhiwandi, Thane - 421302.
| As per Actual at site | Arihant Aaradhya Phase I, Survey No.14, near Jay Ambe Park, Kalyan Sape Road, Bapgaon, Bapgaon, Bhiwandi, Bhiwandi, Thane - 421302.
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Town Planning, Thane
RERA Registration No. | : | Arihant Aaradhya Phase I - P51700045430 Arihant Aaradhya Phase II -P51700049981 |  | RERA Registration Validity | : | Arihant Aaradhya Phase I -31/03/2029 Arihant Aaradhya Phase II - 31/12/2030
Project Launch Date | : | Arihant Aaradhya Phase I - 18/05/2022 Arihant Aaradhya Phase II - 06/03/2023 |  | Construction Start Date | : | Arihant Aaradhya Phase I -May - 2022 Arihant Aaradhya Phase II - March -2023
Proposed Date of Completion (As per RERA) | : | Arihant Aaradhya Phase I -31/03/2029 Arihant Aaradhya Phase II - 31/12/2030 |  | Developer Bank Name (As per RERA) | : | ICICI BANK IFSC Code ICIC0002841
Project Type (Mixed, Residential, Comm.) | : | Residential |  | Plot Area (In Sq.Mt) | : | 26700
FSI/FAR Permissible | : | 1.1 |  | Net Plot Area (In Sq.Mt) | : | 26144.99
Permissible Built up Area (In Sq.Mt) | : | 68966.49 |  | Proposed Built up Area (In Sq.Mt) | : | 68966.49
Total Number of Units Approved | : | Flats = 852 |  | Total Number of Units Planned | : | As per RERA Site Flats = 852
Latitude, Longitude | : | 19.2707314,73.1445402 |  | Landmark | : | Moreshwar Residency
Location Link | : | https://maps.app.goo.gl/uPLpNNHBCz5pZeF99
Extra Amenities available | : | Garden, Kids Play Area, Clubhouse, Banquet Hall, Gym, Multi Sports Court, Senior Citizen Seating Area, Podium Landscaped, Indoor games, etc. | [5 empty] | From Official Website
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 9m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 1.5 KM from Balasaheb Thakare Bus Stop
Distance from the nearest School (Km) | : | About 1.2 KM from St Mary's School |  | Distance from Hospital (Km) | : | About 1.3KM form Vedant Kalyan Hospital
Distance from the Main Market (Km) | : | 1. Approx. 600M from R Mart. 2. Approx. 2.4 KM from D Mart. |  | Distance from Railway Station (Km) | : | 5.3 KM from Kalyan Railway Station 4.7 KM from Ambivali Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East | West
East |  | Adj. S. No.13 & 19 |  |  | Open Plot
West |  | Open Plot |  |  | Open Plot
North |  | 12 M W Road |  |  | Road
South |  | Adj. S. No.118 |  |  | Open Plot
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Laura |  | Sale | G + 1st to 14th Floor |  |  | G + 1st to 14th Floor
Mable |  | Sale | G + 1st to 14th Floor |  |  | G + 1st to 14th Floor
Valentia |  | Sale | G + 1st to 14th Floor |  |  | G + 1st to 14th Floor
Wesley |  | Sale | G + 1st to 14th Floor |  |  | G + 1st to 14th Floor
Naldo |  | Sale | G + 1st to 14th Floor |  |  | G + 1st to 14th Floor
Patracia |  | Sale | G + 1st to 14th Floor |  |  | G + 1st to 14th Floor
Querida |  | Sale | G + 1st to 14th Floor |  |  | G + 1st to 14th Floor
Osane |  | Sale | G + 1st to 14th Floor |  |  | G + 1st to 14th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | BS/Rekhankan/BP/Mouje-Bapgaon/T- Bhiwandi/ SSTN/784 |  |  |  | Date: | 2022-03-14
Approved Plan Details | : | BS/Rekhankan/BP/Mouje-Bapgaon/T- Bhiwandi/ SSTN/785 |  |  |  | Date: | 2022-03-14
CC Details Valid Up to: |  | Mahsul/K-1/T-8/B.P/Mj-Bapgaon-Bhiwandi/SR-09/2022 |  |  |  | Date: | 2022-03-24
Laura = G + 1st to 14th Floor Mable = G + 1st to 14th Floor Valentia = G + 1st to 14th Floor Wisley = G + 1st to 14th Floor Naldo = G + 1st to 14th Floor Patracia = G + 1st to 14th Floor Querida = G + 1st to 14th Floor Osane = G + 1st to 14th Floor
Environmental Clearance Details | : |  |  |  |  | Date:
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Other NOC Details | : |  |  |  |  | Date:
Construction Status | [7 empty] | Construction table updated 19/11/2024
Laura = G + 1st to 14th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 9 Floor, Flooring & Fitting upto 4 Floor Completed
|  |  | 0 | 1 |  | 0 | 14 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 66.07% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 9 Floor, Flooring & Fitting upto 4 Floor Completed |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 2.8
Brickwork |  | 14 | 100% |  |  |  |  | Footing Completed | 5.6
Internal Plaster |  | 14 | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 14 | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 9 | 64.29% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 4 | 28.57% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 9.8
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Mable = G + 1st to 14th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 10 Floor, Flooring & Fitting upto 8 Floor, Wooden Work upto 8 Floor Completed
|  |  | 0 | 1 |  | 0 | 14 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 70.71% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 10 Floor, Flooring & Fitting upto 8 Floor, Wooden Work upto 8 Floor Completed |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 2.8
Brickwork |  | 14 | 100% |  |  |  |  | Footing Completed | 5.6
Internal Plaster |  | 14 | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 14 | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 10 | 71.43% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 8 | 57.14% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 8 | 57.14% |  |  |  |  | Plinth in process | 9.8
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Valentia = G + 1st to 14th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 12 Floor, Flooring & Fitting upto 10 Floor, Wooden Work upto 8 Floor, Electrical & Sanitary fittings upto 3 Floor Completed
|  |  | 0 | 1 |  | 0 | 14 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 73.39% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 12 Floor, Flooring & Fitting upto 10 Floor, Wooden Work upto 8 Floor, Electrical & Sanitary fittings upto 3 Floor Completed |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 2.8
Brickwork |  | 14 | 100% |  |  |  |  | Footing Completed | 5.6
Internal Plaster |  | 14 | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 14 | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 12 | 85.71% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 10 | 71.43% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 8 | 57.14% |  |  |  |  | Plinth in process | 9.8
Electrical & Sanitary fittings |  | 3 | 21.43% |  |  |  |  | Plinth completed | 14
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Wesley = G + 1st to 14th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work upto 12 Floor, Electrical & Sanitary fittings upto 8 Floor Completed
|  |  | 0 | 1 |  | 0 | 14 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 78.57% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work upto 12 Floor, Electrical & Sanitary fittings upto 8 Floor Completed |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 2.8
Brickwork |  | 14 | 100% |  |  |  |  | Footing Completed | 5.6
Internal Plaster |  | 14 | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 14 | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 14 | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 14 | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 12 | 85.71% |  |  |  |  | Plinth in process | 9.8
Electrical & Sanitary fittings |  | 8 | 57.14% |  |  |  |  | Plinth completed | 14
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Naldo = G + 1st to 14th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 5 Floor, Internal Plaster upto 2 Floor Completed
|  |  | 0 | 1 |  | 0 | 14 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 40.48% |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 5 Floor, Internal Plaster upto 2 Floor Completed |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 8 | 53.33% |  |  |  |  | Footing in Process | 2.8
Brickwork |  | 5 | 35.71% |  |  |  |  | Footing Completed | 5.6
Internal Plaster |  | 2 | 14.29% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 9.8
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Patracia = G + 1st to 14th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
|  |  | 0 | 1 |  | 0 | 14 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 28.33% |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 2 | 13.33% |  |  |  |  | Footing in Process | 2.8
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 5.6
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 9.8
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Querida = G + 1st to 14th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 14 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 2.8
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 5.6
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 9.8
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Osane = G + 1st to 14th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 4 Floor Completed
|  |  | 0 | 1 |  | 0 | 14 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 39.76% |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 4 Floor Completed |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 8 | 53.33% |  |  |  |  | Footing in Process | 2.8
Brickwork |  | 4 | 28.57% |  |  |  |  | Footing Completed | 5.6
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 9.8
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 52.79%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 8700 to 9200 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 300000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 575
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 2259.38
Distress Value (Rs. Per sqft) |  |  |  |  | : | 460
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Laura |  | - |  | 110 |  | 40986.9439
Mable |  | - |  | 110 |  | 40986.9439
Valentia |  | - |  | 110 |  | 40986.9439
Wisley |  | - |  | 110 |  | 58270.914
Naldo |  | - |  | 82 |  | 42908.9638
Patracia |  | - |  | 110 |  | 40986.9439
Querida |  | - |  | 110 |  | 58270.914
Osane |  | - |  | 110 |  | 58270.914
Total |  | - |  | 852 |  | 381669.4814
Grand Total |  | - |  | 852 |  | 381669.4814
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Phase I
Laura
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential | [8 empty] | 10.764
101,..,1401 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 101,..,1401 | 101 | 1401
102,..,1402 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 102,..,1402 | 102 | 1402
103,..,1403 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 103,..,1403 | 103 | 1403
104,..,1404 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 104,..,1404 | 104 | 1404
105,..,1405 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 105,..,1405 | 105 | 1405
106,..,1406 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 106,..,1406 | 106 | 1406
107,..,1407 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 107,..,1407 | 107 | 1407
108,..,1408 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 108,..,1408 | 108 | 1408
8th & 13th Floor (Part Refuge Area)
801 & 1301 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 801 & 1301 | 801 | 1301
802 & 1302 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 802 & 1302 | 802 | 1302
803 & 1303 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 803 & 1303 | 803 | 1303
804 & 1304 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 804 & 1304 | 804 | 1304
805 & 1305 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 805 & 1305 | 805 | 1305
806 & 1306 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 806 & 1306 | 806 | 1306
807 & 1307 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 807 & 1307 | 807 | 1307
808 & 1308 |  | Refuge Area | [11 empty] | 808 & 1308 | 808 | 1308
Mabel
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,..,1401 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 101,..,1401 | 101 | 1401
102,..,1402 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 102,..,1402 | 102 | 1402
103,..,1403 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 103,..,1403 | 103 | 1403
104,..,1404 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 104,..,1404 | 104 | 1404
105,..,1405 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 105,..,1405 | 105 | 1405
106,..,1406 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 106,..,1406 | 106 | 1406
107,..,1407 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 107,..,1407 | 107 | 1407
108,..,1408 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 108,..,1408 | 108 | 1408
8th & 13th Floor (Part Refuge Area)
801 & 1301 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 801 & 1301 | 801 | 1301
802 & 1302 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 802 & 1302 | 802 | 1302
803 & 1303 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 803 & 1303 | 803 | 1303
804 & 1304 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 804 & 1304 | 804 | 1304
805 & 1305 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 805 & 1305 | 805 | 1305
806 & 1306 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 806 & 1306 | 806 | 1306
807 & 1307 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 807 & 1307 | 807 | 1307
808 & 1308 |  | Refuge Area | [11 empty] | 808 & 1308 | 808 | 1308
Valentia
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,..,1401 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 101,..,1401 | 101 | 1401
102,..,1402 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 102,..,1402 | 102 | 1402
103,..,1403 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 103,..,1403 | 103 | 1403
104,..,1404 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 104,..,1404 | 104 | 1404
105,..,1405 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 105,..,1405 | 105 | 1405
106,..,1406 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 106,..,1406 | 106 | 1406
107,..,1407 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 107,..,1407 | 107 | 1407
108,..,1408 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 108,..,1408 | 108 | 1408
8th & 13th Floor (Part Refuge Area)
801 & 1301 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 801 & 1301 | 801 | 1301
802 & 1302 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 802 & 1302 | 802 | 1302
803 & 1303 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 803 & 1303 | 803 | 1303
804 & 1304 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 804 & 1304 | 804 | 1304
805 & 1305 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 805 & 1305 | 805 | 1305
806 & 1306 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 806 & 1306 | 806 | 1306
807 & 1307 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 807 & 1307 | 807 | 1307
808 & 1308 |  | Refuge Area | [11 empty] | 808 & 1308 | 808 | 1308
Wesley
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,..,1401 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 101,..,1401 | 101 | 1401
102,..,1402 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 102,..,1402 | 102 | 1402
103,..,1403 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 103,..,1403 | 103 | 1403
104,..,1404 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 104,..,1404 | 104 | 1404
105,..,1405 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 105,..,1405 | 105 | 1405
106,..,1406 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 106,..,1406 | 106 | 1406
107,..,1407 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 107,..,1407 | 107 | 1407
108,..,1408 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 108,..,1408 | 108 | 1408
8th & 13th Floor (Part Refuge Area) | [7 empty] | `
801 & 1301 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 801 & 1301 | 801 | 1301
802 & 1302 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 802 & 1302 | 802 | 1302
803 & 1303 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 803 & 1303 | 803 | 1303
804 & 1304 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 804 & 1304 | 804 | 1304
805 & 1305 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 805 & 1305 | 805 | 1305
806 & 1306 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 806 & 1306 | 806 | 1306
807 & 1307 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 807 & 1307 | 807 | 1307
808 & 1308 |  | Refuge Area | [11 empty] | 808 & 1308 | 808 | 1308
Phase II
Naldo
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,..,1401 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 101,..,1401 | 101 | 1401
102,..,1402 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 102,..,1402 | 102 | 1402
103,..,1403 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 103,..,1403 | 103 | 1403
104,..,1404 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 104,..,1404 | 104 | 1404
105,..,1405 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 105,..,1405 | 105 | 1405
106,..,1406 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 106,..,1406 | 106 | 1406
8th & 13th Floor (Part Refuge Area)
801 & 1301 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 801 & 1301 | 801 | 1301
802 & 1302 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 802 & 1302 | 802 | 1302
803 & 1303 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 803 & 1303 | 803 | 1303
804 & 1304 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 804 & 1304 | 804 | 1304
805 & 1305 |  | - | Refuge Area | [10 empty] | 805 & 1305 | 805 | 1305
806 & 1306 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 806 & 1306 | 806 | 1306
Pantracia
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,..,1401 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 101,..,1401 | 101 | 1401
102,..,1402 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 102,..,1402 | 102 | 1402
103,..,1403 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 103,..,1403 | 103 | 1403
104,..,1404 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 104,..,1404 | 104 | 1404
105,..,1405 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 105,..,1405 | 105 | 1405
106,..,1406 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 106,..,1406 | 106 | 1406
107,..,1407 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 107,..,1407 | 107 | 1407
108,..,1408 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 108,..,1408 | 108 | 1408
8th & 13th Floor (Part Refuge Area)
801 & 1301 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 801 & 1301 | 801 | 1301
802 & 1302 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 802 & 1302 | 802 | 1302
803 & 1303 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 803 & 1303 | 803 | 1303
804 & 1304 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 804 & 1304 | 804 | 1304
805 & 1305 |  | - | 1BHK | 355.5349 | 25.403 | 0 | 380.938 | [6 empty] | 805 & 1305 | 805 | 1305
806 & 1306 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 806 & 1306 | 806 | 1306
807 & 1307 |  | - | 1BHK | 340.8959 | 23.6808 | 0 | 364.5767 | [6 empty] | 807 & 1307 | 807 | 1307
808 & 1308 |  | Refuge Area | [11 empty] | 808 & 1308 | 808 | 1308
Querida
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,..,1401 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 101,..,1401 | 101 | 1401
102,..,1402 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 102,..,1402 | 102 | 1402
103,..,1403 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 103,..,1403 | 103 | 1403
104,..,1404 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 104,..,1404 | 104 | 1404
105,..,1405 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 105,..,1405 | 105 | 1405
106,..,1406 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 106,..,1406 | 106 | 1406
107,..,1407 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 107,..,1407 | 107 | 1407
108,..,1408 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 108,..,1408 | 108 | 1408
8th & 13th Floor (Part Refuge Area)
801 & 1301 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 801 & 1301 | 801 | 1301
802 & 1302 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 802 & 1302 | 802 | 1302
803 & 1303 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 803 & 1303 | 803 | 1303
804 & 1304 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 804 & 1304 | 804 | 1304
805 & 1305 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 805 & 1305 | 805 | 1305
806 & 1306 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 806 & 1306 | 806 | 1306
807 & 1307 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 807 & 1307 | 807 | 1307
808 & 1308 |  | Refuge Area | [11 empty] | 808 & 1308 | 808 | 1308
Osane
Ground Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
101,..,1401 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 101,..,1401 | 101 | 1401
102,..,1402 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 102,..,1402 | 102 | 1402
103,..,1403 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 103,..,1403 | 103 | 1403
104,..,1404 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 104,..,1404 | 104 | 1404
105,..,1405 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 105,..,1405 | 105 | 1405
106,..,1406 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 106,..,1406 | 106 | 1406
107,..,1407 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 107,..,1407 | 107 | 1407
108,..,1408 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 108,..,1408 | 108 | 1408
8th & 13th Floor (Part Refuge Area) | [7 empty] | `
801 & 1301 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 801 & 1301 | 801 | 1301
802 & 1302 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 802 & 1302 | 802 | 1302
803 & 1303 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 803 & 1303 | 803 | 1303
804 & 1304 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 804 & 1304 | 804 | 1304
805 & 1305 |  | - | 2BHK | 523.238 | 25.403 | 0 | 548.6411 | [6 empty] | 805 & 1305 | 805 | 1305
806 & 1306 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 806 & 1306 | 806 | 1306
807 & 1307 |  | - | 2BHK | 489.4391 | 22.0662 | 0 | 511.5053 | [6 empty] | 807 & 1307 | 807 | 1307
808 & 1308 |  | Refuge Area | [11 empty] | 808 & 1308 | 808 | 1308
1st Floor
101 |  |  |  | 0 | 0 | 0 | 0
102 | [6 empty] | 0
103 | [6 empty] | 0
104 | [6 empty] | 0
105 | [6 empty] | 0
106 | [6 empty] | 0
107 | [6 empty] | 0
108 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [6 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [6 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [6 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [6 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [6 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [6 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [6 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [6 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [6 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [6 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [6 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [6 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [6 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [6 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [6 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [6 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [6 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [6 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [6 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [6 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [6 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit. Internal visit not allowed.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Fire NOC
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs | [8 empty] | (Naldo, Patracia, Querida, Osane)
Name of the Project |  |  | Arihant Aaradhya Phase I (Valentia, Wesley, Laura, Mabel) Arihant Aaradhya Phase II (Naldo, Patracia, Querida, Osane)
Project Site Address |  |  | Survey No.14/1, Village, Sonale-Bapgaon Rd, Taluka, Bhiwandi, Maharashtra 421302
Site Visit Date & Time |  |  | 02/08/2025 @02:52 PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Inspected By : |  | Mr. Mangesh Bapardekar |  | Authorized Signatory Name & Signature:
N
MABEL
Laura
Wesley
Valentia
Querida
Patracia
Naldo
Osane
Note on C9: SACHIN: As per initiation Mail
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on C20: From RERA
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G198: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%