## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 |  | 2025-08-01 | 90
Project Name |  | Bellissimo Mulund T2 Sale Building No.3 (Tower 2) (Wing C & D) |  | Date & Time of Site Visit |  | 01/08/2025 at 01:50PM |  | 2025-05-03
Name of the person met at site & Contact No. |  | Mr. Rajendra Giri |  | Date of Report Release |  | 08/08/2025
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Macrotech Developers Limited |  | Developer Name |  | Lodha Group
Developer Office Address |  | Bellissimo Mulund T2, Plot Bearing / CTS / Survey / Final Plot No.: 669 669/1 to 35 670 at Kurla, Kurla, Mumbai Suburban, 400081
Project Address | As per ARF | Bellissimo Mulund T2, Plot Bearing / CTS / Survey / Final Plot No.: 669 669/1 to 35 670 at Kurla, Kurla, Mumbai Suburban, 400082
| As per Legal Documents | Proposed Bldg. No.3 (Sale) Under S.R Scheme On Plot Bearing C.T.S No. 669, 669/1 to 35 & 670, 673, 673/1 to 7, 610, 610/1 to 26 & 666 of Village Mulund (E), Mumbai 400081
| As per Actual at site | Proposed Bldg. No.3 (Sale) Under S.R Scheme On Plot Bearing C.T.S No. 669, 669/1 to 35 & 670, 673, 673/1 to 7, 610, 610/1 to 26 & 666 of Village Mulund (E), Mumbai 400082
Documents Provided by GHF |  | CC.
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Slum Rehabilitation Authority (SRA)
RERA Registration No. | : | P51800018893 |  | RERA Registration Validity | : | 2026-12-30
Project Launch Date | : | 2018-12-11 |  | Construction Start Date | : | 2018-12-11
Proposed Date of Completion (As per RERA) | : | 2026-12-30 |  | Developer Bank Name (As per RERA) | : | HDFC Bank IFSC Code HDFC0000084
Project Type (Mixed, Residential, Comm.) | : | Residential |  | Plot Area (In Sq.Mt) | : | 9394.2
FSI/FAR Permissible | : | 2.4 |  | Net Plot Area (In Sq.Mt) | : | 9394.2
Permissible Built up Area (In Sq.Mt) | : | 51903.43 |  | Proposed Built up Area (In Sq.Mt) | : | 51903.43
Total Number of Units Approved | : | Flats = 204 |  | Total Number of Units Planned | : | As per RERA Site Flats = 216
Latitude, Longitude | : | 19.170722,72.958500 |  | Landmark | : | Lodha Regalia
Location Link | : | https://maps.app.goo.gl/4s3uo3ZjqLDb39PEA
Extra Amenities available | : | Jacuzzi, Maintenance Staff, Water Storage, Visitor Parking, Reserved Parking, Library, Service Lift, Football Field, Volleyball Court, Steam Room, Party Lawn, Temple, Swimming Pool, Cricket Pitch,Gated Community, Children's Play Area, Indoor Games, Fire Fighting System, Intercom, Club House, Gymnasium, Lift(s), 24x7 Security, 24X7 Water Supply, Car Parking, Power Backup etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Concrete |  | Width of the Road | : | 18.30 m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 140 M from Hanuman Chowk Bus Stop
Distance from the nearest School (Km) | : | About 350 M from Vidya Prabodhini English School |  | Distance from Hospital (Km) | : | About 350 M form Swatantryaveer V.D.Sawarkar BMC Hospital
Distance from the Main Market (Km) | : | 1. Approx. 120 M from Sahakar Dhanya Bhandar 2. Approx. 130 M from Shreenath Plaza Shopping complex. |  | Distance from Railway Station (Km) | : | 300 M from Mulund Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East | West
East |  | Other Plot |  |  | Building / Lokmanya Tilak Road
West |  | CTS No. 657, 668, 667 & 611 |  |  | Shri Harihareshwar Cooperative Housing Society
North |  | CTS No. 523, 525, 528, 526 & 609 |  |  | Ashirwad Critical Care Unit & Multi speciality
South |  | CTS No. 676, 674 |  |  | Building/Gopal Krishna Gokhale Road
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower 2 (Wing C & D) |  | Sale | 1B + Gr + 1st to 39th Floor |  |  | Wing C & D = 1B + Gr + 1st to 32nd Floor
Tower 2 |  | Sale
Tower 3 |  | Sale
Tower 4 |  | Sale
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | T/PVT/0040/20040928/AP/S3 |  |  |  | Date: | 2023-11-09
Approved Plan Details | : | T/PVT/0040/20040928/AP/S3 |  |  |  | Date: | 2023-11-09
CC Details Valid Up to: |  | T/PVT/0040/20040928/S3 |  |  |  | Date: | 2023-05-12
This C.C is re-endorsed as per approved amended plan dated 12/05/2023 i.e C.C upto plinth/podium top for tower 2 & 3 and upto full height i.e 39th part floors including LMR & OHT for tower - 1
CC Details Valid Up to: |  | T/PVT/0040/20040928/S3 |  |  |  | Date: | 2024-04-25
This CC is re-endorsed as per approved amended plans dtd 25/04/2024 further extended upto 33rd (pt) floor for wing C & D of proposed sale Building No.3.
Environmental Clearance Details | : |  |  |  |  | Date:
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Tower 2 (Wing C & D) = 1B + Gr + 1st to 39th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 24 Floor, Internal Plaster upto 19.2 Floor, External Plaster upto 19.2 Floor Completed
|  |  | 1 | 1 |  | 0 | 39 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.75
Excavation |  | 39 | 100% | 46.16% |  | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 24 Floor, Internal Plaster upto 19.2 Floor, External Plaster upto 19.2 Floor Completed |  | Excavation in process | 19.5
Plinth |  | 39 | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 25 | 62.5% |  |  |  |  | Footing in Process | 7.8
Brickwork |  | 24 | 61.54% |  |  |  |  | Footing Completed | 15.6
Internal Plaster |  | 19.2 | 49.23% |  |  |  |  | Basement 1 | 0
External Plaster |  | 19.2 | 49.23% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 25.35
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 39
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Tower 2= . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 2 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 1
Plinth |  | 2 | 100% |  |  |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.4
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 0.8
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 1.4
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 2
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 46.16%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 25000 to 26000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 1000000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 6272.7611
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 12386.6592
Distress Value (Rs. Per sqft) |  |  |  |  | : | 5018.2088
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing C |  | - |  | 112 |  | 92984.1682 |  |  | 25500
Wing D |  | - |  | 92 |  | 75492.7758
Total |  | - |  | 204 |  | 168476.944
Grand Total |  | - |  | 0 |  | 0
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Sale Building No. 3 (Tower 2)
Wing C
Basement Floor For Parking & STP
Ground Floor For Amenities
1st to 7th, 9th to 12th, 14th, 15th & 17th to 19th Floor For Residential
101,..,1901 |  | - | 2BHK | 663.0624 | 24.219 | 0 | 687.2814 | [5 empty] | 101,..,1901 | 101 | 1901
102,..,1902 |  | - | 2BHK | 650.5762 | 24.219 | 0 | 674.7952 | [5 empty] | 102,..,1902 | 102 | 1902
103,..,1903 |  | - | 3BHK | 876.1896 | 64.2611 | 0 | 940.4507 | [5 empty] | 103,..,1903 | 103 | 1903
104,..,1904 |  | - | 3BHK | 918.9227 | 64.2611 | 0 | 983.1838 | [5 empty] | 104,..,1904 | 104 | 1904
8th Floor (Part Refuge Area)
801 |  | - | 2BHK | 663.0624 | 24.219 | 0 | 687.2814
802 |  | - | Refuge Area
803 |  | -
804 |  | - | 3BHK | 918.9227 | 64.2611 | 0 | 983.1838
16th Floor (Part Refuge Area)
1601 |  | - | 2BHK | 663.0624 | 24.219 | 0 | 687.2814
1602 |  | - | Refuge Area
1603 |  | -
1604 |  | - | 3BHK | 918.9227 | 64.2611 | 0 | 983.1838
20th to 22nd, 24th to 29th & 31st Floor
2001,..,3101 |  | - | 2BHK | 663.0624 | 63.9382 | 0 | 727.0006 | [5 empty] | 2001,..,3101 | 2001 | 3101
2002,..,3102 |  | - | 2BHK | 650.5762 | 63.9382 | 0 | 714.5143 | [5 empty] | 2002,..,3102 | 2002 | 3102
2003,..,3103 |  | - | 3BHK | 876.1896 | 64.2611 | 0 | 940.4507 | [5 empty] | 2003,..,3103 | 2003 | 3103
2004,..,3104 |  | - | 3BHK | 918.9227 | 64.2611 | 0 | 983.1838 | [5 empty] | 2004,..,3104 | 2004 | 3104
23rd & 30th Floor (Part Refuge Area)
2301 & 3001 |  | - | 2BHK | 663.0624 | 63.9382 | 0 | 727.0006 | [5 empty] | 2301 & 3001 | 2301 | 3001
2302 & 3002 |  | - | Refuge Area | [9 empty] | 2302 & 3002 | 2302 | 3002
2303 & 3003 |  | - | [10 empty] | 2303 & 3003 | 2303 | 3003
2304 & 3004 |  | - | 3BHK | 918.9227 | 64.2611 | 0 | 983.1838 | [5 empty] | 2304 & 3004 | 2304 | 3004
32nd Floor For Terrace Open to Sky
Wing D
Basement Floor For Parking & STP
Ground Floor For Amenities
1st to 7th, 9th to 12th, 14th, 15th & 17th to 19th Floor For Residential
101,..,1901 |  | - | 3BHK | 917.9539 | 64.2611 | 0 | 982.215 | [5 empty] | 101,..,1901 | 101 | 1901
102,..,1902 |  | - | 2.5BHK | 722.1568 | 64.2611 | 0 | 786.4178 | [5 empty] | 102,..,1902 | 102 | 1902
103,..,1903 |  | - | 2BHK | 661.986 | 24.219 | 0 | 686.205 | [5 empty] | 103,..,1903 | 103 | 1903
8th Floor
801 |  | - | 3BHK | 917.9539 | 64.2611 | 0 | 982.215
802 |  | - | 2.5BHK | 722.1568 | 64.2611 | 0 | 786.4178
803 |  | - | 2BHK | 661.986 | 24.219 | 0 | 686.205
16th Floor
1601 |  | - | 3BHK | 917.9539 | 64.2611 | 0 | 982.215
1602 |  | - | 2.5BHK | 722.1568 | 64.2611 | 0 | 786.4178
1603 |  | - | 2BHK | 661.986 | 24.219 | 0 | 686.205
20th to 22nd, 24th to 29th & 31st Floor
2001,..,3101 |  | - | 3BHK | 917.9539 | 64.2611 | 0 | 982.215 | [5 empty] | 2001,..,3101 | 2001 | 3101
2002,..,3102 |  | - | 2.5BHK | 722.1568 | 64.2611 | 0 | 786.4178 | [5 empty] | 2002,..,3102 | 2002 | 3102
2003,..,3103 |  | - | 2BHK | 650.7914 | 64.2611 | 0 | 715.0525 | [5 empty] | 2003,..,3103 | 2003 | 3103
23rd & 30th Floor
2301 & 3001 |  | - | 3BHK | 917.9539 | 64.2611 | 0 | 982.215 | [5 empty] | 2301 & 3001 | 2301 | 3001
2302 & 3002 |  | - | 2.5BHK | 722.1568 | 64.2611 | 0 | 786.4178 | [5 empty] | 2302 & 3002 | 2302 | 3002
2303 & 3003 |  | - | 2BHK | 650.7914 | 64.2611 | 0 | 715.0525 | [5 empty] | 2303 & 3003 | 2303 | 3003
32nd Floor (Part Terrace Area)
3201 |  | - | Terrace Area
3202 |  | - | 2.5BHK | 722.1568 | 64.2611 | 0 | 786.4178
3203 |  | - | 2BHK | 650.7914 | 64.2611 | 0 | 715.0525
1st Floor
101 |  |  |  | 0 | 0 | 0 | 0
102 | [6 empty] | 0
103 | [6 empty] | 0
104 | [6 empty] | 0
105 | [6 empty] | 0
106 | [6 empty] | 0
107 | [6 empty] | 0
108 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [5 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [5 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [5 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [5 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [5 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [5 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [5 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [5 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [5 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [5 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [5 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [5 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [5 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [5 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [5 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [5 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [5 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [5 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [5 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [5 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [5 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit (Internal visit not allowed)
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Deck Area + Utility Area
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | In approved plan 13th Floor is not considered in the area & elevation plan so we have not considered 13th Floor
* | Please Ckeck For Fire NOC.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs
Name of the Project |  |  | Bellissimo Mulund T2 Sale Building No.3 (Tower 2) (Wing C & D)
Project Site Address |  |  | Bellissimo Mulund T2, Plot Bearing / CTS / Survey / Final Plot No.: 669 669/1 to 35 670 at Kurla, Kurla, Mumbai Suburban, 400082
Site Visit Date & Time |  |  | 01/08/2025 at 01:50PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Nainesh Tambe |  | Authorized Signatory Name & Signature
Sale Building No.3 Tower 2 (Wing C & D)
N
Bellissimo Mulund T2
Wing D
Wing C
D Wing
C Wing
Wing D
Wing C
Wing D
Wing C
Note on C9: SACHIN: As per initiation Mail
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G100: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%