## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 | 1 | 2025-08-06
Project Name |  |  | : | Wadhwa Atmosphere O2 (Wing D, E, F and G) |  | Date & Time of Site Visit |  | 06/08/2025 at 03:50PM
Name of the person met at site & Contact No. |  |  | : | Ms Trupti |  | Date of Report Release |  | 07/08/2025 | Ms.Sakshi 9088766829
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Atmosphere Realty Pvt Ltd | Developer Name | : | Atmosphere Realty Pvt Ltd |  |  | 2024-11-21
Developer Office Address |  |  | : | Plot No - 808, Building Name - Krushal Commercial Complex, Street Name - G M Road, Locality - Chembur (West)
Project Address | : | As per ARF | : | Building No. 2, CTS NO. 784-1, 785,.., 793 & 848, Village - Nahur, Mulund link road, Mulund (W), Mumbai - 4000080.
| : | As per Legal Documents | : | Building No. 2,on Plot Bearing CTS No.- 784-1, 785, 786, 787, 788, 790, 791, 792-A, 793 & 848 Of Village Nahur At Goregaon, Mulund Link Road, Mulund (W), Mumbai - 4000080.
| : | As per Actual at site | : | Building No. 2, CTS NO. 784-1, 785,.., 793 & 848, Village - Nahur, Mulund link road, Mulund (W), Mumbai - 4000080.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation Of Greater Mumbai (MCGM)
RERA Registration No. | : | D, E, F Wing - P51800019950 G Wing - P51800033845 |  |  | RERA Registration Validity | : | D, E, F Wing - Completed G Wing - 31/12/2028
Project Launch Date | : | 15/03/2019 - D, E, F Wing & 14/03/2022 - G Wing |  |  | Construction Start Date | : | 2019-03-15
Proposed Date of Completion (As per RERA) | : | D, E, F Wing - Completed G Wing - 31/12/2028 |  |  | Developer Bank Name (As per RERA) | : | ICICI IFSC Code - ICIC0000038
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 55509.5
FSI/FAR Permissible | : | 1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 115742.38
Permissible Built up Area (In Sq.Mt) | : | 115927.64 |  |  | Total Number of Units Planned | : | As Per RERA - Flats = 1250 |  | 1250
Total Number of Units Approved | : | Flats = 1101 |  |  | If Mixed, No. of Commercial Units | : | NA
Latitude | : | 19.1599 |  |  | Longitude | : | 72.948
Location Link | : | https://goo.gl/maps/kAkLMJE3nvxikFAq8?coh=178572&entry=tt
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | .4 KM from Nahur Bus Stop
Distance from the nearest School (Km) | : | About 0.27 KM from Somani Foundation School |  |  | Distance from Hospital (Km) | : | About 0.5KM form Fortis Hospital Mulund
Distance from the Main Market (Km) | : | 1. Approx. 1.6 KM from D Mart. 2. Approx. 2.4KM from Mulund Main Market. |  |  | Distance from Railway Station (Km) | : | 1.1 KM from Nahur Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Open Plot | Building No.1 | Road |  | Mulund - Goregaon Link Rd
As per Site / Actual |  |  | : | Open Plot | Building No.1 | Road |  | The Gateway Mulund
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing - D, E & F |  | Sale |  | 2Basement + Gr/St + 1st to 4th Podium + 5th to 47th Floor |  |  | 2Basement + Gr/St + 1st to 4th Podium + 5th to 47th Floor
Wing - G |  | Sale |  | 2Basement + Gr/St + 1st to 4th Podium + 5th to 47th Floor |  |  | 2Basement + Gr/St + 1st to 4th Podium + 5th to 32nd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | CHE/ES/1321/T/337(NEW) Date: 12/04/2023
CC Details | : | CHE/ES/1321/T/337(NEW)/FCC/6/Amend Date: 26/06/2023 Valid Up to Date: 28/10/2024 Valid Up to: Full CC is re endorsed for Residential Wings ‘D’, ‘E’ & ‘F’ i.e., upto top of 47th upper floor + LMR/OHT and for Commercial Wing i.e., upto top of 18th floor + LMR/OHT and further CC is granted upto top of 20th floor for Wing ‘G’ by restricting temporary structure area admeasuring 762.68 sq.mt and set back area admeasuring 6079.80 sq.mt as per last approved plans dated 12.04.2023. |  |  | Approved Plan Details Approved Plan Details For (Wing G) | : | CHE/ES/1321/T/337(NEW) Date: 30/12/2021 CHE/ES/1321/T/337(NEW) Date: 12/04/2023 |  | CHE/ES/1321/T/337(NEW
CHE/ES/1321/T/337(NEW)/FCC/8/Amend Date: 13/03/2025 Valid Up to Date: 28/10/2025 Valid Up to: This CC is re-endorsed and further CC is granted upto top of 32nd floor for Wing ‘G’ by restricting temporary structure area admeasuring 762.68 sqm and one time set back area admeasuring 900.45 Sqm + 2081.50 Sqm respectively along with its proportionate fungible area as per last approved plans dated 29.01.2025.
OC Details Approved upto : OC Details Approved upto : | : | CHE/ES/1321/T/337(NEW)/OCC/1/New Dated - 27/09/2023 Wing D & E = 2B + Gr/Stilt + 1st to 47th Floor CHE/ES/1321/T/337(NEW)/OCC/2/New Date: 24/09/2024 Part occupation to building no. 2 i.e. Full occupation to F wing comprising of 2 level Basement + part stilt & part ground floor +1st to 47th upper residential floors with Podium Parking Building from 1st (Pt.) to 3rd (Pt.) Podium floors. |  |  | Environmental Clearance Details | : | SEIAA-EC-0000002339 Date: 24/01/2020
Solid Waste Management Department NOC Details | : | CHE/ES/1321/T/337(NEW)/SWM/1/Amend Dated - 03/11/2021 |  |  | Railway NOC Details | : | BB/W/6561/NOC/MLND/1223/DB Date: 09/06/2021
Airport Authority Clearance Details | : | SNCR/WEST/B/090721/574103 Date:28/09/2021 |  |  | Fire NOC Details | : | CHE/ES/1321/T/337(NEW)-CFO Date: 07/02/2020
Change of User/Zone Certificate Details | : | - |  |  | Environmental Clearance Details | : | SEIAA-EC-0000002339 Date: 24/01/2020
Construction Status
Wing D & E = 2Basement + Gr/St + 1st to 4th Podium + 5th to 47th Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 2 | 1 |  | 0 | 47 | All work Completed. OC Received. |  |  |  | 217
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11.75 |  |  | 257
Excavation |  | 47 |  | 100% | 100% |  | All work Completed. OC Received. |  | Excavation in process | 23.5
Plinth |  | 47 |  | 100% |  |  |  |  | Excavation Completed | 47
RCC (Including podiums) |  | 48 |  | 100% |  |  |  |  | Footing in Process | 11.75
Brickwork |  | 47 |  | 100% |  |  |  |  | Footing Completed | 23.5
Door & Window Frames |  | 47 |  | 100% |  |  |  |  | Basement 1 | 35.25
Internal Plaster |  | 47 |  | 100% |  |  |  |  | Basement 2 | 0
Ext.Plaster |  | 47 |  | 100% |  |  |  |  | Basement 3 | 0
Plumb.& Electri. |  | 47 |  | 100% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 47 |  | 100% |  |  |  |  | Plinth in process | 0
Painting |  | 47 |  | 100% |  |  |  |  | Plinth completed | 47
Building Common Amenities |  | 47 |  | 100%
Possession |  | 47 |  | 100%
Construction Status
Wing F = 2Basement + Gr/St + 1st to 4th Podium + 5th to 47th Floor |  |  | : | Basement | Ground |  | Podium | Floors | All work completed. Please provide OC.
|  |  |  | 2 | 1 |  | 0 | 47 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11.75
Excavation |  | 47 |  | 100% | 100% |  | All work Completed. OC Received. |  | Excavation in process | 23.5
Plinth |  | 47 |  | 100% |  |  |  |  | Excavation Completed | 47
RCC (Including podiums) |  | 48 |  | 100% |  |  |  |  | Footing in Process | 11.75
Brickwork |  | 47 |  | 100% |  |  |  |  | Footing Completed | 23.5
Internal Plaster |  | 47 |  | 100% |  |  |  |  | Basement 1 | 35.25
External Plaster |  | 47 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 47 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 47 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 47 |  | 100% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 47 |  | 100% |  |  |  |  | Plinth completed | 47
Building Common Amenities |  | 47 |  | 100%
Possession |  | 47 |  | 100%
Construction Status
Wing G (Wing A) = 2Basement + Gr/St + 1st to 4th Podium + 5th to 47th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 16 Floor Completed
|  |  |  | 2 | 1 |  | 0 | 47 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11.75
Excavation |  | 47 |  | 100% | 39.77% |  | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 16 Floor Completed |  | Excavation in process | 23.5
Plinth |  | 47 |  | 100% |  |  |  |  | Excavation Completed | 47
RCC (Including podiums) |  | 21 |  | 43.75% |  |  |  |  | Footing in Process | 11.75
Brickwork |  | 20 |  | 42.55% |  |  |  |  | Footing Completed | 23.5
Internal Plaster |  | 16 |  | 34.04% |  |  |  |  | Basement 1 | 35.25
External Plaster |  | 16 |  | 34.04% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 47 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing G (Wing B) = 2Basement + Gr/St + 1st to 4th Podium + 5th to 47th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 24 Floor, Internal Plaster upto 19.2 Floor, External Plaster upto 19.2 Floor Completed
|  |  |  | 2 | 1 |  | 0 | 47 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11.75
Excavation |  | 47 |  | 100% | 42.62% |  | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 24 Floor, Internal Plaster upto 19.2 Floor, External Plaster upto 19.2 Floor Completed |  | Excavation in process | 23.5
Plinth |  | 47 |  | 100% |  |  |  |  | Excavation Completed | 47
RCC (Including podiums) |  | 25 |  | 52.08% |  |  |  |  | Footing in Process | 11.75
Brickwork |  | 24 |  | 51.06% |  |  |  |  | Footing Completed | 23.5
Internal Plaster |  | 19.2 |  | 40.85% |  |  |  |  | Basement 1 | 35.25
External Plaster |  | 19.2 |  | 40.85% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 47 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Wing G Average |  |  |  |  | 41.19%
Project Completion % | [6 empty] | 85.3%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 23500 to 25000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | 50/- (From 2nd floor)
Car Parking Charges |  |  | : | 700000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 6622.0736
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 14994.4259
Distress Value (Rs. Per sqft) | [5 empty] | : | 5297.6589
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Wing D |  | Sale |  | Flats | 211 |  | 161285.9461 | 258057.5138
Wing E |  | Sale |  | Flats | 256 |  | 199039.7074 | 318463.5318
Wing F |  | Sale |  | Flats | 342 |  | 215889.0271 | 345422.4434
Wing G (A Wing) |  | Sale |  | Flats | 145 |  | 97749.8721 | 156399.7954
Wing G (B Wing) |  | Sale |  | Flats | 147 |  | 101110.0485 | 161776.0775
Total |  |  |  |  | 1101 |  | 775074.6012 | 1240119.3619 | 315
Details of Flats in Building
Floor |  | Flat No. (As per plan) |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
D Wing - Ciana
2nd & 1st Basement Floor for Parking
Ground/Stilt Floor for Parking
1st Floor (Podium) for Residential
1st Floor (Podium) for Residential |  | 4 |  | 2BHK | 631.5239 |  | 0 | 1010.4382
1st Floor (Podium) for Residential |  | 5 |  | 2BHK | 631.5239 |  | 0 | 1010.4382
2nd & 3rd Floor (Podium)
2nd & 3rd Floor (Podium) |  | 3 |  | 2BHK | 832.3801 |  | 0 | 1331.8082
2nd & 3rd Floor (Podium) |  | 4 |  | 2BHK | 631.5239 |  | 0 | 1010.4382
2nd & 3rd Floor (Podium) |  | 5 |  | 2BHK | 631.5239 |  | 0 | 1010.4382
4th Floor (Podium) for Amenities (Yogalaya)
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 34th Floor
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 34th Floor |  | 1 |  | 2.5BHK | 756.171 |  | 0 | 1209.8736
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 34th Floor |  | 2 |  | 2.5BHK | 756.171 |  | 0 | 1209.8736
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 34th Floor |  | 3 |  | 3BHK | 989.9651 |  | 0 | 1583.9441
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 34th Floor |  | 4 |  | 2BHK | 631.5239 |  | 0 | 1010.4382
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 34th Floor |  | 5 |  | 2BHK | 631.5239 |  | 0 | 1010.4382
8th, 15th, 22nd & 29th Floor (Part Refuge Area)
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 1 |  | 2.5BHK | 756.171 |  | 0 | 1209.8736
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 2 |  | 2.5BHK | 756.171 |  | 0 | 1209.8736
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 3 |  | 3BHK | 989.9651 |  | 0 | 1583.9441
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 4 |  | Refuge Area
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 5 |  | Refuge Area
35th Floor
35th Floor |  | 1 |  | 2.5BHK | 756.171 |  | 0 | 1209.8736
35th Floor |  | 2 |  | 2.5BHK | 756.171 |  | 0 | 1209.8736
35th Floor |  | 3 |  | 3BHK | 989.9651 |  | 0 | 1583.9441
35th Floor |  | 4 |  | 2BHK | 631.5239 |  | 0 | 1010.4382
35th Floor |  | 5 |  | 2BHK | 631.5239 |  | 0 | 1010.4382
36th Floor (Part Refuge & Store Area)
36th Floor (Part Refuge & Store Area) |  | 1 |  | 2.5BHK | 756.171 |  | 0 | 1209.8736
36th Floor (Part Refuge & Store Area) |  | 2 |  | 2.5BHK | 756.171 |  | 0 | 1209.8736
36th Floor (Part Refuge & Store Area) |  | 3 |  | 3BHK | 995.9929 |  | 0 | 1593.5887
36th Floor (Part Refuge & Store Area) |  | 4 |  | Refuge & Store Area
36th Floor (Part Refuge & Store Area) |  | 5
37th to 42nd & 44th to 47th Floor
37th to 42nd & 44th to 47th Floor |  | 1 |  | 2.5BHK | 773.6087 |  | 0 | 1237.7739
37th to 42nd & 44th to 47th Floor |  | 2 |  | 2.5BHK | 773.6087 |  | 0 | 1237.7739
37th to 42nd & 44th to 47th Floor |  | 3 |  | 3BHK | 995.9929 |  | 0 | 1593.5887
37th to 42nd & 44th to 47th Floor |  | 4 |  | 2BHK | 683.7293 |  | 0 | 1093.9668
37th to 42nd & 44th to 47th Floor |  | 5 |  | 2BHK | 683.7293 |  | 0 | 1093.9668
43rd Floor (Part Refuge & Store Area)
43rd Floor (Part Refuge & Store Area) |  | 1 |  | 2.5BHK | 773.6087 |  | 0 | 1237.7739
43rd Floor (Part Refuge & Store Area) |  | 2 |  | 2.5BHK | 773.6087 |  | 0 | 1237.7739
43rd Floor (Part Refuge & Store Area) |  | 3 |  | 3BHK | 995.9929 |  | 0 | 1593.5887
43rd Floor (Part Refuge & Store Area) |  | 4 |  | Part Refuge & Store Area
43rd Floor (Part Refuge & Store Area) |  | 5
E Wing - Auris
2nd & 1st Basement Floor for Parking
Ground/Stilt Floor for Parking
1st Floor (Podium) for Residential
1st Floor (Podium) for Residential |  | 4 |  | 2BHK | 641.1038 |  | 0 | 1025.7661
1st Floor (Podium) for Residential |  | 5 |  | 2BHK | 641.1038 |  | 0 | 1025.7661
2nd & 3rd Floor (Podium)
2nd & 3rd Floor (Podium) |  | 3 |  | 2BHK | 824.4148 |  | 0 | 1319.0636
2nd & 3rd Floor (Podium) |  | 4 |  | 2BHK | 641.1038 |  | 0 | 1025.7661
2nd & 3rd Floor (Podium) |  | 5 |  | 2BHK | 641.1038 |  | 0 | 1025.7661
2nd & 3rd Floor (Podium) |  | 6 |  | 2BHK | 820.6474 |  | 0 | 1313.0358
4th Floor (Podium) for Amenities (Yogalaya)
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 33rd Floor
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 33rd Floor |  | 1 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 33rd Floor |  | 2 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 33rd Floor |  | 3 |  | 3BHK | 979.8469 |  | 0 | 1567.7551
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 33rd Floor |  | 4 |  | 2BHK | 641.3191 |  | 0 | 1026.1106
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 33rd Floor |  | 5 |  | 2BHK | 641.3191 |  | 0 | 1026.1106
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 33rd Floor |  | 6 |  | 3BHK | 978.7705 |  | 0 | 1566.0328
8th, 15th, 22nd & 29th Floor (Part Refuge Area)
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 3 |  | 3BHK | 979.8469 |  | 0 | 1567.7551
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 4 |  | Refuge Area
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 5 |  | Refuge Area
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 6 |  | 3BHK | 978.7705 |  | 0 | 1566.0328
34th & 35th Floor
34th & 35th Floor |  | 1 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
34th & 35th Floor |  | 2 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
34th & 35th Floor |  | 3 |  | 3BHK | 979.8469 |  | 0 | 1567.7551
34th & 35th Floor |  | 4 |  | 2BHK | 641.3191 |  | 0 | 1026.1106
34th & 35th Floor |  | 5 |  | 2BHK | 641.3191 |  | 0 | 1026.1106
34th & 35th Floor |  | 6 |  | 3BHK | 978.7705 |  | 0 | 1566.0328
36th Floor (Part Refuge Area)
36th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
36th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
36th Floor (Part Refuge Area) |  | 3 |  | 3BHK | 986.3053 |  | 0 | 1578.0885
36th Floor (Part Refuge Area) |  | 4 |  | Refuge Area
36th Floor (Part Refuge Area) |  | 5
36th Floor (Part Refuge Area) |  | 6 |  | 3BHK | 986.3053 |  | 0 | 1578.0885
37th to 42nd & 44th to 47th Floor
37th to 42nd & 44th to 47th Floor |  | 1 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
37th to 42nd & 44th to 47th Floor |  | 2 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
37th to 42nd & 44th to 47th Floor |  | 3 |  | 3BHK | 986.3053 |  | 0 | 1578.0885
37th to 42nd & 44th to 47th Floor |  | 4 |  | 2BHK | 692.5558 |  | 0 | 1108.0892
37th to 42nd & 44th to 47th Floor |  | 5 |  | 2BHK | 692.5558 |  | 0 | 1108.0892
37th to 42nd & 44th to 47th Floor |  | 6 |  | 3BHK | 986.3053 |  | 0 | 1578.0885
43rd Floor (Part Refuge & Store Area)
43rd Floor (Part Refuge & Store Area) |  | 1 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
43rd Floor (Part Refuge & Store Area) |  | 2 |  | 2BHK | 686.4203 |  | 0 | 1098.2724
43rd Floor (Part Refuge & Store Area) |  | 3 |  | 3BHK | 986.3053 |  | 0 | 1578.0885
43rd Floor (Part Refuge & Store Area) |  | 4 |  | Part Refuge & Store Area
43rd Floor (Part Refuge & Store Area) |  | 5
43rd Floor (Part Refuge & Store Area) |  | 6 |  | 3BHK | 986.3053 |  | 0 | 1578.0885
F Wing - Azure
2nd & 1st Basement Floor for Parking
Ground/Stilt Floor for Parking
1st Floor (Podium) for Residential
1st Floor (Podium) for Residential |  | 5 |  | 2BHK | 623.8814 |  | 0 | 998.2103
1st Floor (Podium) for Residential |  | 6 |  | 2BHK | 623.8814 |  | 0 | 998.2103
2nd & 3rd Floor (Podium)
2nd & 3rd Floor (Podium) |  | 4 |  | 2BHK | 573.0754 |  | 0 | 916.9206
2nd & 3rd Floor (Podium) |  | 5 |  | 2BHK | 623.8814 |  | 0 | 998.2103
2nd & 3rd Floor (Podium) |  | 6 |  | 2BHK | 623.8814 |  | 0 | 998.2103
2nd & 3rd Floor (Podium) |  | 7 |  | 2BHK | 572.2142 |  | 0 | 915.5428
4th Floor (Podium) for Amenities (Yogalaya)
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 35th Floor
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 35th Floor |  | 1 |  | 2.5BHK | 756.3863 |  | 0 | 1210.218
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 35th Floor |  | 2 |  | 2.5BHK | 756.3863 |  | 0 | 1210.218
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 35th Floor |  | 3 |  | 2BHK | 573.0754 |  | 0 | 916.9206
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 35th Floor |  | 4 |  | 2BHK | 573.0754 |  | 0 | 916.9206
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 35th Floor |  | 5 |  | 2BHK | 623.8814 |  | 0 | 998.2103
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 35th Floor |  | 6 |  | 2BHK | 623.8814 |  | 0 | 998.2103
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 35th Floor |  | 7 |  | 2BHK | 572.2142 |  | 0 | 915.5428
5th to 7th, 9th to 14th,16th to 21st, 23rd to 28th, 30th to 35th Floor |  | 8 |  | 2BHK | 572.2142 |  | 0 | 915.5428
8th, 15th, 22nd & 29th Floor (Part Refuge Area)
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 1 |  | 2.5BHK | 756.3863 |  | 0 | 1210.218
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 2 |  | 2.5BHK | 756.3863 |  | 0 | 1210.218
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 573.0754 |  | 0 | 916.9206
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 573.0754 |  | 0 | 916.9206
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 5 |  | Refuge Area
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 6 |  | Refuge Area
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 572.2142 |  | 0 | 915.5428
8th, 15th, 22nd & 29th Floor (Part Refuge Area) |  | 8 |  | 2BHK | 572.2142 |  | 0 | 915.5428
37th to 42nd & 44th to 47th Floor
37th to 42nd & 44th to 47th Floor |  | 1 |  | 2.5BHK | 761.1224 |  | 0 | 1217.7959
37th to 42nd & 44th to 47th Floor |  | 2 |  | 2.5BHK | 761.1224 |  | 0 | 1217.7959
37th to 42nd & 44th to 47th Floor |  | 3 |  | 2BHK | 573.0754 |  | 0 | 916.9206
37th to 42nd & 44th to 47th Floor |  | 4 |  | 2BHK | 573.0754 |  | 0 | 916.9206
37th to 42nd & 44th to 47th Floor |  | 5 |  | 2BHK | 625.3884 |  | 0 | 1000.6214
37th to 42nd & 44th to 47th Floor |  | 6 |  | 2BHK | 625.3884 |  | 0 | 1000.6214
37th to 42nd & 44th to 47th Floor |  | 7 |  | 2BHK | 572.2142 |  | 0 | 915.5428
37th to 42nd & 44th to 47th Floor |  | 8 |  | 2BHK | 572.2142 |  | 0 | 915.5428
36th Floor (Part Refuge Area)
36th Floor (Part Refuge Area) |  | 1 |  | 2.5BHK | 761.1224 |  | 0 | 1217.7959
36th Floor (Part Refuge Area) |  | 2 |  | 2.5BHK | 761.1224 |  | 0 | 1217.7959
36th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 573.0754 |  | 0 | 916.9206
36th Floor (Part Refuge Area) |  | 4 |  | 2BHK | 573.0754 |  | 0 | 916.9206
36th Floor (Part Refuge Area) |  | 5 |  | Refuge Area
36th Floor (Part Refuge Area) |  | 6 |  | Refuge Area
36th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 572.2142 |  | 0 | 915.5428
36th Floor (Part Refuge Area) |  | 8 |  | 2BHK | 572.2142 |  | 0 | 915.5428
43rd Floor (Part Refuge Area)
43rd Floor (Part Refuge Area) |  | 1 |  | 2.5BHK | 761.1224 |  | 0 | 1217.7959
43rd Floor (Part Refuge Area) |  | 2 |  | 2.5BHK | 761.1224 |  | 0 | 1217.7959
43rd Floor (Part Refuge Area) |  | 3 |  | 2BHK | 573.0754 |  | 0 | 916.9206
43rd Floor (Part Refuge Area) |  | 4 |  | 2BHK | 573.0754 |  | 0 | 916.9206
43rd Floor (Part Refuge Area) |  | 5 |  | Refuge Area
43rd Floor (Part Refuge Area) |  | 6 |  | Refuge Area
43rd Floor (Part Refuge Area) |  | 7 |  | 2BHK | 572.2142 |  | 0 | 915.5428
43rd Floor (Part Refuge Area) |  | 8 |  | 2BHK | 572.2142 |  | 0 | 915.5428
G Wing - Solis
A Wing
2nd & 1st Basement Floor for Parking
Ground/Stilt Floor for Parking
1st Floor (Podium) For Part Residential & Parking
1st Floor (Podium) For Part Residential & Parking |  | - |  | -
|  | A2 |  | 2BHK | 552.2675 |  | 0 | 883.628 |  | 51.3069 | 552.2675
|  | A3 |  | 2BHK | 552.2675 |  | 0 | 883.628
2nd Floor (Podium) For Part Residential & Parking
2nd Floor (Podium) For Part Residential & Parking |  | A1 |  | 2BHK | 649.2877 |  | 0 | 1038.8603 |  | 60.3203 | 649.2877
A2 |  | A2 |  | 2BHK | 552.2675 |  | 0 | 883.628
A3 |  | A3 |  | 2BHK | 552.2675 |  | 0 | 883.628
3rd Floor (Podium)For Part Residential & Parking
3rd Floor (Podium)For Part Residential & Parking |  | A1 |  | 3BHK | 794.2185 |  | 0 | 1270.7496
A2 |  | A2 |  | 2BHK | 552.2675 |  | 0 | 883.628
A3 |  | A3 |  | 2BHK | 552.2675 |  | 0 | 883.628
4th Floor (Podium) For Part Residential & Parking
4th Floor (Podium) For Part Residential & Parking |  | A1 |  | 3BHK | 794.2185 |  | 0 | 1270.7496
A2 |  | A2 |  | 2BHK | 552.2675 |  | 0 | 883.628
A3 |  | A3 |  | 2BHK | 552.2675 |  | 0 | 883.628
5th to 7th, 9th to 14th,16th to 21st, 23rd & 24th Floor For Residential
5th to 7th, 9th to 14th,16th to 21st, 23rd & 24th Floor For Residential |  | A1 |  | 3BHK | 794.2185 |  | 0 | 1270.7496
A2 |  | A2 |  | 2BHK | 552.2675 |  | 0 | 883.628
A3 |  | A3 |  | 2BHK | 552.2675 |  | 0 | 883.628
A4 |  | A4 |  | 2.5BHK | 711.0354 |  | 0 | 1137.6566 |  | 66.0568
A5 |  | A5 |  | 2.5BHK | 732.882 |  | 0 | 1172.6112
8th, 15th & 22nd Floor (Part Refuge Area)
8th, 15th & 22nd Floor (Part Refuge Area) |  | A1 |  | 3BHK | 794.2185 |  | 0 | 1270.7496
A2 |  | A2 |  | Refuge Area
A3 |  | A3
A4 |  | A4 |  | 2.5BHK | 711.0354 |  | 0 | 1137.6566
A5 |  | A5 |  | 2.5BHK | 732.882 |  | 0 | 1172.6112
25th to 28th, 30th to 32nd Floor | [9 empty] | balcony from 25th
25th to 28th, 30th to 32nd Floor |  | A1 |  | 3BHK | 830.9087 |  | 0 | 1329.4539
A2 |  | A2 |  | 2BHK | 552.2675 |  | 0 | 883.628
A3 |  | A3 |  | 2BHK | 552.2675 |  | 0 | 883.628
A4 |  | A4 |  | 2.5BHK | 743.7149 |  | 0 | 1189.9438 |  | 66.0568
A5 |  | A5 |  | 2.5BHK | 765.1159 |  | 0 | 1224.1854
29th Floor (Part Refuge Area)
29th Floor (Part Refuge Area) |  | A1 |  | 3BHK | 830.9087 |  | 0 | 1329.4539
A2 |  | A2 |  | 2BHK | 552.2675 |  | 0 | 883.628
A3 |  | A3 |  | 2BHK | 552.2675 |  | 0 | 883.628
A4 |  | A4 |  | 2.5BHK | 743.7149 |  | 0 | 1189.9438 |  | 66.0568
A5 |  | A5 |  | 2.5BHK | 765.1159 |  | 0 | 1224.1854
B Wing
2nd & 1st Basement Floor for Parking
Ground/Stilt Floor for Parking
1st Floor (Podium) For Part Residential & Parking
1st Floor (Podium) For Part Residential & Parking |  | B2 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B3 |  | 2BHK | 606.8894 |  | 0 | 971.023
2nd Floor (Podium) For Part Residential & Parking
2nd Floor (Podium) For Part Residential & Parking |  | B1 |  | 2.5BHK | 756.2668 |  | 0 | 1210.0269
|  | B2 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B3 |  | 2BHK | 606.8894 |  | 0 | 971.023
3rd Floor (Podium) For Part Residential & Parking
3rd Floor (Podium) For Part Residential & Parking |  | B1 |  | 2.5BHK | 756.2668 |  | 0 | 1210.0269
|  | B2 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B3 |  | 2BHK | 606.8894 |  | 0 | 971.023
4th Floor (Podium) For Part Residential & Parking
4th Floor (Podium) For Part Residential & Parking |  | B1 |  | 2.5BHK | 756.2668 |  | 0 | 1210.0269
|  | B2 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B3 |  | 2BHK | 606.8894 |  | 0 | 971.023
5th to 7th, 9th to 14th,16th to 21st, 23rd & 24th Floor For Residential
5th to 7th, 9th to 14th,16th to 21st, 23rd & 24th Floor For Residential |  | B1 |  | 2.5BHK | 756.2668 |  | 0 | 1210.0269
|  | B2 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B3 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B4 |  | 2.5BHK | 718.6617 |  | 0 | 1149.8587
|  | B5 |  | 2.5BHK | 724.3784 |  | 0 | 1159.0055
8th, 15th & 22nd Floor (Part Refuge Area)
8th, 15th & 22nd Floor (Part Refuge Area) |  | B1 |  | 2.5BHK | 756.2668 |  | 0 | 1210.0269
|  | B2 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B3 |  | Refuge Area
|  | B4 |  | 2.5BHK | 718.6617 |  | 0 | 1149.8587
|  | B5 |  | 2.5BHK | 724.3784 |  | 0 | 1159.0055
25th to 28th, 30th to 32nd Floor
25th to 28th, 30th to 32nd Floor |  | B1 |  | 2.5BHK | 792.957 |  | 0 | 1268.7312
|  | B2 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B3 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B4 |  | 2.5BHK | 753.2723 |  | 0 | 1205.2356
|  | B5 |  | 2.5BHK | 758.989 |  | 0 | 1214.3824
29th Floor (Part Refuge Area)
29th Floor (Part Refuge Area) |  | B1 |  | 2.5BHK | 792.957 |  | 0 | 1268.7312
|  | B2 |  | 2BHK | 606.8894 |  | 0 | 971.023
|  | B3 |  | Refuge Area
|  | B4 |  | 2.5BHK | 753.2723 |  | 0 | 1205.2356
|  | B5 |  | 2.5BHK | 758.989 |  | 0 | 1214.3824
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Wing D, E & F = All work completed. OC Received. Wing G = Construction work is in process at the time of Visit. Internal visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Ms.Sakshi 9088766829. 8. We have updated Approved Layout plan, Floor plan (i.e for Wing G) & CC from MCGM site (on 18/11/2023). 9. We have updated OC (Wing D & E) from MCGM site (on 11/02/2024). 10. We have updated OC (Wing F) from MCGM site (on 21/11/2024). 11. We have updated the revised construction table on dated 21/11/2024, which is shared with us by the Godrej officials. 12. We have updated CC from MCGM site on 05/06/2025. 13. Please provide revised approved plans.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Wadhwa Atmosphere O2 (Wing D, E, F and G)
Project Site Address |  |  | : | Building No. 2, CTS NO. 784-1, 785,.., 793 & 848, Village - Nahur, Mulund link road, Mulund (W), Mumbai - 4000080.
Site Visit Date & Time |  |  | : | 06/08/2025 at 03:50PM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nainesh Tambe | Authorized Signatory Name & Signature | :