## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 | 2025-05-05 | #VALUE!
Project Name |  |  | : | Dosti Greater Thane - Sector 3A - Cluster 2 - Phase 1, 2 & 3 |  | Date & Time of Site Visit |  | 03/08/2025 at 02:16PM | construction table referred from youtube video
Name of the person met at site & Contact No. |  |  | : | Mr. Shubham 9619081618 |  | Date of Report Release |  | 07/08/2025 | Mr. Chetan 9167700142
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare |  |  | 2025-02-04
Builder Group Name |  |  | : | Adrika Developers Private Limited | Developer Name | : | Dosti |  |  | 2025-05-05
Developer Office Address |  |  | : | DWC,Balkum, thane w
Project Address | : | As per ARF | : | Dosti Greater Thane - Sector 3A - Cluster 2 - Phase 1, 2 & 3 162 (pt), 163/1 (pt), 163/2 (pt), 151/2A (pt), 159/2 (pt), 153 (pt), 154/3A (pt), 154/3B (pt), 154/7 (pt), 159/1A (pt), 159/1B (pt), 159/1C (pt)at Purne (CT), Bhiwandi, Thane, 421302
| : | As per Legal Documents | : | Dosti Greater Thane - Sector 3A - Cluster 2 - Phase 1, 2 & 3, Survey No.25/2, 25/3, 26/10, 26/13/7, 190, 23/1/C of village Rahanal, S.No.40/7 of Kevani, S.No.151/2/A, 1528/1, 152/2,165/2B, 165/3, 174/5 & others of Purna, S.No.14/3, 15/5, 16/1a, 19/7 to 13 & others of Kopar, near Dosti Fortune, Bhiwandi - Wada Road, Shree Arihant Compound, Purna, Bhiwandi West, Bhiwandi, Thane - 421302.
| : | As per Actual at site | : | Dosti Greater Thane - Sector 3A - Cluster 2 - Phase 1, 2 & 3 of village Rahanal, Kevaniothers, Purna, Kopar, near Dosti Fortune, Bhiwandi - Wada Road, Shree Arihant Compound, Purna, Bhiwandi West, Bhiwandi, Thane - 421302.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Mumbai Metropolitan Region Development Authority
RERA Registration No. | : | DGT - Sector 3A - Cluster 2 Phase I = P51700048334 Phase II = P51700048335 Phase III = P51700048333 |  |  | RERA Registration Validity | : | Phase I = 30/06/2028 Phase II = 31/12/2027 Phase III = 30/06/2028
Project Launch Date | : | 31/11/2022 |  |  | Construction Start Date | : | 31/11/2022
Proposed Date of Completion (As per RERA) | : | Phase I = 30/06/2028 Phase II = 31/12/2027 Phase III = 30/06/2028 |  |  | Developer Bank Name (As per RERA) | : | HDFC Bank
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | : | 136743.24
FSI/FAR Permissible | : | 1.1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 306191.88
Permissible Built up Area (In Sq.Mt) | : | 306191.88 |  |  | Total Number of Units Planned | : | As per RERA Site Flats = 3376 |  | 230+480 240+590 1826+10
Total Number of Units Approved | : | 3376 |  |  | If Mixed, No. of Commercial Units | : | 20
Latitude, Longitude | : | 19.254551, 73.017559 |  |  | Landmark | : | Dosti Fortune
Location Link | : | https://goo.gl/maps/nabs9yCsDhfPjfmN6
Extra Amenities available | : | Billiards Table, Jogging Track, Basketball Court, Swimming Pools, Basketball Court, Tennis Court , Gymnasium
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle Class
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 2.1 KM from Kalher pipeline bus stop
Distance from the nearest School (Km) | : | About 1.9 KM from Zilla Parishad School |  |  | Distance from Hospital (Km) | : | About 1.8 KM form Maruti Healthcare Hospital
Distance from the Main Market (Km) | : | Approx. 1.9 KM from Super Market. |  |  | Distance from Railway Station (Km) | : | 5.7KM from Bhiwandi Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Road | Road | Other Plot |  | Road
As per Site / Actual |  |  | : | Open Plot | Internal Road | Open Plot |  | Open Plot
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Phase I (Dosti Pride) |  | Sale |  | Tower 2A, 1I, 1J & 5B = St + 1st to 29th floors |  |  | Tower 2A, 1I, 1J & 5B = St + 1st to 29th floors
Phase II ( Dosti Charm) |  | Sale |  | Tower 1K & 1L = St + 1st to 35th floors |  |  | Tower 1K & 1L = St + 1st to 30th floors
Phase III ( Dosti Grace) |  | Sale |  | Tower 1M & 4K = St + 1st to 35th floors |  |  | Tower 1M & 4K = St + 1st to 30th floors
Building & Wing Details
Phases |  |  |  | As Per RERA / Builder |  |  | As Per Approved Floor Plans
Phase I = Dosti Pride |  |  |  | Wing A |  |  | Tower 2A
|  |  |  | Wing B |  |  | Tower 1I
|  |  |  | Wing C |  |  | Tower 1J
|  |  |  | Wing D |  |  | Tower 5B
Phase II = Dosti Charm |  |  |  | Wing B |  |  | Tower 1K
|  |  |  | Wing C |  |  | Tower 1L
Phase III = Dosti Grace |  |  |  | Wing A |  |  | Tower 1M
|  |  |  | Wing B |  |  | Tower 4A
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | SROT/BSNA/2501/BP/Rahanal-Kevani-Purna-Kopar -02 /Amended CC/1073/2023 Date: 02/08/2023
CC Details | : | SROT/BSNA/2501/BP/Rahanal-Kevani-Purna-Kopar -02 /Amended CC Date: 17/11/2022 Valid Up to: Phase 1 ( Dosti Pride) Tower 1 ( I & J ) = St + 1st to 26th upper floor Tower 2A & 5B = St + 1st to 26th upper floor |  |  | Approved Plan Details | : | SROT/BSNA/2501/BP/Rahanal-Kevani-Purna-Kopar -02 /Amended CC/1073/2023 Date: 02/08/2023
Environmental Clearance Details | : | Date:
Change of User/Zone Certificate Details | : | -
Commencement-CC No Valid Up to: Sector 3A - Cluster 2 | : | SROT/BSNA/2501/BP/Rahanal-KevaniPurna-Kopar -02 /CC/1073/2023 Date: 02/08/2023 Valid Up to: Phase 2 ( Dosti Charm) Tower T3 Bldg 4 (Wing B) = St + 1st to 30th Floor Tower T3 Bldg 3 (Wing C) = St + 1st to 30th Floor Phase 3 ( Dosti Grace) Tower T4 Bldg 5 (Wing A) = St + 1st to 30th Floor Tower T4 Bldg 6 (Wing B) = St + 1st to 30th Floor
Construction Status
Phase I (Dosti Pride) Wing A = St + 1st to 29th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 22 Slab, Brickwork upto 21 Floor, Internal Plaster upto 16.8 Floor, External Plaster upto 16.8 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 29 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.25
Excavation |  | 29 |  | 100% | 49.85% |  | Excavation work Completed. Plinth work completed, RCC upto 22 Slab, Brickwork upto 21 Floor, Internal Plaster upto 16.8 Floor, External Plaster upto 16.8 Floor Completed |  | Excavation in process | 14.5
Plinth |  | 29 |  | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 22 |  | 73.33% |  |  |  |  | Footing in Process | 7.25
Brickwork |  | 21 |  | 72.41% |  |  |  |  | Footing Completed | 14.5
Internal Plaster |  | 16.8 |  | 57.93% |  |  |  |  | Basement 1 | 0
External Plaster |  | 16.8 |  | 57.93% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 21.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 29 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Phase I (Dosti Pride) Wing B = St + 1st to 29th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 23 Floor, Internal Plaster upto 14.95 Floor, External Plaster upto 14.95 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 29 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.25
Excavation |  | 29 |  | 100% | 51.54% |  | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 23 Floor, Internal Plaster upto 14.95 Floor, External Plaster upto 14.95 Floor Completed |  | Excavation in process | 14.5
Plinth |  | 29 |  | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 24 |  | 80% |  |  |  |  | Footing in Process | 7.25
Brickwork |  | 23 |  | 79.31% |  |  |  |  | Footing Completed | 14.5
Internal Plaster |  | 14.95 |  | 51.55% |  |  |  |  | Basement 1 | 0
External Plaster |  | 14.95 |  | 51.55% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 21.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 29 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Phase I (Dosti Pride) Wing C = St + 1st to 29th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 24 Floor, Internal Plaster upto 19.2 Floor, External Plaster upto 19.2 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 29 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.25
Excavation |  | 29 |  | 100% | 53.28% |  | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 24 Floor, Internal Plaster upto 19.2 Floor, External Plaster upto 19.2 Floor Completed |  | Excavation in process | 14.5
Plinth |  | 29 |  | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 25 |  | 83.33% |  |  |  |  | Footing in Process | 7.25
Brickwork |  | 24 |  | 82.76% |  |  |  |  | Footing Completed | 14.5
Internal Plaster |  | 19.2 |  | 66.21% |  |  |  |  | Basement 1 | 0
External Plaster |  | 19.2 |  | 66.21% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 21.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 29 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Phase I (Dosti Pride) Wing D = St + 1st to 29th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 16 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 29 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.25
Excavation |  | 29 |  | 100% | 48.71% |  | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 16 Floor Completed |  | Excavation in process | 14.5
Plinth |  | 29 |  | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 21 |  | 70% |  |  |  |  | Footing in Process | 7.25
Brickwork |  | 20 |  | 68.97% |  |  |  |  | Footing Completed | 14.5
Internal Plaster |  | 16 |  | 55.17% |  |  |  |  | Basement 1 | 0
External Plaster |  | 16 |  | 55.17% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 21.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 29 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Phase II ( Dosti Charm) Wing B = St + 1st to 35th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 4 Floor, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 29.47% |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 4 Floor, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 5 |  | 13.89% |  |  |  |  | Footing in Process | 8.75
Brickwork |  | 4 |  | 11.43% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 3 |  | 8.571% |  |  |  |  | Basement 1 | 0
External Plaster |  | 3 |  | 8.571% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Phase II ( Dosti Charm) Wing C = St + 1st to 35th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 9 Floor, Internal Plaster upto 6.75 Floor, External Plaster upto 6.75 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 34.19% |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab, Brickwork upto 9 Floor, Internal Plaster upto 6.75 Floor, External Plaster upto 6.75 Floor Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 10 |  | 27.78% |  |  |  |  | Footing in Process | 8.75
Brickwork |  | 9 |  | 25.71% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 6.75 |  | 19.29% |  |  |  |  | Basement 1 | 0
External Plaster |  | 6.75 |  | 19.29% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Phase III ( Dosti Grace) Wing A = St + 1st to 35th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 17 Floor, Internal Plaster upto 13.6 Floor, External Plaster upto 13.6 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 41.87% |  | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 17 Floor, Internal Plaster upto 13.6 Floor, External Plaster upto 13.6 Floor Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 18 |  | 50% |  |  |  |  | Footing in Process | 8.75
Brickwork |  | 17 |  | 48.57% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 13.6 |  | 38.86% |  |  |  |  | Basement 1 | 0
External Plaster |  | 13.6 |  | 38.86% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Phase III ( Dosti Grace) Wing B = St + 1st to 35th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12.8 Floor, External Plaster upto 12.8 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 35 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.75
Excavation |  | 35 |  | 100% | 40.92% |  | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12.8 Floor, External Plaster upto 12.8 Floor Completed |  | Excavation in process | 17.5
Plinth |  | 35 |  | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 17 |  | 47.22% |  |  |  |  | Footing in Process | 8.75
Brickwork |  | 16 |  | 45.71% |  |  |  |  | Footing Completed | 17.5
Internal Plaster |  | 12.8 |  | 36.57% |  |  |  |  | Basement 1 | 0
External Plaster |  | 12.8 |  | 36.57% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 26.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 35 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 43.73%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 10000 to 11000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Rate of Shops Per Sq. Ft. (on Carpet area) |  |  | : : | 18000 to 19000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  |  | : | 300000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 3595.32
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 9271.65
Distress Value (Rs. Per sqft) | [5 empty] | : | 2876.256
Unit Details, Nomenclature and Residential Area Details
Building & Wing |  | Sale |  | Flats | No. of Unit |  | Total Carpet Area | Total Saleable Area
Phase I (Tower 2A) |  | Sale |  | Flats | 401 |  | 139362.5575 | 209043.8362
Phase I (Tower 1I) |  | Sale |  | Flats | 517 |  | 179764.9086 | 269647.3629
Phase I (Tower 1J) |  | Sale |  | Flats | 517 |  | 179764.9086 | 242049.0777
Phase I (Tower 5B) |  | Sale |  | Flats | 401 |  | 141673.4462 | 212510.1693
Phase II (Tower 1K) |  | Sale |  | Flats | 415 |  | 148103.4906 | 222155.2359
Phase II (Tower 1L) |  | Sale |  | Flats | 415 |  | 148103.4906 | 222155.2359
Phase III (Tower 1M) |  | Sale |  | Flats | 355 |  | 169893.594 | 254840.391
Phase III (Tower 4A) |  | Sale |  | Flats | 355 |  | 169893.594 | 254840.391
Total |  | Sale |  | Flats | 3376 |  | 1276559.99 | 1887241.6999
Unit Details, Nomenclature and Commercial Area Details
Building & Wing |  | Sale |  | Shops | No. of Unit |  | Total Carpet Area | Total Saleable Area
Phase III ( Tower 1K ) |  | Sale |  | Shops | 10 |  | 1811.0861 | 2716.6291
Phase III ( Tower 4A ) |  | Sale |  | Shops | 10 |  | 1811.0861 | 2716.6291
Total |  | Sale |  | Shops | 20 |  | 3622.1721 | 5433.2582
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
50%
Sector 3A - Cluster 2
Phase I (Dosti Pride)
Wing A (Tower 2A)
Ground Floor For Parking, Fitness Center, Creche, Meter Room, Drivers Room & Society Office
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 2 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 3 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 4 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 5 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 6 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 7 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 8 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 9 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 10 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 11 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 12 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 13 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 14 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 1 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 2 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2701,..,2901 | 2701 | 2901
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 3 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2702,..,2902 | 2702 | 2902
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 4 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2703,..,2903 | 2703 | 2903
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 5 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2704,..,2904 | 2704 | 2904
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 6 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2705,..,2905 | 2705 | 2905
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 7 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2706,..,2906 | 2706 | 2906
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 8 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2707,..,2907 | 2707 | 2907
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 9 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2708,..,2908 | 2708 | 2908
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 10 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2709,..,2909 | 2709 | 2909
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 11 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2710,..,2910 | 2710 | 2910
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 12 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2711,..,2911 | 2711 | 2911
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 13 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2712,..,2912 | 2712 | 2912
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 14 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 2713,..,2913 | 2713 | 2913
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) | [11 empty] | 2710,..,2910 | 2710 | 2910
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 2 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8101 to 2801 | 8101 | 2801
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 3 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8102 to 2802 | 8102 | 2802
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 4 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8103 to 2803 | 8103 | 2803
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 5 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8104 to 2804 | 8104 | 2804
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 6 |  | Refuge Area |  |  |  | 0 |  |  |  | 8105 to 2805 | 8105 | 2805
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 7 |  | 1 | 287.458 |  | 0 | 431.187 |  |  |  | 8106 to 2806 | 8106 | 2806
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 8 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8107 to 2807 | 8107 | 2807
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 9 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8108 to 2808 | 8108 | 2808
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 10 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8109 to 2809 | 8109 | 2809
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 11 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8110 to 2810 | 8110 | 2810
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 12 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8111 to 2811 | 8111 | 2811
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 13 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8112 to 2812 | 8112 | 2812
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 14 |  | 1 | 348.2961 |  | 0 | 522.4442 |  |  |  | 8113 to 2813 | 8113 | 2813
Wing B ( Tower 1I )
Ground Floor For Parking, Fitness Center, Creche, Meter Room, Drivers Room & Society Office
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 2 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 3 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 4 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 5 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 6 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 7 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 8 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 9 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 10 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 11 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 12 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 13 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 14 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 15 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 16 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 17 |  | 1 | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 18 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 1 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 2 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 3 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 4 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 5 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 6 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 7 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 8 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 9 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 10 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 11 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 12 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 13 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 14 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 15 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 16 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 17 |  | 1 | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 18 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 2 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 3 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 4 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 5 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 6 |  | Refuge Area |  |  |  | 0
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 7 |  | 1 | 287.458 |  | 0 | 431.187
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 8 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 9 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 10 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 11 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 12 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 13 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 14 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 15 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 16 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 17 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 18 |  | 1 | 348.2961 |  | 0 | 522.4442
Wing C ( Tower 1J )
Ground Floor For Parking, Fitness Center, Creche, Meter Room, Drivers Room & Society Office
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 2 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 3 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 4 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 5 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 6 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 7 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 8 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 9 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 10 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 11 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 12 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 13 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 14 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 15 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 16 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 17 |  | 1BHK | 348.2961 |  | 0 | 522.4442
1st Floor For Residential |  | 18 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 1 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 2 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 3 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 4 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 5 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 6 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 7 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 8 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 9 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 10 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 11 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 12 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 13 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 14 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 15 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 16 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 17 |  | 1BHK | 348.2961 |  | 0 | 522.4442
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 18 |  | 1BHK | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 2 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 3 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 4 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 5 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 6 |  | Refuge Area |  |  |  | 0
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 7 |  | 1 | 287.458 |  | 0 | 431.187
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 8 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 9 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 10 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 11 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 12 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 13 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 14 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 15 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 16 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 17 |  | 1 | 348.2961 |  | 0 | 522.4442
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 18 |  | 1 | 348.2961 |  | 0 | 522.4442
Wing D ( Tower 5B )
Ground Floor For Parking, Fitness Center, Creche, Meter Room, Drivers Room & Society Office
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 2 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 3 |  | 1BHK | 352.3649 |  | 0 | 528.5474
1st Floor For Residential |  | 4 |  | 1BHK | 352.3649 |  | 0 | 528.5474
1st Floor For Residential |  | 5 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 6 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 7 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 8 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 9 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 10 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 11 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 12 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 13 |  | 1BHK | 353.4585 |  | 0 | 530.1878
1st Floor For Residential |  | 14 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 1 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 2 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 3 |  | 1BHK | 352.3649 |  | 0 | 528.5474
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 4 |  | 1BHK | 352.3649 |  | 0 | 528.5474
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 5 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 6 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 7 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 8 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 9 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 10 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 11 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 12 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 13 |  | 1BHK | 353.4585 |  | 0 | 530.1878
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  | 14 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 2 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 3 |  | 1BHK | 352.3649 |  | 0 | 528.5474
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 4 |  | 1BHK | 352.3649 |  | 0 | 528.5474
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 5 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 6 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 7 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 8 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 9 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 10 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 11 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 12 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 13 |  | 1BHK | 353.4585 |  | 0 | 530.1878
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 14 |  | Refuge Area |  |  |  | 0
Phase II (Dosti Charm)
Wing B ( Tower 1K ) ( Tower 3 Bldg4 )
Ground Floor For Parking, Fitness Center, Creche, Meter Room, Drivers Room & Society Office
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 1 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 2 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 3 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 4 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 5 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 6 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 7 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 8 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 9 |  | 1BHK | 322.5971 |  | 0 | 483.8956
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 10 |  | 1BHK | 322.5971 |  | 0 | 483.8956
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 11 |  | 1BHK | 322.5971 |  | 0 | 483.8956
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 12 |  | 1BHK | 322.5971 |  | 0 | 483.8956
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 13 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 14 |  | 1BHK | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 2 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 3 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 4 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 5 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 6 |  | Refuge Area |  |  |  | 0
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 7 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 8 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 9 |  | 1 | 322.5971 |  | 0 | 483.8956
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 10 |  | 1 | 322.5971 |  | 0 | 483.8956
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 11 |  | 1 | 322.5971 |  | 0 | 483.8956
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 12 |  | 1 | 322.5971 |  | 0 | 483.8956
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 13 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 14 |  | 1 | 370.8198 |  | 0 | 556.2297
Wing C ( Tower 1L ) ( Tower 3 Bldg3 )
Ground Floor For Parking, Fitness Center, Creche, Meter Room, Drivers Room & Society Office
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 1 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 2 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 3 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 4 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 5 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 6 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 7 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 8 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 9 |  | 1BHK | 322.5971 |  | 0 | 483.8956
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 10 |  | 1BHK | 322.5971 |  | 0 | 483.8956
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 11 |  | 1BHK | 322.5971 |  | 0 | 483.8956
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 12 |  | 1BHK | 322.5971 |  | 0 | 483.8956
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 13 |  | 1BHK | 370.8198 |  | 0 | 556.2297
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 14 |  | 1BHK | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 2 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 3 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 4 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 5 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 6 |  | Refuge Area |  |  |  | 0
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 7 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 8 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 9 |  | 1 | 322.5971 |  | 0 | 483.8956
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 10 |  | 1 | 322.5971 |  | 0 | 483.8956
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 11 |  | 1 | 322.5971 |  | 0 | 483.8956
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 12 |  | 1 | 322.5971 |  | 0 | 483.8956
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 13 |  | 1 | 370.8198 |  | 0 | 556.2297
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 14 |  | 1 | 370.8198 |  | 0 | 556.2297
Phase III ( Dosti Grace )
Wing A ( Tower 1 M ) ( Tower 4 Bldg5 )
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 1 |  | Shop | 219.5748 |  | 0 | 329.3623
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 2 |  | Shop | 147.4797 |  | 0 | 221.2196
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 3 |  | Shop | 195.823 |  | 0 | 293.7345
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 4 |  | Shop | 194.5851 |  | 0 | 291.8777
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 5 |  | Shop | 148.0803 |  | 0 | 222.1205
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 6 |  | Shop | 148.0803 |  | 0 | 222.1205
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 7 |  | Shop | 194.5851 |  | 0 | 291.8777
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 8 |  | Shop | 195.823 |  | 0 | 293.7345
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 9 |  | Shop | 147.4797 |  | 0 | 221.2196
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 10 |  | Shop | 219.5748 |  | 0 | 329.3623
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 1 |  | 2BHK | 534.9708 |  | 0 | 802.4562
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 2 |  | 2BHK | 534.9708 |  | 0 | 802.4562
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 3 |  | 2BHK | 534.9708 |  | 0 | 802.4562
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 4 |  | 2BHK | 534.9708 |  | 0 | 802.4562
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 5 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 6 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 7 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 8 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 9 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 10 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 11 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 12 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 534.9708 |  | 0 | 802.4562
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 534.9708 |  | 0 | 802.4562
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 534.9708 |  | 0 | 802.4562
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 4 |  | Refuge Area |  |  |  | 0
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 5 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 6 |  | 3BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 8 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 9 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 10 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 11 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 12 |  | 2BHK | 451.5498 |  | 0 | 677.3247
Wing B ( Tower 4 Bldg 6 )
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 1 |  | Shop | 219.5748 |  | 0 | 329.3623
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 2 |  | Shop | 147.4797 |  | 0 | 221.2196
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 3 |  | Shop | 195.823 |  | 0 | 293.7345
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 4 |  | Shop | 194.5851 |  | 0 | 291.8777
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 5 |  | Shop | 148.0803 |  | 0 | 222.1205
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 6 |  | Shop | 148.0803 |  | 0 | 222.1205
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 7 |  | Shop | 194.5851 |  | 0 | 291.8777
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 8 |  | Shop | 195.823 |  | 0 | 293.7345
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 9 |  | Shop | 147.4797 |  | 0 | 221.2196
Ground Floor For Part Commercial, Fitness Center, Creche, Meter Room, Drivers Room & Society Office |  | 10 |  | Shop | 219.5748 |  | 0 | 329.3623
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 1 |  | 2BHK | 534.9708 |  | 0 | 802.4562
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 2 |  | 2BHK | 534.9708 |  | 0 | 802.4562
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 3 |  | 2BHK | 534.9708 |  | 0 | 802.4562
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 4 |  | 2BHK | 534.9708 |  | 0 | 802.4562
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 5 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 6 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 7 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 8 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 9 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 10 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 11 |  | 2BHK | 451.5498 |  | 0 | 677.3247
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor For Residential |  | 12 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 534.9708 |  | 0 | 802.4562
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 2 |  | 2BHK | 534.9708 |  | 0 | 802.4562
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 3 |  | 2BHK | 534.9708 |  | 0 | 802.4562
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 4 |  | Refuge Area |  |  |  | 0
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 5 |  | 1BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 6 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 7 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 8 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 9 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 10 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 11 |  | 2BHK | 451.5498 |  | 0 | 677.3247
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  | 12 |  | 2BHK | 451.5498 |  | 0 | 677.3247
Project Specific Remarks & Observation | [11 empty] | #REF! | #REF! | #REF!
Remarks / Observations | : | 1. Construction work is in process at the time of Visit.(Internal visit not allowed). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. As per RERA, Approved floor plan & CC the nomenclature of the buildings in phases 2 and 3 have been changed. 8. We have updated revised approved floor plan & C.C for Phase 1, 2 & 3 (on 24/11/2023). 9. We have updated revised approved floor plan & C.C for Phase 1, 2 & 3 (on 28/11/2024). 10. The nomenclature of the buildings in phases 2 and 3 have been changed as mentioned below. 7. On Site, we meet Mr........(........).
Phases |  |  |  | As per Previous Approved Plan |  |  | As per Revised Approved Plan
Phase II = Dosti Charm |  |  |  | Wing B - Tower 1L |  |  | Wing C - Tower T3-3
|  |  |  | Wing A - Tower 1K |  |  | Wing B - Tower T3-4
Phase III = Dosti Grace |  |  |  | Wing A - Tower 1M |  |  | Wing A - Tower T4-5
|  |  |  | Wing B - Tower 4A |  |  | Wing B - Tower T4-6
Site & Building/Tower Photographs
Name of the Project |  |  | : | Dosti Greater Thane - Sector 3A - Cluster 2 - Phase 1, 2 & 3
Project Site Address |  |  | : | Dosti Greater Thane - Sector 3A - Cluster 2 - Phase 1, 2 & 3 162 (pt), 163/1 (pt), 163/2 (pt), 151/2A (pt), 159/2 (pt), 153 (pt), 154/3A (pt), 154/3B (pt), 154/7 (pt), 159/1A (pt), 159/1B (pt), 159/1C (pt)at Purne (CT), Bhiwandi, Thane, 421302
Site Visit Date & Time |  |  | : | 03/08/2025 at 02:16PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Mangesh | Authorized Signatory Name & Signature | :
Cluster II
Phase 1,2 & 3
https://vsjcllp.vsjadon.com/upload/insp-151402-843.jpg
https://vsjcllp.vsjadon.com/upload/insp-151402-843.jpg
Phase I
Phase II
Phase III
2A
1K
1J
5B
1K
1L
1M
4A
Dosti Grace (A & B)
Dosti Pride
Dosti Charm
A
B
C
D
A
B
C
Note on H6: Rushil Sanghvi or Fahad
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Map Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H20: From RERA
Note on A39: As per Layout
Note on H204: Ready Recknor

## Sheet1
303.4425