## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05
Project Name |  | Dosti West County - Phase 5 - Dosti Olive - Wing B |  | Date & Time of Site Visit |  | 06/08/2025 at 12:05PM |  | 2025-08-06
Name of the person met at site & Contact No. |  | NA |  | Date of Report Release |  | 07/08/2025 |  | 84 |  | 2025-05-14
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Dosti Enterprises |  | Developer Name |  | Dosti Realty LTD
Developer Office Address |  | Lawrency & Mayo House 1st Floor,276 Dr.D.N.Road, Fort Mumbai Mh 400001
Project Address | As per ARF | Dosti West County Phase 5 Dosti Olive Wing B, Bhiwandi - Wadpa Road, Old, Mumbai - Agra National Hwy, Balkum Pada, Thane West, Thane, Maharashtra 400608
| As per Legal Documents | Dosti West County Phase 5 Dosti Olive Wing B, Survey No.16/10/A/1(Pt), 16/11/A(Pt), 16/12/1/A(Pt) & 17/13(Pt), near Dosti Oak, Dosti West County Road, Kolshet, Balkum, Thane West, Thane, Thane - 400608
| As per Actual at site | Dosti West County Phase 5 Dosti Olive Wing B, Survey No.16/10/A/1(Pt), 16/11/A(Pt), 16/12/1/A(Pt) & 17/13(Pt), near Dosti Oak, Dosti West County Road, Kolshet, Balkum, Thane West, Thane, Thane - 400608
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Thane Muncipal Cooperation (TMC)
RERA Registration No. | : | P51700054037 |  | RERA Registration Validity | : | 2028-09-30
Project Launch Date | : | 2023-12-27 |  | Construction Start Date | : | 2023-12-27
Proposed Date of Completion (As per RERA) | : | 2028-09-30 |  | Developer Bank Name (As per RERA) | : | Kotak Mahindra Bank Ltd IFSC Code KKBK0000957
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 54750
FSI/FAR Permissible | : | 4 |  | Net Plot Area (In Sq.Mt) | : | 54750
Permissible Built up Area (In Sq.Mt) | : | 252452.1 |  | Proposed Built up Area (In Sq.Mt) | : | 251296.32
Total Number of Units Approved | : | Flats = 192 & Shop = 7 |  | Total Number of Units Planned | : | As per RERA Site Flats = 192 & Shop = 7
Latitude, Longitude | : | 19.226164,72.993572 |  | Landmark | : | Dosti Oak
Location Link | : | https://maps.app.goo.gl/nryoa7zgYBER7DTS9
Extra Amenities available | : | Open Party Lawn, Jogging Track, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Swimming Pool, Kids Play Area, Seating Promenade, Basketball Court, Cricket pitch, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 30 m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 900 M from Balkum Bus Stop
Distance from the nearest School (Km) | : | About 1.3 KM from Narayana e -Techno School |  | Distance from Hospital (Km) | : | About 1.2 KM form Ashtavinayak Multispeciality Hospital
Distance from the Main Market (Km) | : | 1. Approx. 3KM from Low Price Super Mart. 2. Approx. 3.5KM from R Mall. |  | Distance from Railway Station (Km) | : | 5.9 KM from Thane Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East | West
East |  | Building No. 11 |  |  | Open Plot
West |  | Building No. 09 |  |  | Dosti Realty Regional Office
North |  | Building No. 17,18, 19 |  |  | Dosti Pine & Oak
South |  | 30.00M. Wide Road |  |  | Dosti West County Road
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No. 10 |  | Sale | B + Gr -Mezz. (Pt)/Stilt (Pt) + Podium + 1st to 33rd Floor |  |  | B + Gr -Mezz.(Pt)/Stilt (Pt) + Podium + 1st to 33rd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | S05/0006/08 TMC/TD-DP/TPS/4472/23 |  |  |  | Date: | 26/09/2023
Approved Plan Details | : | S05/0006/08 TMC/TD-DP/TPS/4472/23 |  |  |  | Date: | 26/09/2023
CC Details Valid Up to: |  | S05/0006/08/ TMC/TDD/4472/23 |  |  |  | Date: | 26/09/2023
Building No. 10 = Basement + Gr -Mezz. (Pt) (Commercial)/Stilt (Pt) + Podium + 1st to 5th Floor
Environmental Clearance Details | : | Ministry of Environment, Forest and Climate Change IA/MH/MIS/67197/2017 Valid Up for: Survey No.16/10/A/1(Pt), 16/11/A(Pt), 16/12/1/A(Pt) & 17/13(Pt) |  |  |  | Date: | 14/01/2019
Fire NOC Details | : | TMC/CFO/M/HR/162/161 Valid Up to: B + Gr/Stilt + Mezzanine + Podium + 1st to 10th Floor (Height 39.40Mtrs) |  |  |  | Date: | 2023-09-11
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Building No. 10 = B + Gr -Mezz. (Pt)/Stilt (Pt) + Podium + 1st to 33rd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 23 Floor, Internal Plaster upto 18.4 Floor, External Plaster upto 18.4 Floor Completed
|  |  | 0 | 1 |  | 1 | 33 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 8.25
Excavation |  | 33 | 100% | 49.13% |  | Excavation work Completed. Plinth work completed, RCC upto 25 Slab, Brickwork upto 23 Floor, Internal Plaster upto 18.4 Floor, External Plaster upto 18.4 Floor Completed |  | Excavation in process | 16.5
Plinth |  | 33 | 100% |  |  |  |  | Excavation Completed | 33
RCC (Including podiums) |  | 25 | 71.43% |  |  |  |  | Footing in Process | 6.6
Brickwork |  | 23 | 69.7% |  |  |  |  | Footing Completed | 13.2
Internal Plaster |  | 18.4 | 55.76% |  |  |  |  | Basement 1 | 0
External Plaster |  | 18.4 | 55.76% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 23.1
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 33
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
#REF! |  |  | Basement | Ground |  | Podium | Floors | #REF!
|  |  | 0 | 1 |  | 0 | #REF! | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | 0 | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork |  | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster |  | 0 | #REF! |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | #REF! |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | #REF! |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Electrical & Sanitary fittings |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Building Common Amenities |  | 0 | #REF!
Possession |  | 0 | #REF!
Project Completion % | [5 empty] | 49.13%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 16000 to 16500 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 600000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 3084.3553
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 9624.6748
Distress Value (Rs. Per sqft) |  |  |  |  | : | 2467.4842
Unit Details, Nomenclature and Area Details (Commercial) Building No.10
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Shops (Olive Wing B) |  | - |  | 7 |  | 5411.7086
Total |  | - |  | 7 |  | 5411.7086
Unit Details, Nomenclature and Area Details (Flats) Building No.10
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Flats (Olive Wing B) |  | - |  | 192 |  | 152856.4424
Total |  | - |  | 192 |  | 152856.4424
Grand Total |  | - |  | 199 |  | 158268.1511
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Plot A1
Phase 5 (Buidling No. 10)
Dosti Olive Wing B
Basement Floor For Parking
Ground Floor For Commercial, Entrance Lobby, Drivers Room, L.V. Room, Panel Room, Fire Control Room, Society office, Meter Room & Parking
7 |  | - | Shop | 506.4462 | 229.7038 | 0 | 736.15
8 |  | - | Shop | 602.8916 | 302.4684 | 0 | 905.36
9 |  | - | Shop | 381.3685 | 174.5921 | 0 | 555.9606
10 |  | - | Shop | 358.3336 | 191.5992 | 0 | 549.9328
11 |  | - | Shop | 642.0726 | 288.7981 | 0 | 930.8707
12 |  | - | Shop | 551.4397 | 246.4956 | 0 | 797.9353
13 |  | - | Shop | 634.5378 | 300.9614 | 0 | 935.4992
Podium Floor For Parking
1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd & 33rd Floor For Residential
1 |  | - | 3BHK | 910.9573 | 36.7052 | 0 | 947.6626 | [6 empty] | 15701,..,3301 | 15701 | 3301
2 |  | - | 3BHK | 986.1977 | 36.49 | 0 | 1022.6876 | [6 empty] | 15702,..,3302 | 15702 | 3302
3 |  | - | 2BHK | 728.077 | 29.2781 | 0 | 757.355 | [6 empty] | 15703,..,3303 | 15703 | 3303
4 |  | - | 1.5BHK | 594.3881 | 27.5558 | 0 | 621.9439 | 15917.8339 | [5 empty] | 15704,..,3304 | 15704 | 3304
5 |  | - | 2BHK | 635.5066 | 27.5558 | 0 | 663.0624 | [6 empty] | 15705,..,3305 | 15705 | 3305
6 |  | - | 2BHK | 703.1045 | 29.2781 | 0 | 732.3826 | 16500 | [5 empty] | 15706,..,3306 | 15706 | 3306
6th, 11th, 16th, 21st, 26th & 31st Floor for Residential (Part Refuge Area)
1 |  | - | 3BHK | 910.9573 | 36.7052 | 0 | 947.6626 | [6 empty] | 61101,..,3101 | 61101 | 3101
2 |  | - | 3BHK | 986.1977 | 36.49 | 0 | 1022.6876 | [6 empty] | 61102,..,3102 | 61102 | 3102
3 |  | - | 2BHK | 728.077 | 29.2781 | 0 | 757.355 | [6 empty] | 61103,..,3103 | 61103 | 3103
4 |  | Refuge Area | [11 empty] | 61104,..,3104 | 61104 | 3104
5 |  | - | 2BHK | 635.5066 | 27.5558 | 0 | 663.0624 | [6 empty] | 61105,..,3105 | 61105 | 3105
6 |  | - | 2BHK | 703.1045 | 29.2781 | 0 | 732.3826 | [6 empty] | 61106,..,3106 | 61106 | 3106
1st Floor
101 |  |  |  | 0 | 0 | 0 | 0
102 | [6 empty] | 0
103 | [6 empty] | 0
104 | [6 empty] | 0
105 | [6 empty] | 0
106 | [6 empty] | 0
107 | [6 empty] | 0
108 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [6 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [6 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [6 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [6 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [6 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [6 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [6 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [6 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [6 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [6 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [6 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [6 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [6 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [6 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [6 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [6 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [6 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [6 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [6 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [6 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [6 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit. (Internal Visit not allowed)
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | Construction goes beyond approved CC permission. Please provide revised approved CC.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Remark for NOCs
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs
Name of the Project |  |  | Dosti West County - Phase 5 - Dosti Olive - Wing B
Project Site Address |  |  | Dosti West County Phase 5 Dosti Olive Wing B, Bhiwandi - Wadpa Road, Old, Mumbai - Agra National Hwy, Balkum Pada, Thane West, Thane, Maharashtra 400608
Site Visit Date & Time |  |  | 06/08/2025 at 12:05PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Ajay Songare |  | Authorized Signatory Name & Signature
Building No 10
Bldg No. 10
Bldg No. 9
Note on C9: SACHIN: As per initiation Mail
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G96: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%