## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 | 2025-05-07 |  | 90
Project Name |  |  | : | Dosti West County - Dosti Tulip |  | Date & Time of Site Visit |  | 05/08/2025 at 12:09PM | 2025-08-05
Name of the person met at site & Contact No. |  |  | : | Security |  | Date of Report Release |  | 08/08/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr.Suraj Khare
Builder Group Name |  |  | : | M/s.Dosti Enterprises | Developer Name | : | M/s.Dosti Realty LTD
Developer Office Address |  |  | : | Lawrency & Mayo House 1st Floor, 276 Dr.D.N.Road, Fort Mumbai Maharashtra 400001
Project Address | : | As per ARF | : | Bhiwandi - Wadpa Road, Old, Mumbai - Agra National Hwy, Balkum Pada, Thane West, Thane, Maharashtra 400608
| : | As per Legal Documents | : | S.no 43/2 (pt), 43/3, 43/4, 43/5, 44/1(pt), 45/1 (pt), 46/1/A, 47/1, 47/2/A, 47/2/3/2 A(pt), 47/3/1/A, 47/4/A, 47/5(pt) at Village Balkum, Tal. & Dist Thane
| : | As per Actual at site | : | Dosti West County Dosti Tulip, Road - Bhiwandi - Wada Road, Near - Dosti Cedar, Village Balkum, Taluka & District - Thane, Thane West, Maharashtra 400608
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation (TMC)
RERA Registration No. | : | P51700032666 |  |  | RERA Registration Validity | : | 2026-10-31
Project Launch Date | : | 2021-12-10 |  |  | Construction Start Date | : | 2022-01-17
Proposed Date of Completion (As per RERA) | : | 2026-10-31 |  |  | Developer Bank Name (As per RERA) | : | KOTAK MAHINDRA BANK IFSC Code - KKBK0000957
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | : | 11210
FSI/FAR Permissible | : | 1.1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 50174.8
Permissible Built up Area (In Sq.Mt) | : | 50246.5 |  |  | Total Number of Units Planned | : | As per RERA - Flats = 658 & Shop = 26
Total Number of Units Approved | : | Sale Flats = 517 Mhada Flats = 49 |  |  | If Mixed, No. of Commercial Units | : | Shop = 26
Latitude, Longitude | : | 19.228309, 72.996451
Location Link | : | https://maps.app.goo.gl/PB83GigtvspGuSfN7
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 1.1 KM from Balkum Pada Number 1 Bus Stop
Distance from the nearest School (Km) | : | About 1.5 KM from Narayana e-Techno School |  |  | Distance from Hospital (Km) | : | About 3.1KM form Highland Speciality Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.5KM from Balaji Super Market. 2. Approx. 7.5KM from D-Mart. |  |  | Distance from Railway Station (Km) | : | 5.9 KM from Thane Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Open Plot | Road | Road |  | Road
As per Site / Actual |  |  | : | Open Plot | Open Plot | Balkum Pipeline Road |  | Open Plot
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No.1 (A Wing) |  | Sale |  | G + 1st to 4th Podium Floor + 1st to 30th floor |  |  | G + 1st to 4th Podium Floor + 1st to 29th floor
Building No.2 (A Wing) |  | Sale |  | G + 1st to 4th Podium Floor + 1st to 30th floor |  |  | G + 1st to 4th Podium Floor + 1st to 29th floor
Building No.3 |  | Sale |  | G + 1st to 4th Podium Floor + 1st to 30th floor |  |  | G + 1st to 4th Podium Floor + 1st to 13th floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | V.P.SO5/0177/19/TMC/TDD/3803/21 Date: 10/12/2021
CC Details | : | V.P.SO5/0177/19/TMC/TDD/4428/23 Date: 27/06/2023 Valid Up to: Building No.1 (A wing) = G + 1st to 4th Podium Floors + 1st to 14th Floor Building No.2 (A wing) = G + 1st to 4th Podium Floors + 1st to 14th Floor Building No.3 = G + 1st to 4th Podium Floors + 1st to 13th floors. |  |  | Approved Plan Details | : | V.P.SO5/0177/19/TMC/TDD/3803/21 Date: 10/12/2021 | [5 empty] | Tulip ABC S+3P+1-30 8 units 5 Lifts 2,3BHK 661 to 923 sq ft 18500 On carpet Excavation work in progress Plinth in progress | Building No.19 (A Wing) 29th slab in Complete (Resi) Building No.18 (B Wing) 29th slab in complete (Resi.) Building No.17 (C Wing) 2nd slab is completed (Resi) Building No.7 (D Wing) 2nd slab in Complete Building No.8 (E Wing) 2nd slb in complete | Crest in not launched | Ceder Structure complete Block work completed Gypsum work completed 19th flooring in Completed Windows and door work completed Partly painting work completed
Environmental Clearance Details | : | - |  |  | Airport Authority Clearance Details | : | -
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Building No.1 (A Wing) = G + 1st to 4th Podium Floors + 1st to 30th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work, Electrical & Sanitary fittings upto 29 Floor, Finishing upto 7 Floor Completed
|  |  |  | 0 | 1 |  | 4 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 30 |  | 100% | 82.25% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work, Electrical & Sanitary fittings upto 29 Floor, Finishing upto 7 Floor Completed |  | Excavation in process | 15
Plinth |  | 30 |  | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 35 |  | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork |  | 30 |  | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster |  | 30 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 30 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 30 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 30 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 30 |  | 100% |  |  |  |  | Plinth in process | 22.5
Electrical & Sanitary fittings |  | 29 |  | 96.67% |  |  |  |  | Plinth completed | 30 |  | #VALUE!
Building Common Amenities |  | 7 |  | 23.33%
Possession |  | 0 |  | 0%
Construction Status
Building No.2 (A Wing) = G + 1st to 4th Podium Floor + 1st to 30th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work, Electrical & Sanitary fittings, Finishing upto 17 Floor Completed
|  |  |  | 0 | 1 |  | 4 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 30 |  | 100% | 85.67% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work, Electrical & Sanitary fittings, Finishing upto 17 Floor Completed |  | Excavation in process | 15
Plinth |  | 30 |  | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 35 |  | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork |  | 30 |  | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster |  | 30 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 30 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 30 |  | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 30 |  | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 30 |  | 100% |  |  |  |  | Plinth in process | 22.5
Electrical & Sanitary fittings |  | 30 |  | 100% |  |  |  |  | Plinth completed | 30 |  | #VALUE!
Building Common Amenities |  | 17 |  | 56.67%
Possession |  | 0 |  | 0%
Construction Status | [8 empty] | 16.32
Building No.3 = G + 1st to 4th Podium Floors + 1st to 30th floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 28 Slab, Brickwork upto 23 Floor, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor Completed
|  |  |  | 0 | 1 |  | 4 | 30 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.5
Excavation |  | 30 |  | 100% | 51.33% |  | Excavation work Completed. Plinth work completed, RCC upto 28 Slab, Brickwork upto 23 Floor, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor Completed |  | Excavation in process | 15
Plinth |  | 30 |  | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 28 |  | 80% |  |  |  |  | Footing in Process | 7.5
Brickwork |  | 23 |  | 76.67% |  |  |  |  | Footing Completed | 15
Internal Plaster |  | 15 |  | 50% |  |  |  |  | Basement 1 | 0
External Plaster |  | 15 |  | 50% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 22.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 30 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 73.08%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 14500 to 15500 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Rate of Shop Per Sq. Ft. (on Carpet area) |  |  | : : | 24000
Car Parking Charges |  |  | : | 500000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 2629.13
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 7710.8881
Distress Value (Rs. Per sqft) | [5 empty] | : | 2103.304
Commercial Area Details :
Building & Wing |  | Sale / Rehab |  | Shops | No. of Unit |  | Total Carpet Area | Total Saleable Area
Building No.1 (A wing) |  | Sale |  | Shops | 13 |  | 4107.1118 | 6571.3789
Building No.2 (A wing) |  | Sale |  | Shops | 13 |  | 4065.4552 | 6504.7283
Total |  | Sale |  | Shops | 26 |  | 8172.567 | 13076.1072
Residential Area Details : (SALE)
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Building No.1( A wing) |  | Sale |  | Flats | 181 |  | 135394.1129 | 216630.5806
Building No.2( A wing) |  | Sale |  | Flats | 230 |  | 163055.3324 | 260888.5319
Building No.3 |  | Sale |  | Flats | 106 |  | 75612.2562 | 120979.6099
Total |  | Sale |  | Flats | 517 |  | 374061.7015 | 477519.1125
Residential Area Details : (MHADA)
Building No.1( A wing) |  | Mhada |  | Flats | 49 |  | 24135.4714 | 38616.7542
Total |  | - |  | - | 49 |  | 24135.4714 | 38616.7542
Grand Total |  | - |  | - | 592 |  | 406369.7399 | 529211.9739
Building details Floor Wise
Details of Shops in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
Building No.1 ( A wing)
Ground Floor for Commercial & Parking
Ground Floor for Commercial & Parking |  | 1 |  | Shop | 346.4932 |  | 0 | 554.3891
Ground Floor for Commercial & Parking |  | 2 |  | Shop | 212.2661 |  | 0 | 339.6257
Ground Floor for Commercial & Parking |  | 3 |  | Shop | 309.8956 |  | 0 | 495.8329
Ground Floor for Commercial & Parking |  | 4 |  | Shop | 321.9512 |  | 0 | 515.122
Ground Floor for Commercial & Parking |  | 5 |  | Shop | 422.9176 |  | 0 | 676.6681
Ground Floor for Commercial & Parking |  | 6 |  | Shop | 325.611 |  | 0 | 520.9776
Ground Floor for Commercial & Parking |  | 7 |  | Shop | 366.2989 |  | 0 | 586.0783
Ground Floor for Commercial & Parking |  | 8 |  | Shop | 267.8083 |  | 0 | 428.4933
Ground Floor for Commercial & Parking |  | 9 |  | Shop | 309.8956 |  | 0 | 495.8329
Ground Floor for Commercial & Parking |  | 10 |  | Shop | 212.2661 |  | 0 | 339.6257
Ground Floor for Commercial & Parking |  | 11 |  | Shop | 346.4932 |  | 0 | 554.3891
Ground Floor for Commercial & Parking |  | 12 |  | Shop | 332.6076 |  | 0 | 532.1722
Ground Floor for Commercial & Parking |  | 13 |  | Shop | 332.6076 |  | 0 | 532.1722
Building No.2 ( A wing)
Ground Floor for Commercial & Parking
Ground Floor for Commercial & Parking |  | 14 |  | Shop | 332.6076 |  | 0 | 532.1722
Ground Floor for Commercial & Parking |  | 15 |  | Shop | 332.6076 |  | 0 | 532.1722
Ground Floor for Commercial & Parking |  | 16 |  | Shop | 346.4932 |  | 0 | 554.3891
Ground Floor for Commercial & Parking |  | 17 |  | Shop | 212.2661 |  | 0 | 339.6257
Ground Floor for Commercial & Parking |  | 18 |  | Shop | 309.8956 |  | 0 | 495.8329
Ground Floor for Commercial & Parking |  | 19 |  | Shop | 267.8083 |  | 0 | 428.4933
Ground Floor for Commercial & Parking |  | 20 |  | Shop | 355.8578 |  | 0 | 569.3725
Ground Floor for Commercial & Parking |  | 21 |  | Shop | 306.6664 |  | 0 | 490.6662
Ground Floor for Commercial & Parking |  | 22 |  | Shop | 410.6466 |  | 0 | 657.0346
Ground Floor for Commercial & Parking |  | 23 |  | Shop | 321.9512 |  | 0 | 515.122
Ground Floor for Commercial & Parking |  | 24 |  | Shop | 309.8956 |  | 0 | 495.8329
Ground Floor for Commercial & Parking |  | 25 |  | Shop | 212.2661 |  | 0 | 339.6257
Ground Floor for Commercial & Parking |  | 26 |  | Shop | 346.4932 |  | 0 | 554.3891
Details of Flats in Building
Floor |  | Flat No. - (Sale Or Mhada) |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
Building No.1 ( A wing)
1st to 3rd Podium Floor For Parking
4th Podium Floor For Parking & Residential
4th Podium Floor For Parking & Residential |  | 1 |  | Parking Area
2
3
4
|  | 5 - Sale |  | 2BHK | 752.7265 |  | 0 | 1204.3624
|  | 6 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | 14082.8392
|  | 7 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278
|  | 8 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264
1st Floor
1st Floor |  | 1 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | 58.341 | [7 empty] | 101,..,101 | 101 | 101
|  | 2 - Mhada |  | 1.5BHK | 492.5606 |  | 0 | 788.097 | [8 empty] | 102,..,102 | 102 | 102
|  | 3 - Mhada |  | 1.5BHK | 492.5606 |  | 0 | 788.097 | [8 empty] | 103,..,103 | 103 | 103
|  | 4 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 104,..,104 | 104 | 104
|  | 5 - Sale |  | 2BHK | 752.7265 |  | 0 | 1204.3624 | [8 empty] | 105,..,105 | 105 | 105
|  | 6 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 106,..,106 | 106 | 106
|  | 7 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 107,..,107 | 107 | 107
|  | 8 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 108,..,108 | 108 | 108
2nd, 7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
2nd, 7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 1 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 2701,..,2701 | 2701 | 2701
|  | 2 |  | Refuge Area | [12 empty] | 2702,..,2702 | 2702 | 2702
|  | 3 - Mhada |  | 1.5BHK | 492.5606 |  | 0 | 788.097 | [8 empty] | 2703,..,2703 | 2703 | 2703
|  | 4 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 2704,..,2704 | 2704 | 2704
|  | 5 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 2705,..,2705 | 2705 | 2705
|  | 6 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 2706,..,2706 | 2706 | 2706
|  | 7 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 2707,..,2707 | 2707 | 2707
|  | 8 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 2708,..,2708 | 2708 | 2708
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th Floor
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th Floor |  | 1 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 3601,..,2601 | 3601 | 2601
|  | 2 - Mhada |  | 1.5BHK | 492.5606 |  | 0 | 788.097 | [8 empty] | 3602,..,2602 | 3602 | 2602
|  | 3 - Mhada |  | 1.5BHK | 492.5606 |  | 0 | 788.097 | [8 empty] | 3603,..,2603 | 3603 | 2603
|  | 4 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 3604,..,2604 | 3604 | 2604
|  | 5 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 3605,..,2605 | 3605 | 2605
|  | 6 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 3606,..,2606 | 3606 | 2606
|  | 7 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 3607,..,2607 | 3607 | 2607
|  | 8 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 3608,..,2608 | 3608 | 2608
28th Floor
28th Floor |  | 1 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 201,..,2801 | 201 | 2801
|  | 2 - Mhada |  | 1.5BHK | 492.5606 |  | 0 | 788.097 | [8 empty] | 202,..,2802 | 202 | 2802
|  | 3 - Sale |  | 1.5BHK | 492.5606 |  | 0 | 788.097 | [8 empty] | 203,..,2803 | 203 | 2803
|  | 4 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 204,..,2804 | 204 | 2804
|  | 5 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 205,..,2805 | 205 | 2805
|  | 6 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 206,..,2806 | 206 | 2806
|  | 7 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 207,..,2807 | 207 | 2807
|  | 8 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 208,..,2808 | 208 | 2808
29th Floor
29th Floor |  | 1 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 201,..,2901 | 201 | 2901
|  | 2 - Sale |  | 1.5BHK | 492.5606 |  | 0 | 788.097 | [8 empty] | 202,..,2902 | 202 | 2902
|  | 3 - Sale |  | 1.5BHK | 492.5606 |  | 0 | 788.097 | [8 empty] | 203,..,2903 | 203 | 2903
|  | 4 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 204,..,2904 | 204 | 2904
|  | 5 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 205,..,2905 | 205 | 2905
|  | 6 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 206,..,2906 | 206 | 2906
|  | 7 - Sale |  | 2BHK | 674.5799 |  | 0 | 1079.3278 | [8 empty] | 207,..,2907 | 207 | 2907
|  | 8 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 208,..,2908 | 208 | 2908
Building No.2 ( A wing)
1st to 3rd Podium Floor For Parking
4th Podium Floor For Parking & Residential
4th Podium Floor For Parking & Residential |  | 1 |  | Parking Area
2
3
4
|  | 5 - Sale |  | 2BHK | 752.7265 |  | 0 | 1204.3624
|  | 6 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331
|  | 7 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331
|  | 8 - Sale |  | 2BHK | 752.7265 |  | 0 | 1204.3624
1st Floor
1st Floor |  | 1 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | 13306.3143 | [7 empty] | 101,..,101 | 101 | 101
|  | 2 - Sale |  | 1.5BHK | 580.6102 |  | 0 | 928.9763 | [8 empty] | 102,..,102 | 102 | 102
|  | 3 - Sale |  | 1.5BHK | 580.6102 |  | 0 | 928.9763 | [8 empty] | 103,..,103 | 103 | 103
|  | 4 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 104,..,104 | 104 | 104
|  | 5 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | 14614.083 | [7 empty] | 105,..,105 | 105 | 105
|  | 6 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 106,..,106 | 106 | 106
|  | 7 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 107,..,107 | 107 | 107
|  | 8 - Sale |  | 2BHK | 752.7265 |  | 0 | 1204.3624 | [8 empty] | 108,..,108 | 108 | 108
2nd, 7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area)
2nd, 7th, 12th, 17th, 22nd & 27th Floor (Part Refuge Area) |  | 1 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 2701,..,2701 | 2701 | 2701
|  | 2 |  | Refuge Area | [12 empty] | 2702,..,2702 | 2702 | 2702
|  | 3 - Sale |  | 1.5BHK | 580.6102 |  | 0 | 928.9763 | [8 empty] | 2703,..,2703 | 2703 | 2703
|  | 4 - Sale |  | 2BHK | 661.4478 |  | 0 | 1058.3165 | [8 empty] | 2704,..,2704 | 2704 | 2704
|  | 5 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 2705,..,2705 | 2705 | 2705
|  | 6 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 2706,..,2706 | 2706 | 2706
|  | 7 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 2707,..,2707 | 2707 | 2707
|  | 8 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 2708,..,2708 | 2708 | 2708
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th & 29th Floor
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th & 29th Floor |  | 1 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 36801,..,2901 | 36801 | 2901
|  | 2 - Sale |  | 1.5BHK | 580.6102 |  | 0 | 928.9763 | [8 empty] | 36802,..,2902 | 36802 | 2902
|  | 3 - Sale |  | 1.5BHK | 580.6102 |  | 0 | 928.9763 | [8 empty] | 36803,..,2903 | 36803 | 2903
|  | 4 - Sale |  | 2BHK | 661.4478 |  | 0 | 1058.3165 | [8 empty] | 36804,..,2904 | 36804 | 2904
|  | 5 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 36805,..,2905 | 36805 | 2905
|  | 6 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 36806,..,2906 | 36806 | 2906
|  | 7 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 36807,..,2907 | 36807 | 2907
|  | 8 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 36808,..,2908 | 36808 | 2908
Building No.3
Ground Floor for Parking
1st to 3rd Podium Floor For Parking
4th Podium Floor For Parking & Residential
4th Podium Floor For Parking & Residential |  | 1 - Sale |  | 2BHK | 674.0417 |  | 0 | 1078.4667
|  | 2 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331
|  | 3 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331
|  | 4 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264
|  | 5 - Sale |  | 2BHK | 752.7265 |  | 0 | 1204.3624
1st to 6th, 8th to 11th, 13th Floor
1st to 6th, 8th to 11th, 13th Floor |  | 1 - Sale |  | 2BHK | 674.0417 |  | 0 | 1078.4667 | [8 empty] | 101,..,1301 | 101 | 1301
|  | 2 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 102,..,1302 | 102 | 1302
|  | 3 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 103,..,1303 | 103 | 1303
|  | 4 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 104,..,1304 | 104 | 1304
|  | 5 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 105,..,1305 | 105 | 1305
|  | 6 - Sale |  | 1.5BHK | 582.9782 |  | 0 | 932.7652 | [8 empty] | 106,..,1306 | 106 | 1306
|  | 7 - Sale |  | 1.5BHK | 582.9782 |  | 0 | 932.7652 | [8 empty] | 107,..,1307 | 107 | 1307
|  | 8 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 108,..,1308 | 108 | 1308
2nd, 7th & 12th Floor (Part Refuge Area)
2nd, 7th & 12th Floor (Part Refuge Area) |  | 1 - Sale |  | 2BHK | 674.0417 |  | 0 | 1078.4667 | [8 empty] | 201,..,1201 | 201 | 1201
|  | 2 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 202,..,1202 | 202 | 1202
|  | 3 - Sale |  | 2BHK | 659.8332 |  | 0 | 1055.7331 | [8 empty] | 203,..,1203 | 203 | 1203
|  | 4 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 204,..,1204 | 204 | 1204
|  | 5 - Sale |  | 3BHK | 923.7665 |  | 0 | 1478.0264 | [8 empty] | 205,..,1205 | 205 | 1205
|  | 6 - Sale |  | Refuge Area | 582.9782 |  | 0 | 932.7652 | [8 empty] | 206,..,1206 | 206 | 1206
|  | 7 - Sale |  | 1.5BHK | 582.9782 |  | 0 | 932.7652 | [8 empty] | 207,..,1207 | 207 | 1207
|  | 8 - Sale |  | 2BHK | 661.3402 |  | 0 | 1058.1443 | [8 empty] | 208,..,1208 | 208 | 1208
Project Specific Remarks & Observation
Remarks / Observations | : | 1. A & B & C Wing - Construction work is in process at the time of Visit. Internal visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Utility Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Mr. Sandeep Jha (Sales) - 08097547099 8. We have updated revised approved CC from RERA (on 29/09/2024). 9. Construction work goes beyond approved plan and CC permission. Please provide revised approved plan and CC.
|  | Sr. No |  | Name of Building as per Builder |  |  | Name of Building as per TMC
|  | 1 |  | Wing A |  |  | Building No.1 ( A wing)
|  | 2 |  | Wing B |  |  | Building No.2 ( A wing)
| : | 3 |  | Wing C |  |  | Building No.3
Site & Building/Tower Photographs
Name of the Project |  |  | : | Dosti West County - Dosti Tulip
Project Site Address |  |  | : | Bhiwandi - Wadpa Road, Old, Mumbai - Agra National Hwy, Balkum Pada, Thane West, Thane, Maharashtra 400608
Site Visit Date & Time |  |  | : | 05/08/2025 at 12:09PM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Ajay Songare | Authorized Signatory Name & Signature | :
A & B
A & B
C