## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 | 2025-08-03 | 90
Project Name |  |  | : | Godrej Riviera Phase 1 (Building No. 1 to 4) |  | Date of Site Visit |  | 03/08/2025 at 03:05PM | 2025-05-05
Name of the person met at site & Contact No. |  |  | : | Mr. Sushil Singh (Sales) 7777081413 |  | Date of Report Release |  | 08/08/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Godrej Properties Limited | Developer Name | : | Godrej Properties
Developer Office Address |  |  | : | Unit No. 5C, 5th Floor, Godrej One, Pirojshanagar, Vikhroli East
Project Address | : | As per ARF | : | Godrej Riviera Phase 1, New Survey number. 54B/1, 54B/2, 54B/3 and 52/1 of Village - Vadavli, Taluka - Kalyan
| : | As per Legal Documents | : | New Survey number. 54B/1, 54B/2, 54B/3 and 52/1 of Village - Vadavli, Taluka - Kalyan
| : | As per Actual at site | : | Godrej Riviera Phase 1, Road - Mohane Road, Near - Water Treatment Plant Vadavli, New Survey number. 54B/1, 54B/2, 54B/3 and 52/1 of Village - Vadavli, Taluka - Kalyan
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Kalyan Dombivli Municipal Corporation (KDMC)
RERA Registration No. | : | P51700032552 |  |  | RERA Registration Validity | : | 2026-12-16
Project Launch Date | : | 2021-12-13 |  |  | Construction Start Date | : | 2022-01-11
Proposed Date of Completion (As per RERA) | : | 2026-12-16 |  |  | Developer Bank Name (As per RERA) | : | AXIS BANK IFSC Code - UTIB0000004
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | : | 80947
FSI/FAR Permissible | : | 1.1 |  |  | Net Plot Area (In Sq.Mt) | : | 42681.71
Permissible Built up Area (In Sq.Mt) | : | 46949.88 |  |  | Proposed Built up Area (In Sq.Mt) | : | 111408.69
Total Number of Units Approved | : | Flats = 942 & Shop = 79 |  |  | Total Number of Units Planned. | : | As per RERA Site Flats = 942 & Shop = 79
Latitude, Longitude | : | 19.259026,73.163924
Location Link | : | https://maps.app.goo.gl/yWDB2YBaxcMz26vb7
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 30M
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 2.9 KM from KDMT Bus Depot
Distance from the nearest School (Km) | : | About 4.1 KM from D.S.D School |  |  | Distance from Hospital (Km) | : | About 5 KM form Satya Sai Platinum Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.1KM from Kailash Parbat Super market. 2. Approx. 4.6 KM from D Mart. |  |  | Distance from Railway Station (Km) | : | 3.2 KM from Shahad Railway Station 5.8 KM from Kalyan Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Road | Building | Road |  | Building
As per Site / Actual |  |  | : | Open Plot | Mohane Road | Nirmal Lifestyles Road |  | Open Plot
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No. 1 to 4 (Tower 1 to 4) |  | Sale |  | G + 1st to 22nd Floor |  |  | G + 1st to 22nd Floor
Building No. 2 |  | Sale
Building No. 3 |  | Sale
Building No. 4 |  | Sale
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | KDMC/TPD/BP/KD/2021-22/58/108 Date: 07/06/2023
CC Details | : | KDMC/TPD/BP/KD/2021-22/58/108 Date: 07/06/2023 Valid Up to: Building No.1 to 4 = St/Gr + 1st to 22nd floor |  |  | Approved Plan Details | : | KDMC/TPD/BP/KD/2021-22/58/108 Date: 07/06/2023
Fire Noc Details | : | FIRE/HQ/KDMC/OW/2021/656 Date: 21/10/2021 |  |  | Garden NOC Details | : | KDMP/Garden/VP/446 Date:11/10/2021
Change of User/Zone Certificate Details | : | - |  |  | SWD NOC Details | : | KDMP/KA/JN/419 Date:25/10/2021
Construction Status
Tower 1 = G + 1st to 22nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 17 Floor, Internal Plaster upto 12.75 Floor, External Plaster upto 12.75 Floor, External Plumbing, Elevation and Waterproofing upto 3 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 |  | 100% | 52.01% |  | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 17 Floor, Internal Plaster upto 12.75 Floor, External Plaster upto 12.75 Floor, External Plumbing, Elevation and Waterproofing upto 3 Floor Completed |  | Excavation in process | 11
Plinth |  | 22 |  | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 18 |  | 78.26% |  |  |  |  | Footing in Process | 5.5
Brickwork |  | 17 |  | 77.27% |  |  |  |  | Footing Completed | 11
Internal Plaster |  | 12.75 |  | 57.95% |  |  |  |  | Basement 1 | 0
External Plaster |  | 12.75 |  | 57.95% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 3 |  | 13.64% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 16.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 22 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Building No. = G + 20th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 20 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5
Excavation |  | 20 |  | 100% | 20% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 10
Plinth |  | 20 |  | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 4
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 8
Door & Window Frames |  | 0 |  | 0% |  |  |  |  | Basement 1 | 12
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 16
Ext.Plaster |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Plumb.& Electri. |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Painting |  | 0 |  | 0% |  |  |  |  | Plinth completed | 20
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 2 = G + 1st to 22nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 16 Slab, Brickwork upto 15 Floor, Internal Plaster upto 11.25 Floor, External Plaster upto 11.25 Floor, External Plumbing, Elevation and Waterproofing upto 3 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 |  | 100% | 49.04% |  | Excavation work Completed. Plinth work completed, RCC upto 16 Slab, Brickwork upto 15 Floor, Internal Plaster upto 11.25 Floor, External Plaster upto 11.25 Floor, External Plumbing, Elevation and Waterproofing upto 3 Floor Completed |  | Excavation in process | 11
Plinth |  | 22 |  | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 16 |  | 69.57% |  |  |  |  | Footing in Process | 5.5
Brickwork |  | 15 |  | 68.18% |  |  |  |  | Footing Completed | 11
Internal Plaster |  | 11.25 |  | 51.14% |  |  |  |  | Basement 1 | 0
External Plaster |  | 11.25 |  | 51.14% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 3 |  | 13.64% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 16.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 22 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 3 = G + 1st to 22nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 18 Floor, Internal Plaster upto 13.5 Floor, External Plaster upto 13.5 Floor, External Plumbing, Elevation and Waterproofing upto 3 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 |  | 100% | 53.49% |  | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 18 Floor, Internal Plaster upto 13.5 Floor, External Plaster upto 13.5 Floor, External Plumbing, Elevation and Waterproofing upto 3 Floor Completed |  | Excavation in process | 11
Plinth |  | 22 |  | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 19 |  | 82.61% |  |  |  |  | Footing in Process | 5.5
Brickwork |  | 18 |  | 81.82% |  |  |  |  | Footing Completed | 11
Internal Plaster |  | 13.5 |  | 61.36% |  |  |  |  | Basement 1 | 0
External Plaster |  | 13.5 |  | 61.36% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 3 |  | 13.64% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 16.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 22 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 4 = G + 1st to 22nd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 22 Slab, Brickwork upto 21 Floor, Internal Plaster upto 15.75 Floor, External Plaster upto 15.75 Floor, External Plumbing, Elevation and Waterproofing upto 8 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 |  | 100% | 59.08% |  | Excavation work Completed. Plinth work completed, RCC upto 22 Slab, Brickwork upto 21 Floor, Internal Plaster upto 15.75 Floor, External Plaster upto 15.75 Floor, External Plumbing, Elevation and Waterproofing upto 8 Floor Completed |  | Excavation in process | 11
Plinth |  | 22 |  | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 22 |  | 95.65% |  |  |  |  | Footing in Process | 5.5
Brickwork |  | 21 |  | 95.45% |  |  |  |  | Footing Completed | 11
Internal Plaster |  | 15.75 |  | 71.59% |  |  |  |  | Basement 1 | 0
External Plaster |  | 15.75 |  | 71.59% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 8 |  | 36.36% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 16.5
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 22 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 53.41%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 10400/- to 10900/- | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Rate of Shop Per Sq. Ft. (on Carpet area) For Ground Floor |  |  | : : | 20000/- to 21000/- | Rate of Shop Per Sq. Ft. (on Carpet area) For 1st Floor | : | 19000/- to 20000/-
Car Parking Charges |  |  | : | 200000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 650.3159
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 4403.5674
Government Guideline/ Circle rate for shop up (Rs per sqft) | [5 empty] | : | 5462.2656
Distress Value (Rs. Per sqft) | [5 empty] | : | 520.2527
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Building No.1 |  | Sale |  | Shops | 15 |  | 3219.62 | 4990.4111
Building No.2 |  | Sale |  | Shops | 30 |  | 8165.536 | 12656.5807
Building No.3 |  | Sale |  | Shops | 22 |  | 7645.3463 | 11850.2867
Building No.4 |  | Sale |  | Shops | 12 |  | 4055.5523 | 6286.106
Total |  | Sale |  | Shops | 79 |  | 23086.0546 | 35783.3846
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Building No.1 |  | Sale |  | Flats | 238 |  | 109796.2445 | 171410.4138
Building No.2 |  | Sale |  | Flats | 233 |  | 107152.8214 | 166872.7998
Building No.3 |  | Sale |  | Flats | 233 |  | 107028.8201 | 166163.4111
Building No.4 |  | Sale |  | Flats | 238 |  | 109436.9422 | 169926.2724
Total |  | Sale |  | Flats | 942 |  | 433414.8281 | 674372.8972
Grand Total |  | Sale |  | Flats | 1021 |  | 456500.8826 | 710156.2817
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
55%
Building Type 1
Ground Floor For Entrance Lobby, Store, Pannel Room, Meter Room, ELV Room, Facility Management Room, Parking & Commercial
Ground Floor For Entrance Lobby, Store, Pannel Room, Meter Room, ELV Room, Facility Management Room, Parking & Commercial |  | 1 |  | Shop | 177.7136 |  | 0 | 275.4561
|  | 2 |  | Shop | 203.4396 |  | 0 | 315.3314
|  | 3 |  | Shop | 153.8176 |  | 0 | 238.4172
|  | 4 |  | Shop | 153.8176 |  | 0 | 238.4172
|  | 5 |  | Shop | 203.4396 |  | 0 | 315.3314
|  | 6 |  | Shop | 178.2518 |  | 0 | 276.2904
|  | 7 |  | Shop | 190.9534 |  | 0 | 295.9777
|  | 8 |  | Shop | 348.5383 |  | 0 | 540.2344
|  | 9 |  | Shop | 72.8723 |  | 0 | 112.952
|  | 10 |  | Shop | 196.0124 |  | 0 | 303.8193
|  | 11 |  | Shop | 233.6864 |  | 0 | 362.214
|  | 12 |  | Shop | 329.1631 |  | 0 | 510.2028
|  | 13 |  | Shop | 316.4616 |  | 0 | 490.5155
|  | 14 |  | Shop | 252.6311 |  | 0 | 391.5782
|  | 15 |  | Shop | 208.8216 |  | 0 | 323.6735
1st Floor for Residential
1st Floor for Residential |  | 1 |  | 1BHK | 462.3138 |  | 0 | 716.5864 | 40.5089
|  | 2 |  | 1BHK | 462.3138 |  | 0 | 716.5864
|  | 3 |  | 1BHK | 427.5461 |  | 309.7233 | 817.5581
|  | 4 |  | 1BHK | 427.5461 |  | 281.6293 | 803.5111
|  | 5 |  | 1BHK | 466.1888 |  | 235.301 | 957.8937 | 40.8257
|  | 6 |  | 2BHK | 663.0624 |  | 398.564 | 1426.3107 | 56.0372 |  | Check from here
|  | 7 |  | 2BHK | 659.0797 |  | 296.6935 | 1318.2671
|  | 8 |  | 1BHK | 370.3892 |  | 0 | 574.1033
|  | 9 |  | 1BHK | 370.3892 |  | 0 | 574.1033
|  | 10 |  | 1BHK | 380.3998 |  | 0 | 589.6196
|  | 11 |  | 1BHK | 380.3998 |  | 0 | 589.6196
2nd to 6th, 8th to 11th, 13th to 16th, 18th to 21st Floor
2nd to 6th, 8th to 11th, 13th to 16th, 18th to 21st Floor |  | 1 |  | 1BHK | 463.2826 |  | 0 | 718.088 | 8526.1142 |  |  |  | 2601,..,2101 | 2601 | 2101
|  | 2 |  | 1BHK | 463.2826 |  | 0 | 718.088 |  |  |  |  | 2602,..,2102 | 2602 | 2102
|  | 3 |  | 1BHK | 428.4072 |  | 0 | 664.0312 | 5 |  |  |  | 2603,..,2103 | 2603 | 2103
|  | 4 |  | 1BHK | 428.4072 |  | 0 | 664.0312 | 4 |  |  |  | 2604,..,2104 | 2604 | 2104
|  | 5 |  | 1BHK | 466.1888 |  | 0 | 722.5927 | 4 |  |  |  | 2605,..,2105 | 2605 | 2105
|  | 6 |  | 2BHK | 663.0624 |  | 0 | 1027.7467 | 4 |  |  |  | 2606,..,2106 | 2606 | 2106
|  | 7 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 |  |  |  |  | 2607,..,2107 | 2607 | 2107
|  | 8 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 2608,..,2108 | 2608 | 2108
|  | 9 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 2609,..,2109 | 2609 | 2109
|  | 10 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 2610,..,2110 | 2610 | 2110
|  | 11 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 2611,..,2111 | 2611 | 2111
7th, 12th, 17th & 22nd Floor (Part Refuge Area)
7th, 12th, 17th & 22nd Floor (Part Refuge Area) |  | 1 |  | Refuge Area | [8 empty] | 701,..,2201 | 701 | 2201
|  | 2 |  | 1BHK | 463.2826 |  | 0 | 718.088 |  |  |  |  | 702,..,2202 | 702 | 2202
|  | 3 |  | 1BHK | 428.4072 |  | 0 | 664.0312 |  |  |  |  | 703,..,2203 | 703 | 2203
|  | 4 |  | 1BHK | 428.4072 |  | 0 | 664.0312 |  |  |  |  | 704,..,2204 | 704 | 2204
|  | 5 |  | 1BHK | 466.1888 |  | 0 | 722.5927 |  |  |  |  | 705,..,2205 | 705 | 2205
|  | 6 |  | 2BHK | 663.0624 |  | 0 | 1027.7467 |  |  |  |  | 706,..,2206 | 706 | 2206
|  | 7 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 |  |  |  |  | 707,..,2207 | 707 | 2207
|  | 8 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 708,..,2208 | 708 | 2208
|  | 9 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 709,..,2209 | 709 | 2209
|  | 10 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 710,..,2210 | 710 | 2210
|  | 11 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 711,..,2211 | 711 | 2211
Building Type 2
Ground Floor For Entrance Lobby, Retail Meter Room, Society Office, Meter Room, Panel Room, Stack Parking & Commercial
Ground Floor For Entrance Lobby, Retail Meter Room, Society Office, Meter Room, Panel Room, Stack Parking & Commercial |  | 16 |  | Shop | 208.8216 |  | 0 | 323.6735
|  | 17 |  | Shop | 252.8464 |  | 0 | 391.9119
|  | 18 |  | Shop | 328.6249 |  | 0 | 509.3686
|  | 19 |  | Shop | 233.4712 |  | 0 | 361.8803
|  | 20 |  | Shop | 196.5506 |  | 0 | 304.6535
|  | 21 |  | Shop | 71.7959 |  | 0 | 111.2836
|  | 22 |  | Shop | 349.5071 |  | 0 | 541.736
|  | 23 |  | Shop | 190.9534 |  | 0 | 295.9777
|  | 24 |  | Shop | 178.8977 |  | 0 | 277.2914
|  | 25 |  | Shop | 368.8823 |  | 0 | 571.7675
|  | 26 |  | Shop | 372.3268 |  | 0 | 577.1065
|  | 27 |  | Shop | 313.663 |  | 0 | 486.1776
|  | 28 |  | Shop | 334.1146 |  | 0 | 517.8776
|  | 29 |  | Shop | 339.9271 |  | 0 | 526.887
|  | 30 |  | Shop | 343.9098 |  | 0 | 533.0602
1st Floor For Commercial & Residential
1st Floor For Commercial & Residential |  | 1 |  | Shop | 209.898 |  | 0 | 325.3419
|  | 2 |  | Shop | 255.1068 |  | 0 | 395.4155
|  | 3 |  | Shop | 326.2224 |  | 0 | 505.6447
|  | 4 |  | Shop | 234.2246 |  | 0 | 363.0482
|  | 5 |  | Shop | 198.0576 |  | 0 | 306.9893
|  | 6 |  | Shop | 72.0112 |  | 0 | 111.6173
|  | 7 |  | Shop | 350.2606 |  | 0 | 542.9039
|  | 8 |  | Shop | 192.6756 |  | 0 | 298.6472
|  | 9 |  | Shop | 179.5435 |  | 0 | 278.2925
|  | 10 |  | Shop | 369.6358 |  | 0 | 572.9354
|  | 11 |  | Shop | 371.2504 |  | 0 | 575.4381 | 33.1725
|  | 12 |  | Shop | 305.267 |  | 0 | 473.1639
|  | 13 |  | Shop | 330.993 |  | 0 | 513.0392 | 33.1725
|  | 14 |  | Shop | 340.4653 |  | 0 | 527.7212
|  | 15 |  | Shop | 345.632 |  | 0 | 535.7297
|  | 1 |  | 1BHK | 370.3892 |  | 0 | 574.1033 | 33.1725
|  | 2 |  | 1BHK | 370.3892 |  | 0 | 574.1033
|  | 8 |  | 1BHK | 462.3138 |  | 0 | 716.5864 | 33.1725
|  | 9 |  | 1BHK | 462.3138 |  | 0 | 716.5864
|  | 10 |  | 1BHK | 380.3998 |  | 0 | 589.6196 | 33.1725
|  | 11 |  | 1BHK | 380.3998 |  | 0 | 589.6196
2nd Floor
2nd Floor |  | 1 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 201,..,201 | 201 | 201
|  | 2 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 202,..,202 | 202 | 202
|  | 3 |  | 2BHK | 659.0797 |  | 326.4183 | 1184.7827 |  |  |  |  | 203,..,203 | 203 | 203
|  | 4 |  | 2BHK | 663.0624 |  | 428.2888 | 1241.8911 |  |  |  |  | 204,..,204 | 204 | 204
|  | 5 |  | 1BHK | 466.1888 |  | 276.1397 | 860.6625 |  |  |  |  | 205,..,205 | 205 | 205
|  | 6 |  | 1BHK | 428.4072 |  | 276.1908 | 802.1266 |  |  |  |  | 206,..,206 | 206 | 206
|  | 7 |  | 1BHK | 428.4072 |  | 264.8159 | 796.4391 |  |  |  |  | 207,..,207 | 207 | 207
|  | 8 |  | 1BHK | 463.2826 |  | 0 | 718.088 |  |  |  |  | 208,..,208 | 208 | 208
|  | 9 |  | 1BHK | 463.2826 |  | 0 | 718.088 |  |  |  |  | 209,..,209 | 209 | 209
|  | 10 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 210,..,210 | 210 | 210
|  | 11 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 211,..,211 | 211 | 211
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st Floor
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st Floor |  | 1 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 3601,..,2101 | 3601 | 2101
|  | 2 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 3602,..,2102 | 3602 | 2102
|  | 3 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 |  |  |  |  | 3603,..,2103 | 3603 | 2103
|  | 4 |  | 2BHK | 663.0624 |  | 0 | 1027.7467 |  |  |  |  | 3604,..,2104 | 3604 | 2104
|  | 5 |  | 1BHK | 466.1888 |  | 0 | 722.5927 |  |  |  |  | 3605,..,2105 | 3605 | 2105
|  | 6 |  | 1BHK | 428.4072 |  | 0 | 664.0312 |  |  |  |  | 3606,..,2106 | 3606 | 2106
|  | 7 |  | 1BHK | 428.4072 |  | 0 | 664.0312 |  |  |  |  | 3607,..,2107 | 3607 | 2107
|  | 8 |  | 1BHK | 463.2826 |  | 0 | 718.088 |  |  |  |  | 3608,..,2108 | 3608 | 2108
|  | 9 |  | 1BHK | 463.2826 |  | 0 | 718.088 |  |  |  |  | 3609,..,2109 | 3609 | 2109
|  | 10 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 3610,..,2110 | 3610 | 2110
|  | 11 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 3611,..,2111 | 3611 | 2111
7th, 12th, 17th & 22nd Floor (Part Refuge Area)
7th, 12th, 17th & 22nd Floor (Part Refuge Area) |  | 1 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 701,..,2201 | 701 | 2201
|  | 2 |  | 1BHK | 371.358 |  | 0 | 575.6049 |  |  |  |  | 702,..,2202 | 702 | 2202
|  | 3 |  | 2BHK | 659.0797 |  | 0 | 1021.5736 |  |  |  |  | 703,..,2203 | 703 | 2203
|  | 4 |  | 2BHK | 663.0624 |  | 0 | 1027.7467 |  |  |  |  | 704,..,2204 | 704 | 2204
|  | 5 |  | 1BHK | 466.1888 |  | 0 | 722.5927 |  |  |  |  | 705,..,2205 | 705 | 2205
|  | 6 |  | 1BHK | 428.4072 |  | 0 | 664.0312 |  |  |  |  | 706,..,2206 | 706 | 2206
|  | 7 |  | 1BHK | 428.4072 |  | 0 | 664.0312 |  |  |  |  | 707,..,2207 | 707 | 2207
|  | 8 |  | 1BHK | 463.2826 |  | 0 | 718.088 |  |  |  |  | 708,..,2208 | 708 | 2208
|  | 9 |  | Refuge Area | [8 empty] | 709,..,2209 | 709 | 2209
|  | 10 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 710,..,2210 | 710 | 2210
|  | 11 |  | 1BHK | 380.3998 |  | 0 | 589.6196 |  |  |  |  | 711,..,2211 | 711 | 2211
Building Type 3
Ground Floor For Entrance Lobby, OWC Room, Panel Room, Meter Room, Store, Stack Parking & Commercial
Ground Floor For Entrance Lobby, OWC Room, Panel Room, Meter Room, Store, Stack Parking & Commercial |  | 31 |  | Shop | 442.9386 |  | 0 | 686.5548
|  | 32 |  | Shop | 472.0014 |  | 0 | 731.6022
|  | 33 |  | Shop | 238.4226 |  | 0 | 369.555
|  | 34 |  | Shop | 443.2615 |  | 0 | 687.0554
|  | 35 |  | Shop | 195.5819 |  | 0 | 303.1519
|  | 36 |  | Shop | 272.1139 |  | 0 | 421.7766
|  | 37 |  | Shop | 379.5386 |  | 0 | 588.2849
|  | 38 |  | Shop (Duplex With 1st floor) | 461.668 |  | 0 | 715.5853
|  | 39 |  | Shop | 237.4538 |  | 0 | 368.0535
|  | 40 |  | Shop | 228.735 |  | 0 | 354.5392
|  | 41 |  | Shop | 444.8761 |  | 0 | 689.558
1st Floor For Commercial & Residential
1st Floor For Commercial & Residential |  | 16 |  | Shop | 444.2303 |  | 0 | 688.5569 | 33.0059
|  | 17 |  | Shop | 473.8313 |  | 0 | 734.4385
|  | 18 |  | Shop | 240.0372 |  | 0 | 372.0577
|  | 19 |  | Shop | 443.7997 |  | 0 | 687.8896
|  | 20 |  | Shop | 196.5506 |  | 0 | 304.6535
|  | 21 |  | Shop | 275.1278 |  | 0 | 426.4482
|  | 22 |  | Shop | 379.7539 |  | 0 | 588.6186
|  | 23 |  | Shop | 462.3138 |  | 0 | 716.5864
|  | 24 |  | Shop | 237.4538 |  | 0 | 368.0535
|  | 25 |  | Shop | 230.4572 |  | 0 | 357.2087
|  | 26 |  | Shop | 445.199 |  | 0 | 690.0585
|  | 1 |  | 1BHK | 371.2504 |  | 0 | 575.4381
|  | 2 |  | 2BHK | 503.4323 |  | 0 | 780.32
|  | 8 |  | 2BHK | 503.4323 |  | 0 | 780.32
|  | 9 |  | 1BHK | 371.2504 |  | 0 | 575.4381
|  | 10 |  | 1BHK | 442.0775 |  | 0 | 685.2201 | 37.9883
|  | 11 |  | 1BHK | 442.0775 |  | 0 | 685.2201
2nd Floor
2nd Floor |  | 1 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 201,..,201 | 201 | 201
|  | 2 |  | 2BHK | 503.4323 |  | 0 | 780.32 | 274 |  |  |  | 202,..,202 | 202 | 202
|  | 3 |  | 2BHK | 502.6788 |  | 625.1839 | 488.9735 | 274 |  |  |  | 203,..,203 | 203 | 203
|  | 4 |  | 1BHK | 370.3892 |  | 476.0702 | 693.1209 | 254 |  |  |  | 204,..,204 | 204 | 204
|  | 5 |  | 2BHK | 659.1874 |  | 438.3747 | 1240.9277 | 248 |  |  |  | 205,..,205 | 205 | 205
|  | 6 |  | 1BHK | 370.3892 |  | 505.5636 | 700.4942 | 1050 |  |  |  | 206,..,206 | 206 | 206
|  | 7 |  | 2BHK | 502.6788 |  | 471.6139 | 873.4749 |  |  |  |  | 207,..,207 | 207 | 207
|  | 8 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 208,..,208 | 208 | 208
|  | 9 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 209,..,209 | 209 | 209
|  | 10 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 210,..,210 | 210 | 210
|  | 11 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 211,..,211 | 211 | 211
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st Floor
3rd to 6th, 8th to 11th, 13th to 16th, 18th to 21st Floor |  | 1 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 3601,..,2101 | 3601 | 2101
|  | 2 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 3602,..,2102 | 3602 | 2102
|  | 3 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 3603,..,2103 | 3603 | 2103
|  | 4 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 3604,..,2104 | 3604 | 2104
|  | 5 |  | 2BHK | 659.1874 |  | 0 | 1021.7404 |  |  |  |  | 3605,..,2105 | 3605 | 2105
|  | 6 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 3606,..,2106 | 3606 | 2106
|  | 7 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 3607,..,2107 | 3607 | 2107
|  | 8 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 3608,..,2108 | 3608 | 2108
|  | 9 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 3609,..,2109 | 3609 | 2109
|  | 10 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 3610,..,2110 | 3610 | 2110
|  | 11 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 3611,..,2111 | 3611 | 2111
7th, 12th, 17th & 22nd Floor (Part Refuge Area)
7th, 12th, 17th & 22nd Floor (Part Refuge Area) |  | 1 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 701,..,2201 | 701 | 2201
|  | 2 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 702,..,2202 | 702 | 2202
|  | 3 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 703,..,2203 | 703 | 2203
|  | 4 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 704,..,2204 | 704 | 2204
|  | 5 |  | 2BHK | 659.1874 |  | 0 | 1021.7404 |  |  |  |  | 705,..,2205 | 705 | 2205
|  | 6 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 706,..,2206 | 706 | 2206
|  | 7 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 707,..,2207 | 707 | 2207
|  | 8 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 708,..,2208 | 708 | 2208
|  | 9 |  | Refuge Area | [8 empty] | 709,..,2209 | 709 | 2209
|  | 10 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 710,..,2210 | 710 | 2210
|  | 11 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 711,..,2211 | 711 | 2211
Building No.4
Ground Floor For Entrance Lobby, Meter Room, Panel Room, Parking & Commercial
Ground Floor For Entrance Lobby, Meter Room, Panel Room, Parking & Commercial |  | 42 |  | Shop | 445.8449 |  | 0 | 691.0596
|  | 43 |  | Shop | 266.0861 |  | 0 | 412.4334
|  | 44 |  | Shop | 195.3666 |  | 0 | 302.8182
|  | 45 |  | Shop | 237.4538 |  | 0 | 368.0535
|  | 46 |  | Shop | 461.668 |  | 0 | 715.5853
|  | 47 |  | Shop | 379.5386 |  | 0 | 588.2849
|  | 48 |  | Shop | 272.2216 |  | 0 | 421.9434
|  | 49 |  | Shop (Duplex With 1st floor) | 195.5819 |  | 0 | 303.1519
|  | 50 |  | Shop | 445.3067 |  | 0 | 690.2254
|  | 51 |  | Shop | 237.992 |  | 0 | 368.8877
|  | 52 |  | Shop | 469.9562 |  | 0 | 728.4322
|  | 53 |  | Shop | 448.5359 |  | 0 | 695.2306
1st Floor
1st Floor |  | 1 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 101,..,101 | 101 | 101
|  | 2 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 102,..,102 | 102 | 102
|  | 3 |  | 2BHK | 502.6788 |  | 641.007 | 488.9735 |  |  |  |  | 103,..,103 | 103 | 103
|  | 4 |  | 1BHK | 370.3892 |  | 489.3099 | 696.4308 |  |  |  |  | 104,..,104 | 104 | 104
|  | 5 |  | 2BHK | 658.7568 |  | 432.11 | 1237.128 |  |  |  |  | 105,..,105 | 105 | 105
|  | 6 |  | 1BHK | 370.3892 |  | 486.1561 | 695.6423 |  |  |  |  | 106,..,106 | 106 | 106
|  | 7 |  | 2BHK | 502.6788 |  | 646.3459 | 908.4213 |  |  |  |  | 107,..,107 | 107 | 107
|  | 8 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 108,..,108 | 108 | 108
|  | 9 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 109,..,109 | 109 | 109
|  | 10 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 110,..,110 | 110 | 110
|  | 11 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 111,..,111 | 111 | 111
2nd to 6th, 8th to 11th, 13th to 16th, 18th to 21st Floor
2nd to 6th, 8th to 11th, 13th to 16th, 18th to 21st Floor |  | 1 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 2601,..,2101 | 2601 | 2101
|  | 2 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 2602,..,2102 | 2602 | 2102
|  | 3 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 2603,..,2103 | 2603 | 2103
|  | 4 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 2604,..,2104 | 2604 | 2104
|  | 5 |  | 2BHK | 659.1874 |  | 0 | 1021.7404 |  |  |  |  | 2605,..,2105 | 2605 | 2105
|  | 6 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 2606,..,2106 | 2606 | 2106
|  | 7 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 2607,..,2107 | 2607 | 2107
|  | 8 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 2608,..,2108 | 2608 | 2108
|  | 9 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 2609,..,2109 | 2609 | 2109
|  | 10 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 2610,..,2110 | 2610 | 2110
|  | 11 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 2611,..,2111 | 2611 | 2111
7th, 12th, 17th & 22nd Floor (Part Refuge Area)
7th, 12th, 17th & 22nd Floor (Part Refuge Area) |  | 1 |  | Refuge Area | [8 empty] | 701,..,2201 | 701 | 2201
|  | 2 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 702,..,2202 | 702 | 2202
|  | 3 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 703,..,2203 | 703 | 2203
|  | 4 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 704,..,2204 | 704 | 2204
|  | 5 |  | 2BHK | 659.1874 |  | 0 | 1021.7404 |  |  |  |  | 705,..,2205 | 705 | 2205
|  | 6 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 706,..,2206 | 706 | 2206
|  | 7 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 707,..,2207 | 707 | 2207
|  | 8 |  | 2BHK | 503.4323 |  | 0 | 780.32 |  |  |  |  | 708,..,2208 | 708 | 2208
|  | 9 |  | 1BHK | 371.2504 |  | 0 | 575.4381 |  |  |  |  | 709,..,2209 | 709 | 2209
|  | 10 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 710,..,2210 | 710 | 2210
|  | 11 |  | 1BHK | 442.0775 |  | 0 | 685.2201 |  |  |  |  | 711,..,2211 | 711 | 2211
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of visit. Interal visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony + Dry Balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated revised approved CC from RERA site (On 05/08/2024). 8. We have updated approved plans (On 13/11/2024). 9. Approved plans consist of Building Type 1 to 6 but Building Type 1 to 4 is registered on RERA site. Hence we have not drafted Building Type 5 & 6.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Godrej Riviera Phase 1 (Building No. 1 to 4)
Project Site Address |  |  | : | Godrej Riviera Phase 1, New Survey number. 54B/1, 54B/2, 54B/3 and 52/1 of Village - Vadavli, Taluka - Kalyan
Site Visit Date & Time |  |  | : | 03/08/2025 at 03:05PM
Layout Plan
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Krishna Kambali | Authorized Signatory Name & Signature | :
Building No. 1
Building No. 2
Building No. 3
Type 1
Type 2
Type 3
Type 4
Tower 1
Tower 2
Tower 3
Tower 4
Tower 3
Tower 1
Tower 2
Tower 4
Tower 1
Tower 2
Tower 3
Tower 4