## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 |  | 2025-08-08 | 80
Project Name |  | Platinum Oceanic |  | Date & Time of Site Visit |  | 08/08/2025 at 02:19PM |  | 2025-05-20
Name of the person met at site & Contact No. |  | Mr. Ronnie Mali 9819477776 |  | Date of Report Release |  | 08/08/2025 |  | Mr. Sudam Ishi 9220387309
Data from APF Request Form
Branch Name/ID |  | Mumbai-RO Thane |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | M/s. Platinumcorp Lifescapes LLP |  | Developer Name |  | M/s. Platinumcorp Lifescapes LLP
Developer Office Address |  | 2nd, 8th & 9th Floors, Peninsula Heights, CD Barfiwala Marg, Juhu Lane, Andheri (W), Mumbai - 400 058 | [5 empty] | Address was not in RERA Site.
Project Address | As per ARF | Platinum Oceanic, Off Carter Rd, Pyari Nagar, Chuim Village, Danda, Khar West, Mumbai, Maharashtra 400052
| As per Legal Documents | Plan Showing Property Bearing C.T.S. No. 926 A of Village Bandra - D, Govind Patil Road, Taluka Andheri, Khar West, 'H/W' Ward, Mumbai.
| As per Actual at site | Platinum Oceanic, Redevelopment of Gulmohr Co-operative Housing Scoiety, Near Pimpleshwar Hanuman Mandir, Khar Danda Road, Pyari Nagar, Chuim Village, Danda, Khar West, Mumbai, Maharashtra 400052
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, Airport NOC, Fire NOC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Slum Rehabilitation Authority (SRA)
RERA Registration No. | : | P51800078789 |  | RERA Registration Validity | : | 2028-12-31
Project Launch Date | : | 2025-01-13 |  | Construction Start Date | : | 2025-01-01
Proposed Date of Completion (As per RERA) | : | 2028-12-31 |  | Developer Bank Name (As per RERA) | : | HDFC Bank Limited
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 1112.9
FSI/FAR Permissible | : | 1 |  | Net Plot Area (In Sq.Mt) | : | 943
Permissible Built up Area (In Sq.Mt) | : | 5425.39 |  | Proposed Built up Area (In Sq.Mt) | : | 4831.53
Total Number of Units Approved | : | Sale Flat = 11 Commercial = 3 PTC Flat = 40 Rehab Flat = 20 |  | Total Number of Units Planned | : | Sale Flat = 19 Office = 3 PTC Flat = 40 Rehab Flat = 20 |  | In RERA Portal Rehab Flats are stated as 2BHK or 3BHK Member, Shops as Office Space and Sale Flats as 2BHK or 3BHK. Sale Flats count are more than Approved Sale Flats
Latitude, Longitude | : | 19.075059,72.825289 |  | Landmark | : | Pimpleshwar Hanuman Mandir
Location Link | : | https://maps.app.goo.gl/vvBMu4rSA5oWAxbY7
Extra Amenities available | : | Swimming Pool, Deck Area, Party Lounge, Sitouts, Yoga, Meditation Zone, Advanced Security with Ample Car Parking Spaces etc. | [5 empty] | https://oceanic.platinumcorp.in/
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  | Width of the Road | : | 18m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.15 KM from Dandpada Bus Stop
Distance from the nearest School (Km) | : | About 0.35 KM from Khar Danda Municipal School |  | Distance from Hospital (Km) | : | About 1.50 KM from Ramkrishna Mision Hospital
Distance from the Main Market (Km) | : | 1. Approx. 0.30 KM from Danda Fish Market. 2. Approx. 0.35 KM from Bombay Gourmet Market. |  | Distance from Railway Station (Km) | : | 1.80 KM from Khar Road Railway Station 2.80 KM from Santacruz Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East | West
East |  | Other Plot |  |  | Bungalow
West |  | Proposed 18.30 Mtr Wide Eventide Cross Road |  |  | Internal Road
North |  | Proposed 18.30 Mtr Wide Govind Patil Road |  |  | Khar Danda Road
South |  | Other Plot |  |  | Building
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building |  | Sale | 1B + G + 1st to 18th Floor |  |  | 1B + G + 1st to 17th Floor |  | https://oceanic.platinumcorp.in/
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | H-W/PVT/0117/20240116/AP/C |  |  |  | Date: | 2024-09-13
Approved Plan Details | : | H-W/PVT/0117/20240116/AP/C |  |  |  | Date: | 2024-09-13
CC Details Valid Up to: |  | H-W/PVT/0117/20240116/AP/C |  |  |  | Date: | 2024-12-26
This C.C is granted for work upto Plinth Level
Fire NOC No. Valid Up to: |  | P-20379/2024/(C.T.S. No. 926/A situated at Village– Bandra-D And Other)/H/W Ward/BANDRA-D/SRACFO/1/New. Basement + Ground Floor + 1st to 18th upper Residential Floors = 63.75 mtrs height |  |  |  | Date: | 2024-05-13
Environmental Clearance Details | : |  |  |  |  | Date:
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details Valid Up to: |  | JUHU/WEST/B/021722/655160 |  |  |  | Date: | 2023-12-11
|  | Site Elevation (AMSL) = 4.74 M Permissible Top Elevation (AMSL) = 57.13 M |  |  |  | Valid up to Date: | 2030-05-25 | 52.39
Revised Airport Authority Clearance Details Valid Up to: |  | AAI/RHQ/WR/DoAS/Auth./JUHU/WEST/B/021722/655160/158 |  |  |  | Date: | 2023-12-11
Permissible Top Elevation (AMSL) = 68.63 M
Construction Status
Building= 1B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 1 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 11.7
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 25%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 64000 to 65000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 1200000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 21401.8952
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 39092.3449
Distress Value (Rs. Per sqft) |  |  |  |  | : | 17121.5162
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Commercial |  | - |  | 3 |  | 8517.1402 |  | OK
Total |  | - |  | 3 |  | 8517.1402
Unit Details, Nomenclature and Area Details (Multipurpose Room)
Building & Wing |  | Sale / Rehab/ PTC |  | No. of Unit |  | Total Gross Carpet Area
Building |  | PTC |  | 40 |  | 11954.2673 |  | OK
Total |  | - |  | 40 |  | 11954.2673
Unit Details, Nomenclature and Area Details (Flat)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area |  | 74
Building |  | Sale |  | 11 |  | 7512.8414 |  | OK
Building |  | Rehab |  | 20 |  | 13626.5782 |  | OK
Total |  | - |  | 31 |  | 21139.4196
Grand Total |  | - |  | 74 |  | 41610.8271
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PTC | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area | 10.764
Basement Floor For Parking Tower, Fire Water Tank, Domestic Water Tank, Flushing Water Tank & Pump Room
Ground Floor For Commercial, Parking, Entrance Lobby & Driveway
Commercial - G1 |  | - | Commercial | 2299.8484 | 0 | 0 | 2299.8484
1st Floor For Commercial, Parking Tower & Entrance Lobby | [7 empty] | 1
Commercial - F1 |  | - | Commercial | 3468.9323 | 0 | 0 | 3468.9323
2nd Floor For Commercial, Parking Tower, Entrance Lobby & Part Terrace Area | [7 empty] | 1
Commercial - S1 |  | - | Commercial | 2748.3595 | 0 | 0 | 2748.3595
3rd Floor For Multipurpose Room & Fitness Centre | [7 empty] | 1
1 |  | PTC | Multipurpose Room | 301.1475 | 0 | 0 | 301.1475 | [5 empty] | 301,..,301 | 301 | 301
2 |  | PTC | Multipurpose Room | 284.3552 | 0 | 0 | 284.3552 | [5 empty] | 302,..,302 | 302 | 302
3 |  | PTC | Multipurpose Room | 357.3481 | 0 | 0 | 357.3481 | [5 empty] | 303,..,303 | 303 | 303
4 |  | PTC | Multipurpose Room | 300.1353 | 0 | 0 | 300.1353 | [5 empty] | 304,..,304 | 304 | 304
5 |  | PTC | Multipurpose Room | 300.2876 | 0 | 0 | 300.2876 | [5 empty] | 305,..,305 | 305 | 305
6 |  | PTC | Multipurpose Room | 301.4437 | 0 | 0 | 301.4437 | [5 empty] | 306,..,306 | 306 | 306
7 |  | Fitness Centre | [10 empty] | 307,..,307 | 307 | 307
4th & 5th Floor | [7 empty] | 2
1 |  | Rehab | 2.5BHK | 702.8085 | 0 | 0 | 702.8085 | [5 empty] | #REF! | #REF! | 501
2 |  | Rehab | 2.5BHK | 731.5214 | 0 | 0 | 731.5214 | [5 empty] | #REF! | #REF! | 502
3 |  | Rehab | 2BHK | 593.3117 | 0 | 0 | 593.3117 | [5 empty] | #REF! | #REF! | 503
4 |  | Rehab | 2BHK | 539.3302 | 0 | 0 | 539.3302 | [5 empty] | #REF! | #REF! | 504
6th Floor | [7 empty] | 1
1 |  | Rehab | 2.5BHK | 734.9928 | 0 | 0 | 734.9928 | 73.8679 |  |  |  |  | #REF! | #REF! | 601
2 |  | Rehab | 2.5BHK | 731.5214 | 0 | 0 | 731.5214 | [5 empty] | #REF! | #REF! | 602
3 |  | Rehab | 2BHK | 593.3117 | 0 | 0 | 593.3117 | [5 empty] | #REF! | #REF! | 603
4 |  | Rehab | 2BHK | 541.9136 | 0 | 0 | 541.9136 | [5 empty] | #REF! | #REF! | 604
7th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Rehab | 2.5BHK | 823.2576 | 0 | 0 | 823.2576 | [5 empty] | #REF! | #REF! | 701
2 |  | Refuge Area | [10 empty] | #REF! | #REF! | 702
3 |  | Rehab | 2BHK | 593.3117 | 0 | 0 | 593.3117 | [5 empty] | #REF! | #REF! | 703
4 |  | Rehab | 2BHK | 541.9136 | 0 | 0 | 541.9136 | [5 empty] | #REF! | #REF! | 704
8th Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 1016.3907 | 0 | 0 | 1016.3907 | [5 empty] | #REF! | #REF! | 801
2 |  | Rehab | 2.5BHK | 731.5214 | 0 | 0 | 731.5214 | [5 empty] | #REF! | #REF! | 802
3 |  | Rehab | 2BHK | 688.0887 | 0 | 0 | 688.0887 | [5 empty] | #REF! | #REF! | 803
4 |  | Rehab | 2BHK | 541.9136 | 0 | 0 | 541.9136 | [5 empty] | #REF! | #REF! | 804
9th Floor | [7 empty] | 1 |  | 62000
1 |  | Sale | 3BHK | 1016.3907 | 0 | 0 | 1016.3907 | 67381600 | 66294.9789 | 63016223.4 |  |  | #REF! | #REF! | 901
2 |  | Rehab | 3BHK | 954.4977 | 0 | 0 | 954.4977 |  |  | 59178857.4 |  |  | #REF! | #REF! | 902
3 |  | Sale | 2BHK | 688.0887 | 0 | 0 | 688.0887 | 61474.6326 |  | 42661499.4 |  |  | #REF! | #REF! | 903
4 |  | Sale | 2BHK | 662.8471 | 0 | 0 | 662.8471 | 83639.1957 | 126.1817 | 41096521.44 |  |  | #REF! | #REF! | 904
10th & 11th Floor | [7 empty] | 2 |  | 0
1 |  | PTC | Multipurpose Room | 301.0852 | 0 | 0 | 301.0852 | [5 empty] | #REF! | #REF! | 401
2 |  | PTC | Multipurpose Room | 306.6341 | 0 | 0 | 306.6341 | [5 empty] | #REF! | #REF! | 402
3 |  | PTC | Multipurpose Room | 277.271 | 0 | 0 | 277.271 | [5 empty] | #REF! | #REF! | 403
4 |  | PTC | Multipurpose Room | 300.0831 | 0 | 0 | 300.0831 | [5 empty] | #REF! | #REF! | 404
5 |  | PTC | Multipurpose Room | 302.1724 | 0 | 0 | 302.1724 | [5 empty] | #REF! | #REF! | 405
6 |  | Sale | 2BHK | 613.4942 | 0 | 0 | 613.4942 | [5 empty] | #REF! | #REF! | 406
7 |  | Sale | 2BHK | 662.8471 | 0 | 0 | 662.8471 | [5 empty] | #REF! | #REF! | 407
12th Floor | [7 empty] | 1
1 |  | PTC | Multipurpose Room | 301.0852 | 0 | 0 | 301.0852 | [5 empty] | #REF! | #REF! | 701
2 |  | PTC | Multipurpose Room | 306.6341 | 0 | 0 | 306.6341 | [5 empty] | #REF! | #REF! | 702
3 |  | PTC | Multipurpose Room | 277.271 | 0 | 0 | 277.271 | [5 empty] | #REF! | #REF! | 703
4 |  | PTC | Multipurpose Room | 300.0831 | 0 | 0 | 300.0831 | [5 empty] | #REF! | #REF! | 704
5 |  | PTC | Multipurpose Room | 302.1724 | 0 | 0 | 302.1724 | [5 empty] | #REF! | #REF! | 705
6 |  | Sale | 2BHK | 688.0887 | 0 | 0 | 688.0887 | 81530.1864 | 56100000 |  |  |  | #REF! | #REF! | 706
7 |  | Sale | 2BHK | 662.8471 | 0 | 0 | 662.8471 | [5 empty] | #REF! | #REF! | 707
13th Floor | [7 empty] | 1
1 |  | PTC | Multipurpose Room | 301.0852 | 0 | 0 | 301.0852 | [5 empty] | #REF! | #REF! | 701
2 |  | PTC | Multipurpose Room | 306.6341 | 0 | 0 | 306.6341 | [5 empty] | #REF! | #REF! | 702
3 |  | PTC | Multipurpose Room | 277.271 | 0 | 0 | 277.271 | [5 empty] | #REF! | #REF! | 703
4 |  | PTC | Multipurpose Room | 300.0831 | 0 | 0 | 300.0831 | [5 empty] | #REF! | #REF! | 704
5 |  | PTC | Multipurpose Room | 302.1724 | 0 | 0 | 302.1724 | [5 empty] | #REF! | #REF! | 705
6 |  | Sale | 2BHK | 613.4942 | 0 | 0 | 613.4942 | [5 empty] | #REF! | #REF! | 706
7 |  | Sale | 2BHK | 628.4023 | 0 | 0 | 628.4023 | [5 empty] | #REF! | #REF! | 707
14th Floor For Residential, Balwadi, Amenity & Welfare Center (Part Refuge Area) | [7 empty] | 1
1 |  | PTC | Multipurpose Room | 301.0852 | 0 | 0 | 301.0852 | [5 empty] | #REF! | #REF! | 701
2 |  | PTC | Balwadi | [9 empty] | #REF! | #REF! | 702
3 |  | PTC | Amenity-1 | [9 empty] | #REF! | #REF! | 703
4 |  | PTC | Amenity-2 | [9 empty] | #REF! | #REF! | 704
5 |  | PTC | Welfare Center | [9 empty] | #REF! | #REF! | 705
- |  | Refuge Area | [10 empty] | #REF! | #REF! | 706
- | [12 empty] | #REF! | #REF! | 707
15th Floor For Residential (Part Terrace & Refuge Area) | [7 empty] | 1
1 |  | PTC | Multipurpose Room | 301.0852 | 0 | 0 | 301.0852 | [5 empty] | #REF! | #REF! | #NUM!
2 |  | PTC | Multipurpose Room | 306.6341 | 0 | 0 | 306.6341 | [5 empty] | #REF! | #REF! | #NUM!
3 |  | PTC | Multipurpose Room | 277.271 | 0 | 0 | 277.271 | [5 empty] | #REF! | #REF! | #NUM!
4 |  | PTC | Multipurpose Room | 300.0831 | 0 | 0 | 300.0831 | [5 empty] | #REF! | #REF! | #NUM!
5 |  | PTC | Multipurpose Room | 302.1724 | 0 | 0 | 302.1724 | [5 empty] | #REF! | #REF! | #NUM!
- |  | Terrace & Refuge Area | [10 empty] | #REF! | #REF! | #NUM!
- | [12 empty] | #REF! | #REF! | #NUM!
16th Floor | [7 empty] | 1
1 |  | PTC | Multipurpose Room | 301.0852 | 0 | 0 | 301.0852 | [5 empty] | #REF! | #REF! | #NUM!
2 |  | PTC | Multipurpose Room | 306.6341 | 0 | 0 | 306.6341 | [5 empty] | #REF! | #REF! | #NUM!
3 |  | PTC | Multipurpose Room | 277.271 | 0 | 0 | 277.271 | [5 empty] | #REF! | #REF! | #NUM!
4 |  | PTC | Multipurpose Room | 300.0831 | 0 | 0 | 300.0831 | [5 empty] | #REF! | #REF! | #NUM!
5 |  | PTC | Multipurpose Room | 302.1724 | 0 | 0 | 302.1724 | [5 empty] | #REF! | #REF! | #NUM!
17th Floor For Residential & Amenity Area (Part Terrace Area) | [7 empty] | 1
1 |  | PTC | Multipurpose Room | 301.0852 | 0 | 0 | 301.0852 | [5 empty] | #REF! | #REF! | 501
2 |  | PTC | Multipurpose Room | 306.6341 | 0 | 0 | 306.6341 | [5 empty] | #REF! | #REF! | 502
3 |  | PTC | Multipurpose Room | 277.271 | 0 | 0 | 277.271 | [5 empty] | #REF! | #REF! | 503
4 |  | PTC | Amenity-3 | [9 empty] | #REF! | #REF! | 504
- |  | Terrace Area | [10 empty] | #REF! | #REF! | 505
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit (labour found).
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We have given Valuation for Sale Flats only.
Site & Building/Tower Photographs
Name of the Project |  |  | Platinum Oceanic
Project Site Address |  |  | Platinum Oceanic, Off Carter Rd, Pyari Nagar, Chuim Village, Danda, Khar West, Mumbai, Maharashtra 400052
Site Visit Date & Time |  |  | 08/08/2025 at 02:19PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Tushar Bhuwad |  | Authorized Signatory Name & Signature
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per maps
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G82: Ready Recknor
Platinum Oceanic

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0