## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 |  | 2025-08-06 | 2025-05-23
Project Name |  | Mahaavir Exotique Phase I & II |  | Date & Time of Site Visit |  | 06/08/2025 at 01:36PM |  | 75
Name of the person met at site & Contact No. |  | Mr. Somnath 9702108280 |  | Date of Report Release |  | 06/08/2025
Data from APF Request Form
Branch Name/ID |  | Godrej One, Mumbai-RO Thane |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | M/s. Mahaavir Superstructures Private Limited |  | Developer Name |  | M/s. Mahaavir Superstructures Private Limited
Developer Office Address |  | A-1003 To 1009, 10th Floor, Mahaavir Icon, Plot No 89-90, Near Reliance Fresh, Sector 15, CBD Belapur, Tal. Thane, Dist. Thane 400614
Project Address | As per ARF | Mahaavir Exotique Phase I & II, Survey No. 19, 29, 24 A 8/B, Rohinjan, Navi Mumbai, Maharashtra 410210.
| As per Legal Documents | Mahaavir Exotique Phase I & II, Proposed Residential / Commercial Building On S. No. 19/1, 20, 24/A/8/B, Rohinjan, Dist. Raigad
| As per Actual at site | Mahaavir Exotique Phase I & II, S. No. 19/1, 20, 24/A/8/B, Near Today Royal Aikyam, Airport Expressway, Navin Vasahat, Rohinjan, Taloja, Navi Mumbai, Panvel, Raigad 410208
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, EC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Panvel Municipal Corporation (PMC)
RERA Registration No. | : | Phase I = P52000031173 Phase II = P52000053208 |  | RERA Registration Validity | : | Phase I = 31/12/2026 Phase II = 31/12/2027
Project Launch Date | : | Phase I = 11/10/2021 Phase II = 23/10/2023 |  | Construction Start Date | : | Phase I = Oct - 21 Phase II = Oct - 23
Proposed Date of Completion (As per RERA) | : | Phase I = 31/12/2026 Phase II = 31/12/2027 |  | Developer Bank Name (As per RERA) | : | State Bank Of India
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 24055 |  |  |  |  | 968
FSI/FAR Permissible | : | 2.7 |  | Net Plot Area (In Sq.Mt) | : | 21592 |  | 1.1792 |  |  | 12
Permissible Built up Area (In Sq.Mt) | : | 64953.5 |  | Proposed Built up Area (In Sq.Mt) | : | 64948.75
Total Number of Units Approved | : | Flats = 807 & Shop = 12 |  | Total Number of Units Planned | : | As per RERA Site Flats = 807 & Shop = 12 |  | 485 | 322
Latitude, Longitude | : | 19.092582,73.080321 |  | Landmark | : | Ekvira apartment
Location Link | : | https://goo.gl/maps/SY5LzJwJ3ZkiAQXM9
Extra Amenities available | : | Club House, Swimming Pool, Banquet Hall, Kids Playing Area, Temple, Garden Court, Multipurpose Court, Party Lawn, Kids Pool, Lap Pool, Outdooor Gym, Senior Citizen Seating Area etc. | [5 empty] | https://www.mahaavirsexotique.com/?utm_source=google&utm_medium=cpc&utm_campaign=Mahaavir+Exotique+NAVI&utm_term=mahaavir%20exotique&utm_Physical_Location=9062232&utm_Targetid=kwd-1462184513981&utm_Target=&utm_Placement=&utm_Adposition=&gad_source=1&gad_campaignid=21846766926&gbraid=0AAAAA-ZZrXyC8pE4_Kjr03HwGzZFSx5vO&gclid=Cj0KCQjwxdXBBhDEARIsAAUkP6gxJuKCBTV9zKxQqQ3LhN1fIpDLjVI-JfNSFEcGLyHs5wU3rVT8VCoaAriiEALw_wcB
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 15M
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 3.50 KM from Mumbra Highway Bus Stop
Distance from the nearest School (Km) | : | About 0.19KM from Raja Prasenjeet Public School & Junior College |  | Distance from Hospital (Km) | : | About 3.80 KM from Rana NX Hospital
Distance from the Main Market (Km) | : | 1. Approx. 3.90 KM from Taloja Market. |  | Distance from Railway Station (Km) | : | 2.40 KM from Taloja Panchanand Railway Station 7.40 KM from Navade Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East | West
East |  | S. No. 25/1 |  |  | Today Royal Aikyam
West |  | S. No. 24A/8 |  |  | Open plot
North |  | S. No. 24A/4 |  |  | Buildings
South |  | 15.00 M. Wide Road |  |  | Pisarve Road
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Phse I Wing A |  | Sale | G + 1st to 29th Floor |  |  | G + 1st to 29th Floor
Phse I Wing B |  | Sale | G + 1st to 22nd Floor |  |  | G + 1st to 22nd Floor
Phse I Wing C |  | Sale | G + 1st to 22nd Floor |  |  | G + 1st to 22nd Floor
Phse II Wing D |  | Sale | G + 1st to 22nd Floor |  |  | G + 1st to 22nd Floor
Phse II Wing E |  | Sale | G + 1st to 22nd Floor |  |  | G + 1st to 22nd Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | PMP/NRV/16030/JK-1906/2021 |  |  |  | Date: | 2021-09-17
Approved Plan Details | : | PMP/NRV/16030/JK-1906/2021 |  |  |  | Date: | 2021-09-17
CC Details Valid Up to: |  | PMC/TP/Rohinjan/19/1,20,24/A/8/B/ 16030/1906/2021 |  |  |  | Date: | 2021-09-17
Building No. A = G + 1st to 29th Upper Floor Building No. B, C, D, E = G + 1st to 22nd Upper Floor
Environmental Clearance Details | : | SIA/MH/MIS/213444/2021 Proposed Builtup Area = 92561.00 Sq. M 05 Buildings = Gr + 3P + 19 Floors 01 Building = Gr + 3P + 26 Floors |  |  |  | Date: | 2021-12-21
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Phse I Wing A= G + 1st to 29th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work upto 25 Floor, Electrical & Sanitary fittings upto 15 Floor, Finishing upto 15 Floor Completed
|  |  | 0 | 1 |  | 0 | 29 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 7.25
Excavation |  | 29 | 100% | 83.62% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work upto 25 Floor, Electrical & Sanitary fittings upto 15 Floor, Finishing upto 15 Floor Completed |  | Excavation in process | 14.5
Plinth |  | 29 | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 30 | 100% |  |  |  |  | Footing in Process | 5.8
Brickwork |  | 29 | 100% |  |  |  |  | Footing Completed | 11.6
Internal Plaster |  | 29 | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 29 | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 29 | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 29 | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 25 | 86.21% |  |  |  |  | Plinth in process | 20.3
Electrical & Sanitary fittings |  | 15 | 51.72% |  |  |  |  | Plinth completed | 29
Building Common Amenities |  | 15 | 51.72%
Possession |  | 0 | 0%
Construction Status
Phse I Wing B= G + 1st to 22nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work upto 18 Floor, Electrical & Sanitary fittings upto 14 Floor, Finishing upto 14 Floor Completed
|  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 85% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing, Flooring & Fitting, Wooden Work upto 18 Floor, Electrical & Sanitary fittings upto 14 Floor, Finishing upto 14 Floor Completed |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 4.4
Brickwork |  | 22 | 100% |  |  |  |  | Footing Completed | 8.8
Internal Plaster |  | 22 | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 22 | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 22 | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 22 | 100% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 18 | 81.82% |  |  |  |  | Plinth in process | 15.4
Electrical & Sanitary fittings |  | 14 | 63.64% |  |  |  |  | Plinth completed | 22
Building Common Amenities |  | 14 | 63.64%
Possession |  | 0 | 0%
Construction Status
Phse I Wing C= G + 1st to 22nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 20 Floor, External Plaster upto 20 Floor, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 12 Floor Completed
|  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 69.55% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 20 Floor, External Plaster upto 20 Floor, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 12 Floor Completed |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 4.4
Brickwork |  | 22 | 100% |  |  |  |  | Footing Completed | 8.8
Internal Plaster |  | 20 | 90.91% |  |  |  |  | Basement 1 | 0
External Plaster |  | 20 | 90.91% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 20 | 90.91% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 12 | 54.55% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 15.4
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Phse II Wing D= G + 1st to 22nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 17 Floor, External Plaster upto 17 Floor, External Plumbing, Elevation and Waterproofing upto 8 Floor Completed
|  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 60.68% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 17 Floor, External Plaster upto 17 Floor, External Plumbing, Elevation and Waterproofing upto 8 Floor Completed |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 4.4
Brickwork |  | 22 | 100% |  |  |  |  | Footing Completed | 8.8
Internal Plaster |  | 17 | 77.27% |  |  |  |  | Basement 1 | 0
External Plaster |  | 17 | 77.27% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 8 | 36.36% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 15.4
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Phse II Wing E= G + 1st to 22nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.4
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 8.8
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 15.4
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 64.77%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 12000 to 13000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 400000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 603.8647
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 5462.6533
Distress Value (Rs. Per sqft) |  |  |  |  | : | 483.0918
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Shop Line |  | Sale |  | 12 |  | 3880.5296
Total |  | - |  | 12 |  | 3880.5296
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing A |  | Sale |  | 163 |  | 114829.2218
Wing B |  | Sale |  | 161 |  | 89746.4538
Wing C |  | Sale |  | 161 |  | 89746.4538
Wing D |  | Sale |  | 161 |  | 89630.2026
Wing E |  | Sale |  | 161 |  | 89746.4538
Total |  | - |  | 807 |  | 473698.7859 |  | 968
Grand Total |  | - |  | 819 |  | 477579.3156
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony + Chajja Area | Attached Terrace area | Gross Carpet area
Phase I
Shop Line
Ground Floor for Commercial & Parking
1 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
2 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
3 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
4 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
5 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
6 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
7 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
8 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
9 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
10 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
11 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
12 |  | Sale | Shop | 323.3775 | 0 | 0 | 323.3775
Wing A
Ground Florr For Entrance Lobby & Parking
1st & 2nd Floor for Residential & Parking | [7 empty] | 2
1 |  | Sale | 2BHK | 572.4026 | 73.868 | 0 | 646.2706 | [5 empty] | 101,..,201 | 101 | 201
2 |  | Sale | 2BHK | 572.4026 | 73.868 | 0 | 646.2706 | [5 empty] | 102,..,202 | 102 | 202
3 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 103,..,203 | 103 | 203
4 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 104,..,204 | 104 | 204
5 |  | - | Parking | [9 empty] | 105,..,205 | 105 | 205
6 |  | - | [10 empty] | 106,..,206 | 106 | 206
3rd Floor For Residential, Society Office, Creche & Amenities | [7 empty] | 1
1 |  | Sale | 2BHK | 572.4026 | 73.868 | 0 | 646.2706 | [5 empty] | 301 to 301 | 301 | 301
2 |  | Sale | 2BHK | 572.4026 | 73.868 | 0 | 646.2706 | [5 empty] | 302 to 302 | 302 | 302
3 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 303 to 303 | 303 | 303
4 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 304 to 304 | 304 | 304
5 |  | - | Society Office | [9 empty] | 305 to 305 | 305 | 305
6 |  | - | Creche | [9 empty] | 306 to 306 | 306 | 306
4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor | [7 empty] | 21
1 |  | Sale | 2BHK | 572.4026 | 73.868 | 0 | 646.2706 | [5 empty] | 4701 & 2901 | 4701 | 2901
2 |  | Sale | 2BHK | 572.4026 | 73.868 | 0 | 646.2706 | [5 empty] | 4702 & 2902 | 4702 | 2902
3 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 4703 & 2903 | 4703 | 2903
4 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 4704 & 2904 | 4704 | 2904
5 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 4705 & 2905 | 4705 | 2905
6 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 4706 & 2906 | 4706 | 2906
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) | [7 empty] | 5
1 |  | Sale | 2BHK | 572.4026 | 73.868 | 0 | 646.2706 | [5 empty] | 8101 & 2801 | 8101 | 2801
- |  | - | Refuge Area | [9 empty] | 8102 & 2802 | 8102 | 2802
2 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 8103 & 2803 | 8103 | 2803
3 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 8104 & 2804 | 8104 | 2804
4 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 8105 & 2805 | 8105 | 2805
5 |  | Sale | 2.5BHK | 609.8882 | 122.6289 | 0 | 732.5171 | [5 empty] | 8106 & 2806 | 8106 | 2806
Wing B
1st, 2nd & 3rd Floor for Residential & Parking | [7 empty] | 3
- |  | - | Parking | [9 empty] | 105 & 305 | 105 | 305
- |  | - | [10 empty] | 106 & 306 | 106 | 306
- |  | - | [10 empty] | 107 & 307 | 107 | 307
1 |  | Sale | 2BHK | 584.3184 | 73.0606 | 0 | 657.379 | [5 empty] | 101 & 301 | 101 | 301
2 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 102 & 302 | 102 | 302
3 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 103 & 303 | 103 | 303
4 |  | Sale | 2BHK | 584.3184 | 73.0606 | 0 | 657.379 | [5 empty] | 104 & 304 | 104 | 304
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor | [7 empty] | 16
1 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 401 & 2201 | 401 | 2201
2 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 |  | 13020 |  |  |  | 402 & 2202 | 402 | 2202
3 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 403 & 2203 | 403 | 2203
4 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 404 & 2204 | 404 | 2204
5 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 |  | 11904.9969 |  |  |  | 405 & 2205 | 405 | 2205
6 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 406 & 2206 | 406 | 2206
7 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 407 & 2207 | 407 | 2207
8 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 408 & 2208 | 408 | 2208
8th, 13th & 18th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 1BHK | 403.058 | 56.1074 | 0 | 459.1653 | [5 empty] | 801 & 1801 | 801 | 1801
2 |  | Sale | 1BHK | 403.058 | 56.1074 | 0 | 459.1653 | [5 empty] | 802 & 1802 | 802 | 1802
3 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 803 & 1803 | 803 | 1803
4 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 804 & 1804 | 804 | 1804
- |  | - | Refuge Area | [9 empty] | 805 & 1805 | 805 | 1805
5 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 806 & 1806 | 806 | 1806
6 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 807 & 1807 | 807 | 1807
7 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 808 & 1808 | 808 | 1808
Wing C
Ground Floor for Parking
1st, 2nd & 3rd Floor for Residential & Parking | [7 empty] | 3
- |  | - | Parking | [9 empty] | 105 & 305 | 105 | 305
- |  | - | [10 empty] | 106 & 306 | 106 | 306
- |  | - | [10 empty] | 107 & 307 | 107 | 307
1 |  | Sale | 2BHK | 584.3184 | 73.0606 | 0 | 657.379 | [5 empty] | 101 & 301 | 101 | 301
2 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 102 & 302 | 102 | 302
3 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 103 & 303 | 103 | 303
4 |  | Sale | 2BHK | 584.3184 | 73.0606 | 0 | 657.379 | [5 empty] | 104 & 304 | 104 | 304
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor | [7 empty] | 16
1 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 401 & 2201 | 401 | 2201
2 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 402 & 2202 | 402 | 2202
3 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 403 & 2203 | 403 | 2203
4 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 404 & 2204 | 404 | 2204
5 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 405 & 2205 | 405 | 2205
6 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 406 & 2206 | 406 | 2206
7 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 407 & 2207 | 407 | 2207
8 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 408 & 2208 | 408 | 2208
8th, 13th & 18th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 1BHK | 403.058 | 56.1074 | 0 | 459.1653 | [5 empty] | 801 & 1801 | 801 | 1801
2 |  | Sale | 1BHK | 403.058 | 56.1074 | 0 | 459.1653 | [5 empty] | 802 & 1802 | 802 | 1802
3 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 803 & 1803 | 803 | 1803
4 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 804 & 1804 | 804 | 1804
- |  | - | Refuge Area | [9 empty] | 805 & 1805 | 805 | 1805
5 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 806 & 1806 | 806 | 1806
6 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 807 & 1807 | 807 | 1807
7 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 808 & 1808 | 808 | 1808
Phase II
Wing D
Ground Floor for Parking
1st & 2nd Floor for Residential & Parking | [7 empty] | 2
- |  | - | Parking | [9 empty] | 105 & 205 | 105 | 205
- |  | - | [10 empty] | 106 & 206 | 106 | 206
- |  | - | [10 empty] | 107 & 207 | 107 | 207
1 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 101 & 201 | 101 | 201
2 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 102 & 202 | 102 | 202
3 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 103 & 203 | 103 | 203
4 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 104 & 204 | 104 | 204
3rd Floor For Residential, Society Office, Creche & Society Office | [7 empty] | 1
- |  | - | Society Office | [9 empty] | 305 & 305 | 305 | 305
- |  | - | [10 empty] | 306 & 306 | 306 | 306
- |  | - | Creche | [9 empty] | 307 & 307 | 307 | 307
1 |  | - | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 301 & 301 | 301 | 301
2 |  | - | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 302 & 302 | 302 | 302
3 |  | - | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 303 & 303 | 303 | 303
4 |  | - | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 304 & 304 | 304 | 304
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor | [7 empty] | 16
1 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 401 & 2201 | 401 | 2201
2 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 402 & 2202 | 402 | 2202
3 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 403 & 2203 | 403 | 2203
4 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 404 & 2204 | 404 | 2204
5 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 405 & 2205 | 405 | 2205
6 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 406 & 2206 | 406 | 2206
7 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 407 & 2207 | 407 | 2207
8 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 408 & 2208 | 408 | 2208
8th, 13th & 18th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 1BHK | 403.058 | 56.1074 | 0 | 459.1653 | [5 empty] | 801 & 1801 | 801 | 1801
2 |  | Sale | 1BHK | 403.058 | 56.1074 | 0 | 459.1653 | [5 empty] | 802 & 1802 | 802 | 1802
3 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 803 & 1803 | 803 | 1803
4 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 804 & 1804 | 804 | 1804
- |  | - | Refuge Area | [9 empty] | 805 & 1805 | 805 | 1805
5 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 806 & 1806 | 806 | 1806
6 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 807 & 1807 | 807 | 1807
7 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 808 & 1808 | 808 | 1808
Wing E
Ground Floor for Parking
1st, 2nd & 3rd Floor for Residential & Parking | [7 empty] | 3
- |  | - | Parking | [9 empty] | 105 & 305 | 105 | 305
- |  | - | [10 empty] | 106 & 306 | 106 | 306
- |  | - | [10 empty] | 107 & 307 | 107 | 307
1 |  | Sale | 2BHK | 584.3184 | 73.0606 | 0 | 657.379 | [5 empty] | 101 & 301 | 101 | 301
2 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 102 & 302 | 102 | 302
3 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 103 & 303 | 103 | 303
4 |  | Sale | 2BHK | 584.3184 | 73.0606 | 0 | 657.379 | [5 empty] | 104 & 304 | 104 | 304
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor | [7 empty] | 16
1 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 401 & 2201 | 401 | 2201
2 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 402 & 2202 | 402 | 2202
3 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 403 & 2203 | 403 | 2203
4 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 404 & 2204 | 404 | 2204
5 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 405 & 2205 | 405 | 2205
6 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 406 & 2206 | 406 | 2206
7 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 407 & 2207 | 407 | 2207
8 |  | Sale | 2BHK | 577.9676 | 73.0606 | 0 | 651.0282 | [5 empty] | 408 & 2208 | 408 | 2208
8th, 13th & 18th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 1BHK | 403.058 | 56.1074 | 0 | 459.1653 | [5 empty] | 801 & 1801 | 801 | 1801
2 |  | Sale | 1BHK | 403.058 | 56.1074 | 0 | 459.1653 | [5 empty] | 802 & 1802 | 802 | 1802
3 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 803 & 1803 | 803 | 1803
4 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 804 & 1804 | 804 | 1804
- |  | - | Refuge Area | [9 empty] | 805 & 1805 | 805 | 1805
5 |  | Sale | 1BHK | 403.058 | 58.9329 | 0 | 461.9909 | [5 empty] | 806 & 1806 | 806 | 1806
6 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 807 & 1807 | 807 | 1807
7 |  | Sale | 2BHK | 564.9432 | 73.0606 | 0 | 638.0038 | [5 empty] | 808 & 1808 | 808 | 1808
Project Specific Remarks & Observation
* | Phase I (Wing A & B) = Construction work is in process at the time of Visit (Internal Visit not allowed). Phase I (Wing C) & Phase II (Wing D) = Construction work is in process at the time of Visit (Internal Visit not allowed). (Slow speed). Phase II (Wing E) = Construction work same as last visit dtd. 24/05/2025 but work is in process. (Slow Speed)
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Chajja Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | Remark for NOCs
* | Please check for Fire NOC.
Site & Building/Tower Photographs
Name of the Project |  |  | Mahaavir Exotique Phase I & II
Project Site Address |  |  | Mahaavir Exotique Phase I & II, Survey No. 19, 29, 24 A 8/B, Rohinjan, Navi Mumbai, Maharashtra 410210.
Site Visit Date & Time |  |  | 06/08/2025 at 01:36PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Sunil Peravi |  | Authorized Signatory Name & Signature
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per maps
Note on G17: From Rera
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G147: Ready Recknor
WING A
WING F
WING E
WING D
WING C
WING B
Mahaavir Exotique
Phase I & II
Wing A
Wing B
Wing C
Wing D
Wing E
Wing A
Wing B
Wing C
Wing C
Wing D
Wing E

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0