## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 |  | 2025-08-06 | 65
Project Name |  | Godrej Nurture (Tower 2 & 3) & Godrej Square |  | Date & Time of Site Visit |  | 06/08/2025 at 03:27PM |  | 2025-06-02
Name of the person met at site & Contact No. |  | Ms Riya CRM 8655769885 |  | Date of Report Release |  | 08/08/2025 |  | Mr. Alex CRM 9819803277 &
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Godrej Properties Limited |  | Developer Name |  | Godrej Properties Limited
Developer Office Address |  | 5th Floor, Godrej One, Pirojshanagar, Vikhroli East, Eastern Express Highway, Kurla, Vikhroli, Mumbai Suburban, Maharashtra, 400079
Project Address | As per ARF | Godrej Nurture & Godrej Square, Plot Bearing / CTS / Survey / Final Plot No.: 216A & 216C at Bhandup, Kurla, Mumbai Suburban, 400078.
| As per Legal Documents | Godrej Nurture & Godrej Square, CTS No.216-A & 216-C (Pt), near Filix Tower, LBS Marg, Sonapur, Bhandup, Nahur West, Mumbai, Mumbai - 400078.
| As per Actual at site | Godrej Nurture & Godrej Square, CTS No.216-A & 216-C (Pt), near Filix Tower, LBS Marg, Sonapur, Bhandup, Nahur West, Mumbai, Mumbai - 400078.
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai (MCGM)
RERA Registration No. | : | Tower 2 = P51800077080 Tower 3 = P51800077085 Godrej Square = P51800077810 |  | RERA Registration Validity | : | Tower 2 & 3 - 31/03/2031 Godrej Square - 31/10/2028
Project Launch Date | : | Tower 2 & 3 - 19/06/2024 & Godrej Square - 07/11/2024 |  | Construction Start Date | : | 2024-07-23
Proposed Date of Completion (As per RERA) | : | 2031-03-31 |  | Developer Bank Name (As per RERA) | : | State Bank of India IFSC Code SBIN0009995
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 27112.9
FSI/FAR Permissible | : | 1 |  | Net Plot Area (In Sq.Mt) | : | 22268.49
Permissible Built up Area (In Sq.Mt) | : | 43091.56 |  | Proposed Built up Area (In Sq.Mt) | : | 5347013 |  | 53548.01
Total Number of Units Approved | : | Flats = 616 Shops = 17 Offices = 72 |  | Total Number of Units Planned | : | As per RERA, Site Flats = 616 Shops = 17 Offices = 72 |  | 313+303
Latitude, Longitude | : | 19.1604667,72.9368963 |  | Landmark | : | Filix Tower
Location Link | : | https://maps.app.goo.gl/LSM9BWKtLC7513cF6
Extra Amenities available | : | Swimming Pool, Kids Pool, Reading Room, Yoga Room, Fitness Center, etc. | [5 empty] | 19
Zone/Locality/Surrounding/Civic Amenities | [7 empty] | 72
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Concrete |  | Width of the Road | : | 30.5 M
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 130 M from Asian Paints Bus Stop
Distance from the nearest School (Km) | : | About 1.2 KM from Noble Angel High School |  | Distance from Hospital (Km) | : | About 750 M form Navkar Hospital
Distance from the Main Market (Km) | : | 1. Approx. 700 M from D Mart. 2. Approx. 2.9 KM from Mulund Market. |  | Distance from Railway Station (Km) | : | 2.5 KM from Nahur Railway Station 2.6 KM from Bhandup Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East | West
East |  | 30.5 M W Road |  |  | LBS Marg
West |  | 18.3 M W Road |  |  | Lake Road
North |  | Nalla |  |  | Nalla
South |  | Plot EO1.3 (Pt) |  |  | Filix Tower
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower 2 |  | Sale | G + 1st to 44th Floor |  |  | G + 1st to 44th Floor
Tower 3 |  | Sale | G + 1st to 43rd Floor |  |  | G + 1st to 43rd Floor
Commercial Wing |  | Sale | 2B + G + 1st to 4th Floor |  |  | 2B + G + 1st to 4th Floor |  | https://www.godrejsquarelbsmarg.com/?utm_source=google&utm_medium=cpc&utm_campaign=Godrej+Square+Bhandup+Commercial&utm_term=godrej%20square%20bhandup&utm_Physical_Location=9062232&utm_Targetid=kwd-2390437577750&utm_Target=&utm_Placement=&utm_Adposition=&gad_source=1&gad_campaignid=22352411891&gbraid=0AAAAADq4HKc6LO7SpkwUnQwnfiILNaWn0&gclid=CjwKCAjwruXBBhArEiwACBRtHe2U7oK2UoSxs5SOenubtcbgw34ECsOxYzQAHYx0ftFjFroV_cBMqBoCX_IQAvD_BwE
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details (Tower 2 & 3) | : | CE/1068/BPES/AS |  |  |  | Date: | 2024-08-01
LOI/IOD Details | : | CE/1068/BPES/AS/337/4/Amend |  |  |  | Date: | 2024-10-28
Approved Plan Details (Tower 2 & 3) | : | CE/1068/BPES/AS |  |  |  | Date: | 2024-08-01
Approved Plan Details | : | CE/1068/BPES/AS/337/4/Amend |  |  |  | Date: | 2024-10-28
CC Details Valid Up to: |  | CE/1068/BPES/AS/CC/2/Amend |  |  |  | Date: | 2024-06-09 | acquila
|  | Plinth C.C. as per approved IOD plans dated 26.04.2024. |  |  |  | Valid Upto Date | 2025-06-18
CC Details Valid Up to: |  | CE/1068/BPES/AS/CC/3/Amend |  |  |  | Date: | 2024-11-14
|  | CC for shore piling activity only, subject to strict implementation Air Pollution Mitigation Guidelines. (CC Valid upto 17.06.2025) |  |  |  | Valid Upto Date | 2025-11-13
Environmental Clearance Details | : |  |  |  |  | Date:
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Fire NOC Details Valid Up to: | : | CE/1068/BPES/AS-CFO-1 Tower - 2 = Ground/Stilt + 1st to 8th Podium floors + 9th floor + 10th podium floor + 11th to 44th upper residential floors with a (total height of 138.25mtrs). Tower - 3 = Ground + 1st to 8th Podium floors + 9th floor + 10th podium floor top + 11th to 43rd floors (total height of 135.20 mtrs). Commercial Wing = 2B + G + 1st to 4th Floor (Height = 22.20M) |  |  |  | Date: | 2024-02-07
Airport Authority Clearance Details Valid Up to: |  | SNCR/WEST/B/122123/860671 |  |  |  | Date: | 2024-01-23 |  | TOR No. | File No.SIA/MH/INFRA2/452038/2023
|  | Site Elevation AMSL = 15.96 M Permissible Top Elevation AMSL = 196.53 M |  |  |  | Valid Upto Date | 2032-01-22
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Tower 2= G + 1st to 44th Floor. |  |  | Basement | Ground |  | Podium | Floors | Work not yet Started.
|  |  | 0 | 1 |  | 0 | 44 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11
Excavation |  | 0 | 0% | 0% |  | Work not yet Started. |  | Excavation in process | 22
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 44
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 8.8
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 17.6
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0 | Table Updated 16/11/2024
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 30.8
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 44
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Tower 3= G + 1st to 43rd Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work in process
|  |  | 0 | 1 |  | 0 | 43 | All work Completed. OC Received. |  | Table Updated 16/11/2024
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 10.75
Excavation |  | 21.5 | 50% | 5% |  | Excavation work in process |  | Excavation in process | 21.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 43
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 8.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 17.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 30.1
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 43
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Commercial Wing= 2B + G + 1st to 4th Floor. |  |  | Basement | Ground |  | Podium | Floors | Piling work in process
|  |  | 2 | 1 |  | 0 | 4 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 1
Excavation |  | 1 | 25% | 2.5% |  | Piling work in process |  | Excavation in process | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 3
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Project Completion % | [5 empty] | 2.5%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 27000 to 28000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Rate of Shop Per Sq. Ft. (on Carpet area) |  | 37000 to 38000
Rate of Office Per Sq. Ft. (on Carpet area) |  | 31000 to 32000
Car Parking Charges |  | 800000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 8490.3382
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 14934.0394
Distress Value (Rs. Per sqft) |  |  |  |  | : | 6792.2705
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Commercial Wing Shops |  | - |  | 17 |  | 10576.7247
Commercial Wing Offices |  | - |  | 72 |  | 45266.6242
Total |  | - |  | 89 |  | 55843.3489 | 0
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Tower 2 |  | - |  | 303 |  | 249847.881
Tower 3 |  | - |  | 313 |  | 200603.6165
Total |  | - |  | 616 |  | 450451.4974
Grand Total |  | - |  | 705 |  | 506294.8463
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Tower 2
Ground Floor For Meter Room, Society Office, BMS Room, Entrance Lobby & Parking
1st Podium Floor For Residential, Voids & Parking
1 |  | Parking
2
3 |  | Voids
4
5 |  | - | 3BHK | 921.9366 | 61.048 | 0 | 982.9846 | 73.0775
6 |  | - | 2BHK | 743.5771 | 61.048 | 0 | 804.6251
7 |  | Parking
8
2nd to 7th Podium Floor For Residential & Parking
1 |  | Parking | [11 empty] | 201 to 701 | 201 | 701
2 | [13 empty] | 202 to 702 | 202 | 702
3 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164 | [6 empty] | 203 to 703 | 203 | 703
4 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164 | [6 empty] | 204 to 704 | 204 | 704
5 |  | - | 3BHK | 921.9366 | 61.048 | 0 | 982.9846 | [6 empty] | 205 to 705 | 205 | 705
6 |  | - | 2BHK | 743.5771 | 61.048 | 0 | 804.6251 | [6 empty] | 206 to 706 | 206 | 706
7 |  | Parking | [11 empty] | 207 to 707 | 207 | 707
8 | [13 empty] | 208 to 708 | 208 | 708
8th Podium Floor For Residential & Voids (Part Refuge Area)
1 |  | Voids | [11 empty] | #REF! | #REF! | 801
2 | [13 empty] | #REF! | #REF! | 802
3 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164 | [6 empty] | #REF! | #REF! | 803
4 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164 | [6 empty] | #REF! | #REF! | 804
5 |  | Refuge Area | [11 empty] | #REF! | #REF! | 805
6 | [13 empty] | #REF! | #REF! | 806
7 |  | Voids | [11 empty] | #REF! | #REF! | 807
8 | [13 empty] | #REF! | #REF! | 808
9th Podium Floor For Residential, Entrance Lobby & Parking
1 |  | Parking
2
3 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164
4 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164
5 |  | - | 3BHK | 921.9366 | 61.048 | 0 | 982.9846
6 |  | - | 2BHK | 743.5771 | 61.048 | 0 | 804.6251
7 |  | Entrance Lobby
8
10th to 14th, 16th to 20th For Residential
1 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888 | [6 empty] | 1001,..,2001 | 1001 | 2001
2 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888 | [6 empty] | 1002,..,2002 | 1002 | 2002
3 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164 | [6 empty] | 1003,..,2003 | 1003 | 2003
4 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164 | [6 empty] | 1004,..,2004 | 1004 | 2004
5 |  | - | 3BHK | 921.9366 | 61.048 | 0 | 982.9846 | [6 empty] | 1005,..,2005 | 1005 | 2005
6 |  | - | 3BHK | 921.9366 | 61.048 | 0 | 982.9846 | [6 empty] | 1006,..,2006 | 1006 | 2006
7 |  | - | 2BHK | 653.5901 | 50.3378 | 0 | 703.9279 | [6 empty] | 1007,..,2007 | 1007 | 2007
8 |  | - | 2BHK | 653.5901 | 50.3378 | 0 | 703.9279 | [6 empty] | 1008,..,2008 | 1008 | 2008
15th Floor (Part Refuge Area)
1 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888 | [6 empty] | 101,..,1501 | 101 | 1501
2 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888 | [6 empty] | 102,..,1502 | 102 | 1502
3 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164 | [6 empty] | 103,..,1503 | 103 | 1503
4 |  | - | 2BHK | 677.3785 | 50.3378 | 0 | 727.7164 | [6 empty] | 104,..,1504 | 104 | 1504
5 |  | Refuge Area | [11 empty] | 105,..,1505 | 105 | 1505
6 | [13 empty] | 106,..,1506 | 106 | 1506
7 |  | - | 2BHK | 653.5901 | 50.3378 | 0 | 703.9279 | [6 empty] | 107,..,1507 | 107 | 1507
8 |  | - | 2BHK | 653.5901 | 50.3378 | 0 | 703.9279 | [6 empty] | 108,..,1508 | 108 | 1508
21st, 23rd to 28th, 30th to 35th, 37th to 42nd & 44th For Residential
1 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888 | [6 empty] | 212301,..,4401 | 212301 | 4401
2 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888 | [6 empty] | 212302,..,4402 | 212302 | 4402
3 |  | - | 2BHK | 681.8994 | 50.3378 | 0 | 732.2372 | [6 empty] | 212303,..,4403 | 212303 | 4403
4 |  | - | 2BHK | 681.8994 | 50.3378 | 0 | 732.2372 | [6 empty] | 212304,..,4404 | 212304 | 4404
5 |  | - | 3BHK | 921.9366 | 61.048 | 0 | 982.9846 | [6 empty] | 212305,..,4405 | 212305 | 4405
6 |  | - | 3BHK | 921.9366 | 61.048 | 0 | 982.9846 | [6 empty] | 212306,..,4406 | 212306 | 4406
7 |  | - | 2BHK | 658.0033 | 50.3378 | 0 | 708.3412 | [6 empty] | 212307,..,4407 | 212307 | 4407
8 |  | - | 2BHK | 658.0033 | 50.3378 | 0 | 708.3412 | [6 empty] | 212308,..,4408 | 212308 | 4408
22nd, 29th & 36th Floor (Part Refuge Area)
1 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888 | [6 empty] | 2201,..,3601 | 2201 | 3601
2 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888 | [6 empty] | 2202,..,3602 | 2202 | 3602
3 |  | - | 2BHK | 681.8994 | 50.3378 | 0 | 732.2372 | [6 empty] | 2203,..,3603 | 2203 | 3603
4 |  | - | 2BHK | 681.8994 | 50.3378 | 0 | 732.2372 | [6 empty] | 2204,..,3604 | 2204 | 3604
5 |  | Refuge Area | [11 empty] | 2205,..,3605 | 2205 | 3605
6 | [13 empty] | 2206,..,3606 | 2206 | 3606
7 |  | - | 2BHK | 658.0033 | 50.3378 | 0 | 708.3412 | [6 empty] | 2207,..,3607 | 2207 | 3607
8 |  | - | 2BHK | 658.0033 | 50.3378 | 0 | 708.3412 | [6 empty] | 2208,..,3608 | 2208 | 3608
43rd Floor (Part Refuge Area)
1 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888
2 |  | - | 3BHK | 842.8212 | 58.1676 | 0 | 900.9888
3 |  | - | 2BHK | 681.8994 | 50.3378 | 0 | 732.2372
4 |  | - | 2BHK | 681.8994 | 50.3378 | 0 | 732.2372
5 |  | Refuge Area
6 |  | - | 3BHK | 1105.2475 | 106.0631 | 0 | 1211.3106
7 |  | - | 2BHK | 658.0033 | 50.3378 | 0 | 708.3412
8 |  | - | 2BHK | 658.0033 | 50.3378 | 0 | 708.3412
Tower 3
Ground Floor For Meter Room, Society Office, BMS Room, Entrance Lobby & Parking
1st Podium Floor For Residential, Voids & Parking
1 |  | Parking
2
3 |  | Voids
4
5 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441
6 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441
7 |  | - | 2BHK | 531.7416 | 14.0147 | 0 | 545.7563
8 |  | - | 2BHK | 531.7416 | 14.0147 | 0 | 545.7563
2nd to 7th Podium Floor For Residential & Parking
1 |  | Parking | [11 empty] | 201 to 701 | 201 | 701
2 | [13 empty] | 202 to 702 | 202 | 702
3 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356 | [6 empty] | 203 to 703 | 203 | 703
4 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356 | [6 empty] | 204 to 704 | 204 | 704
5 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 205 to 705 | 205 | 705
6 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 206 to 706 | 206 | 706
7 |  | - | 2BHK | 531.7416 | 14.0147 | 0 | 545.7563 | [6 empty] | 207 to 707 | 207 | 707
8 |  | - | 2BHK | 531.7416 | 14.0147 | 0 | 545.7563 | [6 empty] | 208 to 708 | 208 | 708
8th Podium Floor For Residential & Voids (Part Refuge Area)
1 |  | Voids
2
3 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356
4 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356
5 |  | Refuge Area
6
7 |  | - | 2BHK | 531.7416 | 14.0147 | 0 | 545.7563
8 |  | - | 2BHK | 531.7416 | 14.0147 | 0 | 545.7563
9th Podium Floor For Residential & Entrance Lobby
1 |  | Entrance Lobby
2
3 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356
4 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356
5 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441
6 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441
7 |  | - | 2BHK | 531.7416 | 14.0147 | 0 | 545.7563
8 |  | - | 2BHK | 531.7416 | 14.0147 | 0 | 545.7563
10th to 14th & 16th to 20th Floor For Residential
1 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 1001,..,2001 | 1001 | 2001
2 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 1002,..,2002 | 1002 | 2002
3 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356 | [6 empty] | 1003,..,2003 | 1003 | 2003
4 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356 | [6 empty] | 1004,..,2004 | 1004 | 2004
5 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 1005,..,2005 | 1005 | 2005
6 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 1006,..,2006 | 1006 | 2006
7 |  | - | 2BHK | 531.7416 | 14.315 | 0 | 546.0566 | [6 empty] | 1007,..,2007 | 1007 | 2007
8 |  | - | 2BHK | 531.7416 | 14.315 | 0 | 546.0566 | [6 empty] | 1008,..,2008 | 1008 | 2008
15th Floor (Part Refuge Area)
1 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441
2 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441
3 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356
4 |  | - | 2BHK | 653.5901 | 50.4455 | 0 | 704.0356
5 |  | Refuge Area
6
7 |  | - | 2BHK | 531.7416 | 14.315 | 0 | 546.0566
8 |  | - | 2BHK | 531.7416 | 14.315 | 0 | 546.0566
21st, 23rd to 28th, 30th to 35th & 37th to 42nd Floor For Residential
1 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 212301,..,4201 | 212301 | 4201
2 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 212302,..,4202 | 212302 | 4202
3 |  | - | 2BHK | 662.4166 | 50.4455 | 0 | 712.862 | [6 empty] | 212303,..,4203 | 212303 | 4203
4 |  | - | 2BHK | 662.4166 | 50.4455 | 0 | 712.862 | [6 empty] | 212304,..,4204 | 212304 | 4204
5 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 212305,..,4205 | 212305 | 4205
6 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 212306,..,4206 | 212306 | 4206
7 |  | - | 2BHK | 538.0924 | 14.315 | 0 | 552.4074 | [6 empty] | 212307,..,4207 | 212307 | 4207
8 |  | - | 2BHK | 538.0924 | 14.315 | 0 | 552.4074 | [6 empty] | 212308,..,4208 | 212308 | 4208
22nd, 29th & 36th Floor (Part Refuge Area)
1 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 2201,..,3601 | 2201 | 3601
2 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 2202,..,3602 | 2202 | 3602
3 |  | - | 2BHK | 662.4166 | 50.4455 | 0 | 712.862 | [6 empty] | 2203,..,3603 | 2203 | 3603
4 |  | - | 2BHK | 662.4166 | 50.4455 | 0 | 712.862 | [6 empty] | 2204,..,3604 | 2204 | 3604
5 |  | Refuge Area | [11 empty] | 2205,..,3605 | 2205 | 3605
6 | [13 empty] | 2206,..,3606 | 2206 | 3606
7 |  | - | 2BHK | 538.0924 | 14.315 | 0 | 552.4074 | [6 empty] | 2207,..,3607 | 2207 | 3607
8 |  | - | 2BHK | 538.0924 | 14.315 | 0 | 552.4074 | [6 empty] | 2208,..,3608 | 2208 | 3608
43rd Floor (Part Refuge Area)
1 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 401,..,4301 | 401 | 4301
2 |  | - | 2BHK | 607.8431 | 47.001 | 0 | 654.8441 | [6 empty] | 402,..,4302 | 402 | 4302
3 |  | - | 2BHK | 662.4166 | 50.4455 | 0 | 712.862 | [6 empty] | 403,..,4303 | 403 | 4303
4 |  | - | 2BHK | 662.4166 | 50.4455 | 0 | 712.862 | [6 empty] | 404,..,4304 | 404 | 4304
5 |  | Refuge Area | [11 empty] | 405,..,4305 | 405 | 4305
6 |  | - | 2BHK | 744.1153 | 79.0347 | 0 | 823.15 | [6 empty] | 406,..,4306 | 406 | 4306
7 |  | - | 2BHK | 538.0924 | 14.315 | 0 | 552.4074 | [6 empty] | 407,..,4307 | 407 | 4307
8 |  | - | 2BHK | 538.0924 | 14.315 | 0 | 552.4074 | [6 empty] | 408,..,4308 | 408 | 4308
Commercial Wing | [7 empty] | 10.764
Lower Basement Floor For Pump Room & Parking
Upper Basement Floor For Parking
Ground Floor For Commercial & Entrance Lobby
1 |  | - | Shop | 658.2455 | 0 | 0 | 658.2455 | [6 empty] | #REF! | #REF! | #NUM!
2 |  | - | Shop | 659.2896 | 0 | 0 | 659.2896 | [6 empty] | #REF! | #REF! | #NUM!
3 |  | - | Shop | 658.4662 | 0 | 0 | 658.4662 | [6 empty] | #REF! | #REF! | #NUM!
4 |  | - | Shop | 658.6761 | 0 | 0 | 658.6761 | [6 empty] | #REF! | #REF! | #NUM!
5 |  | - | Shop | 658.6761 | 0 | 0 | 658.6761 | [6 empty] | #REF! | #REF! | #NUM!
6 |  | - | Shop | 658.3478 | 0 | 0 | 658.3478 | [6 empty] | #REF! | #REF! | #NUM!
7 |  | - | Shop | 659.0044 | 0 | 0 | 659.0044 | [6 empty] | #REF! | #REF! | #NUM!
8 |  | - | Shop | 766.9027 | 0 | 0 | 766.9027 | [6 empty] | #REF! | #REF! | #NUM!
9 |  | - | Shop | 766.9027 | 0 | 0 | 766.9027 | [6 empty] | #REF! | #REF! | #NUM!
10 |  | - | Shop | 762.6563 | 0 | 0 | 762.6563 | [6 empty] | #REF! | #REF! | #NUM!
11 |  | - | Shop | 517.5159 | 0 | 0 | 517.5159 | [6 empty] | #REF! | #REF! | #NUM!
12 |  | - | Shop | 592.2999 | 0 | 0 | 592.2999 | [6 empty] | #REF! | #REF! | #NUM!
13 |  | - | Shop | 592.2999 | 0 | 0 | 592.2999 | [6 empty] | #REF! | #REF! | #NUM!
14 |  | - | Shop | 388.9948 | 0 | 0 | 388.9948 | [6 empty] | #REF! | #REF! | #NUM!
15 |  | - | Shop | 388.9948 | 0 | 0 | 388.9948 | [6 empty] | #REF! | #REF! | #NUM!
16 |  | - | Shop | 597.4989 | 0 | 0 | 597.4989 | [6 empty] | #REF! | #REF! | #NUM!
17 |  | - | Shop | 591.9533 | 0 | 0 | 591.9533 | [6 empty] | #REF! | #REF! | #NUM!
1st Floor
1 |  | - | Office | 672.454 | 0 | 0 | 672.454 | [6 empty] | 101 to 101 | 101 | 101
2 |  | - | Office | 673.0675 | 0 | 0 | 673.0675 | [6 empty] | 102 to 102 | 102 | 102
3 |  | - | Office | 673.0675 | 0 | 0 | 673.0675 | [6 empty] | 103 to 103 | 103 | 103
4 |  | - | Office | 672.454 | 0 | 0 | 672.454 | [6 empty] | 104 to 104 | 104 | 104
5 |  | - | Office | 672.454 | 0 | 0 | 672.454 | [6 empty] | 105 to 105 | 105 | 105
6 |  | - | Office | 671.8996 | 0 | 0 | 671.8996 | [6 empty] | 106 to 106 | 106 | 106
7 |  | - | Office | 673.0083 | 0 | 0 | 673.0083 | [6 empty] | 107 to 107 | 107 | 107
8 |  | - | Office | 672.7823 | 0 | 0 | 672.7823 | [6 empty] | 108 to 108 | 108 | 108
9 |  | - | Office | 672.7823 | 0 | 0 | 672.7823 | [6 empty] | 109 to 109 | 109 | 109
10 |  | - | Office | 672.454 | 0 | 0 | 672.454 | [6 empty] | 110 to 110 | 110 | 110
11 |  | - | Office | 592.7918 | 0 | 0 | 592.7918 | [6 empty] | 111 to 111 | 111 | 111
12 |  | - | Office | 592.7918 | 0 | 0 | 592.7918 | [6 empty] | 112 to 112 | 112 | 112
13 |  | - | Office | 719.9631 | 0 | 0 | 719.9631 | [6 empty] | 113 to 113 | 113 | 113
14 |  | - | Office | 395.324 | 0 | 0 | 395.324 | [6 empty] | 114 to 114 | 114 | 114
15 |  | - | Office | 395.324 | 0 | 0 | 395.324 | [6 empty] | 115 to 115 | 115 | 115
16 |  | - | Office | 719.9631 | 0 | 0 | 719.9631 | [6 empty] | 116 to 116 | 116 | 116
17 |  | - | Office | 589.7649 | 0 | 0 | 589.7649 | [6 empty] | 117 to 117 | 117 | 117
18 |  | - | Office | 594.133 | 0 | 0 | 594.133 | [6 empty] | 118 to 118 | 118 | 118
2nd to 4th Floor
1 |  | - | Office | 672.454 | 0 | 0 | 672.454 | [6 empty] | 201 to 401 | 201 | 401
2 |  | - | Office | 673.0675 | 0 | 0 | 673.0675 | [6 empty] | 202 to 402 | 202 | 402
3 |  | - | Office | 673.0675 | 0 | 0 | 673.0675 | [6 empty] | 203 to 403 | 203 | 403
4 |  | - | Office | 672.454 | 0 | 0 | 672.454 | [6 empty] | 204 to 404 | 204 | 404
5 |  | - | Office | 672.454 | 0 | 0 | 672.454 | [6 empty] | 205 to 405 | 205 | 405
6 |  | - | Office | 671.8996 | 0 | 0 | 671.8996 | [6 empty] | 206 to 406 | 206 | 406
7 |  | - | Office | 673.0083 | 0 | 0 | 673.0083 | [6 empty] | 207 to 407 | 207 | 407
8 |  | - | Office | 672.7823 | 0 | 0 | 672.7823 | [6 empty] | 208 to 408 | 208 | 408
9 |  | - | Office | 672.7823 | 0 | 0 | 672.7823 | [6 empty] | 209 to 409 | 209 | 409
10 |  | - | Office | 672.454 | 0 | 0 | 672.454 | [6 empty] | 210 to 410 | 210 | 410
11 |  | - | Office | 592.7918 | 0 | 0 | 592.7918 | [6 empty] | 211 to 411 | 211 | 411
12 |  | - | Office | 592.7918 | 0 | 0 | 592.7918 | [6 empty] | 212 to 412 | 212 | 412
13 |  | - | Office | 719.9631 | 0 | 0 | 719.9631 | [6 empty] | 213 to 413 | 213 | 413
14 |  | - | Office | 388.7752 | 0 | 0 | 388.7752 | [6 empty] | 214 to 414 | 214 | 414
15 |  | - | Office | 388.7752 | 0 | 0 | 388.7752 | [6 empty] | 215 to 415 | 215 | 415
16 |  | - | Office | 719.9631 | 0 | 0 | 719.9631 | [6 empty] | 216 to 416 | 216 | 416
17 |  | - | Office | 589.7649 | 0 | 0 | 589.7649 | [6 empty] | 217 to 417 | 217 | 417
18 |  | - | Office | 594.133 | 0 | 0 | 594.133 | [6 empty] | 218 to 418 | 218 | 418
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [6 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [6 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [6 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [6 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [6 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [6 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [6 empty] | 208 & 508 | 208 | 508
Project Specific Remarks & Observation
* | Tower 2 = Work not yet started. Tower 3 & Commercial Wing = Construction work is same as last visit dtd. 02/06/2025 but work is in process at the time of Visit (Slow Speed). Construction Details area taken from Ms. Riya (labour found) Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Utility.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
* | Project Godrej Nurture consists of Tower 2 & Tower 3 and Project Godrej Square consists of Commercial Wing.
* | We have Commercial Wing (On 02/06/2025).
* | We have Update approved plans for Tower 2 & 3 (On 02/06/2025).
* | We have referred revised CC from MCGM site for Commercial Wing. (On 02/06/2025).
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs
Name of the Project |  |  | Godrej Nurture (Tower 2 & 3) & Godrej Square
Project Site Address |  |  | Godrej Nurture & Godrej Square, CTS No.216-A & 216-C (Pt), near Filix Tower, LBS Marg, Sonapur, Bhandup, Nahur West, Mumbai, Mumbai - 400078.
Site Visit Date & Time |  |  | 06/08/2025 at 03:27PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Nainesh Tambe |  | Authorized Signatory Name & Signature
Note on C9: SACHIN: As per initiation Mail
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on I20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G122: Ready Recknor
Tower 2
Tower 3
Commercial Wing

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%