## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 | 2025-08-07 | 59
Project Name |  |  | : | Runwal Avenue - I Wing - First Avenue J Wing - Madison K Wing - Broadway L Wing - Park View M Wing - Manhattan N Wing - Liberty |  | Date & Time of Site Visit |  | 07/08/2025 at 01:12PM | 2025-06-09
Name of the person met at site & Contact No. |  |  | : | Mr. Lalit Thorat 8268917330 |  | Date of Report Release |  | 08/08/2025 | Mr. Abhishek Joshi 9920684949
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Susneh Infrapark Private Limited | Developer Name | : | Susneh Infrapark Private Limited
Developer Office Address |  |  | : | Aryabhatt Building, C G Compound, Kanjurmarg (East), Locality:Kanjurmarg
Project Address | : | As per ARF | : | Runwal Avenue (Wing I, J, K, L, M & N), CTS No. as per CC.1004, 1005, 1005/1, 1006, 1007(pt), 1007/3(pt), 1007/4, 1009(pt), 1009/5, 1009/6, 1010(pt), 1013(pt), 1014(pt), 1014/1 to 16, 1017, 1017/1 to 6, 1018 and 1018/1 to 9, near NG Royal Park, Kanjur Village Road, Kanjur, Datar Colony, Kanjurmarg East, Kurla, Mumbai - 400042.
| : | As per Legal Documents | : | Runwal Avenue (Wing I, J, K, L, M & N), CTS No. as per CC.1004, 1005, 1005/1, 1006, 1007(pt), 1007/3(pt), 1007/4, 1009(pt), 1009/5, 1009/6, 1010(pt), 1013(pt), 1014(pt), 1014/1 to 16, 1017, 1017/1 to 6, 1018 and 1018/1 to 9, near NG Royal Park, Kanjur Village Road, Kanjur, Datar Colony, Kanjurmarg East, Kurla, Mumbai - 400042.
| : | As per Actual at site | : | Runwal Avenue (Wing I, J, K, L, M & N), near NG Royal Park, Kanjur Village Road, Kanjur, Datar Colony, Kanjurmarg East, Kurla, Mumbai - 400042.
Documents Provided by GHF |  |  | : | NA
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation Of Greater Mumbai (MCGM)
RERA Registration No. | : | I Wing - P51800048234 J Wing - P51800026860 K Wing - P51800028811 L Wing - P51800031895 M Wing - P51800033514 N Wing - P51800047714 |  |  | RERA Registration Validity | : | I Wing = 20/04/2028 J & K Wing = 30/06/2027 L Wing = 31/12/2026 M Wing = 18/04/2026 N Wing = 31/12/2027
Project Launch Date | : | 2020-10-31 |  |  | Construction Start Date | : | I Wing = 19/12/2022 J Wing = 31/10/2020 K Wing = 30/03/2021 LWing = 22/11/2021 M Wing = 22/02/2022 N Wing = 21/11/2022
Proposed Date of Completion (As per RERA) | :
Project Type (Mixed, Residential, Comm.) | : | Residential + Comm. |  |  | Proposed Date of Completion (As per RERA) | : | I Wing = 20/04/2028 J & K Wing = 30/06/2027 L Wing = 31/12/2026 M Wing = 18/04/2026 N Wing = 31/12/2027
FSI/FAR Permissible | : |  |  |  | Proposed Built up Area (In Sq.Mt) | :
Permissible Built up Area (In Sq.Mt) | : | 0 |  |  | Total Number of Units Planned | : | Flats = 279 & Shop = 42 |  | 279
Total Number of Units Approved | : | Flats = |  |  | If Mixed, No. of Commercial Units | : | Shop =
Latitude, Longitude | : | 19.1312981,72.9309152 |  |  | Landamrk | : | Kanakia Zen World
Location Link | : | https://goo.gl/maps/yT3qtoy6FjJa1jx69?coh=178572&entry=tt
Extra Amenities available | : | Aqua Gym, Jacuzzi, jogging track, Multipurpose Court, Open Green Vistas, Badminton Court, Yoga Pavilion, Kids play area, creche, Indoor games, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  |  | Class of Locality | : | Upper Class
Type of Road | : | Bitumen |  |  | Width of the Road | : | 12M
Electrification/Electric poles observed | : | Yes |  |  | Distance from Railway Station (Km) | : | 300m from Kanjur Marg Railway Station
Distance from the nearest School (Km) | : | About 1KM from St Francis Xavier's High School |  |  | Distance from Hospital (Km) | : | About 2.8K form Aastha Hospital
Distance from the Main Market (Km) | : | 1. Approx. 3.8 KM from VHuma Mall 2. Approx. 3.7KM from D mart. |  |  | Distance from Railway Station (Km) | : | 2.7KM from Kanjurmarg Railway
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | :
As per Site / Actual |  |  | : | Toyo Engineering India Limited | Internal Road | Other Plot |  | Kanjur Village Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
I Wing |  | Sale |  | Gr + 1 Retail + 1st to 49th Floor |  |  | - |  |  | Gr + 1 Retail + 1st to 49th Floor
J Wing |  | Sale |  | Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | - |  |  | Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 49th Floor
K Wing |  | Sale |  | Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | - |  |  | Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 49th Floor
L Wing |  | Sale |  | Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | - |  |  | Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 49th Floor
M Wing |  | Sale |  | Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | - |  |  | Gr + 1 Retail + 1st + 2nd to 5th Podium/Resi + 8th to 49th Floor
N Wing |  | Sale |  | Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | Gr + 1 Retail + 1st + 2nd to 5th Podium/Resi + 25th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
Approved Layout Details | : | CHE/ES/3092/S/337(NEW)/337/12/Amend |  |  | Date | : | 2024-11-06
Approved Floor Plan Details For Wing N | : | CHE/ES/3092/S/337(NEW)/337/12/Amend |  |  | Date | : | 2024-11-06
CC Details Valid Up to: | : | CHE/ES/3092/S/337(NEW)/FCC/7/Amend Full C.C. is granted for wing 'N' upto 5th floor, Ground & First floor for retail area and re-endorsement of C.C. for wing 'I', ‘'J', 'K’, 'L’, ‘M’ & retail area proposed on Ground & First floor as per approved amended plan dated 14.03.2023 subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  | Date Valid Upto Date | : | 07/07/2023 27/08/2024
Environmental Clearance Details | : |  |  |  | Airport Authority Clearance Details | :
CC Details | : | CHE/ES/3092/S/337(NEW)/FCC/8/Amend Valid Up to: Full C.C. is granted for Wing ‘'J', 'K’, I and N and CC up to 44th upper floors for wing 'L’ & ‘M’ is granted as per approved amended plans dated 14.03.2023 by restricting C.C. of 45th to 47th for wing ‘L’ & ‘M’ for instalment facility subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  | Date: Valid Upto : | : | 28/02/2024 27/02/2025
CC Details Valid Up to: | : | CHE/ES/3092/S/337(NEW)/FCC/9/Amend Further C.C. is granted for Wing ‘I, ‘L’ & ‘M’ upto 47th floor, C.C. for Wing ‘N’ is granted upto 14th upper floors and C.C. is re endorsed for wing ‘J’ & ’K’ as per approved amended plans dated 06.11.2024 by restricting C.C. of 15th to 25th upper floors of wing ‘N’ against instalment facility subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  | Date Valid Upto Date | : | 29/11/2024 27/08/2025
Fire NOC Details | : | CHE/ES/3092/S/337(NEW) Building No. 2 (Wing I to N) = G + 1 st to 5th (Pt) Podium + 8th to 49th Floor (Height = 155.77M) |  |  | Date | : | 07/04/2023
Change of User/Zone Certificate Details | : | -
Construction Status
I Wing - Gr + 1 Retail + 1st to 49th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 19 Floor, Internal Plaster upto 15.2 Floor, External Plaster upto 15.2 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed
|  |  |  | 0 | 2 |  | 0 | 49 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12.25
Excavation |  | 49 |  | 100% | 39.5% |  | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 19 Floor, Internal Plaster upto 15.2 Floor, External Plaster upto 15.2 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed |  | Excavation in process | 24.5
Plinth |  | 49 |  | 100% |  |  |  |  | Excavation Completed | 49
RCC (Including podiums) |  | 21 |  | 41.18% |  |  |  |  | Footing in Process | 12.25
Brickwork |  | 19 |  | 38.78% |  |  |  |  | Footing Completed | 24.5
Internal Plaster |  | 15.2 |  | 31.02% |  |  |  |  | Basement 1 | 0
External Plaster |  | 15.2 |  | 31.02% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 7 |  | 14.29% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 36.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 49 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
J Wing - Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 51 Floor, External Plaster upto 50 Floor, External Plumbing, Elevation and Waterproofing upto 17 Floor, Flooring & Fitting upto 15 Floor Completed
|  |  |  | 0 | 2 |  | 0 | 53 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.25
Excavation |  | 53 |  | 100% | 64.2% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 51 Floor, External Plaster upto 50 Floor, External Plumbing, Elevation and Waterproofing upto 17 Floor, Flooring & Fitting upto 15 Floor Completed |  | Excavation in process | 26.5
Plinth |  | 53 |  | 100% |  |  |  |  | Excavation Completed | 53
RCC (Including podiums) |  | 55 |  | 100% |  |  |  |  | Footing in Process | 13.25
Brickwork |  | 53 |  | 100% |  |  |  |  | Footing Completed | 26.5
Internal Plaster |  | 51 |  | 96.23% |  |  |  |  | Basement 1 | 0
External Plaster |  | 50 |  | 94.34% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 17 |  | 32.08% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 15 |  | 28.3% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 39.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 53 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
K Wing - Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 53 Slab, Brickwork upto 51 Floor, Internal Plaster upto 46 Floor, External Plaster upto 43 Floor, External Plumbing, Elevation and Waterproofing upto 17 Floor, Flooring & Fitting upto 16 Floor Completed
|  |  |  | 0 | 2 |  | 0 | 53 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.25
Excavation |  | 53 |  | 100% | 62.72% |  | Excavation work Completed. Plinth work completed, RCC upto 53 Slab, Brickwork upto 51 Floor, Internal Plaster upto 46 Floor, External Plaster upto 43 Floor, External Plumbing, Elevation and Waterproofing upto 17 Floor, Flooring & Fitting upto 16 Floor Completed |  | Excavation in process | 26.5
Plinth |  | 53 |  | 100% |  |  |  |  | Excavation Completed | 53
RCC (Including podiums) |  | 53 |  | 96.36% |  |  |  |  | Footing in Process | 13.25
Brickwork |  | 51 |  | 96.23% |  |  |  |  | Footing Completed | 26.5
Internal Plaster |  | 46 |  | 86.79% |  |  |  |  | Basement 1 | 0
External Plaster |  | 43 |  | 81.13% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 17 |  | 32.08% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 16 |  | 30.19% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 39.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 53 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
L Wing - Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 20 Slab, Brickwork upto 18 Floor, Internal Plaster upto 14.4 Floor, External Plaster upto 14.4 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed
|  |  |  | 0 | 2 |  | 0 | 53 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.25
Excavation |  | 53 |  | 100% | 37.81% |  | Excavation work Completed. Plinth work completed, RCC upto 20 Slab, Brickwork upto 18 Floor, Internal Plaster upto 14.4 Floor, External Plaster upto 14.4 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed |  | Excavation in process | 26.5
Plinth |  | 53 |  | 100% |  |  |  |  | Excavation Completed | 53
RCC (Including podiums) |  | 20 |  | 36.36% |  |  |  |  | Footing in Process | 13.25
Brickwork |  | 18 |  | 33.96% |  |  |  |  | Footing Completed | 26.5
Internal Plaster |  | 14.4 |  | 27.17% |  |  |  |  | Basement 1 | 0
External Plaster |  | 14.4 |  | 27.17% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 7 |  | 13.21% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 39.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 53 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
M Wing - Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 7 Floor, Internal Plaster upto 6.3 Floor, External Plaster upto 6.3 Floor, External Plumbing, Elevation and Waterproofing upto 6 Floor Completed
|  |  |  | 0 | 2 |  | 0 | 53 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.25
Excavation |  | 53 |  | 100% | 30.91% |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 7 Floor, Internal Plaster upto 6.3 Floor, External Plaster upto 6.3 Floor, External Plumbing, Elevation and Waterproofing upto 6 Floor Completed |  | Excavation in process | 26.5
Plinth |  | 53 |  | 100% |  |  |  |  | Excavation Completed | 53
RCC (Including podiums) |  | 9 |  | 16.36% |  |  |  |  | Footing in Process | 13.25
Brickwork |  | 7 |  | 13.21% |  |  |  |  | Footing Completed | 26.5
Internal Plaster |  | 6.3 |  | 11.89% |  |  |  |  | Basement 1 | 0
External Plaster |  | 6.3 |  | 11.89% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 6 |  | 11.32% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 39.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 53 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
N Wing - Gr + 1 Retail + 1st + 2nd to 7th Podium/Resi + 8th to 53rd Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7.2 Floor, External Plaster upto 7.2 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed
|  |  |  | 0 | 2 |  | 0 | 53 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.25
Excavation |  | 53 |  | 100% | 32.19% |  | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7.2 Floor, External Plaster upto 7.2 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed |  | Excavation in process | 26.5
Plinth |  | 53 |  | 100% |  |  |  |  | Excavation Completed | 53
RCC (Including podiums) |  | 11 |  | 20% |  |  |  |  | Footing in Process | 13.25
Brickwork |  | 9 |  | 16.98% |  |  |  |  | Footing Completed | 26.5
Internal Plaster |  | 7.2 |  | 13.58% |  |  |  |  | Basement 1 | 0
External Plaster |  | 7.2 |  | 13.58% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 7 |  | 13.21% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 39.75
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 53 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 44.55%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 25500 to 26500
Car Parking Charges |  |  | : | 800000 | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 3717.95
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 9750.87
Distress Value (Rs. Per sqft) | [5 empty] | : | 2974.36
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area
Wing N |  | - |  | Shops | 2 |  | 1085.4081
|  | - |  | - | 2 |  | 1085.4081
|  | - |  | Flats | 119 |  | 58246.2752
Total |  | - |  | - | 119 |  | 58246.2752
Grand Total |  | - |  | - | 121 |  | 59331.6833
Details of Flats in Building
Flat/Shop No. |  | Description |  | Net carpet | Fungible Area |  | Attached Terrace area | Gross Carpet area | 10.764
Wing N
1st & 2nd Basement Floor for Parking
Ground Floor For Commercial, Entrance Lobby, Meter Room & Parking
49 |  | Shop |  | 694.8095 | 0 |  | 0 | 694.8095
50 |  | Shop |  | 390.5986 | 0 |  | 0 | 390.5986
Retail 1 Floor For Commercial
1st Floor For Residential & Podium Parking | [8 empty] | 1
1 |  | 2.5BHK |  | 613.7902 | 0 | 0 | 0 | 613.7902 |  |  |  | 101,..,101 | 101 | 101
2 |  | 2.5BHK |  | 613.7902 | 0 | 0 | 0 | 613.7902 |  |  |  | 102,..,102 | 102 | 102
3 |  | - |  | Podium Parking | [7 empty] | 103,..,103 | 103 | 103
4 |  | - | [9 empty] | 104,..,104 | 104 | 104
5 |  | - | [9 empty] | 105,..,105 | 105 | 105
6 |  | - | [9 empty] | 106,..,106 | 106 | 106
2nd to 5th & 7th Floor Residential & Podium Parking | [8 empty] | 5
1 |  | 2.5BHK |  | 613.7902 | 0 | 0 | 0 | 613.7902 |  |  |  | 201,..,701 | 201 | 701
2 |  | 2.5BHK |  | 613.7902 | 0 | 0 | 0 | 613.7902 |  |  |  | 202,..,702 | 202 | 702
3 |  | - |  | Podium Parking | [7 empty] | 203,..,703 | 203 | 703
4 |  | - | [9 empty] | 204,..,704 | 204 | 704
5 |  | - | [9 empty] | 205,..,705 | 205 | 705
6 |  | - | [9 empty] | 206,..,706 | 206 | 706
6th Floor For Residential & Podium Parking (Part Refuge Area) | [8 empty] | 1
1 |  | - |  | Refuge Area | [7 empty] | #REF! | #REF! | 601
2 |  | 2.5BHK |  | 613.7902 | 0 | 0 | 0 | 613.7902 |  |  |  | #REF! | #REF! | 602
3 |  | - |  | Parking | [7 empty] | #REF! | #REF! | 603
4 |  | - | [9 empty] | #REF! | #REF! | 604
5 |  | - | [9 empty] | #REF! | #REF! | 605
6 |  | - | [9 empty] | #REF! | #REF! | 606
8th to 12th, 14th to 19th & 21st to 25th Floor | [8 empty] | 16
1 |  | 2.5BHK |  | 613.7902 | 0 | 0 | 0 | 613.7902 |  |  |  | 801,..,2501 | 801 | 2501
2 |  | 2.5BHK |  | 613.7902 | 0 | 0 | 0 | 613.7902 |  |  |  | 802,..,2502 | 802 | 2502
3 |  | 1.5BHK |  | 442.7516 | 0 | 0 | 0 | 442.7516 |  |  |  | 803,..,2503 | 803 | 2503
4 |  | 1BHK |  | 373.8633 | 0 | 0 | 0 | 373.8633 |  |  |  | 804,..,2504 | 804 | 2504
5 |  | 1BHK |  | 373.8633 | 0 | 0 | 0 | 373.8633 |  |  |  | 805,..,2505 | 805 | 2505
6 |  | 1.5BHK |  | 442.7516 | 0 | 0 | 0 | 442.7516 |  |  |  | 806,..,2506 | 806 | 2506
13th & 20th Floor For Residential (Part Refuge Area) | [8 empty] | 2
1 |  | - |  | Refuge Area | [7 empty] | 1301,..,2001 | 1301 | 2001
2 |  | 2.5BHK |  | 613.7902 | 0 | 0 | 0 | 613.7902 |  |  |  | 1302,..,2002 | 1302 | 2002
3 |  | 1.5BHK |  | 442.7516 | 0 | 0 | 0 | 442.7516 |  |  |  | 1303,..,2003 | 1303 | 2003
4 |  | 1BHK |  | 373.8633 | 0 | 0 | 0 | 373.8633 |  |  |  | 1304,..,2004 | 1304 | 2004
5 |  | 1BHK |  | 373.8633 | 0 | 0 | 0 | 373.8633 |  |  |  | 1305,..,2005 | 1305 | 2005
6 |  | 1.5BHK |  | 442.7516 | 0 | 0 | 0 | 442.7516 |  |  |  | 1306,..,2006 | 1306 | 2006
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Wing I, K & N = Construction work is in process at the time of Visit. Internal Visit was not allowed. Wing J & L = Construction work is in process at the time of Visit. Internal Visit was not allowed (Slow speed). Wing M = Construction work is same as last visit dtd. 09/06/2025 but work is in process. (Slow speed). 2. We have considered rate by verifying it from market inquire. 3. Car parking is subjected to authentic documentation. 4. Type of construction used Mivan Construction. 5. High voltage wires passing between Building No. 1 (F Wing) & Building No. 3 (G Wing). As shown in Layout Page No. 6 6. We have updated revised approved CC from MCGM site on 14/11/2024. 7. We have updated revised approved CC from MCGM site on 04/12/2024. 8. We have updated Wing N (on 07/05/2025). 6. On Site, we meet Mr. Chandan - 8879688457. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Runwal Avenue Wing I to N
Project Site Address |  |  | : | Runwal Avenue (Wing I, J, K, L, M & N), CTS No. as per CC.1004, 1005, 1005/1, 1006, 1007(pt), 1007/3(pt), 1007/4, 1009(pt), 1009/5, 1009/6, 1010(pt), 1013(pt), 1014(pt), 1014/1 to 16, 1017, 1017/1 to 6, 1018 and 1018/1 to 9, near NG Royal Park, Kanjur Village Road, Kanjur, Datar Colony, Kanjurmarg East, Kurla, Mumbai - 400042.
Site Visit Date & Time |  |  | : | 07/08/2025 at 01:12PM
Location Plan
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Nainesh Tambe | Authorized Signatory Name & Signature | :
Railway Track
Wing I
Wing J
Wing K
Wing L
Wing M
High Voltage Line
Building No 2
Wing I to M
N Wing
Tower N
Tower K
Tower I
Wing N
Tower J
Tower M
Tower L
Tower J
Tower I
Tower J
Tower K
Tower L
Tower M
Tower N
Wing I
Wing J
Wing K
Wing L
Wing M
Wing N