## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-05 | 2025-08-02 |  | 2025-05-05
Project Name |  |  | : | Godrej Horizon Phase I Tower 1 (A & B Wing) Godrej Horizon Phase II Tower 2 (A & B Wing) Godrej Horizon Phase III Tower 3 (A & B Wing) |  | Date & Time of Site Visit |  | 02/08/2025 at 05:19PM | 89 | Godrej Horizon Phase I & II
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 07/08/2025 |  |  | 2025-02-17 |  | 169
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Gaurav Pawar
Builder Group Name |  |  | : | Godrej Projects Development Ltd | Developer Name | : | Godrej Projects Development Ltd
Developer Office Address |  |  | : | 5th Floor, Building Name - Godrej One, Street Name - Pirojshanagar, Locality - Vikhroli East, Land mark - Eastern Express Highway
Project Address | : | As per ARF | : | Godrej Horizon Phase 1, Phase 2 & Phase 3, Azad Nagar, Dadar Naigaon Division, Road: Rafi Ahmed Kidwai Road, Near - Vijay Niwas, Wadala (W), Mumbai - 31.
| : | As per Legal Documents | : | Proposed Redevelopment Of Propoerty Known As Azad Nagar, Bearing C.T.S. No.437(pt) ,335(pt) ,338(pt),339(pt), 340(pt),341(pt), 342(pt), 346(pt), 347(pt), 348(pt), 350(pt), 351(pt), 352(pt), 353(pt), 354(pt), 355(pt), 356 (Pt), Wadala (W), Mumbai - 31.
| : | As per Actual at site | : | Godrej Horizon Phase 1, Phase 2 & Phase 3, Azad Nagar, Dadar Naigaon Division, Road: Rafi Ahmed Kidwai Road, Near - Vijay Niwas, Wadala (W), Mumbai - 31.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation Of Greater Mumbai
RERA Registration No. | : | Phase I = P51900034851 Phase II = P51900049757 Phase III = P51900078358 |  |  | RERA Registration Validity | : | Phase I = 31/05/2028 Phase II = 30/06/2029 Phase III = 30/06/2031
Project Launch Date | : | 31-03-2022 Phase III - 06/12/2024 |  |  | Construction Start Date | : | 2022-12-01
Proposed Date of Completion (As per RERA) | : | Phase I = 31/05/2028 Phase II = 30/06/2029 Phase III = 30/06/2031 |  |  | Developer Bank Name (As per RERA) | : | Phase I = Axis Bank IFSC Code - UTIB0004702 Phase II = Axis Bank IFSC Code - UTIB0000004 Phase III = Axis Bank IFSC Code - UTIB0001394
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 30443
FSI/FAR Permissible | : | 3.6 |  |  | Proposed Built up Area (In Sq.Mt) | : | 147870.63 |  | 107709.61
Permissible Built up Area (In Sq.Mt) | : | 134460.41 |  |  | Total Number of Units Planned | : | As per RERA Site - Flats = 1076 |  | 235 | 157
Total Number of Units Approved | : | Flats = 1114 |  |  | If Mixed, No. of Commercial Units | : | Shop = NA |  | 235 | 195 |  | 822
Latitude, Longitude | : | 19.013841,72.856418
Location Link | : | https://goo.gl/maps/tnkAUbrzDFsiPZUq6
Extra Amenities available | : | Walkway, Terraced Pool, Gym, Kids Playing Area, Chess Court, Jogging Track, Green Surrounding, Badminton Court | [8 empty] | 200 |  | 157 | 1076
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Upper |  |  |  | 1184
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 850 M from Wadala Station Bus Stop
Distance from the nearest School (Km) | : | About 1 KM from St. Joseph's High School |  |  | Distance from Hospital (Km) | : | About 2.3KM form Mumbai Port Trust Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.8KM from Gurunanak Market. |  |  | Distance from Railway Station (Km) | : | 500 M from Wadala Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Internal Road | Slum Access Road | Internal Road |  | Internal Road
As per Site / Actual |  |  | : | Rafi Ahmed Kidwai Road | Railway Track | Pardhandas House |  | Amardeep Building
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower 1 (Wing A & B) |  | Sale |  | B + G + 1st to 44th Floor |  |  | B + G + 1st to 44th Floor
Tower 2 (Wing A & B) |  | Sale |  | B + G + 1st to 44th Floor |  |  | B + G + 1st to 44th Floor
Tower 3 (Wing A & B) |  | Sale |  | B + G + 1st to 44th Floor |  |  | B + G + 1st to 40th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | P-9221/2021/(354 And Other)/ F /North/DADAR-NAIGAON/337/6/Amend |  |  | Date |  | 2024-11-14
Approved Plan Details | : | P-9221/2021/(354 And Other)/ F /North/DADAR-NAIGAON/337/6/Amend |  |  | Date |  | 2024-11-14
CC Details | : | P-9221/2021/(354 And Other)/F/North/DADARNAIGAON/FCC/3/Amend |  |  | Date | : | 2025-05-20
Valid Up to: | : | THIS FURTHER C. C. IS EXTENDED UPTO TOP OF 44TH FLOOR FOR WING ‘A’ AND WING ‘B’ OF SALE TOWER 1 INCLUDING OHT & LIFT MACHINE ROOM AS PER LAST APPROVED PLAN DATED. 14.11.2024 SUBJECT TO TAKING ALL PREECAUTIONS DURING CONSTRUCTION IN REGARDS OF AIR POLUTION GUIDLINES ISSUED U/NO. MGC/F/1102 DTD. 25.10.2023 AND D.O.NO. CAP-2023/CR-170/TC-2 DTD. 27.10.2023. |  |  | Date Valid Up to | : | 2026-03-31
CC Details | : | P-9221/2021/(354 And Other)/F/North/DADAR-NAIGAON/CC/3/Amend |  |  | Date | : | 2024-11-28
Valid Up to: | : | Valid Up to: Plinth CC for Sale Tower-3 Wing A and B as per approved plan dated 14/11/2024 |  |  | Date Valid Up to | : | 2025-11-27
Fire Noc Details | : | P-9221/2021(354 And Other)/F/North/DADAR - NAIGAON/CFO/3/Amend |  |  | Date | : | 2024-10-08
| : | Tower 1 (Wing A & B) = B + G + 1st to 44th Floor (Height = 143.95m) Tower 2 (Wing A & B) = B + G + 1st to 44th Floor (Height = 144.25m) Tower 3 (Wing A & B) = B + G + 1st to 40th + 41st (part) Floor (Height = 134.50m)
Airport Authority Clearance Details | : | SNCR/WEST/B/110221/633317 |  |  | Date | : | 2021-12-21
| : |  |  |  | Valid Up to Date | :
Railway NOC Details | : | BB/W/6561/NOC/VDLR/1325/DB |  |  | Date | : | 2023-03-16
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
Construction Status
Tower 1 (Wing A & B) = B + G + 1st to 44th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 40 Slab, Brickwork upto 39 Floor, Internal Plaster upto 31.2 Floor, External Plaster upto 31.2 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 44 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11
Excavation |  | 44 |  | 100% | 55.2% |  | Excavation work Completed. Plinth work completed, RCC upto 40 Slab, Brickwork upto 39 Floor, Internal Plaster upto 31.2 Floor, External Plaster upto 31.2 Floor Completed |  | Excavation in process | 22
Plinth |  | 44 |  | 100% |  |  |  |  | Excavation Completed | 44
RCC (Including podiums) |  | 40 |  | 88.89% |  |  |  |  | Footing in Process | 11
Brickwork |  | 39 |  | 88.64% |  |  |  |  | Footing Completed | 22
Internal Plaster |  | 31.2 |  | 70.91% |  |  |  |  | Basement 1 | 0
External Plaster |  | 31.2 |  | 70.91% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 33
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 44
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 1 (Wing B) = B + G + 1st to 44th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 20.8 Floor, External Plaster upto 20.8 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 44 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11
Excavation |  | 44 |  | 100% | 45.32% |  | Excavation work Completed. Plinth work completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 20.8 Floor, External Plaster upto 20.8 Floor Completed |  | Excavation in process | 22
Plinth |  | 44 |  | 100% |  |  |  |  | Excavation Completed | 44
RCC (Including podiums) |  | 27 |  | 60% |  |  |  |  | Footing in Process | 11
Brickwork |  | 26 |  | 59.09% |  |  |  |  | Footing Completed | 22
Internal Plaster |  | 20.8 |  | 47.27% |  |  |  |  | Basement 1 | 0
External Plaster |  | 20.8 |  | 47.27% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 33
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 44
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 2 (Wing A & B) = B + G + 1st to 44th Floor |  |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 13 Slab, Brickwork upto 12 Floor, Internal Plaster upto 9.6 Floor, External Plaster upto 9.6 Floor Completed
|  |  |  | 1 | 1 |  | 0 | 44 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11
Excavation |  | 44 |  | 100% | 34.68% |  | Excavation work Completed. Plinth work completed, RCC upto 13 Slab, Brickwork upto 12 Floor, Internal Plaster upto 9.6 Floor, External Plaster upto 9.6 Floor Completed |  | Excavation in process | 22
Plinth |  | 44 |  | 100% |  |  |  |  | Excavation Completed | 44
RCC (Including podiums) |  | 13 |  | 28.89% |  |  |  |  | Footing in Process | 11
Brickwork |  | 12 |  | 27.27% |  |  |  |  | Footing Completed | 22
Internal Plaster |  | 9.6 |  | 21.82% |  |  |  |  | Basement 1 | 0
External Plaster |  | 9.6 |  | 21.82% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 33
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 44
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 3 (Wing A & B) = B + G + 1st to 44th Floor |  |  |  | Basement | Ground |  | Podium | Floors | Work not yet Started.
|  |  |  | 1 | 1 |  | 0 | 44 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11
Excavation |  | 0 |  | 0% | 0% |  | Work not yet Started. |  | Excavation in process | 22
Plinth |  | 0 |  | 0% |  |  |  |  | Excavation Completed | 44
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 11
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 22
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 33
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 44
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 38.08%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 44000 to 45000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | Rs.100/- from 10th Floor |  | (Rate Revised 40000 to 49500 & Floor Rise As discussed with Gaurav sir on date 25/12/2024) (Rate Revised 44000 to 45000 as per mail in unit report GHF1004HL0036358 Ankita on 13/01/2025)
Car Parking Charges |  |  | : | 1000000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 5209.9591
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 10103.1215
Distress Value (Rs. Per sqft) | [5 empty] | : | 4167.9673
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Tower 1 Wing A |  | Sale |  | Flats | 200 |  | 165538.372 | 264861.3951
Tower 1 Wing B |  | Sale |  | Flats | 200 |  | 165371.4223 | 264594.2757
Tower 2 Wing A |  | Sale |  | Flats | 157 |  | 151591.6789 | 242546.6862
Tower 2 Wing B |  | Sale |  | Flats | 195 |  | 198486.3301 | 317578.1282
Tower 3 Wing A |  | Sale |  | Flats | 181 |  | 147196.6236 | 235514.5978 | 181
Tower 3 Wing B |  | Sale |  | Flats | 181 |  | 147196.6236 | 235514.5978
Total |  | - |  | - | 1114 |  | 975381.0505 | 1560609.6808
Details of Flats in Building
Floors |  | Flat/Shop No. As per Approved Plan |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
Phase I
Tower 1 Wing A
Basement For Tanks
Ground Floor For Parking
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 2BHK | 651.5449 |  | 0 | 1042.4719 | 38370.3398
|  | 2 |  | 2BHK | 657.6804 |  | 0 | 1052.2886
|  | 3 |  | Double Height Entrance
4
5
2nd Floor
2nd Floor |  | 1 |  | 2BHK | 651.5449 |  | 0 | 1042.4719
|  | 2 |  | 2BHK | 657.6804 |  | 0 | 1052.2886
|  | 3 |  | Void
4
5
3rd to 6th Floor
3rd to 6th Floor |  | 1 |  | 2BHK | 651.5449 |  | 0 | 1042.4719
|  | 2 |  | 2BHK | 657.6804 |  | 0 | 1052.2886
|  | 3 |  | Void
4
|  | 5 |  | 1BHK | 494.7134 |  | 0 | 791.5415
7th Floor (Part Refuge Area)
7th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | #REF! | #REF! | 701
|  | 2 |  | 2BHK | 659.0797 |  | 0 | 1054.5276 | [6 empty] | #REF! | #REF! | 702
|  | 3 |  | 2BHK | 695.5697 |  | 0 | 1112.9115 | [6 empty] | #REF! | #REF! | 703
|  | 4 |  | 3BHK | 1007.8333 |  | 0 | 1612.5333 | [6 empty] | #REF! | #REF! | 704
|  | 5 |  | Refuge Area | [10 empty] | #REF! | #REF! | 705
8th to 13th & 15th to 20th Floor
8th to 13th & 15th to 20th Floor |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 801,..,2001 | 801 | 2001
|  | 2 |  | 2BHK | 659.0797 |  | 0 | 1054.5276 | [6 empty] | 802,..,2002 | 802 | 2002
|  | 3 |  | 2BHK | 695.5697 |  | 0 | 1112.9115 | [6 empty] | 803,..,2003 | 803 | 2003
|  | 4 |  | 3BHK | 1007.8333 |  | 0 | 1612.5333 | [6 empty] | 804,..,2004 | 804 | 2004
|  | 5 |  | 3BHK | 1172.6302 |  | 0 | 1876.2083 | [6 empty] | 805,..,2005 | 805 | 2005
14th Floor (Part Refuge Area)
14th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 101,..,1401 | 101 | 1401
|  | 2 |  | 2BHK | 659.0797 |  | 0 | 1054.5276 | [6 empty] | 102,..,1402 | 102 | 1402
|  | 3 |  | 2BHK | 695.5697 |  | 0 | 1112.9115 | [6 empty] | 103,..,1403 | 103 | 1403
|  | 4 |  | 3BHK | 1007.8333 |  | 0 | 1612.5333 | [6 empty] | 104,..,1404 | 104 | 1404
|  | 5 |  | Refuge Area | [10 empty] | 105,..,1405 | 105 | 1405
21st Floor (Part Refuge Area)
21st Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 2101,..,2101 | 2101 | 2101
|  | 2 |  | 2BHK | 660.6943 |  | 0 | 1057.1109 | [6 empty] | 2102,..,2102 | 2102 | 2102
|  | 3 |  | 2BHK | 697.1843 |  | 0 | 1115.4948 | [6 empty] | 2103,..,2103 | 2103 | 2103
|  | 4 |  | 3BHK | 1011.1702 |  | 0 | 1617.8723 | [6 empty] | 2104,..,2104 | 2104 | 2104
|  | 5 |  | Refuge Area | [10 empty] | 2105,..,2105 | 2105 | 2105
22nd to 24th Floor
22nd to 24th Floor |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 2201,..,2401 | 2201 | 2401
|  | 2 |  | 2BHK | 660.6943 |  | 0 | 1057.1109 | [6 empty] | 2202,..,2402 | 2202 | 2402
|  | 3 |  | 2BHK | 697.1843 |  | 0 | 1115.4948 | [6 empty] | 2203,..,2403 | 2203 | 2403
|  | 4 |  | 3BHK | 1011.1702 |  | 0 | 1617.8723 | [6 empty] | 2204,..,2404 | 2204 | 2404
|  | 5 |  | 3BHK | 1173.8142 |  | 0 | 1878.1027 | [6 empty] | 2205,..,2405 | 2205 | 2405
25th to 27th, 29th & 30th Floor
25th to 27th, 29th & 30th Floor |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 2501,..,3001 | 2501 | 3001
|  | 2 |  | 2BHK | 696.8614 |  | 0 | 1114.9782 | [6 empty] | 2502,..,3002 | 2502 | 3002
|  | 3 |  | 2BHK | 697.1843 |  | 0 | 1115.4948 | [6 empty] | 2503,..,3003 | 2503 | 3003
|  | 4 |  | 3BHK | 1011.1702 |  | 0 | 1617.8723 | [6 empty] | 2504,..,3004 | 2504 | 3004
|  | 5 |  | 3BHK | 1173.8142 |  | 0 | 1878.1027 | [6 empty] | 2505,..,3005 | 2505 | 3005
28th Floor (Part Refuge Area)
28th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 201,..,2801 | 201 | 2801
|  | 2 |  | 2BHK | 696.8614 |  | 0 | 1114.9782 | [6 empty] | 202,..,2802 | 202 | 2802
|  | 3 |  | 2BHK | 697.1843 |  | 0 | 1115.4948 | [6 empty] | 203,..,2803 | 203 | 2803
|  | 4 |  | 3BHK | 1011.1702 |  | 0 | 1617.8723 | [6 empty] | 204,..,2804 | 204 | 2804
|  | 5 |  | Refuge Area | [10 empty] | 205,..,2805 | 205 | 2805
31st to 34th, 36th to 41st, 43rd & 44th Floor
31st to 34th, 36th to 41st, 43rd & 44th Floor |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 3101,..,4401 | 3101 | 4401
|  | 2 |  | 2BHK | 698.9065 |  | 0 | 1118.2504 | [6 empty] | 3102,..,4402 | 3102 | 4402
|  | 3 |  | 2BHK | 699.2294 |  | 0 | 1118.7671 | [6 empty] | 3103,..,4403 | 3103 | 4403
|  | 4 |  | 3BHK | 1032.3752 |  | 0 | 1651.8004 |  | 1146.7966 |  |  |  |  | 3104,..,4404 | 3104 | 4404
|  | 5 |  | 3BHK | 1174.9982 |  | 0 | 1879.9972 | [6 empty] | 3105,..,4405 | 3105 | 4405
35th Floor (Part Refuge Area)
35th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 301,..,3501 | 301 | 3501
|  | 2 |  | 2BHK | 698.9065 |  | 0 | 1118.2504 | [6 empty] | 302,..,3502 | 302 | 3502
|  | 3 |  | 2BHK | 699.2294 |  | 0 | 1118.7671 | [6 empty] | 303,..,3503 | 303 | 3503
|  | 4 |  | 3BHK | 1032.3752 |  | 0 | 1651.8004 | [6 empty] | 304,..,3504 | 304 | 3504
|  | 5 |  | Refuge Area | [10 empty] | 305,..,3505 | 305 | 3505
42nd Floor (Part Refuge Area)
42nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 401,..,4201 | 401 | 4201
|  | 2 |  | Refuge Area | [10 empty] | 402,..,4202 | 402 | 4202
|  | 3 |  | 2BHK | 699.2294 |  | 0 | 1118.7671 | [6 empty] | 403,..,4203 | 403 | 4203
|  | 4 |  | 3BHK | 1032.3752 |  | 0 | 1651.8004 | [6 empty] | 404,..,4204 | 404 | 4204
|  | 5 |  | 3BHK | 1174.9982 |  | 0 | 1879.9972 | [6 empty] | 405,..,4205 | 405 | 4205
Tower 1 Wing B
Basement For Tanks
Ground Floor For Parking
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 2BHK | 651.5449 |  | 0 | 1042.4719 | 38370.3398
|  | 2 |  | 2BHK | 657.6804 |  | 0 | 1052.2886
|  | 3 |  | Double Height Entrance
4
5
2nd Floor
2nd Floor |  | 1 |  | 2BHK | 651.5449 |  | 0 | 1042.4719
|  | 2 |  | 2BHK | 657.6804 |  | 0 | 1052.2886
|  | 3 |  | Void
4
5
3rd to 6th Floor
3rd to 6th Floor |  | 1 |  | 2BHK | 651.5449 |  | 0 | 1042.4719
|  | 2 |  | 2BHK | 657.6804 |  | 0 | 1052.2886
|  | 3 |  | Void
4
|  | 5 |  | 1BHK | 494.7134 |  | 0 | 791.5415
7th Floor (Part Refuge Area)
7th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | #REF! | #REF! | 701
|  | 2 |  | 2BHK | 659.0797 |  | 0 | 1054.5276 | [6 empty] | #REF! | #REF! | 702
|  | 3 |  | 2BHK | 695.5697 |  | 0 | 1112.9115 | [6 empty] | #REF! | #REF! | 703
|  | 4 |  | 3BHK | 1007.8333 |  | 0 | 1612.5333 | [6 empty] | #REF! | #REF! | 704
|  | 5 |  | Refuge Area | [10 empty] | #REF! | #REF! | 705
8th to 13th & 15th to 20th Floor
8th to 13th & 15th to 20th Floor |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 801,..,2001 | 801 | 2001
|  | 2 |  | 2BHK | 659.0797 |  | 0 | 1054.5276 | [6 empty] | 802,..,2002 | 802 | 2002
|  | 3 |  | 2BHK | 695.5697 |  | 0 | 1112.9115 | [6 empty] | 803,..,2003 | 803 | 2003
|  | 4 |  | 3BHK | 1007.8333 |  | 0 | 1612.5333 | [6 empty] | 804,..,2004 | 804 | 2004
|  | 5 |  | 3BHK | 1167.5711 |  | 0 | 1868.1137 | [6 empty] | 805,..,2005 | 805 | 2005
14th Floor (Part Refuge Area)
14th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 101,..,1401 | 101 | 1401
|  | 2 |  | 2BHK | 659.0797 |  | 0 | 1054.5276 | [6 empty] | 102,..,1402 | 102 | 1402
|  | 3 |  | 2BHK | 695.5697 |  | 0 | 1112.9115 | [6 empty] | 103,..,1403 | 103 | 1403
|  | 4 |  | 3BHK | 1007.8333 |  | 0 | 1612.5333 | [6 empty] | 104,..,1404 | 104 | 1404
|  | 5 |  | Refuge Area | [10 empty] | 105,..,1405 | 105 | 1405
21st Floor (Part Refuge Area)
21st Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 2101,..,2101 | 2101 | 2101
|  | 2 |  | 2BHK | 660.6943 |  | 0 | 1057.1109 | [6 empty] | 2102,..,2102 | 2102 | 2102
|  | 3 |  | 2BHK | 697.1843 |  | 0 | 1115.4948 | [6 empty] | 2103,..,2103 | 2103 | 2103
|  | 4 |  | 3BHK | 1011.1702 |  | 0 | 1617.8723 | [6 empty] | 2104,..,2104 | 2104 | 2104
|  | 5 |  | Refuge Area | [10 empty] | 2105,..,2105 | 2105 | 2105
22nd to 24th Floor
22nd to 24th Floor |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 2201,..,2401 | 2201 | 2401
|  | 2 |  | 2BHK | 660.6943 |  | 0 | 1057.1109 | [6 empty] | 2202,..,2402 | 2202 | 2402
|  | 3 |  | 2BHK | 697.1843 |  | 0 | 1115.4948 | [6 empty] | 2203,..,2403 | 2203 | 2403
|  | 4 |  | 3BHK | 1011.1702 |  | 0 | 1617.8723 | [6 empty] | 2204,..,2404 | 2204 | 2404
|  | 5 |  | 3BHK | 1168.7551 |  | 0 | 1870.0082 | [6 empty] | 2205,..,2405 | 2205 | 2405
25th to 27th, 29th & 30th Floor
25th to 27th, 29th & 30th Floor |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 2501,..,3001 | 2501 | 3001
|  | 2 |  | 2BHK | 696.8614 |  | 0 | 1114.9782 | [6 empty] | 2502,..,3002 | 2502 | 3002
|  | 3 |  | 2BHK | 697.1843 |  | 0 | 1115.4948 | [6 empty] | 2503,..,3003 | 2503 | 3003
|  | 4 |  | 3BHK | 1011.1702 |  | 0 | 1617.8723 | [6 empty] | 2504,..,3004 | 2504 | 3004
|  | 5 |  | 3BHK | 1168.7551 |  | 0 | 1870.0082 | [6 empty] | 2505,..,3005 | 2505 | 3005
28th Floor (Part Refuge Area)
28th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 201,..,2801 | 201 | 2801
|  | 2 |  | 2BHK | 696.8614 |  | 0 | 1114.9782 | [6 empty] | 202,..,2802 | 202 | 2802
|  | 3 |  | 2BHK | 697.1843 |  | 0 | 1115.4948 | [6 empty] | 203,..,2803 | 203 | 2803
|  | 4 |  | 3BHK | 1011.1702 |  | 0 | 1617.8723 | [6 empty] | 204,..,2804 | 204 | 2804
|  | 5 |  | Refuge Area | [10 empty] | 205,..,2805 | 205 | 2805
31st to 34th, 36th to 41st, 43rd & 44th Floor
31st to 34th, 36th to 41st, 43rd & 44th Floor |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 3101,..,4401 | 3101 | 4401
|  | 2 |  | 2BHK | 698.9065 |  | 0 | 1118.2504 | [6 empty] | 3102,..,4402 | 3102 | 4402
|  | 3 |  | 2BHK | 699.2294 |  | 0 | 1118.7671 | [6 empty] | 3103,..,4403 | 3103 | 4403
|  | 4 |  | 3BHK | 1032.3752 |  | 0 | 1651.8004 |  | 1146.7966 |  |  |  |  | 3104,..,4404 | 3104 | 4404
|  | 5 |  | 3BHK | 1169.9392 |  | 0 | 1871.9027 | [6 empty] | 3105,..,4405 | 3105 | 4405
35th Floor (Part Refuge Area)
35th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 301,..,3501 | 301 | 3501
|  | 2 |  | 2BHK | 698.9065 |  | 0 | 1118.2504 | [6 empty] | 302,..,3502 | 302 | 3502
|  | 3 |  | 2BHK | 699.2294 |  | 0 | 1118.7671 | [6 empty] | 303,..,3503 | 303 | 3503
|  | 4 |  | 3BHK | 1032.3752 |  | 0 | 1651.8004 | [6 empty] | 304,..,3504 | 304 | 3504
|  | 5 |  | Refuge Area | [10 empty] | 305,..,3505 | 305 | 3505
42nd Floor (Part Refuge Area)
42nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 701.4899 |  | 0 | 1122.3838 | [6 empty] | 401,..,4201 | 401 | 4201
|  | 2 |  | Refuge Area | [10 empty] | 402,..,4202 | 402 | 4202
|  | 3 |  | 2BHK | 699.2294 |  | 0 | 1118.7671 | [6 empty] | 403,..,4203 | 403 | 4203
|  | 4 |  | 3BHK | 1032.3752 |  | 0 | 1651.8004 | [6 empty] | 404,..,4204 | 404 | 4204
|  | 5 |  | 3BHK | 1169.9392 |  | 0 | 1871.9027 | [6 empty] | 405,..,4205 | 405 | 4205
Phase II
Tower 2
Wing A
Basement For Tanks & Pump Room
Ground Floor For Society Office, Meter Room, Substation & Entrance Lobby
1st Floor For Residential
1st Floor For Residential |  | 1 |  | Void | [5 empty] | 63.047 |  |  |  |  | 101,..,101 | 101 | 101
|  | 2 |  | 4BHK | 1206.8597 |  | 0 | 1930.9755 |  | 3.721 |  |  |  |  | 102,..,102 | 102 | 102
|  | 3 |  | Void | [5 empty] | 1.5364 |  |  |  |  | 103,..,103 | 103 | 103
|  | 4 | [7 empty] | 68.3044 |  |  |  |  | 104,..,104 | 104 | 104
2nd Floor
2nd Floor |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | 201,..,201 | 201 | 201
|  | 2 |  | 3BHK | 932.27 |  | 0 | 1491.6321 | [6 empty] | 202,..,202 | 202 | 202
|  | 3 |  | Void | [10 empty] | 203,..,203 | 203 | 203
|  | 4 | [12 empty] | 204,..,204 | 204 | 204
3rd to 6th Floor
3rd to 6th Floor |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | 301,..,601 | 301 | 601
|  | 2 |  | 3BHK | 932.27 |  | 0 | 1491.6321 | [6 empty] | 302,..,602 | 302 | 602
|  | 3 |  | Void | [10 empty] | 303,..,603 | 303 | 603
|  | 4 | [12 empty] | 304,..,604 | 304 | 604
7th Floor (Part Refuge Area)
7th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | #REF! | #REF! | 701
|  | 2 |  | 3BHK | 939.4819 |  | 0 | 1503.1711 | [6 empty] | #REF! | #REF! | 702
|  | 3 |  | 3BHK | 1373.8093 |  | 0 | 2198.0949 | [6 empty] | #REF! | #REF! | 703
|  | 4 |  | Refuge Area | [10 empty] | #REF! | #REF! | 704
8th to 13th & 15th to 20th Floor
8th to 13th & 15th to 20th Floor |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | 801,..,2001 | 801 | 2001
|  | 2 |  | 3BHK | 939.4819 |  | 0 | 1503.1711 | [6 empty] | 802,..,2002 | 802 | 2002
|  | 3 |  | 3BHK | 1373.8093 |  | 0 | 2198.0949 | [6 empty] | 803,..,2003 | 803 | 2003
|  | 4 |  | 2BHK | 794.0603 |  | 0 | 1270.4964 | [6 empty] | 804,..,2004 | 804 | 2004
14th Floor (Part Refuge Area)
14th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | 101,..,1401 | 101 | 1401
|  | 2 |  | 3BHK | 939.4819 |  | 0 | 1503.1711 | [6 empty] | 102,..,1402 | 102 | 1402
|  | 3 |  | 3BHK | 1373.8093 |  | 0 | 2198.0949 | [6 empty] | 103,..,1403 | 103 | 1403
|  | 4 |  | Refuge Area | [10 empty] | 104,..,1404 | 104 | 1404
22nd to 27th, 29th & 30th Floor
22nd to 27th, 29th & 30th Floor |  | 1 |  | 2BHK | 744.5459 |  | 0 | 1191.2734 | [6 empty] | 2201,..,3001 | 2201 | 3001
|  | 2 |  | 3BHK | 939.5896 |  | 0 | 1503.3433 | [6 empty] | 2202,..,3002 | 2202 | 3002
|  | 3 |  | 3BHK | 1377.0385 |  | 0 | 2203.2616 | [6 empty] | 2203,..,3003 | 2203 | 3003
|  | 4 |  | 2BHK | 797.3971 |  | 0 | 1275.8354 | [6 empty] | 2204,..,3004 | 2204 | 3004
21st & 28th Floor (Part Refuge Area)
21st & 28th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 744.5459 |  | 0 | 1191.2734 | [6 empty] | 2101,..,2801 | 2101 | 2801
|  | 2 |  | 3BHK | 939.5896 |  | 0 | 1503.3433 | [6 empty] | 2102,..,2802 | 2102 | 2802
|  | 3 |  | 3BHK | 1377.0385 |  | 0 | 2203.2616 | [6 empty] | 2103,..,2803 | 2103 | 2803
|  | 4 |  | Refuge Area | [10 empty] | 2104,..,2804 | 2104 | 2804
31st to 34th, 36th to 41st, 43rd & 44th Floor
31st to 34th, 36th to 41st, 43rd & 44th Floor |  | 1 |  | 2BHK | 744.5459 |  | 0 | 1191.2734 | [6 empty] | 3101,..,4401 | 3101 | 4401
|  | 2 |  | 3BHK | 943.8187 |  | 0 | 1510.11 | [6 empty] | 3102,..,4402 | 3102 | 4402
|  | 3 |  | 3BHK | 1382.9587 |  | 0 | 2212.734 | [6 empty] | 3103,..,4403 | 3103 | 4403
|  | 4 |  | 2BHK | 803.8555 |  | 0 | 1286.1688 | [6 empty] | 3104,..,4404 | 3104 | 4404
35th Floor (Part Refuge Area)
35th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 744.5459 |  | 0 | 1191.2734 | [6 empty] | 301,..,3501 | 301 | 3501
|  | 2 |  | 3BHK | 943.8187 |  | 0 | 1510.11 | [6 empty] | 302,..,3502 | 302 | 3502
|  | 3 |  | 3BHK | 1382.9587 |  | 0 | 2212.734 | [6 empty] | 303,..,3503 | 303 | 3503
|  | 4 |  | Refuge Area | [10 empty] | 304,..,3504 | 304 | 3504
42nd Floor (Part Refuge Area)
42nd Floor (Part Refuge Area) |  | 1 |  | Refuge Area | [10 empty] | 401,..,4201 | 401 | 4201
|  | 2 |  | 3BHK | 943.8187 |  | 0 | 1510.11 | [6 empty] | 402,..,4202 | 402 | 4202
|  | 3 |  | 3BHK | 1382.9587 |  | 0 | 2212.734 | [6 empty] | 403,..,4203 | 403 | 4203
|  | 4 |  | 2BHK | 803.8555 |  | 0 | 1286.1688 | [6 empty] | 404,..,4204 | 404 | 4204
Deck level Floor For Amenities
Tower 2 Wing B
Basement For Tanks & Pump Room
Ground Floor For Society Office, Meter Room, Substation & Entrance Lobby
1st Floor For Residential
1st Floor For Residential |  | 1 |  | Void | [5 empty] | 63.047 |  |  |  |  | 101,..,101 | 101 | 101
|  | 2 |  | 4BHK | 1206.8597 |  | 0 | 1930.9755 |  | 3.721 |  |  |  |  | 102,..,102 | 102 | 102
|  | 3 |  | Void | [5 empty] | 66.768 |  |  |  |  | 103,..,103 | 103 | 103
|  | 4 | [12 empty] | 104,..,104 | 104 | 104
|  | 5 | [9 empty] | Void |  |  | 105,..,105 | 105 | 105
2nd Floor
2nd Floor |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | 201,..,201 | 201 | 201
|  | 2 |  | 3BHK | 932.27 |  | 0 | 1491.6321 | [6 empty] | 202,..,202 | 202 | 202
|  | 3 |  | Void | [10 empty] | 203,..,203 | 203 | 203
|  | 4 | [12 empty] | 204,..,204 | 204 | 204
|  | 5 | [12 empty] | 205,..,205 | 205 | 205
3rd to 6th Floor
3rd to 6th Floor |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | 301,..,601 | 301 | 601
|  | 2 |  | 3BHK | 932.27 |  | 0 | 1491.6321 | [6 empty] | 302,..,602 | 302 | 602
|  | 3 |  | Void | [10 empty] | 303,..,603 | 303 | 603
|  | 4 | [12 empty] | 304,..,604 | 304 | 604
|  | 5 | [12 empty] | 305,..,605 | 305 | 605
7th Floor (Part Refuge Area)
7th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | #REF! | #REF! | 701
|  | 2 |  | 3BHK | 928.7179 |  | 0 | 1485.9487 | [6 empty] | #REF! | #REF! | 702
|  | 3 |  | 3BHK | 1373.8093 |  | 0 | 2198.0949 | [6 empty] | #REF! | #REF! | 703
|  | 4 |  | 2BHK | 791.2616 |  | 0 | 1266.0186 | [6 empty] | #REF! | #REF! | 704
|  | 5 |  | Refuge Area | [10 empty] | #REF! | #REF! | 705
8th to 13th & 15th to 20th Floor
8th to 13th & 15th to 20th Floor |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | 801,..,2001 | 801 | 2001
|  | 2 |  | 3BHK | 928.7179 |  | 0 | 1485.9487 | [6 empty] | 802,..,2002 | 802 | 2002
|  | 3 |  | 3BHK | 1373.8093 |  | 0 | 2198.0949 | [6 empty] | 803,..,2003 | 803 | 2003
|  | 4 |  | 2BHK | 791.2616 |  | 0 | 1266.0186 | [6 empty] | 804,..,2004 | 804 | 2004
|  | 5 |  | 3BHK | 1308.0413 |  | 0 | 2092.866 | [6 empty] | 805,..,2005 | 805 | 2005
14th Floor (Part Refuge Area)
14th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 742.8236 |  | 0 | 1188.5178 | [6 empty] | 101,..,1401 | 101 | 1401
|  | 2 |  | 3BHK | 928.7179 |  | 0 | 1485.9487 | [6 empty] | 102,..,1402 | 102 | 1402
|  | 3 |  | 3BHK | 1373.8093 |  | 0 | 2198.0949 | [6 empty] | 103,..,1403 | 103 | 1403
|  | 4 |  | 2BHK | 791.2616 |  | 0 | 1266.0186 | [6 empty] | 104,..,1404 | 104 | 1404
|  | 5 |  | Refuge Area | [10 empty] | 105,..,1405 | 105 | 1405
22nd to 27th, 29th & 30th Floor
22nd to 27th, 29th & 30th Floor |  | 1 |  | 2BHK | 744.5459 |  | 0 | 1191.2734 | [6 empty] | 2201,..,3001 | 2201 | 3001
|  | 2 |  | 3BHK | 939.5896 |  | 0 | 1503.3433 | [6 empty] | 2202,..,3002 | 2202 | 3002
|  | 3 |  | 3BHK | 1377.0385 |  | 0 | 2203.2616 | [6 empty] | 2203,..,3003 | 2203 | 3003
|  | 4 |  | 2BHK | 794.5985 |  | 0 | 1271.3576 | [6 empty] | 2204,..,3004 | 2204 | 3004
|  | 5 |  | 3BHK | 1308.0413 |  | 0 | 2092.866 | [6 empty] | 2205,..,3005 | 2205 | 3005
21st & 28th Floor (Part Refuge Area)
21st & 28th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 744.5459 |  | 0 | 1191.2734 | [6 empty] | 2101,..,2801 | 2101 | 2801
|  | 2 |  | 3BHK | 939.5896 |  | 0 | 1503.3433 | [6 empty] | 2102,..,2802 | 2102 | 2802
|  | 3 |  | 3BHK | 1377.0385 |  | 0 | 2203.2616 | [6 empty] | 2103,..,2803 | 2103 | 2803
|  | 4 |  | 2BHK | 794.5985 |  | 0 | 1271.3576 | [6 empty] | 2104,..,2804 | 2104 | 2804
|  | 5 |  | Refuge Area | [10 empty] | 2105,..,2805 | 2105 | 2805
31st to 34th, 36th to 41st, 43rd & 44th Floor
31st to 34th, 36th to 41st, 43rd & 44th Floor |  | 1 |  | 2BHK | 744.5459 |  | 0 | 1191.2734 | [6 empty] | 3101,..,4401 | 3101 | 4401
|  | 2 |  | 3BHK | 943.7875 |  | 0 | 1510.06 | [6 empty] | 3102,..,4402 | 3102 | 4402
|  | 3 |  | 3BHK | 1382.9587 |  | 0 | 2212.734 | [6 empty] | 3103,..,4403 | 3103 | 4403
|  | 4 |  | 2BHK | 801.0569 |  | 0 | 1281.691 | [6 empty] | 3104,..,4404 | 3104 | 4404
|  | 5 |  | 3BHK | 1308.0413 |  | 0 | 2092.866 | [6 empty] | 3105,..,4405 | 3105 | 4405
35th Floor (Part Refuge Area)
35th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 744.5459 |  | 0 | 1191.2734 | [6 empty] | 301,..,3501 | 301 | 3501
|  | 2 |  | 3BHK | 943.7875 |  | 0 | 1510.06 | [6 empty] | 302,..,3502 | 302 | 3502
|  | 3 |  | 3BHK | 1382.9587 |  | 0 | 2212.734 | [6 empty] | 303,..,3503 | 303 | 3503
|  | 4 |  | 2BHK | 801.0569 |  | 0 | 1281.691 | [6 empty] | 304,..,3504 | 304 | 3504
|  | 5 |  | Refuge Area | [10 empty] | 305,..,3505 | 305 | 3505
42nd Floor (Part Refuge Area)
42nd Floor (Part Refuge Area) |  | 1 |  | Refuge Area | [10 empty] | 401,..,4201 | 401 | 4201
|  | 2 |  | 3BHK | 943.7875 |  | 0 | 1510.06 | [6 empty] | 402,..,4202 | 402 | 4202
|  | 3 |  | 3BHK | 1382.9587 |  | 0 | 2212.734 | [6 empty] | 403,..,4203 | 403 | 4203
|  | 4 |  | 2BHK | 801.0569 |  | 0 | 1281.691 | [6 empty] | 404,..,4204 | 404 | 4204
|  | 5 |  | 3BHK | 1308.0413 |  | 0 | 2092.866 | [6 empty] | 405,..,4205 | 405 | 4205
Phase III | [8 empty] | 10.764
Tower 3 Wing A
Basement For Tanks & Pump Room
Ground Floor For Society Office, Meter Room, Substation & Entrance Lobby (Double Heighted)
1st Floor For Residential | [8 empty] | 1
1st Floor For Residential |  | 1 |  | 2BHK | 667.6909 |  | 0 | 1068.3055 | [6 empty] | 101,..,101 | 101 | 101
|  | 2 |  | 2BHK | 684.698 |  | 0 | 1095.5169 | [6 empty] | 102,..,102 | 102 | 102
|  | 3 |  | Terrace Area Above | [10 empty] | 103,..,103 | 103 | 103
|  | 4 |  | Entrance Lobby Below | [10 empty] | 104,..,104 | 104 | 104
|  | 5 |  | Entrance Lobby Below | [10 empty] | 105,..,105 | 105 | 105
2nd Floor | [8 empty] | 1
2nd Floor |  | 1 |  | 2BHK | 667.6909 |  | 0 | 1068.3055 | [6 empty] | 201,..,201 | 201 | 201
|  | 2 |  | 2BHK | 684.698 |  | 0 | 1095.5169 | [6 empty] | 202,..,202 | 202 | 202
|  | 3 |  | Void | [10 empty] | 203,..,203 | 203 | 203
|  | 4 |  | Terrace Area | [10 empty] | 204,..,204 | 204 | 204
|  | 5 |  | Service Area | [10 empty] | 205,..,205 | 205 | 205
3rd to 6th Floor | [8 empty] | 4
3rd to 6th Floor |  | 1 |  | 2BHK | 667.6909 |  | 0 | 1068.3055 | [6 empty] | 301,..,601 | 301 | 601
|  | 2 |  | 2BHK | 684.698 |  | 0 | 1095.5169 | [6 empty] | 302,..,602 | 302 | 602
|  | 3 |  | Void | [10 empty] | 303,..,603 | 303 | 603
|  | 4 |  | Void | [10 empty] | 304,..,604 | 304 | 604
|  | 5 |  | 1BHK | 506.5538 |  | 0 | 810.4861 | [6 empty] | 305,..,605 | 305 | 605
7th Floor (Part Refuge Area) | [8 empty] | 1
7th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | #REF! | #REF! | 701
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | #REF! | #REF! | 702
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | #REF! | #REF! | 703
|  | 4 |  | 3BHK | 978.4476 |  | 0 | 1565.5162 | [6 empty] | #REF! | #REF! | 704
|  | 5 |  | Refuge Area | [10 empty] | #REF! | #REF! | 705
8th to 13th & 15th to 20th Floor | [8 empty] | 12
8th to 13th & 15th to 20th Floor |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 801,..,2001 | 801 | 2001
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 802,..,2002 | 802 | 2002
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 803,..,2003 | 803 | 2003
|  | 4 |  | 3BHK | 978.4476 |  | 0 | 1565.5162 | [6 empty] | 804,..,2004 | 804 | 2004
|  | 5 |  | 3BHK | 1153.255 |  | 0 | 1845.2079 | [6 empty] | 805,..,2005 | 805 | 2005
14th Floor (Part Refuge Area) | [8 empty] | 1
14th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 101,..,1401 | 101 | 1401
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 102,..,1402 | 102 | 1402
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 103,..,1403 | 103 | 1403
|  | 4 |  | 3BHK | 978.4476 |  | 0 | 1565.5162 | [6 empty] | 104,..,1404 | 104 | 1404
|  | 5 |  | Refuge Area | [10 empty] | 105,..,1405 | 105 | 1405
22nd to 27th, 29th & 30th Floor | [8 empty] | 8
22nd to 27th, 29th & 30th Floor |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 2201,..,3001 | 2201 | 3001
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 2202,..,3002 | 2202 | 3002
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 2203,..,3003 | 2203 | 3003
|  | 4 |  | 3BHK | 984.1525 |  | 0 | 1574.644 | [6 empty] | 2204,..,3004 | 2204 | 3004
|  | 5 |  | 3BHK | 1153.255 |  | 0 | 1845.2079 | [6 empty] | 2205,..,3005 | 2205 | 3005
21st & 28th Floor (Part Refuge Area) | [8 empty] | 2
21st & 28th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 2101,..,2801 | 2101 | 2801
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 2102,..,2802 | 2102 | 2802
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 2103,..,2803 | 2103 | 2803
|  | 4 |  | 3BHK | 984.1525 |  | 0 | 1574.644 | [6 empty] | 2104,..,2804 | 2104 | 2804
|  | 5 |  | Refuge Area | [10 empty] | 2105,..,2805 | 2105 | 2805
31st to 34th Floor | [8 empty] | 4
31st to 34th Floor |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 3101,..,3401 | 3101 | 3401
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 3102,..,3402 | 3102 | 3402
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 3103,..,3403 | 3103 | 3403
|  | 4 |  | 3BHK | 995.4547 |  | 0 | 1592.7276 | [6 empty] | 3104,..,3404 | 3104 | 3404
|  | 5 |  | 3BHK | 1153.255 |  | 0 | 1845.2079 | [6 empty] | 3105,..,3405 | 3105 | 3405
35th Floor (Part Refuge Area) | [8 empty] | 1
35th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 301,..,3501 | 301 | 3501
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 302,..,3502 | 302 | 3502
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 303,..,3503 | 303 | 3503
|  | 4 |  | 3BHK | 995.4547 |  | 0 | 1592.7276 | [6 empty] | 304,..,3504 | 304 | 3504
|  | 5 |  | Refuge Area | [10 empty] | 305,..,3505 | 305 | 3505
36th to 40th Floor | [8 empty] | 5
36th to 40th Floor |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 3601,..,4001 | 3601 | 4001
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 3602,..,4002 | 3602 | 4002
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 3603,..,4003 | 3603 | 4003
|  | 4 |  | 3BHK | 995.4547 |  | 0 | 1592.7276 | [6 empty] | 3604,..,4004 | 3604 | 4004
|  | 5 |  | 3BHK | 1153.255 |  | 0 | 1845.2079 | [6 empty] | 3605,..,4005 | 3605 | 4005
Tower 3 Wing B | [8 empty] | 10.764
Basement For Tanks & Pump Room
Ground Floor For Driver Room, Meter Room, Substation & Entrance Lobby (Double Heighted)
1st Floor For Residential
1st Floor For Residential |  | 1 |  | 2BHK | 667.6909 |  | 0 | 1068.3055 | [6 empty] | 101,..,101 | 101 | 101
|  | 2 |  | 2BHK | 684.698 |  | 0 | 1095.5169 | [6 empty] | 102,..,102 | 102 | 102
|  | 3 |  | Terrace Area Above | [10 empty] | 103,..,103 | 103 | 103
|  | 4 |  | Entrance Lobby Below | [10 empty] | 104,..,104 | 104 | 104
|  | 5 |  | Entrance Lobby Below | [10 empty] | 105,..,105 | 105 | 105
2nd Floor
2nd Floor |  | 1 |  | 2BHK | 667.6909 |  | 0 | 1068.3055 | [6 empty] | 201,..,201 | 201 | 201
|  | 2 |  | 2BHK | 684.698 |  | 0 | 1095.5169 | [6 empty] | 202,..,202 | 202 | 202
|  | 3 |  | Void | [10 empty] | 203,..,203 | 203 | 203
|  | 4 |  | Terrace Area | [10 empty] | 204,..,204 | 204 | 204
|  | 5 |  | Service Area | [10 empty] | 205,..,205 | 205 | 205
3rd Floor
3rd Floor |  | 1 |  | 2BHK | 667.6909 |  | 0 | 1068.3055 | [6 empty] | 301,..,301 | 301 | 301
|  | 2 |  | 2BHK | 684.698 |  | 0 | 1095.5169 | [6 empty] | 302,..,302 | 302 | 302
|  | 3 |  | Void | [10 empty] | 303,..,303 | 303 | 303
|  | 4 |  | Void | [10 empty] | 304,..,304 | 304 | 304
|  | 5 |  | 1BHK | 506.5538 |  | 0 | 810.4861 | [6 empty] | 305,..,305 | 305 | 305
7th Floor (Part Refuge Area)
7th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | #REF! | #REF! | 701
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | #REF! | #REF! | 702
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | #REF! | #REF! | 703
|  | 4 |  | 3BHK | 978.4476 |  | 0 | 1565.5162 | [6 empty] | #REF! | #REF! | 704
|  | 5 |  | Refuge Area | [10 empty] | #REF! | #REF! | 705
8th to 13th & 15th to 20th Floor
8th to 13th & 15th to 20th Floor |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 801,..,2001 | 801 | 2001
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 802,..,2002 | 802 | 2002
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 803,..,2003 | 803 | 2003
|  | 4 |  | 3BHK | 978.4476 |  | 0 | 1565.5162 | [6 empty] | 804,..,2004 | 804 | 2004
|  | 5 |  | 3BHK | 1153.255 |  | 0 | 1845.2079 | [6 empty] | 805,..,2005 | 805 | 2005
14th Floor (Part Refuge Area)
14th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 101,..,1401 | 101 | 1401
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 102,..,1402 | 102 | 1402
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 103,..,1403 | 103 | 1403
|  | 4 |  | 3BHK | 978.4476 |  | 0 | 1565.5162 | [6 empty] | 104,..,1404 | 104 | 1404
|  | 5 | [12 empty] | 105,..,1405 | 105 | 1405
22nd to 27th, 29th & 30th Floor
22nd to 27th, 29th & 30th Floor |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 2201,..,3001 | 2201 | 3001
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 2202,..,3002 | 2202 | 3002
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 2203,..,3003 | 2203 | 3003
|  | 4 |  | 3BHK | 984.1525 |  | 0 | 1574.644 | [6 empty] | 2204,..,3004 | 2204 | 3004
|  | 5 |  | 3BHK | 1153.255 |  | 0 | 1845.2079 | [6 empty] | 2205,..,3005 | 2205 | 3005
21st & 28th Floor (Part Refuge Area)
21st & 28th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 2101,..,2801 | 2101 | 2801
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 2102,..,2802 | 2102 | 2802
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 2103,..,2803 | 2103 | 2803
|  | 4 |  | 3BHK | 984.1525 |  | 0 | 1574.644 | [6 empty] | 2104,..,2804 | 2104 | 2804
|  | 5 |  | Refuge Area | [10 empty] | 2105,..,2805 | 2105 | 2805
31st to 34th Floor
31st to 34th Floor |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 3101,..,3401 | 3101 | 3401
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 3102,..,3402 | 3102 | 3402
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 3103,..,3403 | 3103 | 3403
|  | 4 |  | 3BHK | 995.4547 |  | 0 | 1592.7276 | [6 empty] | 3104,..,3404 | 3104 | 3404
|  | 5 |  | 3BHK | 1153.255 |  | 0 | 1845.2079 | [6 empty] | 3105,..,3405 | 3105 | 3405
35th Floor (Part Refuge Area)
35th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 301,..,3501 | 301 | 3501
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 302,..,3502 | 302 | 3502
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 303,..,3503 | 303 | 3503
|  | 4 |  | 3BHK | 995.4547 |  | 0 | 1592.7276 | [6 empty] | 304,..,3504 | 304 | 3504
|  | 5 |  | Refuge Area | [10 empty] | 305,..,3505 | 305 | 3505
36th to 40th Floor
36th to 40th Floor |  | 1 |  | 2BHK | 675.8716 |  | 0 | 1081.3945 | [6 empty] | 3601,..,4001 | 3601 | 4001
|  | 2 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 3602,..,4002 | 3602 | 4002
|  | 3 |  | 2BHK | 693.2016 |  | 0 | 1109.1226 | [6 empty] | 3603,..,4003 | 3603 | 4003
|  | 4 |  | 3BHK | 995.4547 |  | 0 | 1592.7276 | [6 empty] | 3604,..,4004 | 3604 | 4004
|  | 5 |  | 3BHK | 1153.255 |  | 0 | 1845.2079 | [6 empty] | 3605,..,4005 | 3605 | 4005
1st Floor For Residential
1st Floor For Residential |  | 1 |  |  |  |  | 0 | 0 | [6 empty] | 101,..,101 | 101 | 101
|  | 2 |  |  |  |  | 0 | 0 | [6 empty] | 102,..,102 | 102 | 102
|  | 3 |  |  |  |  | 0 | 0 | [6 empty] | 103,..,103 | 103 | 103
|  | 4 |  |  |  |  | 0 | 0 | [6 empty] | 104,..,104 | 104 | 104
|  | 5 |  |  |  |  | 0 | 0 | [6 empty] | 105,..,105 | 105 | 105
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Tower 1 & Tower 2 = Construction work is in process at the time of Visit. Internal visit was not allowed. Tower 3 (Wing A & B) = Work Not Started yet. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony Area + Utility Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated Approved Floor plan & CC of Phase I & II (on 19/04/2023). 8. We have updated Approved Floor plan & CC (on 10/12/2024). 9. We have referred Railway Noc from MCGM site (on 09/12/2024). 10. We have updated CC for Phase I & II from MCGM site (On 07/08/2025).
Site & Building/Tower Photographs
Name of the Project |  |  | : | Godrej Horizon Phase I Tower 1 (A & B Wing) Godrej Horizon Phase II Tower 2 (A & B Wing) Godrej Horizon Phase III Tower 3 (A & B Wing)
Project Site Address |  |  | : | Godrej Horizon Phase 1, Phase 2 & Phase 3, Azad Nagar, Dadar Naigaon Division, Road: Rafi Ahmed Kidwai Road, Near - Vijay Niwas, Wadala (W), Mumbai - 31.
Site Visit Date & Time |  |  | : | 02/08/2025 at 05:19PM
Layout Plan
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Karan Misal | Authorized Signatory Name & Signature | :
Phase I
Phase II
Phase III
A
A
B
B
A
B
Phase I
Phase II
Phase III
Godrej Horizon Phase I, II & III
Tower 1
Tower 1
Tower 2
Tower 1
Tower 2
Tower 2
Tower 1
Tower 1