## Sheet1
PROJECT TECHNICAL REPORT
Project Name | Imperial Splendora A to E, G & H wing |  |  | RBL BRANCH NAME | Airoli
Valuer Details
Name Of Valuation Agency/Firm |  | V.S Jadon & Co.Valuers LLP
Name Of Valuer |  | Mr. V. S. Jadon
Official Email Id |  | vsjc.apf@gmail.com
Contact Person Name & Number |  | Mr. Sachin Sawant 9820058999
Rvo Name Of Which Valuer Is Member
Address Of Valution Agency |  | Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80
Apf Technical Report Assignment Details
Date of Assignment | 2025-08-05 | Assigned By | Mr. Abhishek Manjarekar | Assignment Reference No | NA
Date of Visit | 2025-08-07 | Property Visited By (Name) |  | Mr. Navnath Bhatkar
Date of Valuation | 12/08/2025 | Report Prepared By (Name) |  | Ms. Shruti Tathare
Builder Company/Entity Details - Seller Of The Project
Name Of Entity Formed For Current Project |  | Imperial Lifestyle Private Limited
Project Address Details
Project Name | Imperial Splendora A to E, G & H wing
Survey No. | 275 & H No.1
Street Name &/No. | Internal Rd |  | Sector/Ward No. | -
Village/Location | Gohkiware |  | Landmark | Sterling Heights Gokhivare
City / Taluka/Town | Vasai |  | District | Palghar
State | Maharashtra |  | Country | India
Pincode | 401208 |  | Lat, Long | 19.392703, 72.847879
Location Link | https://goo.gl/maps/HTcSAYund1hnbayB6
Nearest Rbl Bank Location | RBL Bank Ltd, Ambadi Rd, Sai Nagar, Vasai West, Vasai-Virar, Maharashtra 401202 |  | Distance From Rbl Bank Location (Kms.) | 3.8Km
Project Boundaries Verification
|  | North | South | East | West
As Per Ownership Docs |  | NA | NA | NA | NA
As Per Approved Plan |  | NA | NA | NA | NA
As Per Site Investigation |  | Open Plot/ Nicon Infinity | Ditya Luxuria, Ditya construction company | Olympus | Rd/Sterling Heights Gokhivare
General Details
Municipal Limit |  | Vasai-Virar City Municipal Corporation
Municipal Authority (Name) |  | Vasai-Virar City Municipal Corporation
Approach Road To Project |  | Internal Rd
Location Type* |  | Developing
Quality Of Construction* |  | Good
Overall % Completion Of Project |  | 87.52%
Project Falling In Caution Area |  | No
Reason For Caution |  | No
Project Architect Name |  | Mr. Sanat Mehera
Project Area Details ( As Per Approved Plan )
Area Type |  | Square Meter
Total Plot Area |  | 466175
Net Plot Area |  | 280497.9
Total Built Up Area |  | 1021251.42 |  |  |  | 3.6409
Total Residential Built Up Area (A to E, G & H wing) |  | 56093.4 |  |  |  | 353243.16
Total Commercial Built Up Area (A, B, D, E wing) |  | 1551.62
Area Under Road |  | 70997.71
Area Under D.P. Reservation |  | 112931.84
Area Under R.G./Garden
FSI / FAR Details
Plot FSI / FAR |  | 1
Premium FSI / FAR |  | 0.061544
TDR FSI |  | 0
Fungible FSI |  | 0
Addl .FSI Under any Chapter 07 |  | 1.4287
Ancillory FSI |  | 1.1593
Total FSI/FAR |  | 3.6495
Overall Remarks on Project Area & FSI /FAR
Total No. Of Units/Tenaments |  | Shops = 72, Flats = 882
Total No. Of Parking |  | Car = 382 & Scooter = 1195 |  |  |  | 382
Residential /Commercial Ratio |  | 93 : 7 |  |  |  | 1195
Surrounding External Amenities
| Nearestr Bus Stop | Nearest Bank | Nearest School/ College | Nearest Hospital | Nearest Multiplex / Mall/ Market
Name Of The Premises/Description | Golani Naka, | IndusInd Bank, | J.B. Ludhani High School | Shree Siddhivinayak Multispecality Hospital | Dmart
Approx. Distance From Property (In Kms) | 1.6Km | 1.9Km | 1.8Km | 1.4Km | 3.9Km
Internal Project Specs - Comment On Availability & Quality
| Structural Elements & Wall Thickness | Plaster & Painting | Electrification | Plumbing & Bath Fittings | Door, Windows
Availability (Y/N) | Yes | Yes | Yes | Yes | Yes
| Potable Water Connection | Sewerage System | Lift | Power Backup | Parking
Availability (Y/N) | Yes | Yes | Yes | Yes | Yes
QUALITY, SPECS
| Clubhouse | Gym | Swimming Pool | Garden | Community Hall
Availability (Y/N) | Yes | Yes | No | Yes | Yes
QUALITY, SPECS
Any Additional Amenities, To Above, Pls Specify | Sky Jogging Track, Yoga Deck, Senior-Citizen-Lawn, Multipurpose-Activity-Room, Recreation Studio Room, Fire-Sprinklers-in-Apartment, Fire Sprinklers, Grand-Lobby, 24×7-Security, Live CCTV Surveillance, Automatic Lift, Automatic Lifts, ndoor-Games, Kids Play Area, Podium Garden
Technical Documents Details
Approving Authority Name | Vasai-Virar City Municipal Corporation
Document Name | Applicability & Availability | Approving Authority | Details Of Approval
Approved Layout Plan | Applicable and Received | VVCMC | VVCMC/TP/Amend/VP/0329/0815 & 0509/241/2022-23 Date : 29/07/2022
Building No.9 Wing A
Approved Floor Plan | Applicable and Received | VVCMC | VVCMC/TP/Amend/VP-0329/0815 & 0509/253/2022-23 Date : 29/07/2022
Construction / Building Permission / Commencement Certificate | Applicable and Received | VVCMC | VVCMC/TP/RDP/VP-0329, 0815 & 0509/253/2022-23 Date : 29/07/2022 Valid Upto: Wing A = Gr + 1st to 22nd Floor
Building No.9 Wing B
Approved Floor Plan | Applicable and Received | VVCMC | VVCMC/TP/Amend/VP-0329/0815 & 0509/254/2022-23 Date : 29/07/2022
Construction / Building Permission / Commencement Certificate | Applicable and Received | VVCMC | VVCMC/TP/RDP/VP-0329, 0815 & 0509/254/2022-23 Date : 29/07/2022 Valid Upto: Wing B = Gr + 1st to 22nd Floor
Building No.9 Wing C
Approved Floor Plan | Applicable and Received | VVCMC | VVCMC/TP/Amend/VP-0329/0815 & 0509/255/2022-23 Date : 29/07/2022
Construction / Building Permission / Commencement Certificate | Applicable and Received | VVCMC | VVCMC/TP/RDP/VP-0329, 0815 & 0509/255/2022-23 Date : 29/07/2022 Valid Upto: Wing C = Gr + 1st to 22nd Floor
Building No.9 Wing D
Approved Floor Plan | Applicable and Received | VVCMC | VVCMC/TP/Amend/VP-0329/0815 & 0509/256/2022-23 Date : 29/07/2022
Construction / Building Permission / Commencement Certificate | Applicable and Received | VVCMC | VVCMC/TP/RDP/VP-0329, 0815 & 0509/256/2022-23 Date : 29/07/2022 Valid Upto: Wing D= Gr + 1st to 22nd Floor
Building No.9 Wing E
Approved Floor Plan | Applicable and Received | VVCMC | VVCMC/TP/Amend/VP-0329/0815 & 0509/257/2022-23 Date : 29/07/2022
Construction / Building Permission / Commencement Certificate | Applicable and Received | VVCMC | VVCMC/TP/RDP/VP-0329, 0815 & 0509/257/2022-23 Date : 29/07/2022 Valid Upto: Wing E= Gr + 1st to 22nd Floor
Building No.9 Wing G
Approved Floor Plan | Applicable and Received | VVCMC | VVCMC/TP/Amend/VP-0329/0815 & 0509/259/2022-23 Date : 29/07/2022
Construction / Building Permission / Commencement Certificate | Applicable and Received | VVCMC | VVCMC/TP/RDP/VP-0329, 0815 & 0509/259/2022-23 Date : 29/07/2022 Valid Upto: Wing G= Gr + 1st to 22nd Floor
Building No.9 Wing H
Approved Floor Plan | Applicable and Received | VVCMC | VVCMC/TP/Amend/VP-0329/0815 & 0509/260/2022-23 Date : 29/07/2022
Construction / Building Permission / Commencement Certificate | Applicable and Received | VVCMC | VVCMC/TP/RDP/VP-0329, 0815 & 0509/260/2022-23 Date : 29/07/2022 Valid Upto: Wing H= Gr + 1st to 22nd Floor
Non Agricultural Permission / Land Conversion / Diversion | Not Applicable | NA | NA
Building Completion / Occupation Permission / Use Permission | Not Applicable | NA | NA
Location Sketch/ Certificate | Not Applicable | NA | NA
Authority Allotment Letter | Not Applicable | NA | NA
Fire Noc & Plans (As Applicable) | Not Applicable | NA | NA
Environmental Clearance ( As Applicable) | Not Applicable | NA | NA
Coastal Regulatory Zone ( Crz ) Noc (As Applicable) | Not Applicable | NA | NA
Ownership Doc 1 | Applicable and Received | NA | Verified by Adv. Bharat N. Bhoir (Advocate High Court)
Ownership Doc 2 | Not Applicable
Remarks On Documents Verified
Rera Details ( If Applicable)
Rera Applicable | Yes | If Applicable, Rera Registration Status | Registered | Rera Registration No | A, B and D Wing = P99000027833 C & E Wing = P99000032506 G & H Wing = P99000049245
Rera Registration No | A, B and D Wing = P99000027833 C & E Wing = P99000032506 G & H Wing = P99000049245
Project Start Date As Per Rera | 2021-01-08 |  | Project Completion Date As Per Rera | A, B and D Wing = 30/06/2027 C & E Wing = 31/12/2027 G & H Wing = 31/12/2028
If Any Litigation Record On Project As Per Rera | NO |  | Litigation Details As Per Rera Website | NO
Critical Parameters
Seismic Zone | ZONE II |  | Flood Prone Area | NO
Zoning As Per Development Plan | Yes |  | Coastal Regulatory Zone | NOT APPLICABLE
Falling In Reservation As Per Development Plan | NO |  | Falling In Present Or Proposed Road Widening | NO
Property Within 30 Mtrs From Railway Boundary ? | NO |  | Property Near High/Low Tension (Ht)/(Lt) Lines ? | NO
Fsi Deviation | NO |  | Presence Of Nallah/ Lake / Water Body Nearby | NO
Vertical Deviation | NO |  | Unit Deviation | NO
Habitation In ( % ) Within 1 Kms Around Project |  | Yes
Remarks In Case Project Affected By Any Of Critical Parameter |  | No
Technical Deviations Observed In Project
Detail Of Deviation, If Any |  |  |  | Demolition Risk
NA |  |  |  | No
Total Phases | Total No. Of Buildings | Total No. Of Wings | Total No. Of Approved Units (A) | Total No. Of Unapproved Units (B) | Total No. Of (A+B) Units
1 | 1 | 7 | Shops = 72, Flats = 882 | - | 954
Approved no of Floors |  | Wing A, B, C, D, E, G & H = Gr + 1st to 22nd Floor
Proposed no of Floors |  | Wing A, B, C, D, E, G & H = Gr + 1st to 22nd Floor
Overall % Completion Of Project |  | 87.52%
Is The Project Technically Acceptable ? |  | YES
Is The Project Marketable ? |  | YES
Comment On Builder Group Involved In Project Development |  | Imperial Exotica, Imperial Callisto, Imperial Homes, Imperial Palms & Etc
Overall Comments On Project Acceptability & Marketablity |  | Nearby Projects are Sterling Heights, Agrawal Exotica, Nicon Infinity, etc
Construction details:
Wing A, B, D = Gr + 1st + 22nd Floor |  | Basement | Ground | Podium | Floors | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
|  | 0 | 1 | 0 | 22 | [5 empty] | YET TO START
Stage of construction: | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. |  |  |  |  | All work Completed. OC Received. |  |  |  |  | FOUNDATION WIP
Type of Work | Project Progress % | Slab/Floor | Complition % | Completion % |  | Piling Work in process | 5.5 |  |  |  | PLINTH WIP
Excavation | 15% | 22 | 100% | 94.2% |  | Excavation in process | 11
Plinth | 35% | 22 | 100% |  |  | Excavation Completed | 22
RCC (Including podiums) | 35% | 23 | 100% |  |  | Footing in Process | 5.5 |  | #REF!
Brickwork | 5% | 22 | 100% |  |  | Footing Completed | 11
Plaster | 5% | 22 | 100% |  |  | Basement 1 | 0
Flooring & Fitting | 5% | 22 | 100% |  |  | Basement 2 | 0
Electrical & Plumbing | 5% | 22 | 100% |  |  | Basement 3 | 0
Painting & Wooden | 5% | 16 | 72.73% |  |  | Basement 4 | 0
Finishing | 2.5% | 5 | 22.73% |  |  | Plinth in process | 16.5
Possession | 2.5% | 0 | 0% |  |  | Plinth completed | 22
Wing C = Gr + 1st + 22nd Floor |  | Basement | Ground | Podium | Floors | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
|  | 0 | 1 | 0 | 22 | [5 empty] | YET TO START
Stage of construction: | Plinth work completed, RCC Slab, Brickwork, Plaster, Flooring upto 20 Floor, Electrical upto 15 Floor, Painting upto15 Floor Completed |  |  |  |  | All work Completed. OC Received. |  |  |  |  | FOUNDATION WIP
Type of Work | Project Progress % | Slab/Floor | Complition % | Completion % |  | Piling Work in process | 5.5 |  |  |  | PLINTH WIP
Excavation | 15% | 22 | 100% | 92.27% |  | Excavation in process | 11
Plinth | 35% | 22 | 100% |  |  | Excavation Completed | 22
RCC (Including podiums) | 35% | 23 | 100% |  |  | Footing in Process | 5.5 |  | #REF!
Brickwork | 5% | 22 | 100% |  |  | Footing Completed | 11
Plaster | 5% | 22 | 100% |  |  | Basement 1 | 0 | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Flooring & Fitting | 5% | 22 | 100% |  |  | Basement 2 | 0
Electrical & Plumbing | 5% | 17 | 77.27% |  |  | Basement 3 | 0
Painting & Wooden | 5% | 15 | 68.18% |  |  | Basement 4 | 0
Finishing | 2.5% | 0 | 0% |  |  | Plinth in process | 16.5
Possession | 2.5% | 0 | 0% |  |  | Plinth completed | 22
Wing E = Gr + 1st + 22nd Floor |  | Basement | Ground | Podium | Floors | Plinth work completed, RCC Slab, Brickwork, Plaster, Flooring upto 14 Floor, Electrical upto 12 Floor, Painting upto 6 Floor Completed
|  | 0 | 1 | 0 | 22 | [5 empty] | YET TO START
Stage of construction: | Plinth work completed, RCC Slab, Brickwork, Plaster, Flooring upto 14 Floor, Electrical upto 12 Floor, Painting upto 6 Floor Completed |  |  |  |  | All work Completed. OC Received. |  |  |  |  | FOUNDATION WIP
Type of Work | Project Progress % | Slab/Floor | Complition % | Completion % |  | Piling Work in process | 5.5 |  |  |  | PLINTH WIP
Excavation | 15% | 22 | 100% | 87.27% |  | Excavation in process | 11
Plinth | 35% | 22 | 100% |  |  | Excavation Completed | 22
RCC (Including podiums) | 35% | 23 | 100% |  |  | Footing in Process | 5.5 |  | #REF!
Brickwork | 5% | 22 | 100% |  |  | Footing Completed | 11
Plaster | 5% | 22 | 100% |  |  | Basement 1 | 0
Flooring & Fitting | 5% | 14 | 63.64% |  |  | Basement 2 | 0
Electrical & Plumbing | 5% | 12 | 54.55% |  |  | Basement 3 | 0
Painting & Wooden | 5% | 6 | 27.27% |  |  | Basement 4 | 0
Finishing | 2.5% | 0 | 0% |  |  | Plinth in process | 16.5
Possession | 2.5% | 0 | 0% |  |  | Plinth completed | 22
Wing G & H = Gr + 1st + 22nd Floor |  | Basement | Ground | Podium | Floors | Plinth work completed, RCC Slab, Brickwork upto 17 Floor, Plaster upto 6 Floor Completed
|  | 0 | 1 | 0 | 22 | [5 empty] | YET TO START
Stage of construction: | Plinth work completed, RCC Slab, Brickwork upto 17 Floor, Plaster upto 6 Floor Completed |  |  |  |  | All work Completed. OC Received. |  |  |  |  | FOUNDATION WIP
Type of Work | Project Progress % | Slab/Floor | Complition % | Completion % | [6 empty] | PLINTH WIP
Excavation | 15% | 7 | 31.82% | 75.23%
Plinth | 35% | 22 | 100%
RCC (Including podiums) | 35% | 23 | 100% |  |  | Excavation in Process | 3.1429
Brickwork | 5% | 17 | 77.27% |  |  | Foundation in Process | 6.2857
Plaster | 5% | 6 | 27.27% |  |  | Basement 1 | 0
Flooring & Fitting | 5% | 0 | 0% |  |  | Basement 2 | 0
Electrical & Plumbing | 5% | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden | 5% | 0 | 0% |  |  | Basement 4 | 0
Finishing | 2.5% | 0 | 0% |  |  | Plinth in process | 12.5714
Possession | 2.5% | 0 | 0% |  |  | Plinth completed | 22
Overall % Completion Of Project |  |  |  | 87.52%
BUILDING/TOWERWISE UNIT - AREA DETAILS
Total Phases | Total No. Of Buildings | Total No. Of Wings | Total No. Of Approved Units (A) | Total No. Of Unapproved Units (B) | Total No. Of (A+B) Units
1 | 1 | 7 | Shops = 72, Flats = 882 | - | 954
Commercial Area Details :
Building & Wing | No. of Units | Total Carpet Area |  | Total Saleable Area
Wing A | 20 | 3642.4838 |  | 5645.8499
Wing B | 20 | 3643.4794 |  | 5647.3931
Wing D | 22 | 3283.5044 |  | 5089.4318
Wing E | 10 | 1521.4376 |  | 2358.2282
Total | 72 | 12090.9052 |  | 18740.903
Residential Area Details :
Building & Wing | No. of Units | Total Carpet Area |  | Total Saleable Area
Wing A | 143 | 69308.7502 |  | 104247.9766
Wing B | 143 | 69308.7502 |  | 104247.4563
Wing C | 80 | 34744.0392 |  | 52116.0588
Wing D | 124 | 66609.5695 |  | 100268.593
Wing E | 82 | 45557.9842 |  | 68499.4678
Wing G | 146 | 71412.6816 |  | 107119.0224
Wing H | 164 | 95705.1997 |  | 143557.7996
Total | 882 | 452646.9745 |  | 680056.3745
Grand Total | 954 | 464737.8797 |  | 698797.2775
Building details Floor Wise
Details of Commercial in Building
Shop No. (Approved Plan) | Description | Gross Carpet area | Builtup Area | Attached Terrace area | Saleable area Loading:
55%
Sector I - Building No.9
Wing A | [9 empty] | 10.764
Ground Floor For Entrance Lobby, Meter Room, Commercial & Parking | [9 empty] | 10.764
1 | Shop | 181.2658 | 217.5189 | 0 | 280.9619 | 16.84
2 | Shop | 155.0016 | 186.0019 | 0 | 240.2525 | 14.4
3 | Shop | 246.8185 | 296.1822 | 0 | 382.5687 | 17.11
4 | Shop | 195.7972 | 234.9566 | 0 | 303.4856
5 | Shop | 125.9388 | 151.1266 | 0 | 195.2051
6 | Shop | 249.5095 | 299.4114 | 0 | 386.7398
7 | Shop | 269.9073 | 323.8888 | 0 | 418.3563
8 | Shop | 246.8185 | 296.1822 | 0 | 382.5687
9 | Shop | 155.0016 | 186.0019 | 0 | 240.2525
10 | Shop | 181.2658 | 217.5189 | 0 | 280.9619
1st Floor Entrance Lobby, Meter Room, Commercial & Parking
1 | Shop | 143.807 | 172.5684 | 0 | 222.9009
2 | Shop | 124.0013 | 148.8015 | 0 | 192.202
3 | Shop | 209.3598 | 251.2318 | 0 | 324.5077
4 | Shop | 158.8228 | 190.5874 | 0 | 246.1754
5 | Shop | 94.9385 | 113.9262 | 0 | 147.1546
6 | Shop | 212.0508 | 254.461 | 0 | 328.6787
7 | Shop | 215.0109 | 258.0131 | 0 | 333.2669
8 | Shop | 209.3598 | 251.2318 | 0 | 324.5077
9 | Shop | 124.0013 | 148.8015 | 0 | 192.202
10 | Shop | 143.807 | 172.5684 | 0 | 222.9009
Wing B | [9 empty] | 10.764
Ground Floor For Entrance Lobby, Meter Room, Commercial & Parking | [9 empty] | 10.764
1 | Shop | 181.2658 | 217.5189 | 0 | 280.9619
2 | Shop | 155.0016 | 186.0019 | 0 | 240.2525
3 | Shop | 246.8185 | 296.1822 | 0 | 382.5687
4 | Shop | 269.9073 | 323.8888 | 0 | 418.3563
5 | Shop | 249.5095 | 299.4114 | 0 | 386.7398
6 | Shop | 125.9388 | 151.1266 | 0 | 195.2051
7 | Shop | 196.2815 | 235.5378 | 0 | 304.2364
8 | Shop | 246.8185 | 296.1822 | 0 | 382.5687
9 | Shop | 155.0016 | 186.0019 | 0 | 240.2525
10 | Shop | 181.2658 | 217.5189 | 0 | 280.9619
1st Floor Entrance Lobby, Meter Room, Commercial & Parking
1 | Shop | 143.807 | 172.5684 | 0 | 222.9009
2 | Shop | 124.0013 | 148.8015 | 0 | 192.202
3 | Shop | 209.3598 | 251.2318 | 0 | 324.5077
4 | Shop | 215.0109 | 258.0131 | 0 | 333.2669
5 | Shop | 212.5621 | 255.0745 | 0 | 329.4712
6 | Shop | 94.9385 | 113.9262 | 0 | 147.1546
7 | Shop | 158.8228 | 190.5874 | 0 | 246.1754
8 | Shop | 209.3598 | 251.2318 | 0 | 324.5077
9 | Shop | 124.0013 | 148.8015 | 0 | 192.202
10 | Shop | 143.807 | 172.5684 | 0 | 222.9009
Wing D | [9 empty] | 10.764
Ground Floor For Entrance Lobby, Meter Room, Commercial & Parking | [9 empty] | 10.764
1 | Shop | 137.9137 | 165.4965 | 0 | 213.7663
2 | Shop | 121.9023 | 146.2828 | 0 | 188.9486
3 | Shop | 194.0211 | 232.8253 | 0 | 300.7327
4 | Shop | 155.0016 | 186.0019 | 0 | 240.2525
5 | Shop | 137.6447 | 165.1736 | 0 | 213.3492
6 | Shop | 130.9171 | 157.1006 | 0 | 202.9216
7 | Shop | 115.5785 | 138.6941 | 0 | 179.1466
8 | Shop | 162.4826 | 194.9791 | 0 | 251.848
9 | Shop | 185.3023 | 222.3627 | 0 | 287.2185
10 | Shop | 153.8983 | 184.6779 | 0 | 238.5423
11 | Shop | 147.0901 | 176.5081 | 0 | 227.9896
1st Floor Commercial & Parking
1 | Shop | 137.9137 | 165.4965 | 0 | 213.7663
2 | Shop | 121.9023 | 146.2828 | 0 | 188.9486
3 | Shop | 194.0211 | 232.8253 | 0 | 300.7327
4 | Shop | 155.0016 | 186.0019 | 0 | 240.2525
5 | Shop | 137.6447 | 165.1736 | 0 | 213.3492
6 | Shop | 130.9171 | 157.1006 | 0 | 202.9216
7 | Shop | 115.5785 | 138.6941 | 0 | 179.1466
8 | Shop | 162.4826 | 194.9791 | 0 | 251.848
9 | Shop | 185.3023 | 222.3627 | 0 | 287.2185
10 | Shop | 153.8983 | 184.6779 | 0 | 238.5423
11 | Shop | 147.0901 | 176.5081 | 0 | 227.9896
Wing E | [9 empty] | 10.764
Ground Floor For Entrance Lobby, Commercial & Parking | [9 empty] | 10.764
1 | Shop | 123.3554 | 148.0265 | 0 | 191.2009
2 | Shop | 212.5621 | 255.0745 | 0 | 329.4712
3 | Shop | 183.6338 | 220.3606 | 0 | 284.6325
4 | Shop | 107.8553 | 129.4263 | 0 | 167.1757
5 | Shop | 133.3121 | 159.9746 | 0 | 206.6338
1st Floor Commercial & Parking | [9 empty] | 10.764
1 | Shop | 123.3554 | 148.0265 | 0 | 191.2009
2 | Shop | 212.5621 | 255.0745 | 0 | 329.4712
3 | Shop | 183.6338 | 220.3606 | 0 | 284.6325
4 | Shop | 107.8553 | 129.4263 | 0 | 167.1757
5 | Shop | 133.3121 | 159.9746 | 0 | 206.6338
Details of Flats in Building
Shop No. (Approved Plan) | UNIT CONFIG | Gross Carpet area | Builtup Area | Attached Terrace area | Saleable area Loading:
50%
Wing A
2nd Floor For Residential & Parking | [9 empty] | 10.764
1 | Parking |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 | 2BHK | 555.2071 | 666.2485 | 265.0635 | 921.1652 | 48.6675
5 | 1BHK | 379.1081 | 454.9297 | 195.7972 | 666.5607 | 35.09
6 | 2BHK | 568.985 | 682.782 | 295.7947 | 952.0758
7 | Parking |  |  |  | 0
3rd to 7th, 9th to 11th, 13th to 15th, 17th to 19th & 21st & 22nd Floor
1 | 1BHK | 426.1468 | 511.3761 | 0 | 639.2201 | 34.74
2 | 1BHK | 426.1468 | 511.3761 | 0 | 639.2201
3 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
4 | 2BHK | 629.4787 | 755.3745 | 0 | 944.2181
5 | 1BHK | 434.0045 | 520.8054 | 0 | 651.0067
6 | 2BHK | 643.2566 | 771.908 | 0 | 964.885
7 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
8th, 12th, 16th & 20th Floor (Part Refuge Area)
1 | 1BHK | 426.1468 | 511.3761 | 0 | 639.2201
2 | 1BHK | 426.1468 | 511.3761 | 0 | 639.2201
3 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
4 | 2BHK | 629.4787 | 755.3745 | 0 | 944.2181
5 | 1BHK | 434.0045 | 520.8054 | 0 | 651.0067
6 | 1BHK | 456.1783 | 547.414 | 0 | 684.2675
7 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
Wing B
2nd Floor For Residential & Parking | [9 empty] | 10.764
1 | Parking |  |  |  | 0
2 |  |  |  |  | 0
3 | 2BHK | 568.985 | 682.782 | 295.7947 | 952.0758
4 | 1BHK | 379.1081 | 454.9297 | 195.7972 | 666.5607
5 | 2BHK | 555.2071 | 666.2485 | 263.5027 | 920.6449 | 265.0635
6 | Parking |  |  |  | 0
7 |  |  |  |  | 0
3rd to 7th, 9th to 11th, 13th to 15th, 17th to 19th & 21st & 22nd Floor | [5 empty] | ?
1 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
2 | 2BHK | 643.2566 | 771.908 | 0 | 964.885
3 | 1BHK | 434.0045 | 520.8054 | 0 | 651.0067
4 | 2BHK | 629.4787 | 755.3745 | 0 | 944.2181
5 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
6 | 1BHK | 426.1468 | 511.3761 | 0 | 639.2201
7 | 1BHK | 426.1468 | 511.3761 | 0 | 639.2201
8th, 12th, 16th & 20th Floor (Part Refuge Area)
1 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
2 | 1BHK | 456.1783 | 547.414 | 0 | 684.2675
3 | 1BHK | 434.0045 | 520.8054 | 0 | 651.0067
4 | 2BHK | 629.4787 | 755.3745 | 0 | 944.2181
5 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
6 | 1BHK | 426.1468 | 511.3761 | 0 | 639.2201
7 | 1BHK | 426.1468 | 511.3761 | 0 | 639.2201
Wing C
Ground Floor For Entrance Lobby, Meter Room & parking | [9 empty] | 10.764
1st Floor For Entrance Lobby & parking | [9 empty] | 10.764
2nd Floor For Entrance Lobby & parking | [9 empty] | 10.764
3rd to 7th, 9th to 11th, 13th to 15th, 17th to 19th & 21st & 22nd Floor
1 | 1BHK | 435.0809 | 522.0971 | 0 | 652.6213
2 | 1BHK | 433.3586 | 520.0304 | 0 | 650.038
3 | 1BHK | 433.6816 | 520.4179 | 0 | 650.5223
4 | 1BHK | 435.0809 | 522.0971 | 0 | 652.6213
8th, 12th, 16th & 20th Floor (Part Refuge Area)
1 | 1BHK | 435.0809 | 522.0971 | 0 | 652.6213
2 | 1BHK | 433.3586 | 520.0304 | 0 | 650.038
3 | 1BHK | 433.6816 | 520.4179 | 0 | 650.5223
4 | 1BHK | 435.0809 | 522.0971 | 0 | 652.6213
Wing D
2nd Floor For Residential & Parking | [9 empty] | 10.764
1 | Parking |  |  |  | 0
2 | 1BHK | 363.7156 | 436.4587 | 195.9586 | 643.5526
3 | 1BHK | 407.0945 | 488.5134 | 286.5915 | 706.1722
4 | 2BHK | 535.8319 | 642.9983 | 223.4068 | 878.2168
5 | 2BHK | 618.7147 | 742.4577 | 172.52 | 1014.3321 | 265.0635
6 | Parking |  |  |  | 0
3rd to 7th, 9th to 11th, 13th to 15th, 17th to 19th & 21st & 22nd Floor
1 | 1BHK | 418.612 | 502.3344 | 0 | 627.9179
2 | 1BHK | 418.612 | 502.3344 | 0 | 627.9179
3 | 1BHK | 461.7756 | 554.1307 | 0 | 692.6634
4 | 2BHK | 610.8301 | 732.9961 | 0 | 916.2451
5 | 2BHK | 676.7327 | 812.0792 | 0 | 1015.099
6 | 2BHK | 676.7327 | 812.0792 | 0 | 1015.099
8th, 12th, 16th & 20th Floor (Part Refuge Area)
1 | 1BHK | 418.612 | 502.3344 | 0 | 627.9179
2 | 1BHK | 418.612 | 502.3344 | 0 | 627.9179
3 | 1BHK | 461.7756 | 554.1307 | 0 | 692.6634
4 | 1BHK | 465.4084 | 558.4901 | 0 | 698.1127
5 | 2BHK | 676.7327 | 812.0792 | 0 | 1015.099
6 | 2BHK | 676.7327 | 812.0792 | 0 | 1015.099
Wing E
2nd Floor For Entrance Lobby & parking | [9 empty] | 10.764
1 | 1BHK | 376.3094 | 451.5713 | 176.7987 | 652.8635
2 | Parking |  |  |  | 0
3 |  |  |  |  | 0
4 | 2BHK | 616.5619 | 739.8743 | 222.2766 | 998.9351
3rd to 7th, 9th to 11th, 13th to 15th, 17th to 19th & 21st & 22nd Floor
1 | 1BHK | 443.9074 | 532.6888 | 0 | 665.861
2 | 1BHK | 433.6816 | 520.4179 | 0 | 650.5223
3 | 2BHK | 675.3334 | 810.4 | 0 | 1013
4 | 2BHK | 675.3334 | 810.4 | 0 | 1013
8th, 12th, 16th & 20th Floor (Part Refuge Area)
1 | 1BHK | 443.9074 | 532.6888 | 0 | 665.861
2 | 1BHK | 433.6816 | 520.4179 | 0 | 650.5223
3 | 2BHK | 675.3334 | 810.4 | 0 | 1013
4 | 2BHK | 675.3334 | 810.4 | 0 | 1013
Wing G
Ground Floor For Entrance Lobby, Meter Room & parking | [9 empty] | 10.764
1st Floor For Residential & Parking | [9 empty] | 10.764
1 | Parking |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 | 2BHK | 629.4787 | 755.3745 | 0 | 944.2181
5 | 1BHK | 434.0045 | 520.8054 | 0 | 651.0067 | 265.0635
6 | 2BHK | 643.2566 | 771.908 | 0 | 964.885
7 | Parking |  |  |  | 0
2nd Floor For Residential & Parking | [9 empty] | 10.764
1 | Parking |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 | 2BHK | 629.4787 | 755.3745 | 0 | 944.2181
5 | 1BHK | 434.0045 | 520.8054 | 0 | 651.0067 | 265.0635
6 | 2BHK | 643.2566 | 771.908 | 0 | 964.885
7 | Parking |  |  |  | 0
3rd to 7th, 9th to 11th, 13th to 15th, 17th to 19th & 21st & 22nd Floor
1 | 1BHK | 430.9906 | 517.1887 | 0 | 646.4858
2 | 1BHK | 430.9906 | 517.1887 | 0 | 646.4858
3 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
4 | 2BHK | 629.4787 | 755.3745 | 0 | 944.2181
5 | 1BHK | 434.0045 | 520.8054 | 0 | 651.0067
6 | 2BHK | 643.2566 | 771.908 | 0 | 964.885
7 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
8th, 12th, 16th & 20th Floor (Part Refuge Area)
1 | 1BHK | 430.9906 | 517.1887 | 0 | 646.4858
2 | 1BHK | 430.9906 | 517.1887 | 0 | 646.4858
3 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
4 | 2BHK | 629.4787 | 755.3745 | 0 | 944.2181
5 | 1BHK | 434.0045 | 520.8054 | 0 | 651.0067
6 | 1BHK | 456.1783 | 547.414 | 0 | 684.2675
7 | 1BHK | 434.3274 | 521.1929 | 0 | 651.4911
Wing H
Ground Floor For Entrance Lobby, Meter Room, Driver Room & parking | [9 empty] | 10.764
1st Floor For Entrance Lobby, Society Office, Residential & Parking | [9 empty] | 10.764
1 | Parking |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0 | 265.0635
6 | 2BHK | 537.6618 | 645.1942 | 0 | 806.4927
7 | 2BHK | 537.6618 | 645.1942 | 0 | 806.4927
8 | Society Office |  |  |  | 0
2nd Floor For Residential & Parking | [9 empty] | 10.764
1 | Parking |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0 | 265.0635
6 | 2BHK | 537.6618 | 645.1942 | 0 | 806.4927
7 | 2BHK | 537.6618 | 645.1942 | 0 | 806.4927
8 | Indoor Game |  |  |  | 0
3rd to 7th, 9th to 11th, 13th to 15th, 17th to 19th, 21st & 22nd Floor | [5 empty] | ?
1 | 2BHK | 582.9782 | 699.5739 | 0 | 874.4674
2 | 3BHK | 747.0216 | 896.4259 | 0 | 1120.5324
3 | 3BHK | 716.7748 | 860.1297 | 0 | 1075.1621
4 | 2BHK | 576.4122 | 691.6946 | 0 | 864.6183
5 | 1BHK | 379.3234 | 455.188 | 0 | 568.985
6 | 2BHK | 537.6618 | 645.1942 | 0 | 806.4927
7 | 2BHK | 537.6618 | 645.1942 | 0 | 806.4927
8 | 2BHK | 649.3652 | 779.2383 | 0 | 974.0478
8th, 12th, 16th & 20th Floor (Part Refuge Area)
1 | 2BHK | 582.9782 | 699.5739 | 0 | 874.4674
2 | 3BHK | 747.0216 | 896.4259 | 0 | 1120.5324
3 | 3BHK | 716.7748 | 860.1297 | 0 | 1075.1621
4 | 2BHK | 576.4122 | 691.6946 | 0 | 864.6183
5 | 1BHK | 379.3234 | 455.188 | 0 | 568.985
6 | 1BHK | 394.393 | 473.2716 | 0 | 591.5894
7 | 1BHK | 433.5739 | 520.2887 | 0 | 650.3609
8 | 2BHK | 649.3652 | 779.2383 | 0 | 974.0478
VALUE PARAMETERS
Sr.No. | Building/Wing - Name/No |  | Base Rate Psf Rs. | Base Rate Considered On Area - Carpet/Bua/Saleale
1 | Wing A, B, C, D, E, G & H |  | 6200 | Saleable Area
2
3
4
5
6
Floor Rise (If Applicable) | In Rs. Psf (If Applicable) | In Lumpsum Basis (If Applicable) | Applicable From Floor No. | Applicable To Floor No. | Applicable To Building /W ing |  |  |  | Applicable From Floor No. | Applicable To Floor No. | Applicable To Building /W Ing
Floor Rise 1 | NA | NA
Floor Rise 2
Floor Rise 3
Floor Rise 4
Plc Charges (If Applicable) | In Rs. Psf (If Applicable) | In Lumpsum Basis (If Applicable) | Details Of Plc/View |  | List Of Unit Nos - Plc Applicable
PLC Type 1 | NA | NA
PLC Type 2
PLC Type 3
Amenities Details | In Rs. Psf (If Applicable) | In Lumpsum Basis (If Applicable) | Details Of Amenity Cost - Optional/Compulsory To Buyer, No Of Years, Etc |  | Remarks, If Any
Clubhouse & Recreational
Parking | NA | 200000
Electricity & Water Con.
Infra
Development
Maintenance
Any Other Amenity 1
Any Other Amenity 2
Any Other Amenity 3
Remarks:
1. Construction Work is in process at the tme of visit.(Internal Visit Not Allowed) 2. AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity. 3. Labours found on site at the time of visit. 4. We considered Carpet area as per Approved Plan. 5. We considered Saleable area as per our calculation. (i.e 50% Loading) 6. We considered Gross carpet area = Net carpet + Enclose balcony + AP Area. 7. We have considered rate by verifying it from market inquire. 8. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 9. Car parking is subjected to authentic documentation. 10. On Site, we meet Mr. Mishra (8698950092) 11. High-tension lines are passing near by the project. Please provide Power NOC.
Photographs Of Property : |  | Imperial Splendora A to E, G & H wing
Layout Of Property :
Google Map :
Name of Engineer Visited the property | Mr. Navnath Bhatkar | Authorized Signatory Name & Seal of the agency
F
E & F
D
C
D
B
A
G & H
A
B
A
D
B
E
C
D
G & H
High Tension Line
High Tension Line

## Sheet2
Construction details: |  | g +7 |  |  |  | All work completed. Please provide OC.
Basement | 0 | 1 | 0 | 7
Stage of construction: |  | All work Completed. OC Received. |  |  |  | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % | Disbursement % | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% | 100% | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  | Plinth completed | 7
Work not yet Started., RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting