## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 05/08/2025.
Project Name |  |  | : | Ashford Crosstown |  | Date & Time of Site Visit |  | 05/08/2025 @01:25 PM |  | 2025-05-16
Tower Name as per RERA Site |  |  | : | Ashford Regal - Phase I - Wing A Project Ashford Regal - Phase IV- Wing C Project | [5 empty] | 2025-08-05
Name of the person met at site & Contact No. |  |  | : | Mr. Rakesh 9092049887 |  | Date of Report Release |  | 07/08/2025 |  | 81
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Wmi Real Estate Developers LLP | Developer Name | : | Ashford Regal
Developer Office Address |  |  | : | Opp Penninsula corporate park, Lower Parel
Project Address | : | As per ARF | : | Ashford Crosstown, Bhandup Village Rd, Nahur, Industrial Area, Bhandup West, Mumbai, Maharashtra 400078
| : | As per Legal Documents | : | Ashford Crosstown, CTS No.358/11 to 25, near Skyline Sparkle, LBS Road, S Ward, Bhandup, Bhandup West, Kurla, Mumbai - 400078.
| : | As per Actual at site | : | Ashford Regal, CTS No.358/11 to 25, near Skyline Sparkle, LBS Road, S Ward, Bhandup, Bhandup West, Kurla, Mumbai - 400078.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, Fire Noc, EC & CC Revalidation Letter
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation Of Greater Mumbai (MCGM)
RERA Registration No. | : | Wing A (P51800047421) Wing C (PM1183032400064) |  |  | RERA Registration Validity | : | Wing A - 30/06/2027 Wing C - 30/06/2029
Project Launch Date | : | Wing A - 28/09/2022 Wing C - 08/10/2024 |  |  | Construction Start Date | : | Wing A (Oct 2022) Wing C (Sep 2024)
Proposed Date of Completion (As per RERA) | : | Wing A - 30/06/2027 Wing C - 30/06/2029 |  |  | Developer Bank Name (As per RERA) | : | HDFC Bank IFSC Code - HDFC0000501 |  |  | (P51800047421) Ashford Regal ­ Phase I ­ Wing A Project
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | : | 18841.18 |  |  | (PM1183032400064) Ashford Regal - Phase IV- Wing C Project
FSI/FAR Permissible | : | 1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 34593.78
Permissible Built up Area (In Sq.Mt) | : | 35901.8 |  |  | Total Number of Units Planned | : | Flats = 558 & Shop = 32
Total Number of Units Approved | : | Flats = 558 |  |  | If Mixed, No. of Commercial Units | : | Shop = 32 |  | 558
Latitude, Longitude | : | 19.152163,72.944139
Location Link | : | https://goo.gl/maps/kogUHYPcwhDc6ekL7
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 18ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 1 KM from Sadhana Castings
Distance from the nearest School (Km) | : | About 0.55KM from GS Shetty International School |  |  | Distance from Hospital (Km) | : | About 1.5K form Fortis Hospital Mulund
Distance from the Main Market (Km) | : | 1. Approx. 0.6KM from Ramesh Super Market 2. Approx. 2.8KM from Mulund Market. |  |  | Distance from Railway Station (Km) | : | 0.4KM from Nahur Railway Station 1.5KM from Bhandup Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Propose Internal Road | Open Plot | Proposed Road |  | 13.40 M. Wide D.P Road
As per Site / Actual |  |  | : | MTNL Telephone Exchange building | Open Plot | Railway Track |  | Subhash Nagar Road
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing A |  | Sale |  | Gr + P1 to P5 + 6th to 39th Floor |  |  | Gr + P1 to P5 + 6th to 39th Floor
Wing C |  | Sale |  | Gr + P1 to P5 + 6th to 39th Floor |  |  | Gr + P1 to P5 + 6th to 39th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | P-9962/2022/(358/11)/S Ward/BHANDUP-W/337/4/Amend Date: 10/10/2024
Approved Plan Details | : | P-9962/2022/(358/11)/S Ward/BHANDUP-W/337/4/Amend Date: 10/10/2024
CC Details |  | P-9962/2022/(358/11)/S Ward/BHANDUP-W/FCC/3/Amend Date : 28/03/2025 Valid Up to: 27/03/2026 Valid Up to :C.C. re-endorsement up to ‘Top of Plinth’ for wings, ‘C’, ‘D’, ‘E’ ‘F’ and ‘G’ and to Full C.C. re-endorsement up to top of 39th upper floor + LMR & OHT for wing ‘A’ & ‘B’ and Full C.C. re-endorsement up to top of 21st upper floor + OHT/LMR for EWS Wing as per last approved amended plans dated 24.03.2025. (SWM NOC and Janta Insurance Policy shall be renewed time to time.)
| : | P-9962/2022/(358/11)/S Ward/BHANDUP-W/FCC/1/Amend Date: 01/03/2024 Valid Up to: 27/09/2024 Valid upto : Full C.C. is granted up to top of 39th upper floor i.e. total height of 119.75 mt. AGL+ LMR & OHT for Wing ‘A’ and Further C.C. is granted up to Top of 21st upper floor i.e. total height of 66.65 mt. AGL for Wing ‘B’ as per last approved amended plans dated. 21.11.2023 subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution.
CC Revalidation Letter No. |  | P-9962/2022/(358/11)/SWard/BHANDUP-W/Other/6/New Date: 06/09/2024 Valid upto : C.C. is revalidated for the period from 28.09.2024 up to 27.09.2025 subject to timely renewal of B.G., SWM NOC and Workmen’s compensation policy as proposed.
CC Details |  | P-9962/2022/(358/11)/S Ward/BHANDUP-W/FCC/4/Amend Date : 09/05/2025 Valid Up to: 27/09/2025 Valid Up to :Further C.C. is granted up to top of 26th upper floor level for wing ‘C’ and Full C.C. is granted up to top of 4th upper floor + LMR & OHT for wing ‘F’ as per last approved amended plans dated 24.03 .2025, subject to timely renewal of B.G., SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction along with precautionary measures for air pollution.
Environmental Clearance Details | : | SIA/MH/INFRA2/417596/2023 Date:06/06/2023 Valid upto : CTS No. 358/11 to 25 Proposed Builtup Area = 180106.83 Sq. Mt. Wing A & C = 1B + Gr + P1 to P5+ 6th to 39th Floor
Fire NOC Details | : | P9962/2022(358/11)/S WARD/BHANDUP-W-CFO/1/NEW Date: 31/07/2022 Valid Up to :- Wing A & C = 1B + Gr + P1 to P5+ 6th to 39th Floor (Total Height - 119.75 Mtrs)
Construction Status
Wing A = Gr + P1 to P5 + 6th to 39th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 15 Floor Completed
|  |  |  | 0 | 1 |  | 0 | 39 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.75
Excavation |  | 39 |  | 100% | 66.41% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, External Plumbing, Elevation and Waterproofing upto 20 Floor, Flooring & Fitting upto 15 Floor Completed |  | Excavation in process | 19.5
Plinth |  | 39 |  | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 40 |  | 100% |  |  |  |  | Footing in Process | 9.75
Brickwork |  | 39 |  | 100% |  |  |  |  | Footing Completed | 19.5
Internal Plaster |  | 39 |  | 100% |  |  |  |  | Basement 1 | 0
External Plaster |  | 39 |  | 100% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 20 |  | 51.28% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 15 |  | 38.46% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 29.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 39
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing C = Gr + P1 to P5 + 6th to 39th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
|  |  |  | 0 | 1 |  | 0 | 39 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.75
Excavation |  | 39 |  | 100% | 26.25% |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed |  | Excavation in process | 19.5
Plinth |  | 39 |  | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 2 |  | 5% |  |  |  |  | Footing in Process | 9.75
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 19.5
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 29.25
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 39
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 46.33%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 22000/- to 23000/- | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  |  | : | 800000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 5392.9766
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 13213.4894
Distress Value (Rs. Per sqft) | [5 empty] | : | 4314.3813
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Wing A |  | Sale |  | Shops | 16 |  | 3332.9768 | 5166.114
|  | Sale |  | Flats | 279 |  | 142393.1585 | 220709.3956
Wing C |  | Sale |  | Shops | 16 |  | 3332.9768 | 5166.114
|  | Sale |  | Flats | 279 |  | 142393.1585 | 220709.3956
Wing A & C |  | Total |  |  | 590 |  | 291452.2705 | 451751.0193
Details of Residential & Commercial in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
55%
Wing A
Ground Floor For Commercial, Meter Room, Fire Control Room, Panel Room, Society Office & Parking | [10 empty] | 10.764
Ground Floor For Commercial, Meter Room, Fire Control Room, Panel Room, Society Office & Parking |  | 1 |  | Shop | 210.1596 |  | 0 | 325.7473
|  | 2 |  | Shop | 229.101 |  | 0 | 355.1065
|  | 3 |  | Shop | 274.257 |  | 0 | 425.0984
|  | 4 |  | Shop | 228.1968 |  | 0 | 353.705
|  | 5 |  | Shop | 214.5491 |  | 0 | 332.5511
|  | 6 |  | Shop | 229.5584 |  | 0 | 355.8156
|  | 7 |  | Shop | 229.101 |  | 0 | 355.1065
|  | 8 |  | Shop | 210.3426 |  | 0 | 326.031
1st Podium Floor Commercial, Meter Room, LV Room, Panel Room & Parking
1st Podium Floor Commercial, Meter Room, LV Room, Panel Room & Parking |  | 1 |  | Shop | 250.39 |  | 0 | 388.1045
|  | 1A |  | Shop | 156.5215 |  | 0 | 242.6083
|  | 2 |  | Shop | 209.2532 |  | 0 | 324.3425
|  | 3 |  | Shop | 165.4298 |  | 0 | 256.4161
|  | 4 |  | Shop | 152.4979 |  | 0 | 236.3717
|  | 5 |  | Shop | 166.7021 |  | 0 | 258.3882
|  | 6 |  | Shop | 156.5215 |  | 0 | 242.6083
|  | 6A |  | Shop | 250.3954 |  | 0 | 388.1129
2nd Podium Floor For Residential, Part Parking & Meter Room
2nd Podium Floor For Residential, Part Parking & Meter Room |  | 1 |  | Parking & Meter Room |  |  |  | -
2
|  | 3 | [8 empty] | 23000
|  | 4 | [8 empty] | 14375
|  | 5 |  | 2BHK | 602.1382 |  | 0 | 933.3141 |  | 52.9856
|  | 6 |  | 1BHK | 400.4208 |  | 0 | 620.6522 | 22226.6176 | 35.8836 | 22975.8294 | 24025
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522 |  |  |  | 24025
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
3rd & 4th Podium Floor For Residential & Part Parking
3rd & 4th Podium Floor For Residential & Part Parking |  | 1 |  | Parking |  |  |  | -
2
|  | 3 | [8 empty] | 23000
|  | 4 | [8 empty] | 14375
|  | 5 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 6 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
5th Podium Floor
5th Podium Floor |  | 1 |  | Parking |  |  |  | -
2
|  | 3 | [8 empty] | 23000
|  | 4 | [8 empty] | 14375
|  | 5 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 6 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
6th, 7th, 9th to 14th, 16th to 21st & 23rd to 28th Floor For Residential
6th, 7th, 9th to 14th, 16th to 21st & 23rd to 28th Floor For Residential |  | 1 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 2 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 3 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 4 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 5 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 6 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
8th, 15th & 22nd Floor (Part Refuge Area)
8th, 15th & 22nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 2 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 3 |  | 1BHK | 400.4208 |  | 0 | 620.6522 |  |  | 23000
|  | 4 |  | 2BHK | 602.1382 |  | 0 | 933.3141 |  |  | 14375
|  | 5 |  | Refuge Area |  |  |  | -
6
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
29th Floor For Part Refuge Area | [8 empty] | Deck Area Added
29th Floor For Part Refuge Area |  | 1 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 2 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 3 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 4 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 5 |  | Refuge Area |  |  |  | -
6
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
30th to 35th & 37th to 39th Floor
30th to 35th & 37th to 39th Floor |  | 1 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 2 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 3 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 4 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 5 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 6 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 7 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 8 |  | 2BHK | 637.1513 |  | 0 | 987.5845
36th Floor For Part Refuge Area
36th Floor For Part Refuge Area |  | 1 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 2 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 3 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 4 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 5 |  | Refuge Area |  |  |  | -
|  | 6 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 7 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 8 |  | 2BHK | 637.1513 |  | 0 | 987.5845
Wing C
Ground Floor For Commercial, Meter Room Panel Room, Society Office & Parking
Ground Floor For Commercial, Meter Room Panel Room, Society Office & Parking |  | 17 |  | Shop | 210.1596 |  | 0 | 325.7473
|  | 18 |  | Shop | 229.101 |  | 0 | 355.1065
|  | 19 |  | Shop | 274.257 |  | 0 | 425.0984
|  | 20 |  | Shop | 228.1968 |  | 0 | 353.705
|  | 21 |  | Shop | 214.5491 |  | 0 | 332.5511
|  | 22 |  | Shop | 229.5584 |  | 0 | 355.8156
|  | 23 |  | Shop | 229.101 |  | 0 | 355.1065
|  | 24 |  | Shop | 210.3426 |  | 0 | 326.031
1st Podium Floor Commercial, Meter Room, LV Room, Panel Room & Parking
1st Podium Floor Commercial, Meter Room, LV Room, Panel Room & Parking |  | 13 |  | Shop | 250.39 |  | 0 | 388.1045
|  | 13A |  | Shop | 156.5215 |  | 0 | 242.6083
|  | 14 |  | Shop | 209.2532 |  | 0 | 324.3425
|  | 15 |  | Shop | 165.4298 |  | 0 | 256.4161
|  | 16 |  | Shop | 152.4979 |  | 0 | 236.3717 |  | 52.9856
|  | 17 |  | Shop | 166.7021 |  | 0 | 258.3882 |  | 35.8836
|  | 18 |  | Shop | 156.5215 |  | 0 | 242.6083
|  | 18A |  | Shop | 250.3954 |  | 0 | 388.1129
2nd Podium Floor For Residential, Part Parking & Meter Room
2nd Podium Floor For Residential, Part Parking & Meter Room |  | 1 |  | Parking & Meter Room |  |  |  | -
2
3
4
|  | 5 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 6 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
3rd Podium Floor For Residential & Part Parking
3rd Podium Floor For Residential & Part Parking |  | 1 |  | Parking |  |  |  | -
2
3
4
|  | 5 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 6 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
4th Podium Floor
4th Podium Floor |  | 1 |  | Parking |  |  |  | -
2
3
4
|  | 5 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 6 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
5th Podium Floor
5th Podium Floor |  | 1 |  | Parking |  |  |  | -
2
3
4
|  | 5 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 6 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
6th, 7th, 9th to 14th, 16th to 21st & 23rd to 28th Floor For Residential
6th, 7th, 9th to 14th, 16th to 21st & 23rd to 28th Floor For Residential |  | 1 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 2 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 3 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 4 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 5 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 6 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
8th, 15th & 22nd Floor For Part Refuge Area
8th, 15th & 22nd Floor For Part Refuge Area |  | 1 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 2 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 3 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 4 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 5 |  | Refuge Area |  |  |  | -
6
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
29th Floor For Part Refuge Area
29th Floor For Part Refuge Area |  | 1 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 2 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 3 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 4 |  | 2BHK | 602.1382 |  | 0 | 933.3141
|  | 5 |  | Refuge Area |  |  |  | -
6
|  | 7 |  | 1BHK | 400.4208 |  | 0 | 620.6522
|  | 8 |  | 2BHK | 602.1382 |  | 0 | 933.3141
30th to 35th & 37th to 39th Floor
30th to 35th & 37th to 39th Floor |  | 1 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 2 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 3 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 4 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 5 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 6 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 7 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 8 |  | 2BHK | 637.1513 |  | 0 | 987.5845
36th Floor For Part Refuge Area
36th Floor For Part Refuge Area |  | 1 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 2 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 3 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 4 |  | 2BHK | 637.1513 |  | 0 | 987.5845
|  | 5 |  | Refuge Area |  |  |  | -
|  | 6 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 7 |  | 1BHK | 432.209 |  | 0 | 669.924
|  | 8 |  | 2BHK | 637.1513 |  | 0 | 987.5845
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit.(Internal visit not allowed) 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Deck Area. 5. We have considered proposed No. of Floor for Stage Calculation. 6. We have considered rate by verifying it from market inquire. 7. Car parking is subjected to authentic documentation. 8. We have updated Wing A (on 31/10/2024). 9. We have updated revised approved CC of wing A (on 06/08/2024). 10. We have added Wing C (on 31/10/2024). 11. We have updated approved EC (on 31/10/2024). 12. We have updated CC from MCGM site on 16/05/2025. 13. Please provide revised approved plans dtd. 24/03/2025. | [6 empty] | Internal Visit was not allowed
Site & Building/Tower Photographs
Name of the Project |  |  | : | Ashford Crosstown
Project Site Address |  |  | : | Ashford Crosstown, Bhandup Village Rd, Nahur, Industrial Area, Bhandup West, Mumbai, Maharashtra 400078
Site Visit Date & Time |  |  | : | 05/08/2025 @01:25 PM
Layout Plan
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr. Nainesh Tambe | Authorized Signatory Name & Signature | :
Ashford Regal - Phase I - Wing A Project
Ashford Regal - Phase IV- Wing C Project
RailwayTrack
Wing A
Wing C
Wing A
Wing C
Note on H7: Rushil Sanghvi or Fahad
Note on E10: Initiation Address
Note on E11: Plan Address
Note on E12: Map Address
Note on H18: From Rera
Note on H21: From RERA
Note on H100: Ready Recknor