## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 07/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-07
Name of the builder group |  |  |  | M/s.Sai Balaji Buildcon
Name of the builder company |  |  |  | M/s.Sai Balaji Buildcon
Name of the Project |  |  |  | Balaji Estate Phase - 2
Contact Details ( Name & Contact No.) |  |  |  | Mr. Sunil - 8291206833
Name / No of the Building |  |  |  | A Wing (Uma), B Wing (Pavapuri), C Wing (Hansh), D Wing (Shiv) & E Wing (Bhoomi)
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | P51700031992
Project location details |  | Balaji Estate Phase - 2, Survey No.18/5,6, S.No. 20, S.No. 41-1/4., near Janiv Ashram, Kalyan Shil road, Umbroli, Dombivali , Ambarnath, Thane - 421204.
Survey No |  | 18/5,6, S.No. 20, S.No. 41-1/4.
Road |  | Kalyan Shil road |  | Locality/Village |  | Umbroli
City |  | Dombivali |  | District |  | Thane
Taluka |  | Ambarnath |  | Pin Code |  | 421204
Nearby Landmark |  | Janiv Ashram |  | Distance from city centre: |  | 6.7 KM from Dombivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open land
West | NA | NA |  |  | Open land
North | NA | NA |  |  | Kalyan shil road
South | NA | NA |  |  | Open land
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.1817 |  | Longitude |  | 73.104
Location Link |  | https://goo.gl/maps/F9UMzMNU8iYHEcju6?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 10795.28
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.1268
Total FSI availaible for the project |  |  |  | 3.2268
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 34834.04
Total number of Buildings |  |  |  | 5 Wing
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan-Dombivli Municipal Corporation
Layout Approval No |  | KDMC/TPD/BP/27Villages/2019-20/16/62 |  |  | Dated | 2023-05-09
Approved Floor plan No. |  | KDMC/TPD/BP/27Villages/2019-20/16/62 |  |  | Dated | 2023-05-09
Commencement Certificate No. Valid Up to: |  | KDMC/TPD/BP/27Villages/2019-20/16/62 |  |  | Dated | 2023-05-09
Building No. 2 (A, B & D Wing) - G/St + 1st to 21st Floor Building No. 2 (C Wing) - G/St + 1st to 11th Floor Building No. 2 (E Wing) - G/St + 1st to 24th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 34834.04
Approved no of units |  |  | Sale Flat - 627, Mhada Flat - 42
Approved no of Floors |  |  | Building No. 2 (A, B & D Wing) - G/St + 1st to 21st Floor Building No. 2 (C Wing) - G/St + 1st to 11th Floor Building No. 2 (E Wing) - G/St + 1st to 24th Floor
Proposed no of Floors |  |  | Building No. 2 (A Wing) - G/St + 1st to 21st Floor
Building No. 2 (B Wing) - G/St + 1st to 21st Floor
Building No. 2 (C Wing) - G/St + 1st to 21st Floor
Building No. 2 (D Wing) - G/St + 1st to 21st Floor
Building No. 2 (E Wing) - G/St + 1st to 24th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 2 (A Wing) - G/St + 1st to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 13 Slab Completed, Brickwork upto 12 Floor Completed, Internal Plaster upto 9 Floor Completed, External Plaster upto 8.4 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 13 Slab Completed, Brickwork upto 12 Floor Completed, Internal Plaster upto 9 Floor Completed, External Plaster upto 8.4 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 45.14% |  | 69.73% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 13 | 59.09% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 12 | 57.14% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 42.86% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8.4 | 40% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Building No. 2 (B Wing) - G/St + 1st to 21st Floor | [5 empty] | Excavation work Completed. Footing work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Footing work is process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 2.5% |  | 26.25% |  | Excavation in process | 10.5
Plinth |  | 5.25 | 25% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Building No. 2 (C Wing) - G/St + 1st to 21st Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 10.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | Building No. 2 (D Wing) - G/St + 1st to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 11.82% |  | 46.36% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 1 | 4.545% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10.5 | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0 | #REF!
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0 | #REF!
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0 | #REF!
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 | #REF!
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75 | #REF!
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21 | #REF!
Construction details: |  | Building No. 2 (E Wing) (Part 1) = G/St + 1st to 24th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed, Brickwork upto 5 Floor Completed, Internal Plaster upto 3.75 Floor Completed, External Plaster upto 3.5 Floor Completed. |  | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 24
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed, Brickwork upto 5 Floor Completed, Internal Plaster upto 3.75 Floor Completed, External Plaster upto 3.5 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 23.79% |  | 54.75% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 6 | 24% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 5 | 20.83% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 3.75 | 15.63% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3.5 | 14.58% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Construction details: |  | Building No. 2 (E Wing) (Part 2) = G/St + 1st to 24th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed. |  | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 24
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 11.6% |  | 46.2% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 1 | 4% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Building No. 2 (E Wing) Average Progress % |  | 17.7% |  | Building No. 2 (E Wing) Average Disbursement % |  | 50.48% |  | Plinth in process | 0
[8 empty] | Plinth completed | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 6000
Recommended rate of the shop Per Sq. Ft. (on Saleable area)
Recommended rate of the Office Per Sq. Ft. (on Saleable area)
Floor Rise Rate Per Sq.ft
Development Charges
Club Charges
Legal Services Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 4800
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 126 |  | 66163.6439 |  | 99245.4659
Wing B |  | 66 |  | 34407.6104 |  | 51611.4156
Wing C |  | 66 |  | 34679.3476 |  | 52019.0213 |  | 5297.747
Wing D |  | 126 |  | 65802.5386 |  | 98703.8079 |  | 5198.8604
Wing E | Sale Flat | 243 |  | 95670.0014 |  | 143505.0022 |  | 5332.5068 |  | 627
| Mhada Flat | 42 |  | 16516.8629 |  | 24775.2943 |  | 5332.5068 |  |  | 285
Total |  | 669 |  | 313240.0048 |  | 469860.0071 |  | 5187.4016
Building details Floor Wise | [7 empty] | 5345.2739
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Wing A
Ground Floor for Parking
1st to 21st Floor for Residential
1 |  | 2BHK | 606.955 | 0 | 910.4326 | 1st to 21st Floor for Residential
2 |  | 1BHK | 490.65 | 0 | 735.975
3 |  | 1BHK | 490.65 | 0 | 735.975
4 |  | 1BHK | 473.9389 | 0 | 710.9084
5 |  | 1BHK | 488.3627 | 0 | 732.544
6 |  | 2BHK | 600.093 | 0 | 900.1395
Wing B
Ground Floor for Parking
1st to 11th & 12th to 21st Floor for Residential
1 |  | 1BHK | 478.1907 | 0 | 717.286 | 1st to 11th & 12th to 21st Floor for Residential
2 |  | 1BHK | 487.2863 | 0 | 730.9294
3 |  | 2BHK | 600.093 | 0 | 900.1395
4 |  | 2BHK | 600.093 | 0 | 900.1395
5 |  | 1BHK | 488.3627 | 0 | 732.544
6 |  | 1BHK | 473.9389 | 0 | 710.9084
Wing C
Ground Floor for Parking
1st to 11th Floor for Residential
1 |  | 1BHK | 483.7072 | 0 | 725.5609 | 1st to 11th Floor for Residential
2 |  | 1BHK | 488.7663 | 0 | 733.1495 |  |  | 6235.7265
3 |  | 2BHK | 604.5331 | 0 | 906.7997
4 |  | 2BHK | 601.573 | 0 | 902.3596
5 |  | 1BHK | 488.7663 | 0 | 733.1495
6 |  | 1BHK | 485.3218 | 0 | 727.9828
Wing D
Ground Floor for Parking
1st to 21st Floor for Residential
1 |  | 2BHK | 600.093 | 0 | 900.1395 | 1st to 21st Floor for Residential
2 |  | 1BHK | 488.3627 | 0 | 732.544
3 |  | 1BHK | 473.9389 | 0 | 710.9084
4 |  | 1BHK | 478.1907 | 0 | 717.286
5 |  | 1BHK | 487.2863 | 0 | 730.9294
6 |  | 2BHK | 605.5826 | 0 | 908.374
Wing E
Ground Floor for Parking
1st to 3rd Floor for Residential
1 | Mhada | 1RK | 331.4236 | 0 | 497.1353 | 1st to 3rd Floor for Residential
2 | Mhada | 1BHK | 479.3317 | 0 | 718.9975
3 | Mhada | 1RK | 360.8093 | 0 | 541.2139
4 | Mhada | 1RK | 393.1013 | 0 | 589.6519
5 | Mhada | 1BHK | 449.2355 | 0 | 673.8533 |  |  |  | 46.7815
6 | Mhada | 1RK | 331.4236 | 0 | 497.1353
7 | Mhada | 1RK | 331.4236 | 0 | 497.1353
8 | Mhada | 1BHK | 476.1455 | 0 | 714.2183
9 | Mhada | 1RK | 395.1464 | 0 | 592.7197
10 | Mhada | 1RK | 395.1464 | 0 | 592.7197 |  |  |  | 23.375
11 | Mhada | 1BHK | 449.2355 | 0 | 673.8533
12 | Mhada | 1RK | 331.4236 | 0 | 497.1353
4th Floor (Partly alloted to Mhada)
1 | Mhada | 1RK | 331.4236 | 0 | 497.1353 | 4th Floor (Partly alloted to Mhada)
2 | Mhada | 1BHK | 479.3317 | 0 | 718.9975
3 | Mhada | 1RK | 360.8093 | 0 | 541.2139
4 | Mhada | 1RK | 393.1013 | 0 | 589.6519
5 | Mhada | 1BHK | 449.2355 | 0 | 673.8533
6 | Mhada | 1RK | 331.4236 | 0 | 497.1353
7 | Sale | 1RK | 331.4236 | 0 | 497.1353
8 | Sale | 1BHK | 476.1455 | 0 | 714.2183
9 | Sale | 1RK | 395.1464 | 0 | 592.7197
10 | Sale | 1RK | 395.1464 | 0 | 592.7197
11 | Sale | 1BHK | 449.2355 | 0 | 673.8533
12 | Sale | 1RK | 331.4236 | 0 | 497.1353
5th, 6th, 7th, 9th, 10th, 11th, 12th, 14th, 15th, 16th, 17th, 18th, 20th, 21st, 22nd, 23rd & 24th Floor
1 |  | 1RK | 331.4236 | 0 | 497.1353 | 5th, 6th, 7th, 9th, 10th, 11th, 12th, 14th, 15th, 16th, 17th, 18th, 20th, 21st, 22nd, 23rd & 24th Floor
2 |  | 1BHK | 479.3317 | 0 | 718.9975
3 |  | 1RK | 360.8093 | 0 | 541.2139
4 |  | 1RK | 393.1013 | 0 | 589.6519
5 |  | 1BHK | 449.2355 | 0 | 673.8533
6 |  | 1RK | 331.4236 | 0 | 497.1353
7 |  | 1RK | 331.4236 | 0 | 497.1353
8 |  | 1BHK | 476.1455 | 0 | 714.2183
9 |  | 1RK | 395.1464 | 0 | 592.7197
10 |  | 1RK | 395.1464 | 0 | 592.7197
11 |  | 1BHK | 449.2355 | 0 | 673.8533
12 |  | 1RK | 331.4236 | 0 | 497.1353
8th, 13th & 19th Floor (Part Refuge Area)
1 |  | 1RK | 331.4236 | 0 | 497.1353 | 8th, 13th & 19th Floor (Part Refuge Area)
2 |  | 1BHK | 479.3317 | 0 | 718.9975
3 |  | 1RK | 360.8093 | 0 | 541.2139
4 |  | 1RK | 393.1013 | 0 | 589.6519
5 |  | 1BHK | 449.2355 | 0 | 673.8533
6 |  | 1RK | 331.4236 | 0 | 497.1353
7 |  | 1RK | 331.4236 | 0 | 497.1353
8 |  | 1BHK | 476.1455 | 0 | 714.2183
9 |  | Refuge Area
10 |  | 1RK | 395.1464 | 0 | 592.7197
11 |  | 1BHK | 449.2355 | 0 | 673.8533
12 |  | 1RK | 331.4236 | 0 | 497.1353
Remarks:
* | Wing A & Wing E (Part I) = Construction work is in process at the time of visit. Wing B = Construction work was not active at the time of visit. Wing C = Work not yet started. Wing D = Work is same as last visit (07/11/2023). Wing E (Part II) = Work has recently resumed. | [6 empty] | Wing E (Part II) = Work is same as last visit (09/08/2024).
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony + W.S Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Sunil : 8097725003.
* | We have updated revised approved floor plan & C.C (on 29/05/2023).
* | CC taken from RERA site.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area. | [8 empty] | 1
Inspected By : |  | Gangaram parshuram Lambore |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Balaji Estate Phase - 2
Layout :
Google Map :
Formulas:
Umbroli = [Umbroli, row above]
E Wing
(Part I)
E Wing (Part I)
Bldg No.2
Wing A
Bldg No.2
Wing B
Bldg No.2
Wing C
Bldg No.2
Wing D
Bldg No.2
Wing E
E Wing
(Part I)
E Wing (Part II)

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted