## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-07
Project Name |  | Godrej Eternal Palms |  | Date & Time of Site Visit |  | 11/08/2025 @ 05:27 PM
Name of the person met at site & Contact No. |  | NA |  | Date of Report Release |  | 25/09/2025
Data from APF Request Form
Branch Name/ID |  | Mumbai-RO Thane |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | M/s. Godrej Properties Limited |  | Developer Name |  | M/s. Godrej Properties Limited
Developer Office Address |  | 5th Floor, Godrej One, Pirojshanagar, Eastern Express Highway, Vikhroli (East), Vikhroli, Taluka Kurla 400079.
Project Address | As per ARF | Godrej Eternal Palms, Plot no 8 & 9, Sector 18, Off Palm Beach Rd, Navi Mumbai, Maharashtra 400705.
| As per Legal Documents | Proposed Residential Cum Commercial Building On Plot No.8 & 9, Sector 19, Sanpada, Navi Mumbai
| As per Actual at site | Godrej Eternal Palms, Plot No.8 & 9, Sector 19, near Jaipuriar School, Internal Road, Sanpada, Sanpada, Sanpada West, Thane, Thane - 400705.
Documents Provided by GHF |  | Approved Layout & Floor Plans, RERA certificate, Fire Noc, Airport Noc & EC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Navi Mumbai Municipal Corporation (NMMC)
RERA Registration No. | : | PM1330002500429 |  | RERA Registration Validity | : | 2032-12-31
Project Launch Date | : | 2025-07-30 |  | Construction Start Date | : | Not Started
Proposed Date of Completion (As per RERA) | : | 2032-12-31 |  | Developer Bank Name (As per RERA) | : | AXIS Bank IFSC Code = UTIB0001394
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 6616.61
FSI/FAR Permissible | : | 1.1 |  | Net Plot Area (In Sq.Mt) | : | 6616.61
Permissible Built up Area (In Sq.Mt) | : | 32752.217 |  | Proposed Built up Area (In Sq.Mt) | : | 32747.388
Total Number of Units Approved | : | Flats = 236 Shop = 10 |  | Total Number of Units Planned | : | As per RERA Site Flats = 266 & Shop = 10
Latitude, Longitude | : | 19.054284,73.008126 |  | Landmark | : | Jaipuriar School
Location Link | : | https://maps.app.goo.gl/1ZiHTSVCWt6gSir88
Extra Amenities available | : | Creche, Society Office, Aerobics Room, Library, Amenity, Steam Room, Multipupose Room, Hall, Gym, Fitness Center, Indoor Games, Telecom Room, Vitrified tiles flooring, Granite Kitchen Platform, Decorative Entrance, Landscaping & Garden, etc. | [5 empty] | https://godrejs-eternalpalms.com/?mainsource=PPC&keyword=godrej%20eternal%20palms&modelofthedevice=&ads_id=NA&adgroupid=182229778486&ads_extension_id=&ads_set_name=Godrej_Eternal_Palms_Sanpada_MMR-s-bpl-p-217&campaignid=22868979046&campaign_name=Godrej_Eternal_Palms_Sanpada_MMR-s-bpl-p&keywordmatchtype=p&geographiclocation=9303628&ad_strategy=&targetid=kwd-2488918903127&target=&devicetype=c&medium=Paid&gad_source=1&gad_campaignid=22868979046&gbraid=0AAAAA-E4Ke3UGwFCiccQNPGEM8BqsZuwZ&gclid=CjwKCAjwwNbEBhBpEiwAFYLtGDyWxpXzlR82_kTqI0pLwZ_IiN7QwI2CwUW90ECEKOk9S-fnjGCwJhoCIhYQAvD_BwE
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 22m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.85 KM from Sanpada Sonkhar Bus Stop
Distance from the nearest School (Km) | : | About 0.40 KM from Jaipuriar School |  | Distance from Hospital (Km) | : | About 1.20 KM from Suraj Hospital
Distance from the Main Market (Km) | : | 1. Approx. 0.60 KM from One Stop Super Market. 2. Approx. 0.75 KM from Kisan Konnect Farm Store. |  | Distance from Railway Station (Km) | : | 1.80 KM from Sanpada Railway Station 3.50 KM from Juinagar Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East |  | West
East |  | Other Plot |  |  | Open Plot
West |  | Other Plot |  |  | Open Plot
North |  | 22.00 Mtr Wide Road |  |  | Internal Road
South |  | Other Plot |  |  | Open Plot
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing A |  | - | G + 1st to 37th Floor |  |  | G + 1st to 37th Floor
Wing B |  | - | G + 1st to 37th Floor |  |  | G + 1st to 37th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | NMMCC/B/2025/APL/01032 |  |  |  | Date: | 2025-07-17
Approved Plan Details | : | NMMCC/B/2025/APL/01032 |  |  |  | Date: | 2025-07-17
CC Details Valid Up to: |  | NMMCC/B/2025/APL/01032 |  |  |  | Date: | 2025-07-17
Godrej Properties (Wing A & B) = G + 1st to 37th Floor
Fire Noc Details Valid upto |  | Fire/HO/Vashi/1858/2025 |  |  |  | Date: | 2025-04-07 | Fire Noc Details Valid upto | :
Wing A & B = G + 1st to 37th Floor (Height = 121.80 Mtrs)
Airport Authority Clearance Details Valid upto |  | NAVI/WEST/B/040221/538526 |  |  |  | Date: | 2022-08-18 | Airport Authority Clearance Details Valid upto | :
|  | Site Elevation (AMSL) = 4.64 M Permissible Top Elevation (AMSL) = 133.95 M |  |  |  | Valid upto Dated | 2030-08-17 |  |  |  |  | 7 RCC 3Brick 2 plaster
Environmental Clearance Details Valid Up for: |  | SIA/MH/INFRA2/479401/2024 |  |  |  | Date: | 2025-09-23
Plot no. 8 & 9 of Sector 19 Proposed BUA = 56079.60 Sq. mt Sale Tower 1 & 2 = G + 1st to 32nd Floor
Construction Status
Wing A = G + 1st to 37th Floor. |  |  | Basement | Ground |  | Podium | Floors
|  |  | 0 | 1 |  | 0 | 37 | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | All work Completed. OC Received.
Excavation |  | 0 | 0% | 0% |  | Work not yet Started. |  | Piling Work in process | 9.25
Plinth |  | 0 | 0% |  |  |  |  | Excavation in process | 18.5
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Excavation Completed | 37
Brickwork |  | 0 | 0% |  |  |  |  | Footing in Process | 7.4
Internal Plaster |  | 0 | 0% |  |  |  |  | Footing Completed | 14.8
External Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth in process | 25.9
Building Common Amenities |  | 0 | 0% |  |  |  |  | Plinth completed | 37
Possession |  | 0 | 0%
Construction Status
Wing B = G + 1st to 37th Floor. |  |  | Basement | Ground |  | Podium | Floors
|  |  | 0 | 1 |  | 0 | 37 | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | All work Completed. OC Received.
Excavation |  | 0 | 0% | 0% |  | Work not yet Started. |  | Piling Work in process | 9.25
Plinth |  | 0 | 0% |  |  |  |  | Excavation in process | 18.5
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Excavation Completed | 37
Brickwork |  | 0 | 0% |  |  |  |  | Footing in Process | 7.4
Internal Plaster |  | 0 | 0% |  |  |  |  | Footing Completed | 14.8
External Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth in process | 25.9
Building Common Amenities |  | 0 | 0% |  |  |  |  | Plinth completed | 37
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 0%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 34000 to 35000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 700000 |  | Other Charges | : | As applicable and documented.
Guideline Values | [7 empty] | 34500
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 1384.2438
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 4199.1825
Distress Value (Rs. Per sqft) |  |  |  |  | : | 1107.395
Unit Details, Nomenclature and Area Details (Shop)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing A + B |  | - |  | 10 |  | 15057.652
Total |  | - |  | 10 |  | 15057.652
Unit Details, Nomenclature and Area Details (Flat)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area |  | OK
Wing A |  | - |  | 118 |  | 124571.0495 |  | OK
Wing B |  | - |  | 118 |  | 124571.0495
Total |  | - |  | 236 |  | 249142.0989
Grand Total |  | - |  | 246 |  | 264199.7509
Details of Residential & Commercial in Building | [7 empty] | 10.764
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Wing A + B
Ground Floor For Commercial, Entrance Lobby, Driveway, Parking & Ramp Driveway | [7 empty] | 118.5074
1 |  | - | Shop | 1275.4479 | 0 | 0 | 1275.4479
2 |  | - | Shop | 1598.3464 | 0 | 0 | 1598.3464
3 |  | - | Shop | 1433.9693 | 0 | 0 | 1433.9693
4 |  | - | Shop | 1565.6561 | 0 | 0 | 1565.6561
5 |  | - | Shop | 1655.4063 | 0 | 0 | 1655.4063
6 |  | - | Shop | 1655.4063 | 0 | 0 | 1655.4063
7 |  | - | Shop | 1565.6561 | 0 | 0 | 1565.6561
8 |  | - | Shop | 1433.9693 | 0 | 0 | 1433.9693
9 |  | - | Shop | 1598.3464 | 0 | 0 | 1598.3464
10 |  | - | Shop | 1275.4479 | 0 | 0 | 1275.4479 | 5
Wing A | [7 empty] | 1
1st to 5th Podium Floor For Parking
6th Floor For Creche, Society Office, Aerobics Room, Library, Amenity, Steam Room, Multipurpose Hall, Gym/Fitness Center, Indoor Games, Telecom Room & Landscape Area | [7 empty] | 9
8th to 11th, 13th to 16th & 18th Floor For Residential | [7 empty] | 100.6039 | 9.902 | [5 empty] | 801,..,1801 | 801 | 1801
1 |  | - | 3BHK | 1144.084 | 106.5851 | 0 | 1250.6692 | 94.2756 | [6 empty] | 802,..,1802 | 802 | 1802
2 |  | - | 3BHK | 1074.2257 | 90.1081 | 0 | 1164.3338 | 64.1656 | [6 empty] | 803,..,1803 | 803 | 1803
3 |  | - | 2BHK | 721.9092 | 78.8127 | 0 | 800.7219 | [7 empty] | 804,..,1804 | 804 | 1804
4 |  | - | 3BHK | 919.0411 | 77.5116 | 0 | 996.5526 | 6
7th, 12th, 17th, 22nd, 27th & 32nd Floor For (Part Refuge Balcony Area) | [7 empty] | 100.6039 | 9.902 | [5 empty] | 71201,..,3201 | 71201 | 3201
1 |  | - | 3BHK | 1144.084 | 106.5851 | 0 | 1250.6692 | 94.2756 | [6 empty] | 71202,..,3202 | 71202 | 3202
2 |  | - | 3BHK | 1074.2257 | 90.1081 | 0 | 1164.3338 | 64.1656 | [6 empty] | 71203,..,3203 | 71203 | 3203
3 |  | - | 2BHK | 721.9092 | 78.8127 | 0 | 800.7219 | [7 empty] | 71204,..,3204 | 71204 | 3204
4 |  | - | 3BHK | 919.0411 | 77.5116 | 0 | 996.5526 | [7 empty] | 71205,..,3205 | 71205 | 3205
- |  | - | Refuge Balcony Area |  |  |  |  | 14
19th, 21st, 23rd to 26th, 28th to 31st & 33rd to 36th Floor | [7 empty] | 100.6039 | 9.902 | [5 empty] | 192101,..,3601 | 192101 | 3601
1 |  | - | 3BHK | 1144.084 | 106.5851 | 0 | 1250.6692 | 94.2756 | [6 empty] | 192102,..,3602 | 192102 | 3602
2 |  | - | 3BHK | 1074.2257 | 90.1081 | 0 | 1164.3338 | 64.1656 | [6 empty] | 192103,..,3603 | 192103 | 3603
3 |  | - | 2BHK | 721.9092 | 78.8127 | 0 | 800.7219 | [7 empty] | 192104,..,3604 | 192104 | 3604
4 |  | - | 3BHK | 919.0411 | 77.5116 | 0 | 996.5526 | 1 | [5 empty] | 23333.3333
20th Floor For Residential (Part Pump Room & Fire Break Tank Area) | [7 empty] | 100.6039 | 9.902 |  |  |  | 35176.4706 |  | 2001,..,2001 | 2001 | 2001
1 |  | - | 3BHK | 1144.084 | 106.5851 | 0 | 1250.6692 | 94.2756 | [6 empty] | 2002,..,2002 | 2002 | 2002
2 |  | - | 3BHK | 1074.2257 | 90.1081 | 0 | 1164.3338 | 64.1656 | [6 empty] | 2003,..,2003 | 2003 | 2003
- |  | - | Pump Room & Fire Break Tank Area | [11 empty] | 2004,..,2004 | 2004 | 2004
- |  | - | [5 empty] | 1
37th Floor For Recreational Floor
Wing B | [7 empty] | 9
1st to 5th Podium Floor For Parking | [7 empty] | 94.2756 | 9.902 | [5 empty] | 801,..,1801 | 801 | 1801
6th Floor For Creche, Society Office, Aerobics Room, Library, Amenity, Steam Room, Multipurpose Hall, Gym/Fitness Center, Indoor Games, Telecom Room & Landscape Area | [14 empty] | 802,..,1802 | 802 | 1802
8th to 11th, 13th to 16th & 18th Floor For Residential | [7 empty] | 64.1656 | 39898.6411 | 41583.3333 |  |  |  |  | 803,..,1803 | 803 | 1803
1 |  | - | 3BHK | 1144.084 | 106.5851 | 0 | 1250.6692 | 80.1649 | [6 empty] | 804,..,1804 | 804 | 1804
2 |  | - | 3BHK | 1074.2257 | 90.1081 | 0 | 1164.3338 | 6
3 |  | - | 2BHK | 721.9092 | 78.8127 | 0 | 800.7219 | 94.2756 | 9.902 | [5 empty] | 71201,..,3201 | 71201 | 3201
4 |  | - | 3BHK | 919.0411 | 77.5116 | 0 | 996.5526 | [7 empty] | 71202,..,3202 | 71202 | 3202
7th, 12th, 17th, 22nd, 27th & 32nd Floor For (Part Refuge Balcony Area) | [7 empty] | 64.1656 | [6 empty] | 71203,..,3203 | 71203 | 3203
1 |  | - | 3BHK | 1144.084 | 106.5851 | 0 | 1250.6692 | 80.1649 |  | 23333.3333 |  |  |  |  | 71204,..,3204 | 71204 | 3204
2 |  | - | 3BHK | 1074.2257 | 90.1081 | 0 | 1164.3338 |  | 43710.5594 | [5 empty] | 71205,..,3205 | 71205 | 3205
3 |  | - | 2BHK | 721.9092 | 78.8127 | 0 | 800.7219 | 14 |  |  | 16666.6667
4 |  | - | 3BHK | 919.0411 | 77.5116 | 0 | 996.5526 | 94.2756 | 9.902 | [5 empty] | 192101,..,3601 | 192101 | 3601
- |  | - | Refuge Balcony Area | [6 empty] | 24000 |  |  |  |  | 192102,..,3602 | 192102 | 3602
19th, 21st, 23rd to 26th, 28th to 31st & 33rd to 36th Floor | [7 empty] | 64.1656 |  | 30016059.84 |  |  |  |  | 192103,..,3603 | 192103 | 3603
1 |  | - | 3BHK | 1144.084 | 106.5851 | 0 | 1250.6692 | 80.1649 |  | 27944011.368 |  |  |  |  | 192104,..,3604 | 192104 | 3604
2 |  | - | 3BHK | 1074.2257 | 90.1081 | 0 | 1164.3338 | 1 | 36217.3206 | 19217324.412
3 |  | - | 2BHK | 721.9092 | 78.8127 | 0 | 800.7219 | 94.2756 | 9.902 | 23917263.552 |  |  |  |  | 2001,..,2001 | 2001 | 2001
4 |  | - | 3BHK | 919.0411 | 77.5116 | 0 | 996.5526 |  |  | 0 |  |  |  |  | 2002,..,2002 | 2002 | 2002
20th Floor For Residential (Part Pump Room & Fire Break Tank Area) | [7 empty] | 64.1656 |  | 30016059.84 |  |  |  |  | 2003,..,2003 | 2003 | 2003
1 |  | - | 3BHK | 1144.084 | 106.5851 | 0 | 1250.6692 | 80.1649 | [6 empty] | 2004,..,2004 | 2004 | 2004
2 |  | - | 3BHK | 1074.2257 | 90.1081 | 0 | 1164.3338 | 1
3 |  | - | Pump Room & Fire Break Tank Area
4 |  | -
37th Floor For Recreational Floor
Project Specific Remarks & Observation
* | Work not yet Started.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We have referred apprpoved CC from RERA Portal.
* | We have updated Fire Noc & Airport Noc on 13/08/2025
* | We have updated Environment Clearance Certificate on 25/09/2025
* | Remark for NOCs
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs
Name of the Project |  |  | Godrej Eternal Palms
Project Site Address |  |  | Godrej Eternal Palms, Plot no 8 & 9, Sector 18, Off Palm Beach Rd, Navi Mumbai, Maharashtra 400705.
Site Visit Date & Time |  |  | 11/08/2025 @ 05:27 PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Tushar Mohite |  | Authorized Signatory Name & Signature
Godrej Eternal Palms
Wing A
Wing B
EWS Building
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per maps
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G98: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0