## Report
APF Report Format | [9 empty] | Old Int Date
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-07 | 2025-07-22 | 2025-04-23
Project Name |  |  | : | Runwal Pinnacle |  | Date & Time of Site Visit |  | 11/08/2025 at 03:20 PM | 45692 | < 90
Name of the person met at site & Contact No. |  |  | : | Mr Krishna 9372619071 |  | Date of Report Release |  | 11/08/2025 | Mr. Mandar 8655133244 |  |  |  | 2025-02-04
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Runwal Apartments Private Limited | Developer Name | : | Runwal Group
Developer Office Address |  |  | : | Runwal & Omkar Esquare,5th Floor, Eastern Express Highway, Sion (East), Mumbai – 400022
Project Address | : | As per ARF | : | Runwal Pinnacle, near Runwal Greens & Fortis Hospital Goregaon, Mulund West, Mumbai, Maharashtra 400078
| : | As per Legal Documents | : | Runwal Pinnacle, CTS No.681/A/7, 681/A/8 & 681/A/9, near Fortis Hospital, Goregaon Link Road, Nahur, Nahur West, Kurla, Mumbai - 400080.
| : | As per Actual at site | : | Runwal Pinnacle, CTS No.681/A/7, 681/A/8 & 681/A/9, near Fortis Hospital, Goregaon Link Road, Nahur, Nahur West, Kurla, Mumbai - 400080.
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai (MCGM)
RERA Registration No. | : | P51800021322 |  |  | RERA Registration Validity | : | 2027-06-30
Project Launch Date | : | 2018-06-15 |  |  | Construction Start Date | : | 2018-06-15
Proposed Date of Completion (As per RERA) | : | 30/06/2027 |  |  | Developer Bank Name (As per RERA) | : | Indusind Bank Ltd IFSC Code - INDB0000056
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 63288.9
FSI/FAR Permissible | : | 1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 270319.86
Permissible Built up Area (In Sq.Mt) | : | 63288.9 |  |  | Total Number of Units Planned | : | As per RERA, Flats = 1107
Total Number of Units Approved | : | Flats = 982 |  |  | If Mixed, No. of Commercial Units | : | -
Latitude, Longitude | : | 19.16079009,72.9430197
Location | : | https://maps.app.goo.gl/JupUaPsJLVCbtgdK8
Extra Amenities available | : | Swimming Pool, Gym, Jaccuzi, Library, Lawn, Community Hall, Indoor Games, Basket Ball, Jogging track, Yoga, Billiards, Sitting Area, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  |  | Width of the Road | : | 45.70M
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 400 M from Merind Co. Bus Stop
Distance from the nearest School (Km) | : | About 500M from Holy Angels Marthoma School |  |  | Distance from Hospital (Km) | : | About 300 M form Fortis Hospital
Distance from the Main Market (Km) | : | 1. Approx. 1.9KM from STAR Market. 2. Approx. 2.7 KM from FOF Super Mart. |  |  | Distance from Railway Station (Km) | : | 800 M from Nahur Railway Station 4 KM from Bhandup Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Road | Open Plot | Jain Temple |  | Open Plot
As per Site / Actual |  |  | : | Mulund - Goregaon Link Road | Runwal Greens | Runwal Green Maple |  | Fortis Hospital
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower 1 & 2 |  | Sale |  | 5B + G + 9P + 2Lvl Amenity + 1st to 54th Floor |  |  | 5B + G + 9P + 2Lvl Amenity + 1st to 46th Floor |  | 15 | 40
Tower 2 |  | Sale |  | 5B + G + 9P + 2lvl Amenity + 1st to 54th Floor |  |  | 5B + G + 9P + 2lvl Amenity + 1st to 39th Floor
Tower 3 |  | Sale |  | 5B + G + 9P + 2lvl Amenity + 1st to 54th Floor |  |  | 5B + G + 9P + 2lvl Amenity + 1st to 39th Floor
Tower 3 & 4 |  | Sale |  | 5B + G + 9P + 2Lvl Amenity + 1st to 54th Floor |  |  | 5B + G + 9P + 2Lvl Amenity + 1st to 52nd Floor
Tower 5 |  | Sale |  | 5B + G + 9P + 2Lvl Amenity + 1st to 54th Floor |  |  | 5B + G + 9P + 2Lvl Amenity + 1st to 45th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | CHE/ES/4261/S/337(NEW)/337/8/ Amend Date: 21/07/2025
Approved Plan Details | : | CHE/ES/4261/S/337(NEW)/337/8/Amend Date: 21/07/2025
CC Details Valid Up To: | : | CHE/ES/4261/S/337(NEW)/FCC/3/Amend Date: 11/06/2024 Date Valid Up To: 10/06/2025 Further C.C. is granted for tower 03 and 04 upto 48th upper floors and C.C. is re-endorsed for tower 01,02 and 05 as per amended approved plan dated 05.03.2024 subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution.
CC Details Valid Up To: | : | CHE/ES/4261/S/337(NEW)/FCC/4/Amend Date: 19/06/2024 Date Valid Up To: 12/06/2026 Further C.C. is granted for Tower 1, 2 & 5 upto 37th floor as per approved amended plans dated 05/03/2024 by restricting C.C. from 38th to 40th floor for Tower 1, 2 & 5 for instalment facility subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution.
SWM NOC | : | CHE/ES/4261/S/337(NEW)/SWM/2/Amend |  |  | Tree Authority NOC | : | DYSG/TA/MC/451
FIRE NOC | : | CHE/ES/4261/S/337(NEW)-CFO Date : 02/06/2019 Valid For : Building No. 2 (Tower 1 to 5) Basement (Total depth 14.70mtrs.) + Ground floor + 1st to 9th podium floors + Club house level-1 & 2 + 1st to 53rd upper residential floors (Height 210.95mtrs) |  |  | Environmental Clearance | : | SEIAA-EC-0000001541 Date : 28/05/2019 Valid For : Net Plot Area = 60005.18 Sqm, Total Builtup Area = 686525.30
Construction Status
Tower 1 & 2 = 5B + G + 9P + 2Lvl Amenity + 1st to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed
|  |  |  | 3 | 1 |  | 9 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 28.91% |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 10 |  | 15.62% |  |  |  |  | Footing in Process | 10.8
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 21.6
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 32.4
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 43.2
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 1 = 5B + G + 9P + 2Lvl Amenity + 1st to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 9 Floor, Internal Plaster upto 6.75 Floor, External Plaster upto 6.75 Floor Completed
|  |  |  | 5 | 1 |  | 11 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 34.41% |  | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 9 Floor, Internal Plaster upto 6.75 Floor, External Plaster upto 6.75 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 21 |  | 31.82% |  |  |  |  | Footing in Process | 7.7143
Brickwork |  | 9 |  | 16.67% |  |  |  |  | Footing Completed | 15.4286
Internal Plaster |  | 6.75 |  | 12.5% |  |  |  |  | Basement 1 | 23.1429
External Plaster |  | 6.75 |  | 12.5% |  |  |  |  | Basement 2 | 30.8571
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 38.5714
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 46.2857
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 2 = 5B + G + 9P + 2Lvl Amenity + 1st to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 20 Slab, Brickwork upto 8 Floor, Internal Plaster upto 6.4 Floor, External Plaster upto 6.4 Floor Completed
|  |  |  | 5 | 1 |  | 11 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 33.91% |  | Excavation work Completed. Plinth work completed, RCC upto 20 Slab, Brickwork upto 8 Floor, Internal Plaster upto 6.4 Floor, External Plaster upto 6.4 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 20 |  | 30.3% |  |  |  |  | Footing in Process | 7.7143
Brickwork |  | 8 |  | 14.81% |  |  |  |  | Footing Completed | 15.4286
Internal Plaster |  | 6.4 |  | 11.85% |  |  |  |  | Basement 1 | 23.1429
External Plaster |  | 6.4 |  | 11.85% |  |  |  |  | Basement 2 | 30.8571
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 38.5714
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 46.2857
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 3 & 4 = 5B + G + 9P + 2Lvl Amenity + 1st to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 56 Slab, Brickwork upto 44 Floor, Internal Plaster upto 28.6 Floor, External Plaster upto 28.6 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed
|  |  |  | 5 | 1 |  | 11 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 53.58% |  | Excavation work Completed. Plinth work completed, RCC upto 56 Slab, Brickwork upto 44 Floor, Internal Plaster upto 28.6 Floor, External Plaster upto 28.6 Floor, External Plumbing, Elevation and Waterproofing upto 7 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 56 |  | 84.85% |  |  |  |  | Footing in Process | 7.7143
Brickwork |  | 44 |  | 81.48% |  |  |  |  | Footing Completed | 15.4286
Internal Plaster |  | 28.6 |  | 52.96% |  |  |  |  | Basement 1 | 23.1429
External Plaster |  | 28.6 |  | 52.96% |  |  |  |  | Basement 2 | 30.8571
External Plumbing, Elevation and Waterproofing |  | 7 |  | 12.96% |  |  |  |  | Basement 3 | 38.5714
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 46.2857
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 5 = 5B + G + 9P + 2Lvl Amenity + 1st to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed
|  |  |  | 3 | 1 |  | 9 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 28.91% |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 10 |  | 15.62% |  |  |  |  | Footing in Process | 10.8
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 21.6
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 32.4
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 43.2
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Tower 05 - 5B + G + 9P + 2lvl Amenity + 1st to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. 1st to 3rd Basement Completed
|  |  |  | 5 | 1 |  | 9 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 14.29% |  | Excavation work Completed. 1st to 3rd Basement Completed |  | Excavation in process | 27
Plinth |  | 38.5714 |  | 71.43% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 7.7143
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 15.4286
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 23.1429
Ext.Plaster & Plumbing |  | 0 |  | 0% |  |  |  |  | Basement 2 | 30.8571
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 3 | 38.5714
Painting & Wooden |  | 0 |  | 0% |  |  |  |  | Basement 4 | 46.2857
Building Common Amenities |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54
Construction Status
Tower 5 = 5B + G + 9P + 2Lvl Amenity + 1st to 54th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 6 Floor, Internal Plaster upto 3.9 Floor, External Plaster upto 3.9 Floor Completed
|  |  |  | 5 | 1 |  | 11 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 32.73% |  | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 6 Floor, Internal Plaster upto 3.9 Floor, External Plaster upto 3.9 Floor Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 18 |  | 27.27% |  |  |  |  | Footing in Process | 7.7143
Brickwork |  | 6 |  | 11.11% |  |  |  |  | Footing Completed | 15.4286
Internal Plaster |  | 3.9 |  | 7.222% |  |  |  |  | Basement 1 | 23.1429
External Plaster |  | 3.9 |  | 7.222% |  |  |  |  | Basement 2 | 30.8571
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 38.5714
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 46.2857
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 41.64%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 24000/- to 25000/- | Floor Rise Per Sq. Ft. (on Carpet area) | : | 100/- from 2nd Habitual Floor |  | rate has been revised on 11/08/2025
Car Parking Charges |  |  | : | 800000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 6964.8829
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 14286.5106
Distress Value (Rs. Per sqft) | [5 empty] | : | 5571.9064
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
Tower 1 |  | Sale |  | Flats | 177 |  | 149035.653 | 223553.4795 | 150
Tower 2 |  | Sale |  | Flats | 250 |  | 206617.0252 | 309925.5377 | 212
Tower 3 |  | Sale |  | Flats | 178 |  | 98564.8716 | 147847.3074 | 134
Tower 4 |  | Sale |  | Flats | 178 |  | 138116.9743 | 207175.4615 | 137
Tower 5 |  | Sale |  | Flats | 199 |  | 122863.8481 | 184295.7722 | 177
Total |  | Sale |  | Flats | 982 |  | 715198.3722 | 1072797.5583 | 810
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
50%
Tower 1 + 2 + 3 + 4 + 5
1st to 5th Basement Floor For Parking
Ground Floor For Entrance Lobby & Society Office
1st to 9th Podium Floor For Parking
1st & 2nd Club House Level Floor For Amenities
Service Floor (Between Amenity Floor & 1st Floor)
Tower 1
1st Floor for Residential (Part Refuge Area) | [8 empty] | 1
1st Floor for Residential (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
2nd to 4th Floor | [8 empty] | 3
2nd to 4th Floor |  | 1 |  | 3BHK | 967.1454 | 967.1454 | 0 | 1450.7181 |  |  | 32053.0915
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
5th, 16th to 18th Floor | [8 empty] | 4
5th, 16th to 18th Floor |  | 1 |  | 3BHK | 967.1454 | 967.1454 | 0 | 1450.7181
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
8th Floor for Residential (Part Refuge Area) | [8 empty] | 1
8th Floor for Residential (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
6th, 7th, 9th to 14th, 19th to 21st Floor | [8 empty] | 11
6th, 7th, 9th to 14th, 19th to 21st Floor |  | 1 |  | 3BHK | 967.1454 | 967.1454 | 0 | 1450.7181
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
15th Floor for Residential (Part Refuge Area) | [8 empty] | 1
15th Floor for Residential (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [8 empty] | 1
22nd Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
23rd to 28th, 33th to 35th, 37th & 38th Floor | [8 empty] | 11
23rd to 28th, 33th to 35th, 37th & 38th Floor |  | 1 |  | 3BHK | 967.1454 | 967.1454 | 0 | 1450.7181
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
29th & 36th Floor (Part Refuge Area) | [8 empty] | 2
29th & 36th Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
30th to 32nd Floor | [8 empty] | 3
30th to 32nd Floor |  | 1 |  | 3BHK | 967.1454 | 967.1454 | 0 | 1450.7181
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
39th & 40th Floor | [8 empty] | 2
39th & 40th Floor |  | 1 |  | 3BHK | 967.1454 | 967.1454 | 0 | 1450.7181
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 677.8091 | 677.8091 | 0 | 1016.7136
41st & 42nd Floor | [8 empty] | 2
41st & 42nd Floor |  | 1 |  | 3BHK | 967.1454 | 967.1454 | 0 | 1450.7181
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 714.7296 | 677.8091 | 0 | 1072.0944
43rd Floor (Part Refuge Area) | [8 empty] | 1
43rd Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 714.7296 | 677.8091 | 0 | 1072.0944
44th & 45th Floor | [8 empty] | 2
44th & 45th Floor |  | 1 |  | 3BHK | 967.1454 | 967.1454 | 0 | 1450.7181
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 714.7296 | 677.8091 | 0 | 1072.0944
46th Floor | [8 empty] | 1
46th Floor |  | 1 |  | 3BHK | 967.1454 | 967.1454 | 0 | 1450.7181
|  | 2 |  | 2.5BHK | 852.7241 | 852.7241 | 0 | 1279.0861
|  | 3 |  | 3BHK | 884.5855 | 884.5855 | 0 | 1326.8783
|  | 4 |  | 2BHK | 714.7296 | 677.8091 | 0 | 1072.0944
Tower 2
1st Floor for Residential (Part Refuge Area) | [8 empty] | 1
1st Floor for Residential (Part Refuge Area) |  | 1 |  | 2BHK | 661.6631 | 661.6631 | 0 | 992.4946
|  | 2 |  | 2BHK | 709.3476 | 709.3476 | 0 | 1064.0214
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967 |  |  | 17334.6292
|  | 5 |  | Refuge Area
|  | 6 |  | -
2nd to 4th Floor | [8 empty] | 3
2nd to 4th Floor |  | 1 |  | 2BHK | 661.6631 | 661.6631 | 0 | 992.4946
|  | 2 |  | 2BHK | 709.3476 | 709.3476 | 0 | 1064.0214
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | Refuge Area Below @ 1st Floor
|  | 6 |  | -
5th & 16th to 18th Floor For Residential & Girder Beam | [8 empty] | 4
5th & 16th to 18th Floor For Residential & Girder Beam |  | 1 |  | 2BHK | 661.6631 | 661.6631 | 0 | 992.4946
|  | 2 |  | 2BHK | 709.3476 | 709.3476 | 0 | 1064.0214
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | 2BHK | 611.3952 | 611.3952 | 0 | 917.0928
|  | 6 |  | Girder Beam @ 5th & 18th Floor
8th Floor for Residential (Part Refuge Area) | [8 empty] | 1
8th Floor for Residential (Part Refuge Area) |  | 1 |  | 2BHK | 661.6631 | 661.6631 | 0 | 992.4946
|  | 2 |  | 2BHK | 709.3476 | 709.3476 | 0 | 1064.0214
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | Refuge Area
|  | 6 |  | 2BHK | 690.9412 | 690.9412 | 0 | 1036.4117
6th, 7th, 9th to 14th, 19th to 21st Floor | [8 empty] | 11
6th, 7th, 9th to 14th, 19th to 21st Floor |  | 1 |  | 2BHK | 661.6631 | 661.6631 | 0 | 992.4946
|  | 2 |  | 2BHK | 709.3476 | 709.3476 | 0 | 1064.0214
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | 2BHK | 611.3952 | 611.3952 | 0 | 917.0928
|  | 6 |  | 2BHK | 690.9412 | 690.9412 | 0 | 1036.4117
15th Floor for Residential (Part Refuge & Terrace Area) | [8 empty] | 1
15th Floor for Residential (Part Refuge & Terrace Area) |  | 1 |  | 2BHK | 661.6631 | 661.6631 | 0 | 992.4946
|  | 2 |  | 2BHK | 709.3476 | 709.3476 | 0 | 1064.0214
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | Refuge Area
|  | 6 |  | Terrace Area
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [8 empty] | 1
22nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | Refuge Area
|  | 6 |  | 2BHK | 690.9412 | 690.9412 | 0 | 1036.4117
23rd to 28th, 33th to 35th, 37th & 38th Floor | [8 empty] | 11
23rd to 28th, 33th to 35th, 37th & 38th Floor |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | 2BHK | 611.3952 | 611.3952 | 0 | 917.0928
|  | 6 |  | 2BHK | 690.9412 | 690.9412 | 0 | 1036.4117
29th & 36th Floor (Part Refuge Area) | [8 empty] | 2
29th & 36th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | Refuge Area
|  | 6 |  | 2BHK | 690.9412 | 690.9412 | 0 | 1036.4117
30th to 32nd Floor | [8 empty] | 3
30th to 32nd Floor |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | Refuge Area Below @ 29th Floor
|  | 6 |  | 2BHK | 690.9412 | 690.9412 | 0 | 1036.4117
39th Floor For Residential (Part Terrace Area) | [8 empty] | 1
39th Floor For Residential (Part Terrace Area) |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | 2BHK | 611.3952 | 611.3952 | 0 | 917.0928
|  | 6 |  | Terrace Area
40th Floor | [8 empty] | 1
40th Floor |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | 2BHK | 611.3952 | 611.3952 | 0 | 917.0928
|  | 6 |  | Terrace Area Below @ 39th Floor
41st & 42nd Floor | [8 empty] | 2
41st & 42nd Floor |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | 2BHK | 657.788 | 611.3952 | 0 | 986.6821
|  | 6 |  | Girder Beam @ 42nd Floor
43rd Floor (Part Refuge Area) | [8 empty] | 1
43rd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | Refuge Area
|  | 6 |  | 2BHK | 690.9412 | 690.9412 | 0 | 1036.4117
44th & 45th Floor | [8 empty] | 2
44th & 45th Floor |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | 2BHK | 657.788 | 611.3952 | 0 | 986.6821
|  | 6 |  | 2BHK | 690.9412 | 690.9412 | 0 | 1036.4117
46th Floor | [8 empty] | 1
46th Floor |  | 1 |  | 2BHK | 611.2876 | 611.2876 | 0 | 916.9313
|  | 2 |  | 2BHK | 660.0485 | 660.0485 | 0 | 990.0727
|  | 3 |  | 1BHK | 461.4527 | 461.4527 | 0 | 692.179
|  | 4 |  | 1BHK | 458.3311 | 458.3311 | 0 | 687.4967
|  | 5 |  | 2BHK | 657.788 | 611.3952 | 0 | 986.6821
|  | 6 |  | 2BHK | 690.9412 | 690.9412 | 0 | 1036.4117
Tower 3
1st Floor (Part Refuge Area) | [8 empty] | 1
1st Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | -
2nd to 4th Floor | [8 empty] | 3
2nd to 4th Floor |  | 1 |  | Refuge Area Below @ 1st Floor
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | -
5th, 16th to 18th Floor | [8 empty] | 4
5th, 16th to 18th Floor |  | 1 |  | 2BHK | 618.2842 | 618.2842 | 0 | 927.4262
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | Girder Beam @ 5th & 18th Floor
8th Floor for Residential (Part Refuge Area) | [8 empty] | 1
8th Floor for Residential (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
6th, 7th, 9th to 14th, 19th to 21st Floor | [8 empty] | 11
6th, 7th, 9th to 14th, 19th to 21st Floor |  | 1 |  | 2BHK | 618.2842 | 618.2842 | 0 | 927.4262
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
15th Floor for Residential (Part Refuge & Terrace Area) | [8 empty] | 1
15th Floor for Residential (Part Refuge & Terrace Area) |  | 1 |  | Refuge Area
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | Terrace Area
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [8 empty] | 1
22nd Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
23rd to 28th, 33th to 35th, 37th & 38th Floor | [8 empty] | 11
23rd to 28th, 33th to 35th, 37th & 38th Floor |  | 1 |  | 2BHK | 618.2842 | 618.2842 | 0 | 927.4262
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
29th & 36th Floor (Part Refuge Area) | [8 empty] | 2
29th & 36th Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
30th to 32nd Floor | [8 empty] | 3
30th to 32nd Floor |  | 1 |  | Refuge Area Below @ 29th Floor
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
39th Floor (Part Terrace Area) | [8 empty] | 1
39th Floor (Part Terrace Area) |  | 1 |  | 2BHK | 618.2842 | 618.2842 | 0 | 927.4262
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | Terrace Area
40th Floor | [8 empty] | 1
40th Floor |  | 1 |  | 2BHK | 618.2842 | 618.2842 | 0 | 927.4262
|  | 2 |  | 1BHK | 457.3624 | 457.3624 | 0 | 686.0435
|  | 3 |  | 1BHK | 462.9596 | 462.9596 | 0 | 694.4395
|  | 4 |  | Terrace Area Below @ 39th Floor
41st & 42nd Floor | [8 empty] | 2
41st & 42nd Floor |  | 1 |  | 2BHK | 664.677 | 664.677 | 0 | 997.0155
|  | 2 |  | 1BHK | 503.8628 | 503.8628 | 0 | 755.7943
|  | 3 |  | 1BHK | 509.4601 | 509.4601 | 0 | 764.1902
|  | 4 |  | Girder Beam @ 42nd Floor
43rd Floor (Part Refuge Area) | [8 empty] | 1
43rd Floor (Part Refuge Area) |  | 1 |  | Refuge Area
|  | 2 |  | 1BHK | 503.8628 | 503.8628 | 0 | 755.7943
|  | 3 |  | 1BHK | 509.4601 | 509.4601 | 0 | 764.1902
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
44th & 45th Floor | [8 empty] | 2
44th & 45th Floor |  | 1 |  | 2BHK | 664.677 | 664.677 | 0 | 997.0155
|  | 2 |  | 1BHK | 503.8628 | 503.8628 | 0 | 755.7943
|  | 3 |  | 1BHK | 509.4601 | 509.4601 | 0 | 764.1902
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
46th Floor | [8 empty] | 1
46th Floor |  | 1 |  | 2BHK | 664.677 | 664.677 | 0 | 997.0155
|  | 2 |  | 1BHK | 503.8628 | 503.8628 | 0 | 755.7943
|  | 3 |  | 1BHK | 509.4601 | 509.4601 | 0 | 764.1902
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
47th to 49th Floor | [8 empty] | 3
47th to 49th Floor |  | 1 |  | 2BHK | 664.677 | 664.677 | 0 | 997.0155
|  | 2 |  | 1BHK | 503.8628 | 503.8628 | 0 | 755.7943
|  | 3 |  | 1BHK | 509.4601 | 509.4601 | 0 | 764.1902
|  | 4 |  | 2BHK | 712.0386 | 712.0386 | 0 | 1068.0579
50th Floor (Part Regfuge & Terrace Area) | [8 empty] | 1
50th Floor (Part Regfuge & Terrace Area) |  | 1 |  | Refuge Area
|  | 2 |  | 1BHK | 503.8628 | 503.8628 | 0 | 755.7943
|  | 3 |  | 1BHK | 509.4601 | 509.4601 | 0 | 764.1902
|  | 4 |  | Terrace Area
51st & 52nd Floor | [8 empty] | 2
51st & 52nd Floor |  | 1 |  | 2BHK | 664.677 | 664.677 | 0 | 997.0155
|  | 2 |  | 1BHK | 503.8628 | 503.8628 | 0 | 755.7943
|  | 3 |  | 1BHK | 509.4601 | 509.4601 | 0 | 764.1902
|  | 4 |  | Terrace Area Below @ 50th Floor
Tower 4
1st Floor for Residential (Part Refuge Area) | [8 empty] | 1
1st Floor for Residential (Part Refuge Area) |  | 1 |  | -
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | Refuge Area
2nd to 4th Floor | [8 empty] | 3
2nd to 4th Floor |  | 1 |  | -
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | Refuge Area Below @ 1st Floor
5th, 16th to 18th Floor | [8 empty] | 4
5th, 16th to 18th Floor |  | 1 |  | Girder Beam @ 5th & 18th Floor
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782 |  | 30651.0246
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 875.1132 | 875.1132 | 0 | 1312.6698
8th Floor for Residential (Part Refuge Area) | [8 empty] | 1
8th Floor for Residential (Part Refuge Area) |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | Refuge Area
6th, 7th, 9th to 14th, 19th to 21st Floor | [8 empty] | 11
6th, 7th, 9th to 14th, 19th to 21st Floor |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 875.1132 | 875.1132 | 0 | 1312.6698
15th Floor for Residential (Part Refuge Area) | [8 empty] | 1
15th Floor for Residential (Part Refuge Area) |  | 1 |  | Terrace Area
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | Refuge Area
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [8 empty] | 1
22nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | Refuge Area
23rd to 28th, 33th to 35th, 37th & 38th Floor | [8 empty] | 11
23rd to 28th, 33th to 35th, 37th & 38th Floor |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 875.1132 | 875.1132 | 0 | 1312.6698
29th & 36th Floor (Part Refuge Area) | [8 empty] | 2
29th & 36th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | Refuge Area
30th to 32nd Floor | [8 empty] | 3
30th to 32nd Floor |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | Refuge Area Below @ 29th Floor
39th Floor (Part Terrace Area) | [8 empty] | 1
39th Floor (Part Terrace Area) |  | 1 |  | Terrace Area
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 875.1132 | 875.1132 | 0 | 1312.6698
40th Floor | [8 empty] | 1
40th Floor |  | 1 |  | Terrace Area Below @ 39th Floor
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 875.1132 | 875.1132 | 0 | 1312.6698
41st & 42nd Floor | [8 empty] | 2
41st & 42nd Floor |  | 1 |  | Girder Beam @ 42nd Floor
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 921.506 | 875.1132 | 0 | 1382.2591
43rd Floor (Part Refuge Area) | [8 empty] | 1
43rd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | Refuge Area
44th & 45th Floor | [8 empty] | 2
44th & 45th Floor |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 921.506 | 875.1132 | 0 | 1382.2591
46th Floor | [8 empty] | 1
46th Floor |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 921.506 | 875.1132 | 0 | 1382.2591
47th to 49th Floor | [8 empty] | 3
47th to 49th Floor |  | 1 |  | 2BHK | 713.7608 | 713.7608 | 0 | 1070.6413
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 921.506 | 875.1132 | 0 | 1382.2591
50th Floor (Part Refuge & Terrace Area) | [8 empty] | 1
50th Floor (Part Refuge & Terrace Area) |  | 1 |  | Terrace Area
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | Refuge Area
51st & 52nd Floor | [8 empty] | 2
51st & 52nd Floor |  | 1 |  | Terrace Area Below @ 51st Floor
|  | 2 |  | 3BHK | 1011.3854 | 1011.3854 | 0 | 1517.0782
|  | 3 |  | 1BHK | 502.1406 | 502.1406 | 0 | 753.2109
|  | 4 |  | 3BHK | 921.506 | 875.1132 | 0 | 1382.2591
Tower 5
1st Floor for Residential (Part Refuge Area) | [8 empty] | 1
1st Floor for Residential (Part Refuge Area) |  | 1 |  | -
|  | 2 |  | Refuge Area
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
2nd to 4th Floor | [8 empty] | 3
2nd to 4th Floor |  | 1 |  | - |  |  |  |  | Wind Pressure Defusing Shaft
|  | 2 |  | Refuge Area Below @ 1st Floor
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
5th, 16th to 18th Floor | [8 empty] | 4
5th, 16th to 18th Floor |  | 1 |  | Girder Beam @ 5th & 18th Floor
|  | 2 |  | 2BHK | 678.9931 | 678.9931 | 0 | 1018.4897
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
8th Floor for Residential (Part Refuge Area) | [8 empty] | 1
8th Floor for Residential (Part Refuge Area) |  | 1 |  | 2BHK | 686.6356 | 686.6356 | 0 | 1029.9533
|  | 2 |  | Refuge Area
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
6th, 7th, 9th to 14th, 19th to 21st Floor | [8 empty] | 11
6th, 7th, 9th to 14th, 19th to 21st Floor |  | 1 |  | 2BHK | 686.6356 | 686.6356 | 0 | 1029.9533
|  | 2 |  | 2BHK | 678.9931 | 678.9931 | 0 | 1018.4897
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
15th Floor for Residential (Part Refuge & Terrace Area) | [8 empty] | 1
15th Floor for Residential (Part Refuge & Terrace Area) |  | 1 |  | Terrace Area
|  | 2 |  | Refuge Area
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
Service Floor Between 21st & 22nd Floor
22nd Floor (Part Refuge Area) | [8 empty] | 1
22nd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 686.6356 | 686.6356 | 0 | 1029.9533
|  | 2 |  | Refuge Area
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
23rd to 28th, 33th to 35th, 37th & 38th Floor | [8 empty] | 11
23rd to 28th, 33th to 35th, 37th & 38th Floor |  | 1 |  | 2BHK | 686.6356 | 686.6356 | 0 | 1029.9533
|  | 2 |  | 2BHK | 678.9931 | 678.9931 | 0 | 1018.4897
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
29th & 36th Floor (Part Refuge Area) | [8 empty] | 2
29th & 36th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 686.6356 | 686.6356 | 0 | 1029.9533
|  | 2 |  | Refuge Area
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
30th to 32nd Floor | [8 empty] | 3
30th to 32nd Floor |  | 1 |  | 2BHK | 686.6356 | 686.6356 | 0 | 1029.9533
|  | 2 |  | Refuge Area Below @ 29th Floor
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
39th Floor For (Part Terrace Area) | [8 empty] | 1
39th Floor For (Part Terrace Area) |  | 1 |  | Terrace Area
|  | 2 |  | 2BHK | 678.9931 | 678.9931 | 0 | 1018.4897
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
40th Floor | [8 empty] | 1
40th Floor |  | 1 |  | Terrace Area Below @ 39th Floor
|  | 2 |  | 2BHK | 678.9931 | 678.9931 | 0 | 1018.4897
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
41st & 42nd Floor | [8 empty] | 2
41st & 42nd Floor |  | 1 |  | Girder Beam @ 42nd Floor
|  | 2 |  | 2BHK | 725.386 | 678.9931 | 0 | 1088.0789
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
43rd Floor (Part Refuge Area) | [8 empty] | 1
43rd Floor (Part Refuge Area) |  | 1 |  | 2BHK | 686.6356 | 686.6356 | 0 | 1029.9533
|  | 2 |  | Refuge Area
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
44th & 45th Floor | [8 empty] | 2
44th & 45th Floor |  | 1 |  | 2BHK | 686.6356 | 686.6356 | 0 | 1029.9533
|  | 2 |  | 2BHK | 725.386 | 678.9931 | 0 | 1088.0789
|  | 3 |  | 1BHK | 457.7929 | 457.7929 | 0 | 686.6894
|  | 4 |  | 1BHK | 462.0985 | 462.0985 | 0 | 693.1478
|  | 5 |  | 2.5BHK | 835.1788 | 835.1788 | 0 | 1252.7681
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Tower 1 to 5 = Construction work is in process at the time of Visit. Internal Visit was not allowed. (Slow Speed). 2. We considered Carpet area as per Approved Plan. 3. We considered Gross carpet area = Net carpet + Utility + Deck. 4. We have considered rate by verifying it from market inquire. 5. Car parking is subjected to authentic documentation. 6. We have updated revised approved CC (On 30/09/2024). 7.We have updated revised approved floor plan (on 13/03/2024 & 08/08/2025)
Site & Building/Tower Photographs
Name of the Project |  |  | : | Runwal Pinnacle
Project Site Address |  |  | : | Runwal Pinnacle, near Runwal Greens & Fortis Hospital Goregaon, Mulund West, Mumbai, Maharashtra 400078
Site Visit Date & Time |  |  | : | 11/08/2025 at 03:20 PM
Location Plan
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Nainesh Tambe | Authorized Signatory Name & Signature | :
T5
T4
T3
T2
T1
Tower 1
Tower 2
Tower 2
Tower 5
Tower 3
Tower 4
Tower 4
Tower 1
T1
Tower 3 & 4
T5
T2
Tower 4
T5
T4
T3